## Procurement
TOUR OPERATOR'S PLAN FOR SUSTAINABLE TOURISM RG-M1213
Ref. No. | Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequalification (Yes/No) | Estimated procurement costs (US$) | Estimated dates |  | Status (pending, in process, awarded, cancelled)
|  |  |  | IDB | Local/other |  |  | Publication of specific procurement notice | Completion of contract
|  |  |  | % | %
Consulting Services
1.1 | Field Manager: Oversees and facilitate all field work for product development in Central America | SSS | Ex-Post | 100 | 0 | No | 49140 | 2012-10-01 | 2014-11-30 | Awarded
1.1 | Field Manager: Oversees and facilitate all field work for product development in Peru | SSS | Ex-Post | 100 | 0 | No | 45462 | 2012-10-01 | 2014-11-30 | Awarded
1.1 | Field Operations Manager: Oversees progress on all technical assistance contracts for final year | ICQ | Ex-Post | 100 | 0 | No | 26508 | 2014-10-01 | 2015-09-30 | Pending
1.6.1 | Product development and supervision - Restaurant (Peru): Manages technical assistance and capacity-building processes. | CQS | Ex-Post | 100 | 0 | No | 10000 | 2013-04-01 | 2013-03-31 | Pending
1.6.1 | Restaurant & Hospitality Management Technical Assistance | CQS | Ex-Post | 100 | 0 | No | 15000 | 2013-01-15 | 2014-07-15 | Pending
1.6.1 | Agricultural Supply Chain Technical Assistance | CQS | Ex-Post | 100 | 0 | No | 10000 | 2014-01-15 | 2014-07-15 | Pending
1.6.2 | Product development and supervision - Campsite (Peru): Manages technical assistance and capacity-building processes. | CQS | Ex-Post | 100 | 0 | No | 10000 | 2013-04-01 | 2013-03-31 | Pending
1.6.2 | Campsite Landscape Design Assistance | CQS | Ex-Post | 100 | 0 | No | 10000 | 2013-10-01 | 2013-03-31 | Pending
1.6.2 | Campsite Environmental Management Assistance (including showers, composting toilets, waste management) | CQS | Ex-Post | 100 | 0 | No | 10000 | 2013-10-01 | 2013-03-31 | Pending
1.6.2 | Community-based Business Management Technical Assistance | CQS | Ex-Post | 100 | 0 | No | 5000 | 2014-01-15 | 2014-07-15 | Pending
1.6.3 | Product development and supervision (Nicaragua): Manages technical assistance and capacity-building processes. | CQS | Ex-Post | 100 | 0 | No | 5000 | 2013-04-01 | 2013-03-31 | Pending
1.6.4 | Product development and physical improvement supervision (Guatemala): Manages technical assistance and capacity-building processes. | CQS | Ex-Post | 100 | 0 | No | 10000 | 2013-04-01 | 2012-12-31 | Pending
4.4 | Green Economy-sustainable tourism training module and training- | CQS | Ex-Post | 100 | 0 | NO | 25000 | 2013-10-01 | 2014-10-01 | Pending
5.3 | Case Study - Future Sales Model for Tour Operators and tourism-related MSEs | SSS | Ex-Post | 100 | 0 | No | 5000 | 2014-10-01 | 2015-01-30 | Pending
5.4 | Case Study - Product Support Team model for CBT product development | SSS | Ex-Post | 100 | 0 | No | 1000 | 2014-10-01 | 2015-01-30 | Pending
5.5 | Informational and Marketing Videos on Project Model for local, regional, and international operators in English & Spanish (including video capture throughout project) | QCBS | Ex-Post | 100 | 0 | no | 50000 | 2014-04-01 | 2014-10-31 | Pending
5,6 | Development of Evaluation and Monitoring System, Midterm and final evaluations | CQS | Ex-Post | 100 | 0 | No | 70000 | 2012-12-01 | 2015-09-30 | Awarded
5.6(a) | Data collection-mid term and final | ICQ | Ex-Post | 100 | 0 | No | 2400 | 2012-12-01 | 2015-09-30 | Pending
Civil Works
1.6.1 | Remodelling of restaurant facilities | PC | Ex-Post | 0 | 100 | No | 22000 | 2013-10-01 | 2014-01-15 | Pending
1.6.2 | Design and improvement of campsite facilities | PC | Ex-Post | 0 | 100 | No | 22000 | 2013-10-01 | 2014-01-15 | Pending
1.6.4 | Physical Improvement Service Contract, Homestay & Visitor Centre Project | PC | Ex-Post | 0 | 100 | No | 40000 | 2013-04-01 | 2013-12-31 | Pending
Goods and works: CB: Competitive bidding; PC:Price comparison ; DP: Direct procurement.
Consultancy: CQS: Selection based on the consultants’ qualifications; QCBS: Quality- and cost-based selection; LCS: Least-cost selection; FBS: Selection under a fixed budget; SSS: Single-source selection; ICQ Individual Consultant based on qualifications
Ex ante/ex post review: The standard modality is ex post review, depending on the institutional capacity and the risk level associated with the procurement capacity. Ex ante review could be used for critical or complex processes.