## Smart Guide
SMART GUIDE FOR COMPLETING AOP
Note: Information has been inserted in some TABS as examples. Please delete examples once completed
Tab 1 - Project Overview
1 | Insert relevant basic statitstics for the project. Contact the project's OA for assistance.
2 | CPI is Cost Performance Index. This information can be acquired from the Bank's system. Contact the Project's OA for assistance. The cost performance index is a ratio that measures the financial effectiveness of a project by dividing the budgeted cost of work performed by the actual cost of work performed. If the CPI is > 1, as in 1.25, then the project is under budget, which is the best result. A CPI of 1 means the project is on budget, which is also a good result. A CPI of < 1 means the project is over budget.
3 | SPI is Schedule Performance Index. This is a ratio that divides the budgeted cost of work performed by the budgeted cost of work scheduled. SPI < 1 are not good because they mean the project is behind schedule. A SPI of 1 means the project is on schedule, and a SPI >1 means the project is ahead of schedule.
4 | Include summary information of Main issues or contraints affecting project implementation
5 | Include summary information of Main HIGH-LEVEL Risks and the responses to those risks
Tab 2 - Result Matrix
1 | The descriptions of Components and Outputs and WBS codes are entered here and then referenced to in the other tabs.
2 | Insert outputs in accordance with the approved Results Matrix uploaded to the system at start of project
3 | P - Planned Targets. These targets are set at the start of the project and SHOULD NOT be changed.
4 | SP(a) - Suggested Planned Adjusted Targets. These suggested targets are to be discussed with the IDB team leader, adjusted after each annual reporting cycle and are amended in accordance with is already achieved and what is left to be achieved.
6 | In Column T, explain any variance between the planned targets for the current year [P] and the Suggested Planned Targets [SP(a)]. Do not exceed 50 words
Tab 3 - Implementation Plan
1 | Make sure to reference (link) the Output description (Column A) from the Results Matrix TAB
2 | WBS code (Column B) and Deliverables (Column C) should be referenced from the Procurement Plan TAB
3 | Type or Copy Work Packages in Column E, start with the WBS for the workpackage and then the workpackage description
4 | Estimate durations of work packages in calendar days and put in Column F
5 | Calculate Estimated End Date (Column H) by adding Duration (Column F) to Estimated Start date (Column G)
6 | Add names of responsible people in Columns I to L
7 | Describe the milestones in the months from analysing the workpackages
Tab 4 - Procurement Plan
1 | Outline the procurement items for the next 18 months
2 | Align with SEPA
3 | Ensure to include WBS to indicate each Deliverable (= Contract name / Procurement Item) under the Output
Tab 5 - Financial Plan
1 | Reference the Output (gray row) from the Results Matrix TAB
2 | Reference the WBS code and Deliverable from the Implementation Plan TAB
3 | Include amounts in the correct month based on the dates in the Implementation Plan TAB
4 | Determine disbursement projection (row 53) for the next 6 months starting from the first month amounts are going to be made. Remember to update the formulas in Row 53 (Disbursement Projection)
Tab 6 - Consolidated Financial Plan
1 | Reference the Output and Budget amounts from the Results Matrix TAB
2 | Reference estimated budgetary requirements (Column O) form the Financial Plan Tab
3
Tab 7 - Risk Plan
1 | Outline any threats/risks that may affect project work, time, cost or quality
2 | Include WBS code to which this risk relates. If it relates to the whole project, enter 0 (Project), if it relates to component 1, enter 1. If it relates to output 2.3, enter 2.3. If it relates to deliverable 1.3.4, enter 1.3.4
3 | The type of risk may be related to project management, project governance, macroeconomic, environmental, social, development, human resources, communication, fiscal, etc.
4 | The risk should be described in a manner to outline the proposed effect of it happening.
5 | Use the scale for Impact to describe the Imapct [I] of the risk happening and use the scale for Probability to define the Probability [P] of the risk occuring.
6 | Risk Rating is caluculated by multiplying the Impact and the Probalbiity [IxP]
7 | Use the Risk Rating Key to classify the Risk by indicating the value and level.
8 | Outline the Risk Response Strategy and action plan to address the risk
9 | Indicate the Risk Owner
9

## 1. Project Overview
| Project Name : | CITIZEN SECURITY AND JUSTICE PROGRAMME 111
| Project Number : | 3191/OC-JA
Section 1: GENERAL CONTRACTUAL INFORMATION
Date of Approval: | 2014-06-18 | Loan Amount: | 52793208.88
Signature Date: | 2014-12-11 | Amount Disbursed: | 38827424.14
Date of Eligibility: | 2014-12-18 | Amount Committed:
Original Disbursement Expiration Date: | 2019-12-11 | Current Disbursement Period: | July 2018 to December 2018
Last Disbursement Expiration Date: | 2019-12-11 | Reporting Period | 9 Semester
Previous Period CPI*: |  | Previous Period SPI**:
Executing Agency | Ministry of National Security
Project Objective | The general objective is to enhance citizen security and justice in Jamaica in target communities. The specific objecties are to: (i) improve behaviors for non-violent conflict resolution; (ii) increase labor market attachment among youth; and (iii) increase access to effective community alternative justices services.
Programme/project components | Component 1: Will provide knowledge, skills, and opportunities that allow residents to challenge and change attitudes which promote or tolerate violence (including interpersonal relations & gender equality). Activities include: parenting education; counseling and psychological services; violence interruption services; capacity strengthening of local governance structures; situational crime prevention; construction and equipping of community multi-purpose centres. Component 2: Will extend services to youth operating at 3 different job-readiness levels: Group 1 (highest job-readiness): short-term vocational and on the-job training; job-seeking, placement, etc. Group 2 (intermediate job readiness): on-the-job training and work orientation, e.g. construction apprenticeships with the JDF, summer employment internships, etc.; Group 3 (lowest job-readiness): literacy and numeracy skills to equip them to participate in more advanced training at vocational/secondary school levels. Component 3: Seeks to increase access to (and usage of) justice services outside of the formal court system. Activities include: expansion of the Restorative Justice programme to bring eligible cases to resolution; Child Diversion programmes for steering juveniles in conflict with the law away from criminal charges, prosecution, and/or incarceration; mobile-unit delivery of some services will be expanded to target communities, e.g. Legal Aid, Mediation, Justices of the Peace who can address local disputes before they escalate, Victim Services and, strengthening MOJ to manage and monitor community justice services.
Summary Issues/constraints identified
1a. Political Egagement- Partnering with Members of Parliament in delivery of interventions may give the impression that the CSJP is aligned to a particular political party and/or that that the acttivity is the MP's contribution to the community. 1b. Community level violence may impede implementation of activities in some communities. 1c.Governmental or ministerial change may shift policy emphasis.
2. Under Phase 111, the Case-Management approach is being used to track participants benefitting from individual-level interventions. Continuing delays in commissioning into use a suitable Client Management System (CMS), to manage individual participants may render the effectiveness of the approach sub-optimal
3. The number of PEU case managers available, may impact the number and quality of cases under managementand therefore the overall impact on Programme objectives; this will become particularly critical now that all interevntions willbe active and an enhanced need for greater attention to familyand community level interventions. A large number of cases will need to be risk assessed and case managed in a timely manner, giving rise to caseload and workload issues.
4. There is a challenge to find adequate training intitutions to host the numbers of persons to be trained.
5. Sustained high levels of violence in communities may adversely affect delivery of Programme activities across all components.Western region and parts of KMA and Central regions are of particular concern.
6. Fiscal Space: Programme implementation is expected to be in full flight durin g the upcoming year, with all components in play. Current available space may be well below the level needed to support implementation of the multitude of interventions expected during the year. Slow implementation of some activities in previous years was due to the need for extended preparations such as collection of base line data, deveopment and norming of risk assessment instruments, capacity build out of case management etc.; completion of which have now paved the way for robust implementation. Spike in violence across regions is also creating greater demand for CSJP to allocate additional resources to crisis intervention, again in light of ZOSOs
7: As the Programme draws closer to its scheduled end uncertainity among staff consultants is expected to heighten. This may lead to depatures of critical and high performing members of the PEU and lower production/productivity of those who remain.
8. Delays from MNS in responding to PEU requests for approval of key activities may hamper implementation timelines, Jeopardizing output/outcome expectations.
9. Weaknesses in Programme Governance arrangement could jeopardise transition expectations/results
Summary Strategies for addressing issues/constraints identified | 1a. Careful branding of Programme activities will be increased. Caution will also be taken to ensure that the perons spearheading implementation are viewed by communities as non-partisan or bi-partisan. 1b. CSJP will work witht he Police, the Peace Management Initiative and other stakeholders, during these occurences, with a view to minimize negative impacts on the work program.1c. If the Programme continues to perform as it has in the past: meeting its targets and producing evidence-based impact; there will be little justification for policy shift contrary to the Loan and Grant documents. However, it is recognized that changes in Government policy may occur from time to time and need to be accommodated.
2. Whilst the CMS to beused has been settled, some challenges have been experienced in completing customization and population of the system. Work is proceeding apace to complete the process early in the new year as well as to have all relevant staff trained in the new system.An internal committee has been established to provide greater energy to the process so as to avoid further slippage. The inhouse electronic Case Management System which includes standardised forms for capturng data is already in place, and will continue in use pending full transitioning to the main electronic Case Management System. Hand held computer tablets have been acquired to improve efficiency and effectiveness of the system. Notwithstanding, another CMS, being deployed by another Government Agency, is being reviewed for suitability, as plan B
3. Training and cross training of PEU staff in Case Management, commenced in 2015, will continue. Additional trained staff have beendeployed based upon case load assessment and considerations; case load data will be rigorously monitored in the process. Pertinent staff in PMI have been trained and are engaged in the process, however, gaps still remain in the number of trained case managers and recommendations are on the way to address this issue
4. The PEU continues to scope the training environment with a view of identifying suitable trainining institutions. Partnership arrangements via Memoranda of Understanding and contracts will be established with suitable institutions.
5. Heavy reliance will be placed on the ability of the security forces to contain the violence thereby increasing the safety of Programme delivery actors to access said communities. Additionally, both PMIs will be expected to play a crucial role, via the Violence Interruption Programmes, so too other agences including faith based and community level stakeholders
6. The strategy to be adopted is to rapidly advance implementation activities and related expenditures, early in the Fiscal period, with a view to demonstrating the need for increased supplementary fiscal space, and to continue networking with MNS, MOJ, PIOJ and MoFP towards this end.
7. Provide quick replacements for critical staff who exit the programme, working closely with the Bank and provide motovational Programme Leadership to remaining staff to maintain focus and productivity
8. Early notifications to MNS of planned activities and regular folow up of requests for approvals
9. Strong oversight and leadership by MNSexecutive team, supported by the PEU and IDPs.
Summary of High level Risks | 1. (Med) Insufficient coordination among MDAs and donors delivering programs and services in CSJP communities could result in duplication of services or conflicting approaches.
2. (Med) Mandates and priorities of CSJP and MNS not aligned with those of participating MDAs.
3. (Med) Inadequate institutional and financial sustainability as programs are transferred to MDAs
4. (Med) Fiscal limitations and fiscal space to complete the objectives of the Programme
5. (High) Macro-economic conditions and fiscal pressures that may result in a negative impact on the security situation and employment prospects
6. (High) Lack of data generation for effective monitoring and evaluation
Summary of risk response for high level risks | Risk # 5: The economic outlook for the country hasshownimproving throughout 2018 and is expected to continue throughout the life of the programme for example PIOJ has reported growth of approx 1.6% in the quarter ended September 2018.
Risk #6: Technical assistance and human resources are being provided to support the PEU’s information system needs (e.g. database design and management, survey design, data entry, database security, data analysis and dissemination). A Technical Advisory Team and various Consultants have been engaged by the Programme and Bank to offer support and training to the PEU and MNS/REU. The Jamaica Crime Observatory and the M&E Unit within the Ministry of National Security are being resourced. Additionally, a proposal is included in the 2019 AOP to engage the VPA to establish an injury surveillance system at the Cornwall Regional Hospital and to create geospatial mapping of related incidences for improved data/crime analysis and management A Data Analyst was hired additionally traing was provided to the MNS Research Unit and the PEU M & E Unit

## 2. Results Matrix
CITIZEN SECURITY AND JUSTICE PROGRAMME 111
SECTION 2: Results Matrix
Operation Number: 3191/OC-JA
Component 1 -Culture change for Peaceful Co-existence and Community Governance
WBS Code | Output Definition | Unit Of Measure |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | EOP 2023
|  |  |  | Physical | Financial | Physical | Financial | Physical | Financial | Physical | Financial | Physical | Financial | Physical | Financial | Physical | Financial
1.1.1.1 | Training courses provided to community members on parenting. | # parenting workshops | Planned (P) | 25 | 126632 | 0 | 26174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 152806
IDB code: 1.1 |  |  | Suggested Planned Adjusted P(a) | 36 | 358207 | 18 | 490043 | 0 |  |  | 0 |  | 0 |  | 0 | 54 | 848250
|  | # of Beneficiaries |  | 225 |  | 536
1.1.1.1b | Training courses provided to community members on healthy gender norms. | # of outreach Activities | P | 8 | 73913 | 0 | 39130 | 0 |  | 0 |  | 0 |  | 0 |  | 8 | 113043
IDB code: 1.2 |  |  | SP(a) | 252 | 20452 | 144 | 14436 | [8 empty] | 396 | 34888
1.1.1.2 | Counselling / psycho-social support provided to victims/witnesses of violence (including domestic violence). | # of sessions | P | 35 | 587710 | 0 | 564444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1152154
IDB code: 1.3 |  |  | SP(a) | 1740 | 300722 | 3230 | 384752 |  | 0 |  | 0 |  | 0 |  | 0 | 4970 | 685474
1.1.1.3 | Violence interruption services provided (e.g. gang interruption). | # of communities in which violence interruption is offered for at least 6 months | P | 10 | 66087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 66087
IDB code: 1.4 |  |  | SP(a) | 47 | 653714 | 48 | 1063853 |  | 0 |  | 0 |  | 0 |  | 0 | 95 | 1717567
1.1.1.4 | Violence prevention and conflict resolution education and training provided in schools | #of workshops(1314,a) | P | 30 | 21799 | 0 | 10899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 32698
IDB code: 1.5 |  |  | SP(a) | 80 | 454650 | 40 | 119504 |  | 0 |  | 0 |  | 0 |  | 0 | 120 | 574154
|  | # of Beneficiaries (1314,a) | SP(a) | 1125 |  | 1200 | [9 empty] | 2325
|  | # of schools (1314, a) | SP(a) | 40 |  | 20 | [9 empty] | 60
|  | # Mediation Cases (1314e) | SP(a) | 250 |  | 200 | [9 empty] | 450
1.1.1.5 | Social marketing for awareness and attitude change to promote ‘culture of lawfulness’ (e.g. to address violent gender norms, anti-snitch culture). | #of campaigns | P | 1 | 392916 | 1 | 250612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 643528
IDB code: 1.6 |  |  | SP(a) | 5 | 278542 | 5 | 550189 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | 828731
1.1.1.6 | Community events to improve citizen-police relations conducted. | # of events | P | 4 | 29565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 29565
IDB code: 1.7 |  |  | SP(a) | 2 | 5797 | 2 | 2963 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | 8760
1.1.1.7 | Crisis intervention activities conducted (including but not limited to violence and gang interruption). | # of interventions | P | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0
IDB code: 1.8 |  |  | SP(a) | 10 | 87971 | 2 | 175316 |  | 0 |  | 0 |  | 0 |  | 0 | 12 | 263287
Component 5 - Monitoring and Evaluation
WBS Code | Output Definition | Unit Of Measure |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | EOP 2023 |  | Explanation of variance between Planned (P) and Suggested Planned Adjusted (a) [Do not exceed 50 words]
|  |  |  | Physical | Financial | Physical | Financial | Physical | Financial | Physical | Financial | Physical | Financial | Physical | Financial | Physical | Financial
1.5.1.1 | Information system constructed and implemented to disaggregate the statistical data for Comp 1 by age, sex, community, risk profile, and other factors | # of systems | Planned (P) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IDB code: 1.9 |  |  | Suggested Planned Adjusted P(a) | 1 | 21903 | 0 | 7490 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 29393
1.5.1.4 | Feasibility study designed & implemented by M&E consultant to determine add’l indicators to be collected & programs to be evaluated | # of studies | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | SP(a) | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
1.5.2.2 | Women’s Health Survey (incl a module on violence against women) designed and implemented. | # of surveys | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IDB code: 1.10 |  |  | SP(a) | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
1.5.2.4 | Satisfaction surveys conducted and monitored for each type of training or intervention. | # of interventions with satisfaction survey systems active | P | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0
IDB code: 1.11 |  |  | SP(a) | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
1.1.2.1 | Training and technical assistance provided to female and male community leaders and residents to improve community governance capacity on needs assessment and strategic planning. | # of # Registration training provided | P | 3 | 60870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 60870
IDB code: 2.1 |  |  | SP(a) | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
1.1.2.1 | 1121) Training and technical assistance provided to female and male community leaders and residents to improve community governance capacity on operations. | # of CDCs receiving operaions training | P | 10 | 223478 | 0 | 86957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 310435
IDB code: 2.2 |  |  | SP(a) | 0 | 0 | 27 | 116592.59 |  | 0 |  | 0 |  | 0 |  | 0 | 27 | 116592.59
1.1.2.2 | Community infrastructure (situational crime prevention project and multi-purpose centres) built or renovated | # of small infratructure projects and multi-purpose centres | P | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
IDB code: 2.3 |  |  | SP(a) | 6 | 561435 | 3 | 750843 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | 1312278
1.1.2.3 | Community gender-responsive safety plans developed with safety audits for vulnerable groups. | # of community safety plans developed that include women's and children's safetyt audits | P | 6 | 30435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 30435
IDB code: 2.4 |  |  | SP(a) | 0 | 0 | 13 | 50841 |  | 0 |  | 0 |  | 0 |  | 0 | 13 | 50841
1.1.2.3 | Advocacy campaigns developed and implemented for gender-responsive community safety plans. | # of advocacy campaigns by CDCs on community safety plan implementation | P | 4 | 9130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9130
IDB code: 2.5 |  |  | SP(a) | 6 | 5362.32 | 2 | 2962.96 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | 8325.28
1.1.2.4 | Peace-building through cultural and sporting activities. | # of culture/ sporting events with peace messages held | P | 5 | 50435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 50435
IDB code: 2.6 |  |  | SP(a) | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
1.1.2.5 | Coordination at the local level among MDAs and with CDCs/CBOs. | # of events held to facilitate coordination | P | 5 | 30939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 30939
IDB code: 2.7 |  |  | SP(a) | 33 | 23913.04 | 20 | 13703.7 |  | 0 |  | 0 |  | 0 |  | 0 | 53 | 37616.74
Component 2 - Labor Market Attachment and Employability
WBS Code | Output Definition | Unit Of Measure |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | EOP 2023 |  | Comments to team leader on any changed targets between Planned (P) and Suggested Planned Adjusted (a) [Do not exceed 50 words]
|  |  |  | Physical | Financial | Physical | Financial | Physical | Financial | Physical | Financial | Physical | Financial | Physical | Financial | Physical | Financial
1.2.1.1 | Technical assistance delivered on case management system for job training/placement | # of workshops | Planned (P) | 0 | 65217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65217
IDB code: 3.1 |  |  | Suggested Planned Adjusted P(a) | 10 | 5125 | 4 | 2593 |  | 0 |  | 0 |  | 0 |  | 0 | 14 | 7718
1.2.1.2 | Vocational training provided to targeted male and Female beneficiaries. | # of participants | P | 40 | 56522 | 0 | 83044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 139566
IDB code: 3.2-3.3 |  |  | SP(a) | 700 | 2755037 | 788 | 1744608 |  | 0 |  | 0 |  | 0 |  | 0 | 1488 | 4499645
1.2.1.3a | Support for access to tertiary education provided to male & female beneficiaries. | # of students attending tertiary school due to scholarships | P | 0 | 181914 | 0 | 136434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318348
IDB code: 3.4-3.5 |  |  | SP(a) | 30 | 157377 | 26 | 45642 |  | 0 |  | 0 |  | 0 |  | 0 | 56 | 203019
1.2.1.3b | Support for access to secondary education provided to male& female beneficiaries. | # of students attending secondary school due to scholarships | P | 0 | 130000 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
IDB code: 3.6-3.7 |  |  | SP(a) | 300 | 111462 | 300 | 62821 |  | 0 |  | 0 |  | 0 |  | 0 | 600 | 174283
1.2.1.4 | Remedial education provided in or outside communities, with integrated and life-skills training for male & Female participants. | # of participants | P | 300 | 1174684 | 0 | 447306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 1621990
IDB code: 3.8-3.9 |  |  | SP(a) | 300 | 675217 | 300 | 1070267 |  | 0 |  | 0 |  | 0 |  | 0 | 600 | 1745484
1.2.2.1 | Job-seeking, placement, and training services provided to female and male target beneficiaries. | # of participants who received job-seeking/placement services | P | 50 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 180000
IDB code:4.1 |  |  | SP(a) | 420 | 50857 | 330 | 8329 |  | 0 |  | 0 |  | 0 |  | 0 | 750 | 59186
1.2.2.2 | On-the-job or work orientation apprenticeship/internships provided for male youth, with emphasis on life skills and high-demand occupations. | # of participants placed in positions | P | 200 | 917566 | 0 | 427736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 1345302
IDB code: 4.2-4.3 |  |  | SP(a) | 430 | 764123 | 420 | 1003768 |  | 0 |  | 0 |  | 0 |  | 0 | 850 | 1767891
1.2.2.3 | Business development services (BDS) provided for female and male community residents in entrepreneurship; emphasis on high-demand sectors. | # of small business grants disbursed to community members | P | 2 | 20000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 30000
IDB code: 4.4 |  |  | SP(a) | 10 | 30246 | 1 | 40453 |  | 0 |  | 0 |  | 0 |  | 0 | 11 | 70699
Component 3 - Community Justice Services
WBS Code | Output Definition | Unit Of Measure |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | EOP 2023 |  | Explanation of variance between Planned (P) and Suggested Planned Adjusted (a) [Do not exceed 50 words]
|  |  |  | Physical | Financial | Physical | Financial | Physical | Financial | Physical | Financial | Physical | Financial | Physical | Financial | Physical | Financial
1.3.1.1a,c,d | Victim Services expanded and serving new female and male clients in target communities. | # of New clients in victim services | Planned (P) | 572 | 358000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 572 | 358000
IDB code: 5.1 |  |  | Suggested Planned Adjusted P(a) | 591 | 97218 | 557 | 187427.81 |  | 0 |  | 0 |  | 0 |  | 0 | 1148 | 284645.81
1.3.1.4 | Dispute Resolution Foundation services expanded and serving new female and male clients in target communities | # of new Clients | P | 1080 | 130550 | 1080 | 130550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160 | 261100
IDB code: 5.2 |  |  | SP(a) | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
1.3.1.4 | Dispute Resolution Foundation services expanded and conducting new mediation cases in target communities | # of new mediation cases in target commuities | P | 350 | 52174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 52174
IDB code: 5.3 |  |  | SP(a) | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
1.3.1.6c | Child Diversion pilot designed and operational in target communities | # of new participants in Child Diversion | P | 40 | 80000 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 160000
IDB code: 5.4 |  |  | SP(a) | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
1.3.1.5d | Restorative Justice services designed and operational in target communities. | # of new Restorative Justice cases in target communities | P | 70 | 54000 | 0 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 96000
IDB code: 5.5 |  |  | SP(a) | 123 | 6087 | 1500 | 15652.13 |  | 0 |  | 0 |  | 0 |  | 0 | 1623 | 21739.13
1.3.1.1g | Technical assistance and resources provided to Victim Services Division (female/male). | # of new TA sessions | P | 8 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 40000
IDB code: 5.6 |  |  | SP(a) | 0 | 0 | 4 | 10444.44 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | 10444.44
1.3.1.2c | Technical assistance and resources provided to Legal Aid Council (female/male) members/ same as Training of Police Officers & JPs on Legal Aid issues. | # of participants trained on Legal Aid Issues | P | 60 | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 120000
IDB code: 5.7 |  |  | SP(a) | 400 | 6140 | 300 | 14070.48 |  | 0 |  | 0 |  | 0 |  | 0 | 700 | 20210.48
1.3.1.3b,c | Technical assistance and resources provided to (female and male) Justices of the Peace service entities. | # of new JPs trained | P | 116 | 104000 | 0 | 104000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 208000
IDB code: 5.8 |  |  | SP(a) | 2470 | 171333 | 640 | 166724.59 |  | 0 |  | 0 |  | 0 |  | 0 | 3110 | 338057.59
1.3.1.4b | Technical assistance and resources provided to DRF for training police & justice (female and male) officials | # of police & court officials trained | P | 40 | 8000 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 16000
IDB code: 5.9 |  |  | SP(a) | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
1.3.1.5a | Technical assistance and resources provided to Restorative Justice Programme. | # of RJ officers & staff operating | P | 4 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8000
IDB code: 5.10 |  |  | SP(a) | 21 | 297444 | 11 | 295734 |  | 0 |  | 0 |  | 0 |  | 0 | 32 | 593178
1.3.1.6a | Technical assistance and resources provided to Child Diversion Programme. | # of court professionals trained | P | 40 | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 80000
IDB code: 5.11 |  |  | SP(a) | 0 | 7515 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 7515
1311f, 1315b, 1.3.1.6b | Training provided to volunteers (female/male) & facilitators (female/male), and leaders (female/male) in community justice services. | # of volunteers trained | P | 50 | 224000 | 0 | 224000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 448000
IDB code: 5.12 |  |  | SP(a) | 120 | 24154 | 120 | 17680.44 |  | 0 |  | 0 |  | 0 |  | 0 | 240 | 41834.44
1.3.1.7a | Technical assistance provided to the Social Justice Consortium (within MoJ) to support delivery of services and human rights compliance. | # ofworkshops given to government officials | P | 40 | 48756 | 0 | 48756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 97512
IDB code: 5.13 |  |  | SP(a) | 0 | 28727 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 28727
1.3.2.1 {1311e, 1312d, 1315c, 1316e} | Sensitization training and material provided to target community residents (female/male) and justice system officials (female/male) on community justice services. | # of events | P | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0
IDB code: 6.1 |  |  | SP(a) | 15 | 142167 | 16 | 238429.3 |  | 0 |  | 0 |  | 0 |  | 0 | 31 | 380596.3
1.3.2.2 {1311, 1312f, 1314c, 1315, 1316d} | 1322{1311, 1312f, 1314c, 1315, 1316d}) Service points expanded/renovated; mobile service units provided in target communities. | # of service points expanded / made mobile | P | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
IDB code: 6.2 |  |  | SP(a) | 13 | 145984 | 18 | 268997.47 |  | 0 |  | 0 |  | 0 |  | 0 | 31 | 414981.47
1323 {1318} | Outreach conducted (rights-based culture and awareness of services) in target communities. | # of campaigns | P | 1 | 80000 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 880000
IDB code: 6.3 |  |  | SP(a) | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0

## 3. Implementation Plan
CITIZEN SECURITY AND JUSTICE PROGRAMME 111
SECTION 3: Implementation Plan
PROJECT NUMBER: | 3191/OC-JA
JANUARY 2019 TO DECEMBER 2019
[6 empty] | TIMING |  |  | RESPONSIBILITIES | 2019
OUTPUT | TARGET | WBS Code | DELIVERABLE (= Contract name f. Proc Plan) | WORK PACKAGE | INDICATIVE | DURATION (# of cal days) | ESTIMATED START DATE | ESTIMATED END DATE | RESPONSIBLE PERSON | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1.1.1.1
0 | 100% | 1.1.1.1 | 536 Parents engaged; 18 monthly workshops conducted; 63 Community Parent Trainers engaged; 9 Parent Field Officers engaged
|  |  |  | CPTs Stipend | 136771 |  | 2019-01-01 | 2019-07-19 | Joudine, Melva, Orville, Mary | bar: 2019 Jan to 2019 Jul
|  | #REF! |  | PFOs Stipend | 31274 |  | 2019-01-01 | 2019-07-19 | Joudine, Melva, Orville, Mary | bar: 2019 Jan to 2019 Jul
|  | #REF! |  | Consultant Monthly Workshops | 14397 |  | 2019-01-01 | 2019-07-19 | Joudine, Melva, Orville, Mary | bar: 2019 Jan to 2019 Jul
|  |  | Parent Manual completed | Final payment for Review of Parenting Manual | 2704 |  | 2019-08-01 | 2019-08-01 | Joudine, Melva, Orville, Mary | bar: 2019 Aug
|  | #REF! |  | Monthly Meetings for CPTs/PFOs Venue & Refreshment | 16884 |  | 2019-01-01 | 2019-07-19 | Joudine, Melva, Orville, Mary | bar: 2019 Jan to 2019 Jul
|  | #REF! |  | Monthly Workshop for parents and CPTs/PFOs Venues | 15884 |  | 2019-01-01 | 2019-07-19 | Joudine, Melva, Orville, Mary | bar: 2019 Jan to 2019 Jul
|  | #REF! |  | Procure Stationery & Materials (monthly meetings) | 5870 |  | 2019-01-01 | 2019-07-19 | Joudine, Melva, Orville, Mary | bar: 2019 Jan to 2019 Jul
|  |  | Stipend Paid | CPT Travelling Stipend for Workshops/meetings | 383 |  | 2019-01-01 | 2019-07-19 | Joudine, Melva, Orville, Mary | bar: 2019 Jan to 2019 Jul
|  | #REF! |  | Transportation - Monthly Workshop | 7689 |  | 2019-01-01 | 2019-07-19 | Joudine, Melva, Orville, Mary | bar: 2019 Jan to 2019 Jul
|  | #REF! | Printing of 2000 Manuals & Work Books | Printing of manuals | 72995 |  | 2019-08-01 | 2019-09-01 | Joudine, Melva, Orville, Mary | bar: 2019 Aug to 2019 Sep
|  | #REF! | Plaques & Certificates printed | Printing of Plaques & Certificates | 5452 |  | 2019-09-01 | 2019-09-01 | Joudine, Melva, Orville, Mary | bar: 2019 Sep
|  | #REF! | 418 Parents and CPTs Certified | Procure Venue & Refreshment | 30667 |  | 2019-09-01 | 2019-09-01 | Joudine, Melva, Orville, Mary | bar: 2019 Sep
|  | #REF! |  | Procure Transportation for Graduation | 2963 |  | 2019-09-01 | 2019-09-01 | Joudine, Melva, Orville, Mary | bar: 2019 Sep
|  | #REF! |  | Procure Equipment and Decorations for Graduation | 2593 |  | 2019-09-01 | 2019-09-01 | Joudine, Melva, Orville, Mary | bar: 2019 Sep
|  |  | Control Parenting Group Activities (250 Parents 1 child + 20 staff) | Transportation & Entrance Fee | 17533 |  | 2019-11-01 | 2019-11-01 | Joudine, Melva, Orville, Mary | bar: 2019 Nov
|  |  |  | Procure Venue & Refreshment | 23378 |  | 2019-11-01 | 2019-11-01 | Joudine, Melva, Orville, Mary | bar: 2019 Nov
|  |  |  | Procure Materials, Equipment, Prizes | 5622 |  | 2019-11-01 | 2019-11-01 | Joudine, Melva, Orville, Mary | bar: 2019 Nov
|  |  | One Sentization session held | Sensitization Venue & Refreshment | 5711 |  | 2019-10-01 | 2019-10-01 | Joudine, Melva, Orville, Mary | bar: 2019 Oct
|  |  |  | Sensitization Transportation | 1904 |  | 2019-10-01 | 2019-10-01 | Joudine, Melva, Orville, Mary | bar: 2019 Oct
|  | #REF! | MOU with NPSC for training Workshops for Parenting Established | Inception Report reviewed, approved and payment made | 18640 |  | 2019-03-01 | 2019-03-01 | Joudine, Melva, Simeon, Mary | bar: 2019 Mar
|  |  |  | 1 Progress Report reviewed, approved and payment made | 35556 |  | 2019-10-01 | 2019-10-01 | Joudine, Melva, Orville, Mary | bar: 2019 Oct
|  |  |  | Draft/Final Reports reviewed, approved and payment made | 35556 |  | 2019-11-01 | 2019-11-01 | Joudine, Melva, Orville, Mary | bar: 2019 Nov
Sub Total Training courses provided to Community members on Parenting |  |  |  |  | 490426
Training courses provided to community members on healthy gender norms. |  | 1.1.1.1b | 144 MWAM outreach engagements conducted | Pay stipend to MWAM Members for Outreach Activities | 9363 |  | 2019-01-01 | 2019-12-19 | Patrice, Leroy, Orville, Mary, Joudene
|  | #REF! | International Mens Day | Payment Venue | 2100 |  | 2019-02-01 | 2019-02-01 | Patrice, Leroy, Simeon, Mary, Joudene | bar: 2019 Jan
|  |  |  | Live Outside Broadcast | 1778 |  | 2019-11-01 | 2019-11-01 | Patrice, Leroy, Orville, Mary, Joudene | bar: 2019 Nov
|  | #REF! | 1 MWAM Personal Development Workshops & Certified Training courses conducted | Payment made for: Venue, Refreshment and Honorarium for Facilitator/s | 1200 |  | 2019-11-19 | 2019-11-19 | Patrice, Leroy, Orville, Mary, Joudene | bar: 2019 Nov
|  |  | Subtotal MWAM |  | 14441
|  |  | PSU Consultants Paid | PMU Staff Consultants | 261779 |  | 2019-01-01 | 2019-12-01 | Orville, Mary
Total provided to Community members on healthy Gender Norms |  |  |  |  | 766646
Counselling / psycho-social support provided to victims/witnesses of violence (including domestic violence). | 100% | 1.1.1.2 | bar: 2019 Jan; 2019 Dec
|  |  | 170 beneficaries; 1,260 counselling sessions; 315 Drug Tests; 45 group sessions; 9 empowerment sessions | Substance Misuse Treatment |  |  | 2019-01-19 | 2019-12-19 | Joudine, Melva,Orville Mary
|  |  |  | Draft Final Report reviewed, approved and payment made | 27791 |  | 2019-03-01 | 2019-03-01 | bar: 2019 Mar
|  |  |  | Final report reviewed, approved and payment made | 13557 |  | 2019-05-01 | 2019-05-01 | bar: 2019 May
|  | #REF! | 150 beneficaries; 750 counselling sessions; 450 drug tests; 210 group sessions; 6 workshops | NEW MOU nception Report with NCDA reviewed, approved and payment made | 42585 |  | 2019-07-01 | 2019-07-01 | bar: 2019 Jul
|  |  |  | 1st. Progress Report reviewed, approved and payment made | 42585 |  | 2019-08-01 | 2019-08-01 | bar: 2019 Aug
|  |  |  | 2nd. Progress Report reviewed, approved and payment made | 63878 |  | 2019-09-01 | 2019-09-19 | bar: 2019 Sep
|  |  |  | Draft/Final Reports reviewed, approved and payment made | 63878 |  | 2019-12-19 | 2019-12-19 | bar: 2019 Dec
|  |  | 200 beneficaries; 1000 counselling sessions; 500 risk assessed beneficaries for sentization and psycho ed workshops; | Engage participants from referral received from VI |  |  | 2019-01-01 | 2019-12-01 | PSU Team, Regional Coordinators, CCMOs
|  |  | Lifeskills Training- 10 two days workshop | Procure Transportation | 7407 |  | 2019-09-01 | 2019-09-01 | PSU Team, Joudine, Orville, Mary | bar: 2019 Sep
|  |  |  | Procure materials for workshops | 1481 |  | 2019-09-01 | 2019-09-01 | PSU Team, Joudine, Orville, Mary | bar: 2019 Sep
|  | #REF! |  | Procure Refreshment & Venue | 22222 |  | 2019-09-01 | 2019-09-01 | PSU Team, Joudine, Orville, Mary | bar: 2019 Sep
|  |  | Approximate 20 Beneficiaries referred for counselling to specialists for 100 sessions | Review referral forms |  |  | 2019-01-01 | 2019-12-01 | PSU Team
|  |  |  | Conduct assessment of Client | 5722 |  | 2019-01-01 | 2019-12-01 | PSU Team, Joudine, Orville, Mary
|  |  |  | Refer Clients to Pre-Approved Consultants for Treatment |  |  | 2019-01-01 | 2019-12-01 | PSU Team
|  |  |  | Consultant Paid | 2374 |  | 2019-01-01 | 2019-12-01 | PSU Team, Joudine, Orville, Mary
|  |  | Capacity Building in Schools - 10 schools and approximate 1000 students and school personels | Team work with schools |  |  | 2019-01-01 | 2019-06-01 | PSU Team, | bar: 2019 Jan to 2019 Jun
|  | #REF! |  | Venue & Refreshment | 7940 |  | 2019-01-01 | 2019-09-19 | PSU Team, Joudine, Orville, Mary, | bar: 2019 Jan to 2019 Sep
|  | #REF! |  | Materials and Equipment for Training | 37037 |  | 2019-07-01 | 2019-09-19 | bar: 2019 Jul to 2019 Sep
|  | #REF! |  | Stationery and Therapeutic Materials | 37037 |  | 2019-07-01 | 2019-09-19 | bar: 2019 Jul to 2019 Sep
|  | #REF! | 12 Groups/approximately 96 beneficiaries in 120 group sessions | Provide refreshment | 2963 |  | 2019-09-01 | 2019-11-19 | Melva, Joudine, Orville Mary | bar: 2019 Sep to 2019 Nov
TOTAL Counselling/psycho-social support provided to victims/witnesses of violence (including domestic violence) |  |  |  |  | 378457
Violence interruption services provided (e.g. gang interruption). | 100% | 1.1.1.3
|  | 1113 | 48 Communities provided with violence interruption services in the KMA, Central Region & Western
|  |  | 22 communities in St. Catherine (10), Clarendon (5) and KMA (7) provided with violence interruption services | Report reviewed, approved and payments made - Final report | 3160 |  | 2019-01-01 | 2019-01-01 | simmonds' Mary, Robinson | bar: 2019 Jan
|  |  |  | Extension - final Report reviewed, approved and payment made | 136824 |  | 2019-02-01 | 2019-03-01 | simmonds' Mary, Robinson | bar: 2019 Feb to 2019 Mar
|  | #REF! | 26 communities in St. James (10), Westmoreland (10) and Hanover (6) provided with violence interruption services | Progress report reviewed, approved and payment made | 32741 |  | 2019-01-01 | 2019-02-01 | simmonds' Mary, Robinson | bar: 2019 Jan to 2019 Feb
|  |  |  | Final report reviewed, approved and payment made | 48533 |  | 2019-03-01 | 2019-03-01 | simmonds' Mary, Robinson | bar: 2019 Mar
|  |  | 22 communities in St. Catherine (10), Clarendon (5) and KMA (7) provided with violence interruption services | Negotiate and approve new contract for FY 2019/20 |  |  | 2019-03-01 | 2019-03-01 | PMI, Robinson, simmonds | bar: 2019 Mar
|  | #REF! |  | Inception report reviewed, approved and payment made | 228329 |  | 2019-05-01 | 2019-05-01 | Simmonds, Chaday, Bruce | bar: 2019 May
|  |  |  | Progress report reviewed, approved and payment made | 90104 |  | 2019-09-01 | 2019-09-01 | Simmonds, Chaday, Bruce | bar: 2019 Sep
|  |  |  | Draft final report reviewed, approved and payment made | 90104 |  | 2019-11-01 | 2019-11-01 | Simmonds, Chaday, Bruce | bar: 2019 Nov
|  |  | Violence interruption services continued - Western FY 2019/20 | Negotiate and approve new contract for FY 19/20 |  |  | 2019-03-01 | 2019-03-01 | PMI, Stephenson, Simmonds, Robinson, Bruce | bar: 2019 Mar
|  | #REF! |  | Inception Report submitted, reviewed, approved and payment made | 240936 |  | 2019-05-01 | 2019-05-01 | PMI, Stephenson, Simmonds, Bruce | bar: 2019 May
|  |  |  | Progress Report reviewed, approved and payment made | 95080 |  | 2019-09-01 | 2019-09-01 | PMI, Stephenson, Simmonds, Bruce | bar: 2019 Sep
|  |  |  | Draft final Report reviewed, approved and payment made | 95080 |  | 2019-11-01 | 2019-11-01 | PMI, Stephenson, Simmonds, Bruce | bar: 2019 Nov
|  |  |  | Final Report reviewed, approved and payment made |  |  | 2019-12-01 | 2019-12-01 | PMI, Stephenson, Simmonds, Bruce
|  | #REF! | Training of Violence Interupters | Procure Venue & Refreshment | 2963 |  | 2019-07-01 | 2019-07-01 | PMI, Stephenson, Simmonds, Bruce | bar: 2019 Jul
Total Violence Interruption Services provided (e.g gang interruption) |  |  |  |  | 1063854
| 100% | 1.1.1.4 | bar: 2019 Jan; 2019 Dec
Violence prevention and conflict resolution education and training provided in schools |  |  | DRF contract for school intervention programme 1200 student receive intervention for maladaptive behaviour, 1500 rap sessions in schools, 300 beneficiaries for summer programme, and sensitization sessions for 900 parents; Mediation Training for 200 Beneficiaries | Final Payments o existing Contract with DRF for School Suspension Programme Activities | 33562 |  | 2019-01-01 | 2019-03-01 | PSU, Jomie, Robinson, Bruce | bar: 2019 Jan to 2019 Mar
|  |  |  | Mediation Training | 38259 |  | 2019-03-01 | 2019-03-01 | PSU, Jomie, Robinson, Bruce | bar: 2019 Jul to 2019 Aug
|  |  |  | Payment of Staff Consultants | 47684 |  | 2019-01-01 | 2019-05-01 | PSU, Jomie, Robinson, Bruce | bar: 2019 Jan to 2019 May
Total Violence Prevention and Conflict Resolution Training in Schools |  |  |  |  | 119505 | [16 empty] | 0
Social marketing for awareness and attitude change to promote ‘culture of lawfulness’ (e.g. to address violent gender norms, anti-snitch culture). | 100% | 1.1.1.5
|  | #REF! | 1 3-month Multi-media Anti-Gang Campaign implemented | Place Advertisment for Consulting Firm | 593 |  | 2019-08-01 | 2019-08-01 | Leroy, Patrice, Joudine, Mary, Orville | bar: 2019 Aug
|  |  |  | Procure Firm to Design and Implement Anti-Gang Campaign |  |  | 2019-09-01 | 2019-09-01 | Leroy, Patrice, Joudine, Mary, Orville | bar: 2019 Sep
|  |  |  | Consulting Firm Paid | 148148 |  | 2019-09-01 | 2019-12-01 | Leroy, Patrice, Joudine, Mary, Orville | bar: 2019 Sep to 2019 Dec
| Sub-total Anti-Gang Campaign |  |  |  | 148741
|  | #REF! | 1 3-month Multi-media Gender Focused Women Stand Against Crime and Violence Campaign implemented | Place Advertisment for Consulting Firm | 593 |  | 2019-08-01 | 2019-08-01 | Leroy, Patrice, Joudine, Mary, Orville | bar: 2019 Aug
|  |  |  | Procure Firm to Design and Implement Gender Focused Campaign |  |  | 2019-09-01 | 2019-09-01 | Leroy, Patrice, Joudine, Mary, Orville | bar: 2019 Sep
|  |  |  | Consulting Firm Paid | 77037 |  | 2019-09-01 | 2019-12-01 | Leroy, Patrice, Joudine, Mary, Orville | bar: 2019 Sep to 2019 Dec
| Sub-total Gender Focused Campaign |  |  |  | 77630
|  | #REF! | Publicity Campaign to include: CSJP in 5; Advertorials, Think Tanks, Photography, Website Mgmt, Social Media Mgmt; Calendars | Final Payments on existing contract | 33400 |  | 2019-03-01 | 2019-08-01 | Patrice, Joudine, Mary, Orville | bar: 2019 Mar to 2019 Aug
|  | #REF! | 7 CSJP Peace Mobile Community Exit Fairs | CSJP Peace Mobile Payment for services to include: Refreshments, Entertainment, Live OB, Tents, Chairs, Flyers | 35556 |  | 2019-07-01 | 2019-12-01 | Patrice, Joudine, Mary, Orville | bar: 2019 Jul to 2019 Dec
|  | #REF! | 2000 Booklets | Procure Booklets | 11852 |  | 2019-09-01 | 2019-09-01 | Patrice, Joudine, Mary, Orville | bar: 2019 Sep
|  | #REF! | 31 Facilities Branded | Procure company to design and install wall branding at Community Facilities |  |  | 2019-01-01 | 2019-05-01 | Patrice, Joudine, Mary, Orville | bar: 2019 Jan to 2019 May
|  |  |  | Payment for services | 18475 |  | 2019-01-01 | 2019-11-01 | Patrice, Joudine, Mary, Orville
|  |  | 6 Community-based initiative put on by CBO/NGO/Benevolent Societies/MDA/Private Sector | Receive request from Partners |  |  | 2019-01-19 | 2019-03-01 | Leroy, Patrice & Partners | bar: 2019 Jan to 2019 Mar
|  | #REF! |  | Liaise with Partners re Planning and implementation of event |  |  | 2019-01-19 | 2019-03-01 | Leroy, Patrice & Partners | bar: 2019 Jan to 2019 Mar
|  |  |  | Implementation of event and payment of services | 798 |  | 2019-01-01 | 2019-05-01 | Patrice, Joudine, Simeon, Mary | bar: 2019 Jan to 2019 May
|  | #REF! | 1 TV Show - Let's Make Peace; 1 Susan Show Feature | TV Show conducted and payment made | 17778 |  | 2019-08-01 | 2019-10-01 | Patrice, Joudine, Mary, Orville | bar: 2019 Aug to 2019 Oct
|  | #REF! | Good News and Visibility Campaign - Press Conference on Transition | Venue, Refreshment & Décor | 3704 |  | 2019-08-01 | 2019-10-01 | Patrice, Joudine, Mary, Orville | bar: 2019 Aug to 2019 Oct
| Sub-total Good News and Visibility Campaigns |  |  |  | 121563
|  | #REF! |  | Renewal of Software for Laptop | 2362 |  | 2019-04-01 | 2019-07-01 | Patrice, Joudine, Simeon, Leighton | bar: 2019 Apr to 2019 Jul
|  |  | Social Norm Survey completed | Final Payment on Norms Survey | 18918 |  | 2019-03-01 | 2019-03-01 | Patrice, Joudine, Simeon, Mary | bar: 2019 Mar
| Sub-total Enhancing CSJP's Social Marketing Mechanism |  |  |  | 21280
|  | #REF! | 120 Life Skills session held; 450 at-risk youth engaged (150 per region) conducted | Life Skills and Intra Community Competition: Refreshments, Venue, Facilitators, mini football competitions | 87333 |  | 2019-03-19 | 2019-12-01 | Patrice, Adenike, Joudene, Simeon, Mary, Orville | bar: 2019 Mar to 2019 Dec
|  | #REF! | Implement Football component of Goals 4 Life/Peace | Football Component to include: Gears, Trophies, Medals, Referee, First Aid, Spot Prize, Field Preparation | 64025 |  | 2019-01-01 | 2019-12-01 | Patrice, Adenike, Joudene, Simeon, Mary, Orville
|  | #REF! | 1 Opening ceremony implemented for Goals 4 Life/Peace | Opening Ceremony: Refreshment, Entertainment, Décor, Live OB | 7407 |  | 2019-09-19 | 2019-09-19 | Patrice, Adenike, Joudene, Orville, Mary | bar: 2019 Sep
|  | #REF! | 2 Closing ceremonies implemented for Goals 4 Life/Peace | Closing Ceremony: Refreshment, Entertainment, Décor, Live OB | 22222 |  | 2019-12-01 | 2019-12-01 | Patrice, Adenike, Joudene, Orville, Mary | bar: 2019 Dec
| Sub-total Inter-regional Goals 4 Life |  |  |  | 180987
|  |  |  | Staff Consultants | 140623 |  | 2019-01-01 | 2019-12-01 | Orville, Mary, Consultants
Sub-total Social Marketing for awarness and attitude change |  |  |  |  | 690824
Community events to improve citizen-police relations conducted. |  | #REF! | Events implemented (under an MOU between CSJP/CSSB)
|  |  | Support to 1 Summer Camp Programmes | Support to CSSB Summer Camp Programme | 2963 |  | 2019-07-01 | 2019-07-01 | CSSB, SM Unit,Orville, Mary | bar: 2019 Jun
| Total Community Events to improve Citizen-Police relations |  |  |  | 2963
Crisis intervention activities condicted (including but not limited to violence and gang interruption) | 100% | 1.1.1.7
|  |  | 2 Interventions (50 Victims and families receive psychosocial intervention; Data mapping and Geospatial Analysis of major crimes and VRIs in 5 high risk communities) | Contract with VPA negotiated and sign |  |  | 2019-01-01 | 2019-01-01 | PSU Joudine Robinson, Bruce | bar: 2019 Jan
|  |  |  | Inception Report reviewed, approved, payment made | 43915 |  | 2019-02-01 | 2019-02-01 | PSU Joudine Robinson, Bruce | bar: 2019 Feb
|  |  |  | First Progress Report reviewed, approved, payment made | 53271 |  | 2019-05-01 | 2019-05-01 | PSU, Joudine, Orville, Bruce | bar: 2019 May
|  |  |  | Second Progress Report reviewed, approved, payment made | 52086 |  | 2019-07-01 | 2019-07-01 | PSU, Joudine, Orville, Bruce | bar: 2019 Jul
|  |  |  | Draft Final/Final Report reviewed, approved, payment made | 26043 |  | 2019-10-01 | 2019-10-01 | PSU, Joudine, Orville, Bruce | bar: 2019 Oct
| Total Crisis Intervention Activities |  |  |  | 175315
Training and technical assistance provided to female and male community leaders and residents to improve community governance capacity on needs assessment and strategic planning. |  | 1.1.2.1
|  | #REF! | Planned interventions under MOU for 39 CDCs : 34-Administrative Support 6-Advocacy Campaigns 30-Peace Building Through Sports, 20-Centre Management Support 34- MDA Consultations 27-Home work Programme & Summer Camps | MOU Established with CACs to Develop Advocacy Campaigns, Peace Building Through Sports, Centre Management Support &MDA Consultations, Home work Programme & Summer Camps | 139834 |  | 2019-01-01 | 2019-12-01
| Total: Training and Technical Assistance to establish or improve Community Governance Structure |  |  |  | 139834
Community infrastructure (situational crime prevention project and multi-purpose centres) built or renovated | 100% | 1.1.2.1
|  |  | One centre Renovated & Expanded (Gayle Multi-purpose Centre) | Substructure works, commence excavation to foundation, cast foundation, fabricate structural steel & install. | 66902 |  | 2019-02-19 | 2019-02-19 | Shawn, Contractor, Mary Joudine, Simeon | bar: 2019 Feb
|  |  |  | Superstructure works, blockwork , formwork to ground floor slab. Steelwork to GF slab . | 87541 |  | 2019-03-01 | 2019-03-01 | Shawn, Contractor, Mary Joudine, Simeon | bar: 2019 Mar
|  |  |  | Superstructure works, complete blockwork , formwork to ground floor slab. Steelwork to GF slab . | 63098 |  | 2019-05-01 | 2019-05-01 | Shawn, Contractor, Mary Joudine, Orville | bar: 2019 May
|  |  |  | Superstructure works, electrical & plumbing first fix, cast ground floor roof slab. | 104969 |  | 2019-06-01 | 2019-06-01 | Shawn, Contractor, Mary Joudine, Orville | bar: 2019 Jun
|  |  |  | Commence finishes, commence external works, drainage etc. | 116925 |  | 2019-08-01 | 2019-08-01 | Shawn, Contractor, Mary Joudine, Orville | bar: 2019 Aug
|  |  |  | Remove form from slab, complete rendering, electrical & plumbing second fix, continue external works. Install windows & doors. | 74074 |  | 2019-09-01 | 2019-09-01 | Shawn, Contractor, Mary Joudine, Orville | bar: 2019 Sep
|  |  |  | Complete all works and issue practical completion. | 72719 |  | 2019-10-01 | 2019-10-01 | Shawn, Contractor, Mary Joudine, Orville | bar: 2019 Oct
| Sub Total Multi purpose Centre |  |  |  | 586228 | bar: 2019 Jan
|  | #REF! | Gayle Multi-purpose Centre Furnished | Procure furnishing & Distribute to Gayle CMC | 25926 |  | 2019-08-01 | 2019-08-01 | Shawn, Contractor, Mary Joudine, Orville | bar: 2019 Aug
|  | #REF! | Maverley Centre Renovated | Award contract and commence project | 11111 |  | 2019-09-01 | 2019-09-01 | Shawn, Contractor, Mary Joudine, Orville | bar: 2019 Sep
|  |  |  | Internal retrofitting works to container & strengthen concrete building | 12593 |  | 2019-10-01 | 2019-10-01 | Shawn, Contractor, Mary Joudine, Orville | bar: 2019 Oct
|  |  |  | Complete works to concrete building & container building | 2402 |  | 2019-11-01 | 2019-11-01 | Shawn, Contractor, Mary Joudine, Orville | bar: 2019 Nov
|  |  | White Hall Containerized Multipurpose Centre Erection | Tender project, evaluate bids, procurement committee meeting & award cntract |  |  | 2019-01-01 | 2019-03-01 | Shawn, Contractor, Mary Joudine, Simeon | bar: 2019 Jan to 2019 Mar
|  | #REF! |  | Commence project erect container & modify | 37037 |  | 2019-09-01 | 2019-09-01 | Shawn, Contractor, Mary Joudine, Orville | bar: 2019 Sep
|  |  |  | Install partitioning, roof, ceiling, electrical & plumbing works | 37037 |  | 2019-10-01 | 2019-10-01 | Shawn, Contractor, Mary Joudine, Orville | bar: 2019 Oct
|  |  |  | Site infrastructure works completed | 38519 |  | 2019-11-01 | 2019-11-01 | Shawn, Contractor, Mary Joudine, Orville | bar: 2019 Nov
| Total Renovation & expansion of Centres |  |  |  | 164625
|  |  |  | Staff Consultants | 87694 |  | 2019-01-01 | 2019-12-01 | Mary, Simeon, consultants, Orville
| Grand Total Community Infrastructure built and renovated |  |  |  | 838547
Community gender-responsive safety plans developed with safety audits for vulnerable groups. |  | 1.1.2.1
|  | #REF! | 13 Safety Plans 9 Community Profiles completed | Procure consultant |  |  | 2019-04-01 | 2019-12-01 | Joudine, Danielle, Simeon, Mary | bar: 2019 Apr to 2019 Oct
|  |  |  | Inception Report from VPA & SDC | 22596 |  | 2019-11-01 | 2019-11-01 | bar: 2019 Nov
| Community Safety Plans developed, with implementation/advocacy Campaign |  |  |  | 22596
|  |  | Consultants ( Community Case Management Officers) | Staff Consultants Paid | 1272608 |  | 2019-01-01 | 2019-12-01 | Mary, Simeon, consultants, Orville
TOTAL COMPONENT 1 |  |  |  |  | 5471149
1.1.2.5
Vocational training provided to targeted male and Female beneficiaries. |  | WBS Code
|  |  | 788 Beneficaries received training | Stipend Paid | 1745395 |  | 2019-01-01 | 2019-12-01 | Denise, Simeon, Mary, Orville
| Total Vocational training provided to targeted benificaries |  |  |  | 1745395
Support for access to tertiary education provided to male & female beneficiaries. |  | 1.2.1.1
|  |  | Tuition support provided(26 Risk Assessed students) | Evaluation and selection of beneficiaries |  |  | 2019-01-01 | 2019-01-01 | Denise, RCMCs, CCMOS, Social Worker, | bar: 2019 Jan
|  |  | 26 participants | Payment of Fees & Stipend | 45642 |  | 2019-01-01 | 2019-05-01 | Denise, RCMCs, CCMOS, Social Worker, Simeon, Mary, Orville | bar: 2019 Jan to 2019 May
| Total Tertiary Support |  |  |  | 45642
Support for access to secondary education provided to male& female beneficiaries. |  | 1.2.1.2
|  |  | Tuition support provided for 300 Students | Evaluation and selection of beneficiaries |  |  | 2019-01-01 | 2019-09-01 | Denise, RCMCs, CCMOS, Social Worker, | bar: 2019 Jan
|  |  | 300 participants | Payment of stipend | 62819 |  | 2019-01-01 | 2019-12-01 | Denise, RCMCs, CCMOS, Social Worker, Simeon, Mary
| Total Secondary Education Support |  |  |  | 62819
| Total Scholarship support |  |  |  | 108461
Remedial education provided in or outside communities, with integrated and life-skills training for male & Female participants.
|  |  | 400 Beneficiaries trained (100 New & 300 Old) | Payment of stipend | 1071725 |  | 2019-01-01 | 2019-12-01 | Denise, RCMCs, CCMOS, Social Worker, Simeon, Mary
| Total Remedial Education provided, with integrated and life-skills training |  |  |  | 1071725
Technical assistance delivered on case management system for job training/placement |  | 1.2.1.3a
|  |  | 12 job readiness workshops | Identification and Selection of Beneficiaries |  |  |  |  | Karlene/CCMOs,
|  | #REF! |  | Procure Venue & Refreshment | 3886 |  | 2019-01-01 | 2019-12-01 | Karlene/CCMOs, Joudine, Simeon, Mary, Orville
|  | #REF! | 1 job expo conducted | Procure Venue & Refreshment | 4444 |  | 2019-07-01 | 2019-07-01 | Karlene, Joudine, Orville, Mary | bar: 2019 Jul
|  |  |  | Job Placement consultant | 39243 |  | 2019-01-01 | 2019-12-01 | Simeon, Mary, Consultants
| Total Job seeking placement, and training services provided to target beneficaries |  |  |  | 47573
On-the-job or work orientation apprenticeship/internships provided for male youth, with emphasis on life skills and high-demand occupations. |  | 1.2.1.4
|  |  | 70 interns placed | Stipend-EIP | 261772 |  | 2019-01-01 | 2019-12-01 | Karlene, Simeon, Mary, Orville
|  |  | 150 participants | On-the -Job Training-VST - stipend | 557357 |  | 2019-01-01 | 2019-12-01 | Denise, Simeon, MaryOrville
|  |  | 200 particaipants placed | Stipend-Summer Employment Paid | 81732 |  | 2019-07-01 | 2019-08-01 | Denise, , Mary, Orville | bar: 2019 Jul to 2019 Aug
|  | #REF! |  | Refreshment for Summer employment Orientation Sessions | 3704 |  | 2019-07-01 | 2019-07-01 | Denise, Mary, Joudine, Orville | bar: 2019 Jul
|  | #REF! |  | Stationery for Orientation Sessions | 370 |  | 2019-07-01 | 2019-07-01 | Denise, Mary, Joudine, Orville | bar: 2019 Jul
|  |  | 10 Summer Camps supported | Disbursement made | 99630 |  | 2019-07-01 | 2019-08-01 | Denise, , Mary, Orville | bar: 2019 Jul to 2019 Aug
| Total on-the-job training |  |  |  | 1004565
Business development services (BDS) provided for female and male community residents in entrepreneurship; emphasis on high-demand sectors. |  | 1.2.2.1
| 1.2.2.3 | #REF! | One Grant grated two beneficaries | Stipend for fish farmers for Business Development Training | 9071 |  | 2019-01-01 | 2019-12-01 | Orville, Joudene, Kevin, Chaday, Mary
|  |  |  | Business Development Training for fish farmers | 44 |  | 2019-07-01 | 2019-07-01 | Orville, Joudene, Kevin, Chaday, Mary | bar: 2019 Jul
|  | #REF! |  | Procurement of material and equipment | 15519 |  | 2019-07-01 | 2019-08-01 | Orville, Joudene, Kevin, Chaday, Mary | bar: 2019 Jul to 2019 Aug
|  |  |  | Stipend - Fish Growout | 2370 |  | 2019-08-01 | 2019-12-01 | Orville, Joudene, Kevin, Chaday, Mary | bar: 2019 Aug to 2019 Dec
|  |  |  | Inception Report from MICAF | 2222 |  | 2019-08-01 | 2019-08-01 | Orville, Joudene, Kevin, Chaday, Mary | bar: 2019 Aug
|  |  |  | First Pogress Report from MICAF | 2222 |  | 2019-08-01 | 2019-08-01 | Orville, Joudene, Kevin, Chaday, Mary | bar: 2019 Aug
| Total Business Development |  |  |  | 31448
|  |  |  | Staff Consultants (Regional Coordinators & CCMOs) | 109604 |  | 2019-01-01 | 2019-12-01 | Simeon, Mary, Consultants
TOTAL COMPONENT 2 |  |  |  |  | 4118771
Victim Services expanded and serving new female and male clients in target communities. |  | IDB code: 4.2-4.3
|  |  | Payment of rent and utilities for St. Catherine (Spanish Town)VSD Office | Procure and pay rent and utilities | 15429 |  | 2019-05-01 | 2019-12-01 | Bailey, Bruce,Jomie, Orville | bar: 2019 May to 2019 Dec
|  | #REF! | VSD office in Westmoreland renovated | Develop drawing & Bill of quantities. Prepare Procurement requisition & seek approval. |  |  | 2019-01-01 | 2019-03-01 | Bailey, Bruce,Jomie, Robinson | bar: 2019 Jan to 2019 Mar
|  |  |  | Tender project, evaluate bids, procurement committee meeting & award cntract |  |  | 2019-05-01 | 2019-06-01 | Shawn, Bailey, Contractor, Joudine, Orville | bar: 2019 May to 2019 Jun
|  |  |  | Commence project, Install partitioning etc. | 14259 |  | 2019-07-01 | 2019-07-01 | Shawn, Bailey, Contractor, Mary Joudine, Orville | bar: 2019 Jul
|  |  |  | Electrical & plumbing works, finishes | 7407 |  | 2019-08-01 | 2019-08-01 | Shawn, Bailey, Contractor, Mary Joudine, Orville | bar: 2019 Aug
|  |  |  | Complete all works, issue practical completion certificate | 7407 |  | 2019-09-01 | 2019-09-01 | Shawn, Bailey, Contractor, Mary Joudine, Orville | bar: 2019 Sep
|  |  |  | Defects liability period. Correct defects issue final completion cert, release retention & close project | 1530 |  | 2019-12-01 | 2019-12-01 | Shawn, Bailey, Contractor, Mary Joudine, Orville | bar: 2019 Dec
|  | #REF! | Overton Plaza St. James office Retrofitted & renovated | Develop drawing & Bill of quantities. Prepare Procurement requisition & seek approval. |  |  | 2019-02-01 | 2019-06-19 | Bailey, Brooks, Jomie, Orville | bar: 2019 Feb to 2019 Jun
|  |  |  | Tender project, evaluate bids, procurement committee meeting & award Contract |  |  | 2019-07-19 | 2019-08-19 | Bailey, Brooks, Jomie, Orville, Procurment Committee | bar: 2019 Jul to 2019 Aug
|  |  |  | Commence project, Install partitioning etc. | 9815 |  | 2019-09-01 | 2019-09-01 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Sep
|  |  |  | Electrical & plumbing, doors, complete finishes | 8889 |  | 2019-10-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Oct
|  |  |  | Finishing to walls floors etc. Electrical fixtures. Finish all works & issue practical completion | 5926 |  | 2019-11-19 | 2019-11-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Nov
|  |  |  | Defects liability period. Correct defects issue final completion cert, release retention & close project |  |  | 2019-12-19 | 2020-02-01 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Dec
|  | #REF! | VSD Spanish Town Road Office Renovated | Install security system | 4926 |  | 2019-09-01 | 2019-09-01 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Sep
|  |  |  | Finishes to walls & floor, complete all works, issue practical completion certificate | 1535 |  | 2019-02-01 | 2019-02-01 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Feb
|  |  |  | Defects liability period. Correct defects issue final completion cert, release retention & close project | 259 |  | 2019-10-01 | 2019-10-01 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Oct
|  | #REF! | VSD Spanish Town Road Office Renovated | Formulate project,Tender project, evaluate bids, procurement committee meeting, IDB No objection & award cntract |  |  | 2019-07-19 | 2019-09-19 | Bailey, Brooks, Jomie, Orville, | bar: 2019 Jul to 2019 Sep
|  |  |  | Commence project, install partitions | 13333 |  | 2019-10-01 | 2019-10-01 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Oct
|  |  |  | Install electrical, plumbing, doors etc | 7407 |  | 2019-11-01 | 2019-11-01 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Nov
|  |  |  | Finishing to walls floors etc. Electrical fixtures. Issue Practical completion | 7407 |  | 2019-12-19 | 2019-12-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Dec
|  | #REF! | VSD St Mary Office Renovated | Commence project, install partitions | 7407 |  | 2019-09-19 | 2019-09-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Sep
|  |  |  | Install electrical, plumbing, doors etc | 14815 |  | 2019-10-01 | 2019-10-01 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Oct
|  |  |  | Finishing to walls floors etc. Electrical fixtures. Issue Practical completion | 11111 |  | 2019-11-01 | 2019-11-01 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Nov
|  | #REF! | Procure office furniture and equipment, including IT equipment. | Procure office furniture and equipment, including IT equipment | 47144 |  | 2019-03-19 | 2019-08-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Mar to 2019 Aug
|  |  | Provide 96 emergency grants for victims of crimes. | Provide emergency grants (for victims of crime) | 72449 |  | 2019-01-01 | 2019-12-19 | Bailey, Brooks, Jomie, Orville, Mary
|  |  | Support 120 volunteers. | Payment of stipend to volunteers | 16486 |  | 2019-01-01 | 2019-12-19 | Bailey, Brooks, Jomie, Orville, Mary
|  |  | Authenticating and norming VSD's Missing Children Risk Assessment Tool (MCRAT). | Submission, review, approval of Mid-term Report | 12167 |  | 2019-03-19 | 2019-03-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Mar
|  |  |  | Submission, review of draft final and Final Assessment Tool | 22222 |  | 2019-08-19 | 2019-08-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Aug
Speial Intervention Projects - Cutural Resocialisation
Conduct 4 x1-day grief and trauma session conducted (150 beneficiaries).
|  | #REF! |  | Procure venue and refreshments | 23705 |  | 2019-02-19 | 2019-12-01 | Bailey, Brooks, Jomie, Orville, Mary
|  | #REF! |  | Procure therapeutic tools | 14370 |  | 2019-01-01 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Jan to 2019 Oct
|  | #REF! |  | Procure transportation | 4667 |  | 2019-09-19 | 2019-11-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Sep to 2019 Nov
|  | #REF! |  | Procure stationery | 4778 |  | 2019-08-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Sep to 2019 Nov
|  | #REF! |  | Procure T/ Polo Shirts | 7778 |  | 2019-08-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Sep to 2019 Nov
|  | #REF! |  | Procure medical personnel | 1111 |  | 2019-09-19 | 2019-11-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Sep to 2019 Nov
|  | #REF! |  | Procure facilitators | 1778 |  | 2019-09-19 | 2019-11-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Sep to 2019 Nov
Special Intervention Programmes for Schools
Conduct school-based intervention workshop for 100 beneficiaries : 50 children, 50 parents,
|  | #REF! |  | Procure refreshments | 5057 |  | 2019-01-01 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Jan to 2019 Oct
|  | #REF! |  | procure therapeutic tools | 8921 |  | 2019-03-19 | 2019-09-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Mar to 2019 Sep
|  | #REF! |  | Procure resource material and stationery | 1630 |  | 2019-09-19 | 2019-09-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Sep
|  | #REF! |  | Procure facilitators | 1481 |  | 2019-10-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Oct
|  | #REF! |  | Provide graduation certificates | 74 |  | 2019-09-19 | 2019-09-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Sep
|  | #REF! |  | Reinforcement facilitators | 889 |  | 2019-10-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Oct
Overcomers -in-Action Programme
30 sexually abused female children (teenagers) benefitting from grief therapy ( 4 x 6-day sessions conducted).
|  | #REF! |  | Procure venue & refreshments | 8768 |  | 2019-02-19 | 2019-09-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Feb to 2019 Sep
|  |  |  | Payment of transportation stipend | 778 |  | 2019-08-19 | 2019-09-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Aug to 2019 Sep
|  | #REF! |  | Procure facilitators | 444 |  | 2019-08-19 | 2019-09-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Aug to 2019 Sep
|  | #REF! |  | Procure resource material and stationery | 889 |  | 2019-07-19 | 2019-08-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Jul to 2019 Aug
|  | #REF! |  | procure therapeutic tools | 2444 |  | 2019-07-19 | 2019-08-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Jul to 2019 Aug
|  | #REF! | Overcomers-in-Action Graduation held | Procure venue and refreshments | 3259 |  | 2019-10-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Oct
|  | #REF! |  | Certificates and tokens | 1222 |  | 2019-10-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Oct
|  | #REF! | Public awareness materials purchased ( banners, brochures and other paraphernelia). | Procure brochures, paraphernelia, etc. | 18640 |  | 2019-03-19 | 2019-11-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Mar to 2019 Oct
Technical Assistance and Resources Provided to Victim Services Division [Tarining of Male and Female Court Officials, Police Officers, and Other First Responders]. | bar: 2019 Mar to 2019 Oct
Conduct 1 x 2 Day workshop ( 50 beneficiares)
|  | #REF! |  | Procure venue & refreshments | 5778 |  | 2019-10-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Oct
|  | #REF! |  | Procure stationery | 444 |  | 2019-09-19 | 2019-09-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Sep
|  | #REF! |  | Procure facilitators | 889 |  | 2019-10-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Oct
West Kingston: Special Intervention Programmes for Schools
Conduct school-based intervention workshops for 100 beneficiaries : 50 children, 50 parents, covering 6 sessions.
|  | #REF! |  | Procure refreshments | 3815 |  | 2019-11-01 | 2019-11-01 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Nov
|  | #REF! |  | procure therapeutic tools | 2444 |  | 2019-10-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Sep
|  | #REF! |  | Procure resource material and stationery | 1630 |  | 2019-10-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Sep
|  | #REF! |  | Procure facilitators | 1481 |  | 2019-11-01 | 2019-11-01 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Nov
|  | #REF! |  | Provide graduation certificates | 74 |  | 2019-10-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Oct
|  | #REF! |  | Reinforcement facilitators | 889 |  | 2019-11-19 | 2019-11-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Nov
Overcomers -in-Action Programme (West Kingston) | bar: 2019 Nov
15 sexually abused female children (teenagers) benefitting from grief therapy ( 1 x 6-day sessions conducted).
|  | #REF! |  | Procure venue | 519 |  | 2019-10-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Oct
|  | #REF! |  | Procure refreshments | 1667 |  | 2019-10-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Oct
|  |  |  | Payment of transportation stipend | 389 |  | 2019-10-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Oct
|  | #REF! |  | Procure facilitators | 222 |  | 2019-10-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Oct
|  | #REF! |  | Procure resource material and stationery | 444 |  | 2019-09-19 | 2019-09-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Sep
|  | #REF! |  | procure therapeutic tools | 1222 |  | 2019-09-19 | 2019-09-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Sep
|  | #REF! | Graduation Ceremony for Overcomers-in-Action Programme conducted. | Procure venue and refreshments Graduation | 1667 |  | 2019-10-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Oct
|  | #REF! |  | Certificates and tokens | 611 |  | 2019-09-19 | 2019-09-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Sep
|  |  | Public Awareness Programme [West Kingston: Public Awareness Campaign - Production of Animation films for healing of Tivoli incursion victims]. | production of animation film | 5333 |  | 2019-06-19 | 2019-09-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Jun to 2019 Sep
|  | #REF! | Conduct 2 quarterly stakeholder consultations | Procure venue and refreshments | 5259 |  | 2019-11-19 | 2019-11-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Nov
|  | #REF! |  | procure stationery | 296 |  | 2019-10-19 | 2019-10-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Oct
|  | #REF! |  | procure facilitators | 444 |  | 2019-11-19 | 2019-11-19 | Bailey, Brooks, Jomie, Orville, Mary | bar: 2019 Nov
| Total Victim Services expanded snd serving new female and male clinents in target communities |  |  |  | 457530 | [16 empty] | -4
Technical assistance and resources provided to Legal Aid Council (female/male) members/ same as Training of Police Officers & JPs on Legal Aid issues. |  | 1.3.1.6c
|  | #REF! | 4 x1 day workshops conducted for Police Officers & JPs (300 beneficiaries) | Procure refreshments | 7140 |  | 2019-05-19 | 2019-11-19 | Faulkner, MoJ, Jomie, Bruce, Simmonds | bar: 2019 May to 2019 Nov
|  | #REF! |  | Procure venue | 2613 |  | 2019-03-19 | 2019-11-19 | Faulkner, MoJ, Jomie, Bruce, Simmonds | bar: 2019 Mar to 2019 Nov
|  | #REF! |  | Procure facilitators | 3910 |  | 2019-08-19 | 2019-11-19 | Faulkner, MoJ, Jomie, Bruce, Simmonds | bar: 2019 Aug to 2019 Nov
|  | #REF! |  | Procure stationery | 1667 |  | 2019-08-19 | 2019-11-19 | Faulkner, MoJ, Jomie, Bruce, Simmonds | bar: 2019 Aug to 2019 Nov
|  | #REF! | Mobile Unit 50 visits to Communities | Procurement of Venue for Consultations | 6667 |  | 2019-07-19 | 2019-12-19 | Faulkner, MoJ, Jomie, Bruce, Simmonds | bar: 2019 Jul to 2019 Dec
|  |  |  | Toll Fees | 3877 |  | 2019-05-19 | 2019-12-19 | Faulkner, MoJ, Jomie, Bruce, Simmonds | bar: 2019 May to 2019 Dec
|  |  |  | Registration and fitness | 333 |  | 2019-07-19 | 2019-07-19 | Faulkner, MoJ, Jomie, Bruce, Simmonds | bar: 2019 Jul to 2019 Dec
|  | #REF! |  | Salary for driver | 8495 |  | 2019-01-01 | 2019-12-19 | Faulkner, MoJ, Jomie, Bruce, Simmonds
|  |  |  | Maintenance of mobile unit | 1852 |  | 2019-07-19 | 2019-12-19 | Faulkner, MoJ, Jomie, Bruce, Simmonds | bar: 2019 Jul to 2019 Dec
|  |  |  | Gasoline/diesel for mobile unit | 19597 |  | 2019-02-19 | 2019-12-19 | Faulkner, MoJ, Jomie, Bruce, Simmonds
|  |  | One (1) Legal Consultant | Consultant Paid | 18839 |  | 2019-01-01 | 2019-12-19 | Faulkner, MoJ, Jomie, Bruce, Simmonds
|  | #REF! | 1 new Legal Consultants hired | Consultant Paid | 17658 |  | 2019-07-19 | 2019-12-19 | Faulkner, MoJ, Jomie, Bruce, Simmonds | bar: 2019 Jul to 2019 Dec
|  |  | One (1) Legal Research Consultant hired | Consultant Paid | 15072 |  | 2019-01-01 | 2019-12-19 | Faulkner, MoJ, Jomie, Bruce, Simmonds
|  |  | 4 fairs conducted ( 100 beneficiaries) | Procure tables, chairs, tents, and portable toilets, etc., | 2222 |  | 2019-06-19 | 2019-12-01 | Faulkner, MoJ, Jomie, Bruce, Simmonds | bar: 2019 Jun to 2019 Dec
|  |  |  | Procure refreshments | 16418 |  | 2019-08-19 | 2019-12-01 | Faulkner, MoJ, Jomie, Bruce, Simmonds | bar: 2019 Aug to 2019 Dec
|  |  |  | Procure resource materials | 1296 |  | 2019-08-19 | 2019-12-01 | Faulkner, MoJ, Jomie, Bruce, Simmonds | bar: 2019 Aug to 2019 Dec
|  |  |  | Procure PA system | 444 |  | 2019-08-19 | 2019-12-01 | Faulkner, MoJ, Jomie, Bruce, Simmonds | bar: 2019 Aug to 2019 Dec
|  |  |  | Procure Generator | 1296 |  | 2019-08-19 | 2019-12-01 | Faulkner, MoJ, Jomie, Bruce, Simmonds | bar: 2019 Aug to 2019 Dec
|  |  |  | Media Broadcast | 3333 |  | 2019-08-19 | 2019-12-01 | Faulkner, MoJ, Jomie, Bruce, Simmonds | bar: 2019 Aug to 2019 Dec
|  |  |  | Town Crier | 926 |  | 2019-08-19 | 2019-12-01 | Faulkner, MoJ, Jomie, Bruce, Simmonds | bar: 2019 Aug to 2019 Dec
|  |  |  | Security (overnight) | 741 |  | 2019-08-19 | 2019-12-01 | Faulkner, MoJ, Jomie, Bruce, Simmonds | bar: 2019 Aug to 2019 Dec
| Total Legal Aid Council |  |  |  | 134396
Technical assistance and resources provided to DRF for training police & justice (female and male) officials |  | 1.3.1.5d
|  | #REF! | Conduct 2 one day workshops; 25 beneficaries | Procure consultant to review exisitng JP manual and develop trainer's guide. | 5185 |  | 2019-08-19 | 2019-08-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Aug
|  |  |  | Proof-reading, formating, and layout of manuals, and Trainer's Guide. | 2222 |  | 2019-10-19 | 2019-10-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Oct
|  |  |  | Printing of JP Manuals. | 17778 |  | 2019-11-19 | 2019-11-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Nov
|  |  |  | Conduct training workshop in the use of the JP Manual (training of the Trainers). | 2963 |  | 2019-10-19 | 2019-11-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Oct to 2019 Nov
|  | #REF! | Conduct 5x3 days Qualifying Basic Training workshops 280 JPs trained; 40 per cohort). | Procure venue and refreshments | 42230 |  | 2019-01-01 | 2019-12-19 | MOJ, Jomie, Simmonds, Bruce
|  | #REF! |  | Procure stationery and course material | 2593 |  | 2019-07-19 | 2019-12-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Jul to 2019 Dec
|  | #REF! |  | Procure facilitators | 3333 |  | 2019-07-19 | 2019-12-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Jul to 2019 Dec
|  | #REF! |  | Accomodation for facilitators | 12369 |  | 2019-02-19 | 2019-12-19 | MOJ, Jomie, Simmonds, Bruce
Advanced Training of Male and Female JPs: Lay Magistrates' Court].
Conduct 2x6 day Advance Training workshops conducted ( 150 JPs trained; 50 per cohort).
|  | #REF! |  | Procure venue and refreshments | 10012 |  | 2019-01-19 | 2019-08-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Jan to 2019 Aug
|  | #REF! |  | Procure stationery and course material | 1037 |  | 2019-08-19 | 2019-08-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Aug
|  | #REF! |  | Procure facilitators | 342 |  | 2019-08-19 | 2019-08-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Aug
|  | #REF! |  | Procure transportation | 2222 |  | 2019-08-19 | 2019-08-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Aug
|  | #REF! |  | Accomodation for facilitators | 4658 |  | 2019-08-19 | 2019-08-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Aug
Advanced Training of Male and Female JPs: Children's Court, Drug Court].
Conduct 2x3 day Advanced Training workshops (80 JPs trained; 40 per cohort).
|  | #REF! |  | Procure venue and refreshments | 4468 |  | 2019-03-19 | 2019-08-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Mar to 2019 Aug
|  | #REF! |  | Procure stationery and course material | 356 |  | 2019-05-01 | 2019-08-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 May to 2019 Aug
|  | #REF! |  | Procure facilitators | 1111 |  | 2019-08-19 | 2019-08-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Aug
|  | #REF! |  | Procure transportation | 259 |  | 2019-08-19 | 2019-08-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Aug
|  | #REF! |  | Accomodation for facilitators | 2329 |  | 2019-08-19 | 2019-08-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Aug
Advanced Training of Male and Female JPs: Mediation].
Conduct 8x5 day workshops (200 JPs; 25 per workshop).
|  | #REF! |  | Procure venue and refreshments | 33889 |  | 2019-07-19 | 2019-10-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Jul to 2019 Oct
|  | #REF! |  | Accomodation for facilitators | 13973 |  | 2019-08-19 | 2019-10-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Aug to 2019 Oct
|  |  | Conduct 5 parish consultations/sensitizations (1,250 participants) | Conduct parish consultations/sensitizations | 19837 |  | 2019-04-19 | 2019-12-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Apr to 2019 Dec
Advanced Training of Male and Female JPs: Spirit Licence].
Conduct 2x2 day workshops (80 JPs trained; 40 per cohort).
|  | #REF! |  | Procure venue and refreshments | 6167 |  | 2019-08-19 | 2019-08-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Aug
|  | #REF! |  | Procure stationery and course material | 356 |  | 2019-08-19 | 2019-08-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Aug
|  | #REF! |  | Procure facilittaors | 1111 |  | 2019-08-19 | 2019-08-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Aug
|  | #REF! |  | procure transportation | 259 |  | 2019-08-19 | 2019-08-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Aug
|  | #REF! |  | Accomodation for facilitators | 1553 |  | 2019-08-19 | 2019-08-19 | MOJ, Jomie, Simmonds, Bruce | bar: 2019 Aug
|  | #REF! | Mediation Pilot Project conducted | Conduct Mediation Pilot Project | 51528 |  | 2019-01-01 | 2019-12-19 | MOJ, Jomie, Simmonds, Bruce
| Total Jamaica Training Institute |  |  |  | 244140
Technical assistance and resources provided to Restorative Justice Programme. |  | 1.3.1.2c
|  |  | Service Points Expanded/Renovated/Mobile Service Units Provided in Target Communities. | Payment of Rent | 41157 |  | 2019-01-01 | 2019-06-19 | Whyte, MOJ, Jomie, Simmonds, Bruce
|  | #REF! | Service Points Expanded/Renovated/Mobile Service Units Provided in Target Communities . | Develop drawing & Bill of quantities. Prepare Procurement requisition & seek approval. |  |  | 2019-01-01 | 2019-01-02 | Whyte, MOJ, Jomie, Simmonds, Bruce | bar: 2019 Jan
|  |  |  | Tender project, evaluate bids, procurement committee meeting & award cntract |  |  | 2019-02-01 | 2019-02-01 | Whyte, MOJ, Jomie, Simmonds, Bruce | bar: 2019 Feb
|  |  |  | Commence project, Install electrical points, finishes to walls floors, plumbing works etc and complete project. | 18677 |  | 2019-08-19 | 2019-08-19 | Whyte, MOJ, Jomie, Simmonds, Bruce | bar: 2019 Aug
|  |  |  | Obtain GEI approval, Submit application to JPS, await connection to building & issue practical completion certificate upon JPS connection. | 13333 |  | 2019-09-19 | 2019-09-19 | Whyte, MOJ, Jomie, Simmonds, Bruce | bar: 2019 Sep
|  |  |  | Defects liability period. Correct defects issue final completion cert, release retention & close project | 1685 |  | 2019-12-19 | 2019-12-19 | Whyte, MOJ, Jomie, Simmonds, Bruce | bar: 2019 Dec
|  |  | Equipment purchased | Procure Equipment | 18989 |  | 2019-02-19 | 2019-09-19 | Whyte, MOJ, Jomie, Simmonds, Bruce | bar: 2019 Sep
|  |  | Maintenance of Furniture and Equipment. | Maintainance of office equipment and furniture | 2963 |  | 2019-07-19 | 2019-10-19 | Whyte, MOJ, Jomie, Simmonds, Bruce | bar: 2019 Apr to 2019 Nov
|  |  | Payment of Utility Bills. | Payment of utility bills. | 11489 |  | 2019-01-01 | 2019-12-19 | Whyte, MOJ, Jomie, Simmonds, Bruce
1315b: Training (Restorative Practices workshops for School Administrators, Nurses, JPs, Police, Probation Officers , and Community Leaders) )
|  |  | Conduct 30 two-day workshops (1,500 beneficiaries) | Procure venue and refreshments | 37093 |  | 2019-03-19 | 2019-06-19 | Whyte, MOJ, Jomie, Simmonds, Bruce | bar: 2019 Mar to 2019 Jun
1315c: Sensitization for Online Training Candidates Provided to Male and Female Volunteers, Facilitators, and Leaders in Community Justice Services (Training Workshops for RJ Volunteers).
|  |  | Conduct 1 one-day workshops (100 beneficiaries). | Procure venue and refreshments | 1852 |  | 2019-09-19 | 2019-09-19 | Whyte, MOJ, Jomie, Simmonds, Bruce | bar: 2019 Sep
Training provided to male and female volunteers, facilitators, and leaders in community justice services (Graduation Ceremony for RJ volunteers).
|  |  | Conduct Graduation Ceremony for RJ volunteers (50 beneficiaries and Award ceremony for existing RJ facilitators | Procure venue and refreshments | 3704 |  | 2019-12-19 | 2019-12-19 | Whyte, MOJ, Jomie, Simmonds, Bruce | bar: 2019 Dec
|  | #REF! |  | Print Graduation Certificates and Awards | 2623 |  | 2019-12-19 | 2019-12-19 | Whyte, MOJ, Jomie, Simmonds, Bruce | bar: 2019 Dec
|  |  | Training provided to male and female volunteers, facilitators, and leaders in community justice services(1 Staff Development & Educational Workshop conducted 35 beneficaries). | Procure venue and refreshments | 2222 |  | 2019-10-19 | 2019-10-19 | bar: 2019 Oct
|  |  |  | Stationery and resource materials | 566 |  | 2019-09-19 | 2019-09-19 | Whyte, MOJ, Jomie, Simmonds, Bruce | bar: 2019 Sep
|  |  | Sensitization Training and Materials Provided to Justice Officials and Male and Female Residents on Community Justice Services (Conduct 300 sensitizations sessions ( 4800 beneficiaries) | Procure venue & Refreshment | 25064 |  | 2019-01-19 | 2019-12-01 | Whyte, MOJ, Jomie, Simmonds, Bruce
|  |  | Restorative Justice services designed and operational in target communities (Conduct 1500 RJ Case Conferences.) | stipend to facilitators | 12490 |  | 2019-01-19 | 2019-12-01 | Whyte, MOJ, Jomie, Simmonds, Bruce
|  |  |  | procure refreshment | 3192 |  | 2019-01-01 | 2019-12-19 | Whyte, MOJ, Jomie, Simmonds, Bruce
|  | #REF! | Restorative Justice Week | Procure venue & Refreshment | 39182 |  | 2019-01-01 | 2019-05-01 | Whyte, MOJ, Jomie, Simmonds, Bruce | bar: 2019 Jan to 2019 May
|  | #REF! | Procurement of Stationery, Office Supplies, and Paraphenelia. | Procure stationery, office supplies, and RJ paraphenelia | 11847 |  | 2019-01-19 | 2019-10-19 | Whyte/MoJ/Jomie/Bruce/Robinson | bar: 2019 Jan to 2019 Oct
|  |  | Payment of Consultancy fees for staff of RJ Unit | Pay consultancy fees for existing staff of the RJ Centres. | 385377 |  | 2019-01-01 | 2019-12-19 | Whyte/MoJ/Jomie/Bruce/Robinson
| Sub-total Restorative Justice Unit |  |  |  | 633505
Technical assistance and resources provided to Child Diversion Programme. |  | 1.3.1.3b,c
|  | #REF! | 1316: Conduct National Oversight Commitee meetings | Procure Venue and refreshments for participants | 667 |  | 2019-09-19 | 2019-12-19 | Whyte/MoJ/Jomie/Bruce/Simmonds | bar: 2019 Sep to 2019 Dec
|  | #REF! | 1316: Monthly Meetings of Child Diversion Committee Members | Procure Venue and refreshments for participants | 9533 |  | 2019-07-19 | 2019-12-19 | Whyte/MoJ/Jomie/Bruce/Simmonds | bar: 2019 Jul to 2019 Dec
|  | #REF! | 1316: Conduct Child Diversion Coordination Meetings | Procure Venue and refreshments for participants | 1852 |  | 2019-08-19 | 2019-12-19 | Whyte/MoJ/Jomie/Bruce/Simmonds | bar: 2019 Aug to 2019 Dec
|  | #REF! | 1316: Operationalise Child Diversion office space for 14 offices | Procure Ink and toners, papers, etc | 11852 |  | 2019-07-19 | 2019-10-19 | Whyte/MoJ/Jomie/Bruce/Simmonds | bar: 2019 Jul to 2019 Oct
|  | #REF! |  | Procure refridgerators, garbage bins, kettles office equipment etc | 48673 |  | 2019-08-19 | 2019-08-19 | Whyte/MoJ/Jomie/Bruce/Simmonds | bar: 2019 Aug
|  | #REF! |  | Procure LCD Projectors, screen, microphones and speakers | 2597 |  | 2019-08-19 | 2019-08-19 | Whyte/MoJ/Jomie/Bruce/Simmonds | bar: 2019 Aug
|  | #REF! |  | Procure PBX Phones (14 offices equipped) | 2074 |  | 2019-08-19 | 2019-08-19 | Whyte/MoJ/Jomie/Bruce/Simmonds | bar: 2019 Aug
|  |  |  | Payment of Rent, Utilities, and Maintenance | 23932 |  | 2019-01-19 | 2019-12-01 | Whyte/MoJ/Jomie/Bruce/Simmonds
|  |  | 1316: Procure Child Diversion officers. | Procure nine Child Diversion officers for the parishes of, St. Andrew Trelawny, Portland Clarendon, St. Catherine, Hanover and St. James, Westmoreland, St. Mary, | 75997 |  | 2019-08-19 | 2019-12-01 | Whyte/MoJ/Jomie/Bruce/Simmonds | bar: 2019 Aug
|  | #REF! | 1316: Procure Psychologist | One Psychologist contracted. | 12022 |  | 2019-07-19 | 2019-12-01 | Whyte/MoJ/Jomie/Bruce/Simmonds | bar: 2019 Jul to 2019 Dec
|  | #REF! | 1316: Procure Secretary/ Administrative Assistant - Child Diversion Office (AM3) | 1 Secretary contracted | 5333 |  | 2019-07-19 | 2019-12-01 | Whyte/MoJ/Jomie/Bruce/Simmonds | bar: 2019 Jul to 2019 Dec
|  | #REF! | 1316: Procure Child Diversion Coordinator and Staff | Procure 1 Child Diversion Coordinator payment of Consultancy Fees | 162435 |  | 2019-07-19 | 2019-12-01 | Whyte/MoJ/Jomie/Bruce/Simmonds | bar: 2019 Jul to 2019 Dec
|  | #REF! | 1316: Public Awareness Programme | Procure Billboards, Brochures, fliers and Public Service Announcements and other paraphernalia | 111111 |  | 2019-08-19 | 2019-10-19 | Whyte/MoJ/Jomie/Bruce/Simmonds | bar: 2019 Aug to 2019 Oct
| Sub-total Child Diversion |  |  |  | 468078
Technical assistance provided to the Social Justice Consortium (within MoJ) to support delivery of services and human rights compliance. |  | 1.3.1.5a |  |  |  |  | 2019-01-01 | 2019-12-19 | Whyte, MOJ, Jomie, Robinson, Bruce
|  |  | Pay consultantancy fees | Payment of consultantancy fees | 31181 |  | 2019-01-01 | 2019-06-01 | Whyte, MOJ, Jomie, Robinson, Bruce
|  | GRAND TOTAL COMPONENT 3 |  |  | 1968830
Transition |  |  | Support to MDAs | Capacity building of 4 MDAs | 133333 | 2019-09-01 | 2019-12-01 | MNS/PEU | 4 MDAs supported | bar: 2019 Sep to 2019 Dec
|  |  | JIS Conract to support Transition and Exit Communication Strategey (to inlude Documentary) | New JIS contract Negotiated ($7.124M) | 52770 | 2019-08-01 | 2019-12-01 | SM, Orville, procurment, Mary | Publicity Campaign to include: CSJP in 5; Advertorials, Think Tanks, Photography, Website Mgmt, Social Media Mgmt; Documentry | bar: 2019 Aug to 2019 Dec
|  |  | CSJP Good News Campaign - Transition Paraphernalia -Referall [Outwards] Booklets | Delivery and Payment of brochure | 26667 | 2019-09-01 | 2019-09-01 | SM, Orville, procurment, Mary | 7500 Booklets | bar: 2019 Sep
|  | GRAND TOTAL TRANSITION |  |  | 212770
Information system constructed and implemented to disaggregate the statistical data for Comp 1 by age, sex, community, risk profile, and other factors |  | WBS Code
|  |  | Case Management System Implemented & maintained | Provide Internet Service for User Devices (Tablets) | 7053 |  | 2019-01-01 | 2019-12-19 | HR, Orville, Mary
|  | #REF! | 4 case management workshops conducted | Case Mgmt Training | 2593 |  | 2019-09-19 | 2019-10-19 | Joudene, Orville. Brian, Mary | bar: 2019 Sep to 2019 Oct
|  | #REF! | 2 stakeholder engagements conducted | Stakeholders Case Management Referral Workshops | 3333 |  | 2019-09-19 | 2019-09-19 | Joudene, Orville. Brian, Mary | bar: 2019 Sep
|  |  |  | Case Management Stationery | 3333 |  | 2019-06-19 | 2019-09-19 | Joudene, Orville. Brian, Mary | bar: 2019 Jun to 2019 Sep
| Total Case Management System |  |  |  | 16312
|  |  | Technical Assistance & Resources provided to Jamaica Crime Observatory | Payment 4 JCO Staff | 33208 |  | 2019-01-01 | 2019-12-01 | Mary, Simeon, JCO Staff
|  |  | Training technical assistance for improving monitoring systems & reporting | Furniture & Equipment Procured and payment made | 366 |  | 2019-01-19 | 2019-01-19 | Joudine, M&E unit, Simeon, Mary | bar: 2019 Jan
|  | #REF! |  | Traing PEU Staff | 233 |  | 2019-02-01 | 2019-02-01 | Joudine, M&E unit, Simeon, Mary | bar: 2019 Feb
|  |  |  | Procure Stationery | 3481 |  | 2019-02-01 | 2019-09-19 | Joudine, M&E unit, Orville, Mary | bar: 2019 Mar to 2019 Sep
| Total Training technical assistance for improving monitoring systems & reporting |  |  |  | 4080
Implementation of programme evaluations[Impact, Process, Mid-term, Final & Expost Economic Analysis] |  |  | Implementation of programme evaluations[Impact, Process, Mid-term, Final & Expost Economic Analysis] | Payment to Survey Firm | 94740 |  | 2019-01-01 | 2019-12-19 | M&E, Joudine, Simeon, Mary
|  |  |  | Payment to IE Field Coordinator | 27023 |  | 2019-01-01 | 2019-12-19 | M&E, Joudine, Simeon, Mary
|  | #REF! | Final Evaluation | EOI Advertized & Consultant Procured | 370 |  | 2019-06-19 | 2019-06-19 | M&E, Joudine, Simeon, Mary | bar: 2019 Jun
|  |  |  | Interim Report submitted | 37037 |  | 2019-09-19 | 2019-09-19 | M&E, Joudine, Simeon, Mary | bar: 2019 Sep
|  |  |  | Draft Final Report Submitted | 55556 |  | 2019-12-19 | 2019-12-19 | M&E, Joudine, Simeon, Mary | bar: 2019 Dec
| Total Implementation of programme evaluations[Impact, Process, Mid-term, Final & Expost Economic Analysis] |  |  |  | 214726
|  | #REF! | Victimization Survey (JNCVS) | Payment to Consultant | 297072 |  | 2019-03-19 | 2019-12-01 | Mary, Simeon, Joudine, Karlene. MNS | bar: 2019 Mar to 2019 Dec
| Total Other Surveys |  |  |  | 297072
|  |  | Staff Consultants | Consultants Paid | 137174 |  | 2019-01-01 | 2019-12-01 | Simeon, Mary
Total Monitoring and Evaluation |  |  |  |  | 702572
Programme Management
|  |  | Programme Mgmt | Procure stationery | 34268 |  | 2019-01-01 | 2019-12-01 | Mary, Simeon, Kerrian | bar: 2019 Jan to 2019 Sep
|  |  | Utilities | Payment | 147179 |  | 2019-01-01 | 2019-12-01 | Mary, Simeon, Kerrian
|  |  |  | Procure furniture and equipment | 15385 |  | 2019-02-01 | 2019-06-19 | Mary, Simeon, Kerrian
|  |  | Retrofitting of PEU Office Space | Retrofitting of PEU Office Space | 540 |  | 2019-04-01 | 2019-04-01 | Mary, Simeon, Kerrian | bar: 2019 Apr
|  | #REF! | Equipment maintenance | Procure service provider | 4333 |  | 2019-01-01 | 2019-12-01 | Mary, Simeon, Kerrian
|  | #REF! | Other administrative costs | Payment | 186972 |  | 2019-01-01 | 2019-12-01 | Mary, Simeon, Kerrian
|  |  | Audit | Procure consultant | 16578 |  | 2019-01-01 | 2019-12-01 | Mary, Simeon | bar: 2019 Apr to 2019 Jul
|  |  | 24 Consultants | 24 Consultants | 556494 |  | 2019-01-01 | 2019-12-01 | Mary, Simeon
Total Programme Management |  |  |  |  | 961749
Technical Advisory Team
Technical Advisory Team (Consultant)
|  |  |  | Submission, review, approval and payment of progress report | 34283 |  | 2019-02-01 | 2019-06-19 | Mary, orville, Joudine, Karlene. MNS | bar: 2019 Mar to 2019 Jun
|  |  |  | Submission, review, approval and payment of progress report | 19556 |  | 2019-06-19 | 2019-06-19 | Mary, orville, Joudine, Karlene. MNS | bar: 2019 Jun to 2019 Jul
| Total Technical Advisory Team |  |  |  | 53839 | bar: 2019 Jun
|  |  | VI Evaluation Final Payment | Final Payment to Consultant | 8859 |  | 2019-02-01 | 2019-02-01 | Mary, Simeon, Joudine, | bar: 2019 Feb; 2019 Jun
|  | #REF! | Case Mananagement Manual Submitted | Inception Report submitted | 4514 |  | 2019-03-19 | 2019-04-19 | M & E, Simeon, Mary | bar: 2019 Mar to 2019 Apr
|  |  |  | Draft Final Case Management Standard Operations Manual Submitted & Presentation | 15022 |  | 2019-07-19 | 2019-07-19 | M & E, Simeon, Mary | bar: 2019 Jul
|  |  |  | Final Case Management Standard Operations Manual | 3467 |  | 2019-08-19 | 2019-08-19 | M & E, Simeon, Mary | bar: 2019 Aug
| Total Case Management Manual |  |  |  | 31862
|  |  |  | Data Analyst | 22875 |  | 2019-01-01 | 2019-09-19 | Mary, Simeon, | bar: 2019 Jan to 2019 Sep
Total Technical Assistant |  |  |  |  | 108576
GRAND TOTAL |  |  |  |  | 13544417

## 4. Procurement Plan
CITIZEN SECURITY AND JUSTICE PROGRAMME 111
SECTION 4: Procurement Plan
PROJECT NUMBER: 3191/OC-JA
WORKS
Executing Agency: | Component (if applies) | Country's political Division (Region / Department / Jurisdiction, Province) | Region | Contract Name: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency ####) | Comments | [7 empty] | With
[15 empty] | Bidding Document |  | No objection to the Documents |  | Publication |  | Opening |  | Evaluation |  | No Objection to the Evaluation |  | Contract Signing |  | End of Contract | [11 empty] | Without
[15 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | [10 empty] | Planned
MNS |  |  |  | Marvely CMC Renovation |  | Shopping |  | 19-1122b | Price Comparison for Works |  | 28536 | Component 1 |  | Planned | 2019-10-01 |  | n/a |  | 2019-10-01 |  | 2019-10-01 |  | 2019-10-01 |  | n/a |  | 2019-11-01 |  | 2019-12-01 |  |  |  | Without ( the option is not given in the appropriate column ) | [7 empty] | Re-Tendering
MNS |  |  |  | Retrofitting of containers - Whitehall |  | Shopping |  | 19-1122c | Price Comparison for Works |  | 96154 | Component 1 |  | Planned | 2019-10-01 |  | n/a |  | 2019-10-01 |  | 2019-10-01 |  | 2019-10-01 |  | n/a |  | 2019-11-01 |  | 2019-12-01 |  |  |  | Without ( the option is not given in the appropriate column ) | [7 empty] | Cancelled
MNS |  |  |  | VSD -Office Renovations |  | Shopping |  | 19-1311h | Price Comparison for Works |  | 129470.33 | Component 3 |  | Planned | 2019-10-01 |  | n/a |  | 2019-10-01 |  | 2019-10-01 |  | 2019-10-01 |  | n/a |  | 2019-11-01 |  | 2019-12-01 |  |  |  | Without ( the option is not given in the appropriate column ) | [7 empty] | Rejection of all Bids
MNS |  |  |  | Repairs to Granville Center |  | Shopping |  | 19-1315i(i) | Price Comparison for Works |  | 30236 | Component 3 |  | Planned | 2019-11-01 |  | n/a |  | 2019-10-01 |  | 2019-10-01 |  | 2019-10-01 |  | n/a |  | 2019-11-01 |  | 2019-12-01 |  |  |  | Without ( the option is not being in the appropriate column ) | [7 empty] | Null and Void
MNS |  |  |  | RJ Offices- Renovations |  | Shopping |  | 19-1315i | Price Comparison for Works |  | 17308 | Component 3 |  | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-12-01 |  |  |  | Without ( the option is not given in the appropriate column ) | [7 empty] | Contract in Execution
MNS |  |  |  | Retrofitting of PEU Office Space |  | Shopping |  | 19-1611 | Price Comparison for Works |  | 26923 | Programme Mgmt |  | Planned | 2019-10-01 |  | n/a |  | 2019-10-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-12-01 |  |  |  | Without ( the option is not given in the appropriate column ) | [7 empty] | Contract Terminated
MNS |  |  |  | Construction of fish farm |  | Shopping |  | 19-1223b | Price Comparison for Works |  | 54074 | Component 2 |  | Planned | 2019-11-01 |  | n/a |  | 2019-10-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-12-01 |  |  |  | Without ( the option is not given in the appropriate column )
GOODS | [40 empty] | Shopping
Executing Agency: | Component (if applies) | Country's political Division (Region / Department / Jurisdiction, Province) | Region | Contract Name: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency ####) | Comments | [7 empty] | National Competitive Bidding
[15 empty] | Bidding Document |  | No objection to the Documents |  | Publication |  | Opening |  | Evaluation |  | No Objection to the Evaluation |  | Contract Signing |  | End of Contract | [11 empty] | Direct Contracting
[15 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | [10 empty] | Limited International Bidding
MNS |  |  |  | Parenting Programme- Printing of Manual , Plagues and Certificates |  | Shopping |  | 19-1111c | Price Comparison for Goods |  | 26292 | Component 1 | With | Contract in Execution | n/a |  | n/a |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises | [7 empty] | International Competitive Bidding
MNS |  |  |  | MWAM - Promotional Items |  | Shopping |  | 19-1111c | Price Comparison for Goods |  | 3045 | Component 1 | With | Contract in Execution | 2019-05-01 |  | n/a |  | 2019-05-01 |  | 2019-05-01 |  | 2019-05-01 |  | n/a |  | 2019-05-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises | [7 empty] | International Competitive Bidding with Prequalification
MNS |  |  |  | MWAM Oxford Shirt |  | Shopping |  | 19-1111c(i) | Price Comparison for Goods |  | 462 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-04-01 |  | n/a |  | 2019-04-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises | [7 empty] | Two-Stage Bidding
MNS |  |  |  | FEP - Oxford and Polo Shirt |  | Shopping |  | 19-1111c(iv) | Price Comparison for Goods |  | 769 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises | [7 empty] | International Competitive Bidding with Lots
MNS |  |  |  | FEP - Brochures |  | Shopping |  | 19-1111c(v) | Price Comparison for Goods |  | 769 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | PSU- Workshop Material |  | Shopping |  | 19-1112a | Price Comparison for Goods |  | 3846 | Component 1 | With | Contract in Execution | 2019-04-01 |  | n/a |  | 2019-04-01 |  | 2019-04-01 |  | 2019-04-01 |  | n/a |  | 2019-04-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | PSU- Therapeutic Materials and Stationery |  | Shopping |  | 19-1112a(i) | Price Comparison for Goods |  | 2769 | Component 1 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-07-01 |  | 2019-08-01 |  | 2019-08-01 |  | n/a |  | 2019-08-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | Capacity Building in School - Musicial Equipments and Sporting Gears |  | Shopping |  | 19-1112a(ii) | Price Comparison for Goods |  | 74074 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | CSJP-Good News Campaign Brochures |  | Shopping |  | 19-1115b | Price Comparison for Goods |  | 5769 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises | [7 empty] | Direct Contracting
MNS |  |  |  | CSJP Good News -Wall branding at CSJP Communities |  | Shopping |  | 19-1115b(i) | Price Comparison for Goods |  | 16154 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 | [11 empty] | Shopping
MNS |  |  |  | Good News Partnerships with MDA etc. - Flyers |  | Shopping |  | 19-1115b(ii) | Price Comparison for Goods |  | 500 | Component 1 | With | Contract in Execution | 2019-05-01 |  | n/a |  | 2019-05-01 |  | 2019-05-01 |  | 2019-05-01 |  | n/a |  | 2019-05-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises | [7 empty] | Least-Cost Selection
MNS |  |  |  | Good News Partnerships with MDA etc. - Brochures |  | Shopping |  | 19-1115b(iii) | Price Comparison for Goods |  | 500 | Component 1 | With | Contract in Execution | 2019-05-01 |  | n/a |  | 2019-05-01 |  | 2019-05-01 |  | 2019-05-01 |  | n/a |  | 2019-05-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises | [7 empty] | Quality Based Selection
MNS |  |  |  | Youth Ambassadors Oxford Shirts |  | Shopping |  | 19-1115b(ii) | Price Comparison for Goods |  | 962 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 | [11 empty] | Quality and Cost Based Selection
MNS |  |  |  | Youth Ambassadors IDs |  | Shopping |  | 19-1115b(iii) | Price Comparison for Goods |  | 231 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises | [7 empty] | Selection Based on the Consultants' Qualifications
MNS |  |  |  | Peacemobile Exit Fair - Flyers |  | Shopping |  | 19-1115b(iv) | Price Comparison for Goods |  | 2923 | Component 1 | With | Planned | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 | [11 empty] | Comments
MNS |  |  |  | Life Skills- Gears and equipment |  | Shopping |  | 19-1115b(v) | Price Comparison for Goods |  | 50000 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | Life skills - Trophies and medals |  | Shopping |  | 19-1115b(vi) | Price Comparison for Goods |  | 12000 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | Life Skills -Paraphernelias (Branded items i.e. cups,mugs, banner,draw string bags) |  | Shopping |  | 19-1115b(vii) | Price Comparison for Goods |  | 1000 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 | [12 empty] | Goods
MNS |  |  |  | Social Marketing - Software and Equipment |  | Shopping |  | 19-1115b(viii) | Price Comparison for Goods |  | 1846 | Component 1 | With | Contract in Execution | 2019-04-01 |  | n/a |  | 2019-04-01 |  | 2019-04-01 |  | 2019-04-01 |  | n/a |  | 2019-04-01 |  | 2019-12-01
MNS |  |  |  | Furniture and office equipment - Gayle |  | Shopping |  | 19-1122b | Price Comparison for Goods |  | 26923 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | Summer employment - Stationery |  | Shopping |  | 19-1222b | Price Comparison for Goods |  | 385 | component 2 | With |  | 2019-07-01 |  | n/a |  | 2019-07-01 |  | 2019-07-01 |  | 2019-07-01 |  | n/a |  | 2019-07-01 |  | 2019-08-01 |  |  |  | Contract executed
MNS |  |  |  | Business Development - Equipment |  | Shopping |  | 19-1223c | Price Comparison for Goods |  | 7407 | component 2 | With | Contract in Execution | 2019-09-01 |  | n/a |  | 2019-09-01 |  | 2019-09-01 |  | 2019-09-01 |  | n/a |  | 2019-09-01 |  | 2019-09-01
MNS |  |  |  | VSD- Office furntiure and Equipment |  | Shopping |  | 19-1311a | Price Comparison for Goods |  | 23077 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [8 empty] | Non-Consulting Services
MNS |  |  |  | VSD- ResocialisationTheaurapetic Tools |  | Shopping |  | 19-1311a(i) | Price Comparison for Goods |  | 11769 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [8 empty] | Non-Consulting Services
MNS |  |  |  | VSD - Resocialisation - stationery |  | Shopping |  | 19-1311a(ii) | Price Comparison for Goods |  | 4962 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [7 empty] | Lump-Sum | Non-Consulting Services
MNS |  |  |  | VSD - Resocialisation - Polo shirt |  | Shopping |  | 19-1311a(iii) | Price Comparison for Goods |  | 8077 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [7 empty] | Lump-Sum | Consulting Firms
MNS |  |  |  | VSD SIP - Therapeutic tools |  | Shopping |  | 19-1311a(iv) | Price Comparison for Goods |  | 2538 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [7 empty] | Lump-Sum + Reimbursable Expenses | Consulting Firms
MNS |  |  |  | VSD SIP - stationery and material |  | Shopping |  | 19-1311a(v) | Price Comparison for Goods |  | 1692 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [7 empty] | Time-Based | Consulting Firms
MNS |  |  |  | VSD SIP - Graduation Certificates |  | Shopping |  | 19-1311a(vi) | Price Comparison for Goods |  | 77 | Component 3 | With | Planned | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 | [12 empty] | Individual Consultants
MNS |  |  |  | VSD Overcomers in Action - stationery and material |  | Shopping |  | 19-1311a(vii) | Price Comparison for Goods |  | 923 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [8 empty] | Individual Consultants
MNS |  |  |  | VSD Overcomers in Action - Therapeutic tools |  | Shopping |  | 19-1311a(viii) | Price Comparison for Goods |  | 2538 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise
MNS |  |  |  | VSD Overcomers in Action -Graduation- Certificates and tokens |  | Shopping |  | 19-1311a(viiii) | Price Comparison for Goods |  | 1269 | Component 3 | With | Planned | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01
MNS |  |  |  | VSD - Awareness - brochures and Paraphenelia |  | Shopping |  | 19-1311(xi) | Price Comparison for Goods |  | 11538 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise
MNS |  |  |  | VSD - Training of First Responder - Stationery |  | Shopping |  | 19-1311(xii) | Price Comparison for Goods |  | 462 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise
MNS |  |  |  | VSD-stakeholder consultation- stationery |  | Shopping |  | 19-1311a(xiii) | Price Comparison for Goods |  | 615 | Component 3 | With | Contract in Execution | 2019-02-01 |  | n/a |  | 2019-02-01 |  | 2019-02-01 |  | 2019-02-01 |  | n/a |  | 2019-02-01 |  | 2019-06-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise
MNS |  |  |  | Legal Aid- JPS and Police Officers Training - stationery |  | Shopping |  | 19-1312a | Price Comparison for Goods |  | 2462 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [7 empty] | Procurement of Goods | Goods
MNS |  |  |  | Legal Aid Fair - Resource Material |  | Shopping |  | 19-1312a(i) | Price Comparison for Goods |  | 1538 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise
MNS |  |  |  | Legal Aid -Equipment |  | Shopping |  | 19-1312a(ii) | Price Comparison for Goods |  | 19836 | Component 3 | With | Contract in Execution | 2019-03-01 |  | n/a |  | 2019-03-01 |  | 2019-03-01 |  | 2019-03-01 |  | n/a |  | 2019-03-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [7 empty] | Procurement of Health Sector Goods | Goods
MNS |  |  |  | JTI - Printing of JP Manual |  | Shopping |  | 19-1313b | Price Comparison for Goods |  | 18462 | Component 3 | With | Planned | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-03-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [7 empty] | Price Comparison for Goods | Goods
MNS |  |  |  | JTI-Qualifying Training stationery and resource material |  | Shopping |  | 19-1313b(i) | Price Comparison for Goods |  | 4154 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [7 empty] | Technical Specifications | Goods
MNS |  |  |  | JTI-Advance Training stationery and resource material |  | Shopping |  | 19-1313b(ii) | Price Comparison for Goods |  | 8031 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [7 empty] | Procurement of plant Design , Supply and Installation | Goods
MNS |  |  |  | RJ- Staff Development and Workshops Stationery |  | Shopping |  | 19-1315 | Price Comparison for Goods |  | 308 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [7 empty] | Procurement of IT Products and/or Services | Goods
MNS |  |  |  | RJ-Sensitization- Stationery |  | Shopping |  | 19-1315c | Price Comparison for Goods |  | 2500 | Component 3 | With | Contract in Execution | 2019-02-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [7 empty] | Procurement of Non-Consulting Services | Non-Consulting Services
MNS |  |  |  | RJ Week - Paraphernelia (pen, arm bands, pencils, water bottle, mug, draw string bag) |  | Shopping |  | 19-1315c(i) | Price Comparison for Goods |  | 769 | Component 3 | With |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-02-01 |  |  |  | Contract Executed
MNS |  |  |  | RJ Week - Banner and Oxford Shirt |  | Shopping |  | 19-1315c(ii) | Price Comparison for Goods |  | 2077 | Component 3 | With |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-02-01 |  |  |  | Contract Executed | [7 empty] | Request for Proposals and Terms of Reference | Consulting Firms
MNS |  |  |  | RJ Week - Conference Material |  | Shopping |  | 19-1315c(iii) | Price Comparison for Goods |  | 1846 | Component 3 | With |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-02-01 |  |  |  | Contract Executed | [7 empty] | Terms of Reference | Consulting Firms
MNS |  |  |  | RJ-Stationery and Supplies |  | Shopping |  | 19-1315c(iv) | Price Comparison for Goods |  | 1346 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-06-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise
MNS |  |  |  | RJ - Market Campaign -Oxford shirts, paraphernelia(mugs, pen, pencils, draw string bags, bottles) |  | Shopping |  | 19-1315c(vi) | Price Comparison for Goods |  | 7692 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-06-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise
MNS |  |  |  | RJ - Graduation - Certificates and awards |  | Shopping |  | 19-1315c(vii) | Price Comparison for Goods |  | 212 | Component 3 | With | Planned | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 | [11 empty] | Lump-Sum
MNS |  |  |  | Child Diversion - Stationery and office equipment |  | Shopping |  | 19-1316b | Price Comparison for Goods |  | 65.549.13 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [7 empty] | Time-Based
MNS |  |  |  | Child Diversion - Training material |  | Shopping |  | 19-1316b(i) | Price Comparison for Goods |  | 22035 | Component 3 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise
MNS |  |  |  | Child Diversion - Paraphenilia(mugs, pen, pencils, draw string bags, bottles |  | Shopping |  | 19-1316b(i) | Price Comparison for Goods |  | 115382.64 | Component 3 | With | Planned | 2019-07-01 |  | n/a |  | 2019-07-01 |  | 2019-07-01 |  | 2019-07-01 |  | n/a |  | 2019-07-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [7 empty] | Direct Contracting
MNS |  |  |  | Case Mgmt Stationery |  | Shopping |  | 19-1511c | Price Comparison for Goods |  | 3462 | Component 5 | With | Contract in Execution | 2019-04-01 |  | n/a |  | 2019-04-01 |  | 2019-04-01 |  | 2019-04-01 |  | n/a |  | 2019-04-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [7 empty] | Shopping
MNS |  |  |  | M and E Stationery |  | Shopping |  | 19-1513a | Price Comparison for Goods |  | 3846 | Component 5 | With | Contract in Execution | 2019-03-01 |  | n/a |  | 2019-03-01 |  | 2019-03-01 |  | 2019-03-01 |  | n/a |  | 2019-03-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise | [7 empty] | 3CV
MNS |  |  |  | M and E Furniture and Equipment |  | Shopping |  | 19-1513a(i) | Price Comparison for Goods |  | 523 | Component 5 | With | Contract in Execution | 2019-03-01 |  | n/a |  | 2019-03-01 |  | 2019-03-01 |  | 2019-03-01 |  | n/a |  | 2019-03-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise
MNS |  |  |  | Survey - Stationery |  | Shopping |  | 19-1524b | Price Comparison for Goods |  | 308 | Component 5 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | Programme Mgmt - Stationery and office supplies |  | Shopping |  | 19-1611b | Price Comparison for Goods |  | 32686 | Programme Mgmt | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise
MNS |  |  |  | Programme Mgmt -Furniture and Equipment |  | Shopping |  | 19-1611b(i) | Price Comparison for Goods |  | 12373 | Programme Mgmt | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arise
NON CONSULTING SERVICES
Executing Agency: | Component (if applies) | Country's political Division (Region / Department / Jurisdiction, Province) | Region | Contract Name: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency ####) | Comments
[15 empty] | Bidding Document |  | No objection to the Documents |  | Publication |  | Opening |  | Evaluation |  | No Objection to the Evaluation |  | Contract Signing |  | End of Contract
[15 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
MNS |  |  |  | Parenting Programme - Refreshment and venue |  | Shopping |  | 19-1111b(i) | Procurement of Non-Consulting Services | Lump-Sum | 108030 | Component 1 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | Parenting Programme - Transportation |  | Shopping |  | 19-1111b(ii) | Procurement of Non-Consulting Services | Lump-Sum | 18300 | Component 1 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | Parenting Graduation - Refreshment and venue |  | Shopping |  | 19-1111a(iv) | Procurement of Non-Consulting Services | Lump-Sum | 31846 | Component 1 | With | Contract in Execution | 2019-07-01 |  | n/a |  | 2019-07-01 |  | 2019-07-01 |  | 2019-07-01 |  | n/a |  | 2019-07-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | Parenting Graduation - Transportation |  | Shopping |  | 19-1111a(v) | Procurement of Non-Consulting Services | Lump-Sum | 3077 | Component 1 | With | Planned | 2019-10-01 |  | n/a |  | 2019-10-01 |  | 2019-10-01 |  | 2019-10-01 |  | n/a |  | 2019-10-01 |  | 2019-10-01
MNS |  |  |  | Parenting Graduation Décor and rental |  | Shopping |  | 19-1111a(vi) | Procurement of Non-Consulting Services | Lump-Sum | 2692 | Component 1 | With | Planned | 2019-10-01 |  | n/a |  | 2019-10-01 |  | 2019-10-01 |  | 2019-10-01 |  | n/a |  | 2019-10-01 |  | 2019-10-01
MNS |  |  |  | MWAM - Venue and Refreshment |  | Shopping |  | 19-1111c(ii) | Procurement of Non-Consulting Services | Lump-Sum | 3738 | Component 1 | With | Contract in Execution | 2019-10-01 |  | n/a |  | 2019-10-01 |  | 2019-10-01 |  | 2019-10-01 |  | N/A |  | 2019-10-01 |  | 2019-10-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | FEP Personal Development - Venue and Refreshment |  | Shopping |  | 19-1111c(iii) | Procurement of Non-Consulting Services | Lump-Sum | 2492 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | FEP - International Women's Day Celebration - Live Outside Broadcast |  | Shopping |  | 19-1111c(vi) | Procurement of Non-Consulting Services | Lump-Sum | 1846 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | PSU - Refreshing |  | Shopping |  | 19-1112b | Procurement of Non-Consulting Services | Lump-Sum | 6015 | Component 1 | with | Contract in Execution | 2019-02-01 |  | n/a |  | 2019-02-01 |  | 2019-02-01 |  | 2019-02-01 |  | n/a |  | 2019-02-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | PSU- Transportation |  | Shopping |  | 19-1112B(I) | Procurement of Non-Consulting Services | Lump-Sum | 19231 | Component 1 | with | Contract in Execution | 2019-02-01 |  | n/a |  | 2019-02-01 |  | 2019-02-01 |  | 2019-02-01 |  | n/a |  | 2019-02-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | Capacity Building - Refreshment and Venue |  | Shopping |  | 19-1112b(ii) | Procurement of Non-Consulting Services | Lump-Sum | 19232 | Component 1 |  | Contract in Execution | 2019-08-01 |  | n/a |  | 2019-08-01 |  | 2019-08-01 |  | 2019-08-01 |  | n/a |  | 2019-08-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | Training - Violence Interrupters - Refreshment and Venue |  | Shopping |  | 19-1113b | Procurement of Non-Consulting Services | Lump-Sum | 5769.23 | Component 1 |  |  | 2019-06-01 |  |  |  | 2019-06-01 |  | 2019-06-01 |  | 2019-06-01 |  | 2019-06-01 |  | 2019-06-01 |  | 2019-06-01 |  |  |  | Contract Executed
MNS |  |  |  | Advertisement - Anti- Gang Campaign |  | Shopping |  | 19-1115a(i) | Procurement of Non-Consulting Services | Lump-Sum | 615 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | CSJP Peace Mobile Exit Fairs - Venue and Refreshment |  | Shopping |  | 19-1115a(ii) | Procurement of Non-Consulting Services | Lump-Sum | 6923 | Component 1 | With | Planned | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01
MNS |  |  |  | CSJP Peace Mobile Exit Fairs -Entertainment |  | Shopping |  | 19-1115a(iii) | Procurement of Non-Consulting Services | Lump-Sum | 15846 | Component 1 | With | Planned | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01
MNS |  |  |  | CSJP Peace Mobile Exit Fairs - Live Outside Boradcast |  | Shopping |  | 19 -1115a(iv) | Procurement of Non-Consulting Services | Lump-Sum | 12538.46 | Component 1 | With | Planned | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01
MNS |  |  |  | CSJP- Peace Mobile Exit Fairs - Rental Supplies |  | Shopping |  | 19-1115a(v) | Procurement of Non-Consulting Services | Lump-Sum | 7846 | Component 1 | With | Planned | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01
MNS |  |  |  | CSJP PeaceMobile Exit Fairs- Town Crier |  | Shopping |  | 19-1115a(vi) | Procurement of Non-Consulting Services | Lump-Sum | 3307 | Component 1 | With | Planned | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01
MNS |  |  |  | Youth Ambassador Program- Media Launch |  | Shopping |  | 19-1115a(vii) | Procurement of Non-Consulting Services | Lump-Sum | 3846 | Component 1 | with | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | Life Skills - Refreshment and Venue |  | Shopping |  | 19-1115a(viii) | Procurement of Non-Consulting Services | Lump-Sum | 48538 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | Life Skills Opening & Closing ceremony - Entertainment |  | Shopping |  | 19-1115a(viiii) | Procurement of Non-Consulting Services | Lump-Sum | 6000 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | Life Skills - Opening & closing ceremony Live Oustide Broadcast |  | Shopping |  | 19-1115a(x) | Procurement of Non-Consulting Services | Lump-Sum | 4493 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | Life Skills- opening and closing ceremony -Décor |  | Shopping |  | 19-1115a(xi) | Procurement of Non-Consulting Services | Lump-Sum | 5400 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | Life Skills - Refereess and First Aid |  | Shopping |  | 19-1115a(xii) | Procurement of Non-Consulting Services | Lump-Sum | 12000 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | Life Skills- opening and closing ceremony -venue and refreshment |  | Shopping |  | 19-1115a(xiii) | Procurement of Non-Consulting Services | Lump-Sum | 8384 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | Life Skills - field Prep and rental |  | Shopping |  | 19-1115a(xiii) | Procurement of Non-Consulting Services | Lump-Sum | 13000 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | Good News Partnerships with MDA etc. - Refreshment and venues |  | Shopping |  | 19-1115a(xiv) | Procurement of Non-Consulting Services | Lump-Sum | 2869 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | Good News Partnerships with MDA etc. - Live OB |  | Shopping |  | 19-1115(xv) | Procurement of Non-Consulting Services | Lump-Sum | 1900 | Component 1 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | Good News Patnerships with MDA etc. - Tents, tables and chairs |  | Shopping |  | 19-1115(xvi) | Procurement of Non-Consulting Services | Lump-Sum | 1000 | Component 1 | with | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | Good News and Visibility Press Conference and Launch - Venue and Refreshment |  | Shopping |  | 19-1115(xvii) | Procurement of Non-Consulting Services | Lump-Sum | 16000 | Component 1 | with | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | Good News and Visibility Press Conference and Launch - Décor and Lighting |  | Shopping |  | 19-1115(xviii) | Procurement of Non-Consulting Services | Lump-Sum | 4000 | Component 1 | with | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01
MNS |  |  |  | CACs Workshop training - Refreshment and Venue |  | Shopping |  | 19-1121b | Procurement of Non-Consulting Services | Lump-Sum | 39154 | Component 1 | With | Cancelled | 2019-12-01 |  | n/a |  | 2019-04-01 |  | 2019-04-01 |  | 2019-04-01 |  | n/a |  | 2019-04-01 |  | 2019-09-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | CACs Workshop training - Transportation |  | Shopping |  | 19-1121b(i) | Procurement of Non-Consulting Services | Lump-Sum | 9308 | Component 1 | With | Cancelled | 2019-04-01 |  | n/a |  | 2019-04-01 |  | 2019-04-01 |  | 2019-04-01 |  | n/a |  | 2019-04-01 |  | 2019-09-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | Job Readiness -Venue and refreshment |  | Shopping |  | 19-1221a | Procurement of Non-Consulting Services | Lump-Sum | 6130 | Component 2 | With |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-09-01 |  |  |  | Contract Executed
MNS |  |  |  | Job Expo - Venue and Refreshment |  | Shopping |  | 19-1222a(i) | Procurement of Non-Consulting Services | Lump-Sum | 4615 | Component 2 | With |  | 2019-03-01 |  | n/a |  | 2019-03-01 |  | 2019-03-01 |  | 2019-03-01 |  | n/a |  | 2019-03-01 |  | 2019-09-01 |  |  |  | Contract Executed
MNS |  |  |  | Summer Employment - Refreshment |  | Shopping |  | 19-1222a(ii) | Procurement of Non-Consulting Services | Lump-Sum | 3846 | Component 2 | With |  | 2019-07-01 |  | n/a |  | 2019-07-01 |  | 2019-07-01 |  | 2019-07-01 |  | n/a |  | 2019-07-01 |  | 2019-08-01 |  |  |  | Contract Executed
MNS |  |  |  | Cure Violence Event - Air Travel Etc. |  |  |  | 19-1223b | Procurement of Non-Consulting Services | Lump-Sum | 4950 | Component 2 | Without |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  |  |  | Contract Executed
MNS |  |  |  | VSD - Resocialisation - Venue and Refreshment |  | Shopping |  | 19-1311b | Procurement of Non-Consulting Services | Lump-Sum | 12000 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | VSD- Resocialisation - Transportation |  | Shopping |  | 19-1311b(i) | Procurement of Non-Consulting Services | Lump-Sum | 4846 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | VSD- Resocialisation - Medical services |  | Shopping |  | 19-1311b(ii) | Procurement of Non-Consulting Services | Lump-Sum | 3962 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | VSD SIP - Refreshment |  | Shopping |  | 19-1311b(iii) | Procurement of Non-Consulting Services | Lump-Sum | 3962 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | VSD - Overcomers in Action - Venue and refreshment |  | Shopping |  | 19-1311b(iv) | Procurement of Non-Consulting Services | Lump-Sum | 4539 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | VSD Overcomers in Action Graduation - Venue and refreshment |  | Shopping |  | 19-1311b(v) | Procurement of Non-Consulting Services | Lump-Sum | 3385 | Component 3 | With | Contract in Execution | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01
MNS |  |  |  | VSD- Training of First responders - Venue and refreshment |  | Shopping |  | 19-1311b(vi) | Procurement of Non-Consulting Services | Lump-Sum | 65000 | Component 3 | With | Planned | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | VSD- stakeholder consultation -Venue and refreshment |  | Shopping |  | 19-1311b(vii) | Procurement of Non-Consulting Services | Lump-Sum | 5231 | Component 3 | With | Contract in Execution | 2019-02-01 |  | n/a |  | 2019-02-01 |  | 2019-02-01 |  | 2019-02-01 |  | n/a |  | 2019-02-01 |  | 2019-06-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | Legal Aid- JPs and Police Officers Training Refreshment and venue |  | Shopping |  | 19-1312b | Procurement of Non-Consulting Services | Lump-Sum | 6262 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | Legal Aid -Service Points - venue |  | Shopping |  | 19-1312b(i) | Procurement of Non-Consulting Services | Lump-Sum | 12692 | Component 3 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis and as the need arises
MNS |  |  |  | Legal Aid Fair - Rental Chairs, Tent, tables |  | Shopping |  | 19-1312b(ii) | Procurement of Non-Consulting Services | Lump-Sum | 2446 | Component 3 | With |  | 2019-02-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-03-01 |  |  |  | contract executed
MNS |  |  |  | Legal Fair- Refreshment |  | Shopping |  | 19-1312b(iii) | Procurement of Non-Consulting Services | Lump-Sum | 2462 | Component 3 | With |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-03-01 |  |  |  | contract executed
MNS |  |  |  | Legal Aid Fair - Rental PA System and Generator |  | Shopping |  | 19-1312b(iv) | Procurement of Non-Consulting Services | Lump-Sum | 10000 | Component 3 | With |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-03-01 |  |  |  | contract executed
MNS |  |  |  | Legal Aid Fair - Outside Broadcasting |  | Shopping |  | 19-1312b(v) | Procurement of Non-Consulting Services | Lump-Sum | 6154 | Component 3 | With |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-03-01 |  |  |  | contract executed
MNS |  |  |  | Legal Aid Fair - Town Crier |  | Shopping |  | 19-1312b(vi) | Procurement of Non-Consulting Services | Lump-Sum | 1077 | Component 3 | With |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-03-01 |  |  |  | contract executed
MNS |  |  |  | Legal Aid Fair - Rental of Venue |  | Shopping |  | 19-1312b(vii) | Procurement of Non-Consulting Services | Lump-Sum | 3077 | Component 3 | With |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-03-01 |  |  |  | contract executed
MNS |  |  |  | Legal Aid Fair - Security Services |  | Shopping |  | 19-1312b(viii) | Procurement of Non-Consulting Services | Lump-Sum | 923 | Component 3 | With | Cancelled | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-03-01
MNS |  |  |  | JTI- JP Manual Training refreshment and venue |  | Shopping |  | 19-1313c | Procurement of Non-Consulting Services | Lump-Sum | 3077 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | JTI - Qualifying Training - Refreshment and venue |  | Shopping |  | 19-1313c(i) | Procurement of Non-Consulting Services | Lump-Sum | 37385 | Component 3 | with | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | JTI -Qualifying Training - Accomodations |  | Shopping |  | 19-1313c(ii) | Procurement of Non-Consulting Services | Lump-Sum | 10883 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | JTI-Advance Training Venue and Refreshment |  | Shopping |  | 19-1313c(iii) | Procurement of Non-Consulting Services | Lump-Sum | 106270 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | JTI-Advance Training Accomodation |  | Shopping |  | 19-1313c(iv) | Procurement of Non-Consulting Services | Lump-Sum | 82227 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | JTI-Advance Training Transportation |  | Shopping |  | 19-1313c(v) | Procurement of Non-Consulting Services | Lump-Sum | 5183 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | JTI-JP consultation and sensitization- refreshment and venue |  | Shopping |  | 19-1313c(vi) | Procurement of Non-Consulting Services | Lump-Sum | 27692 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | RJ-Maintenance of Equipment |  | Shopping |  | 19-1315b | Procurement of Non-Consulting Services | Lump-Sum | 9231 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | RJ Restorative Practices Workshops - Refreshment and Venue |  | Shopping |  | 19-1315b(i) | Procurement of Non-Consulting Services | Lump-Sum | 42923 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | RJ Restorative Practices Workshops - Accommodations |  | Shopping |  | 19-1315b(ii) | Procurement of Non-Consulting Services | Lump-Sum | 54000 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | RJ Case Conference - refreshment |  | Shopping |  | 19-1315b(vii) | Procurement of Non-Consulting Services | Lump-Sum | 41538 | Component 3 | With | Planned | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | RJ Facilitators - Transportation |  | Shopping |  | 19-1315b(viii) | Procurement of Non-Consulting Services | Lump-Sum | 3846 | Component 3 | With | Planned | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | RJ Week-Refreshment |  | Shopping |  | 19-1315b(viiii) | Procurement of Non-Consulting Services | Lump-Sum | 11692 | Component 3 | With |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-02-01 |  |  |  | Conract executed
MNS |  |  |  | RJ Week- Décor |  | Shopping |  | 19-1315b(x) | Procurement of Non-Consulting Services | Lump-Sum | 770 | Component 3 | With |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-02-01 |  |  |  | Conract executed
MNS |  |  |  | RJ Week - Live Broadcasting |  | Shopping |  | 19-1315b(xi) | Procurement of Non-Consulting Services | Lump-Sum | 3846 | Component 3 | With |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-02-01 |  |  |  | Conract executed
MNS |  |  |  | RJ Week -Transportation |  | Shopping |  | 19-1315b(xii) | Procurement of Non-Consulting Services | Lump-Sum | 1538 | Component 3 | With |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-02-01 |  |  |  | Conract executed
MNS |  |  |  | RJ Week - Rental of Tents |  | Shopping |  | 19-1315b(xiii) | Procurement of Non-Consulting Services | Lump-Sum | 308 | Component 3 | With |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-02-01 |  |  |  | Conract executed
MNS |  |  |  | RJ Week - Rental of PA system |  | Shopping |  | 19-1315b(xiiii) | Procurement of Non-Consulting Services | Lump-Sum | 192 | Component 3 | With |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-02-01 |  |  |  | Conract executed
MNS |  |  |  | RJ Week - Rental Generator, chairs, tables etc |  | Shopping |  | 19-1315b(xv) | Procurement of Non-Consulting Services | Lump-Sum | 1423 | Component 3 | With |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-02-01 |  |  |  | Conract executed
MNS |  |  |  | RJ- Graduation - Venue and Refreshment |  | Shopping |  | 19-1315b(xvi) | Procurement of Non-Consulting Services | Lump-Sum | 2380 | Component 3 | With | Planned | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01
MNS |  |  |  | RJ-Sensitization-Refreshment and venue |  | Shopping |  | 19-1315b(xvii) | Procurement of Non-Consulting Services | Lump-Sum | 11770 | Component 3 | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | Child Diversion -Refreshment |  | Shopping |  | 19-1316a | Procurement of Non-Consulting Services | Lump-Sum | 9577 | Component 3 | With | Planned | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis | [7 empty] | Procurement conducted on an ongoing basis
MNS |  |  |  | Child Diversion- Maintenance of Equipment |  | Shopping |  | 19-1316a(i) | Procurement of Non-Consulting Services | Lump-Sum | 5769 | Component 3 | With | Planned | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | Child Diversion Justice Training and Workshops- refreshment and venue |  | Shopping |  | 19-1316a(ii) | Procurement of Non-Consulting Services | Lump-Sum | 100000 | Component 3 | With | Planned | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | 2019-11-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | Child Diversion - sensitization - venue and refreshment |  | Shopping |  | 19-1316a(iii) | Procurement of Non-Consulting Services | Lump-Sum | 9231 | Component 3 | with | Planned | 2019-10-01 |  | n/a |  | 2019-10-01 |  | 2019-10-01 |  | 2019-10-01 |  | N/A |  | 2019-10-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | Child Diversion - Accommodation |  | Shopping |  | 19-1316a(iv) | Procurement of Non-Consulting Services | Lump-Sum | 16500 | Component 3 | with | Planned | 2019-10-01 |  | n/a |  | 2019-10-01 |  | 2019-10-01 |  | 2019-10-01 |  | N/A |  | 2019-10-01 |  | 2019-12-01
MNS |  |  |  | Case Mgmt Training - Venue and refreshment |  | Shopping |  | 19-1511b | Procurement of Non-Consulting Services | Lump-Sum | 5385 | Component 5 | With | Planned | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01
MNS |  |  |  | Case Mgmt Workshop - Venue, Refereshment and accommodation |  | Shopping |  | 19-1511b(i) | Procurement of Non-Consulting Services | Lump-Sum | 3462 | Component 5 | With | Planned | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | n/a |  | 2019-12-01 |  | 2019-12-01
MNS |  |  |  | M and E Training Refreshment |  | Shopping |  | 19-1513b | Procurement of Non-Consulting Services | Lump-Sum | 1688 | Component 5 | With | Contract in Execution | 2019-02-01 |  | n/a |  | 2019-02-01 |  | 2019-02-01 |  | 2019-02-01 |  | n/a |  | 2019-02-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | Survey -refreshment |  | Shopping |  | 19-1524a | Procurement of Non-Consulting Services | Lump-Sum | 2077 | Component 5 | With | Contract in Execution | 2019-04-01 |  | n/a |  | 2019-04-01 |  | 2019-04-01 |  | 2019-04-01 |  | n/a |  | 2019-04-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | Programme Mgmt - Equipment Maintenance |  | Shopping |  | 19-1611c | Procurement of Non-Consulting Services | Lump-Sum | 6000 | Programme Mgmt | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | Programme Mgmt - Equipment Maintenance |  | Direct Contracting |  | 19-1611c(i) | Procurement of Non-Consulting Services | Lump-Sum | 2708 | Programme Mgmt | With | Contract in Execution | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
MNS |  |  |  | Programme Mgmt - Other Administrative services( Pest control, motor vehicle maintenance, plubing services, locksmith services, assets/ removal disposals etc. ) |  | Shopping |  | 19-1611c(ii) | Procurement of Non-Consulting Services | Lump-Sum | 188561 | Programme Mgmt | With | Planned | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | 2019-01-01 |  | 2019-12-01 |  |  |  | Procurement conducted on an ongoing basis
CONSULTING FIRMS
Executing Agency: | Component (if applies) | Country's political Division (Region / Department / Jurisdiction, Province) | Region | Contract Name: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity | Process Number: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) | [21 empty] | Short List Members | Technical Score Assigned | Evaluated Price Proposal (Currency ####) | Combined Score
[15 empty] | Expression of Interest Notice |  | RFP and Short List |  | No Objection to RFP and Short List |  | RFP Submission |  | Opening |  | Technical Evaluation |  | No Objection to the Technical Evaluation |  | Final Evaluation and Negotiation |  | No Objection to the Contract |  | Contract Signing |  | End of Contract
[15 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
MNS |  |  |  | MOU- NPSC for parenting |  | Direct Contracting |  | 19-1111d | Request for Proposals and Terms of Reference | Lump-Sum | 36923 | Component 1 | Without | Contract in Execution | n/a |  | n/a |  | n/a |  |  |  | n/a | [11 empty] | 2019-12-01
MNS |  |  |  | MOU - National Council on Drug Abuse |  | Direct Contracting |  | 19-1112a | Request for Proposals and Terms of Reference | Lump-Sum | 83965 | Component 1 | Without | Contract in Execution | n/a |  | n/a |  | n/a |  | 2019-03-01 |  | 2019-03-01 |  | n/a |  | 2019-05-01 |  | 2019-04-01 |  | 2019-03-01 | 2019-05-01 | 2019-12-01 |  | 2019-12-01
MNS |  |  |  | Violence Interruption Services - PMI - East |  | Direct Contracting |  | 19-1113a (i) | Request for Proposals and Terms of Reference | Lump-Sum | 419231 | Component 1 | Without | Contract in Execution | n/a |  | n/a |  | n/a |  | 2019-03-01 |  | 2019-03-01 |  | n/a |  | 2019-03-01 |  | n/a |  | 2019-03-01 |  | 2019-12-01 |  | 2019-12-31
MNS |  |  |  | Violence Interruption Services - PMI - West |  | Direct Contracting |  | 19-1113a(ii) | Request for Proposals and Terms of Reference | Lump-Sum | 338461 | Component 1 | Without | Contract in Execution | n/a |  | n/a |  | n/a |  | 2019-03-01 |  | 2019-03-01 |  | n/a |  | 2019-03-01 |  | n/a |  | 2019-03-01 |  | 2019-12-01 |  | 2019-12-31
MNS |  |  |  | Firm to Design and implement Gender Focused Campaign |  | Selection Based on the Consultants' Qualifications |  | 19-1115c | Request for Proposals and Terms of Reference | Lump-Sum | 80615 | Component 1 | Without | Planned | 2019-10-01 |  | 2019-10-01 |  | 2019-10-01 |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  |  |  | 2019-12-31
MNS |  |  |  | Firm to Design and implement Anti gang Campaign |  | Selection Based on the Consultants' Qualifications |  | 19-1115c(i) | Request for Proposals and Terms of Reference | Lump-Sum | 153846 | Component 1 | Without | Planned | 2019-10-02 |  | 2019-11-01 |  | 2019-11-01 |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  |  |  | 2019-12-31
MNS |  |  |  | CSJP 5 - JIS |  | Direct Contracting |  | 19-1115c(ii) | Request for Proposals and Terms of Reference | Lump-Sum | 15385 | Component 1 | Without | Planned | n/a |  | n/a |  | n/a |  | 2019-01-01 |  | 2019-10-01 |  | n/a |  | 2019-10-01 |  | 2019-10-01 |  | 2019-10-01 |  |  |  | 2019-12-31
MNS |  |  |  | Good News Campaign - Let's Make Peace - TVJ |  | Direct Contracting |  | 19-1115c(iii) | Request for Proposals and Terms of Reference | Lump-Sum | 15385 | Component 1 | Without | Planned | n/a |  | n/a |  | n/a |  | 2019-05-01 |  | 2019-10-01 |  | n/a |  | 2019-10-01 |  | 2019-10-01 |  | 2019-10-01 |  |  |  | 2019-12-31
MNS |  |  |  | MOU - Community events/ support Partnership with CSSB |  | Direct Contracting |  | 19-1115c(iv) | Request for Proposals and Terms of Reference | Lump-Sum | 6154 | Component 1 | Without | Planned | n/a |  | n/a |  | n/a |  | 2019-04-01 |  | 2019-10-01 |  | n/a |  | 2019-10-01 |  | 2019-10-01 |  | 2019-10-01 |  |  |  | 2019-12-31
MNS |  |  |  | MOU-Support to CACS |  | Direct Contracting |  | 19-1121a | Request for Proposals and Terms of Reference | Lump-Sum | 312435 | Component 1 | Without | Contract in Execution | n/a |  | n/a |  | n/a |  | 2019-03-01 |  | 2019-03-01 |  | n/a |  | n/a |  | 2019-03-01 |  | 2019-03-01 | 2019-05-01 |  | 2019-05-01 | 2019-12-31
MNS |  |  |  | Community and Safety plans Profiles |  | Direct Contracting |  | 19-1123a | Request for Proposals and Terms of Reference | Lump-Sum | 92882 | Component 1 | Without | Planned | n/a |  | n/a |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | n/a |  | 2019-03-01 |  | 2019-03-01 |  |  |  | 2019-12-31
MNS |  |  |  | RJ- Multi Media Campaign (JIS) |  | Direct Contracting |  | 19-1315e | Request for Proposals and Terms of Reference | Lump-Sum | 23077 | Component 3 | Without | Planned | n/a |  | n/a |  | n/a |  | 2019-01-01 |  | 2019-01-01 |  | n/a |  | n/a |  | 2019-01-01 |  | 2019-03-01 |  |  |  | 2019-12-31
MNS |  |  |  | Child Diversion -Public Awareness Campaign |  | Selection Based on the Consultants' Qualifications |  | 19-1316c | Request for Proposals and Terms of Reference | Lump-Sum | 31384 | Component 3 | Without | Planned | 2019-11-01 |  | n/a |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | n/a |  | n/a |  | 2019-11-01 |  | 2019-11-01 |  | 2019-11-01 |  | 2019-12-31
MNS |  |  |  | Final Evaluation Firm |  | Selection Based on the Consultants' Qualifications |  | 19-1523a | Request for Proposals and Terms of Reference | Lump-Sum | 154231 | component 5 | Without | Planned | 2019-12-01 |  | n/a |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | n/a |  | n/a |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-01 |  | 2019-12-31
MNS |  |  |  | Victimization Survey |  | Direct Contracting |  | 19-1523ai | Request for Proposals and Terms of Reference | Lump-Sum | 201539 | component 5 | Without | Contract in Execution | 2019-02-02 |  | n/a |  | n/a |  | 2019-03-01 |  | 2019-04-01 |  | n/a |  | n/a |  | 2019-02-01 |  | 2019-02-01 |  | 2019-03-29 |  | 2020-06-01
INDIVIDUAL CONSULTANTS
Executing Agency: | Component (if applies) | Country's political Division (Region / Department / Jurisdiction, Province) | Region | Contract Name: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity | Process Number: | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Estimated Number of Consultants: | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) | [5 empty] | Consultant's Name | Period |  | Title | Comments
[15 empty] | No Objection to the TORs |  | Hiring Deadline |  | End of Activity |  |  | From | Until
[15 empty] | Estimated | Real | Estimated | Real | Estimated | Real
MNS |  |  |  | Parenting Field Officers |  | 3CV |  | 19-1111d | Lump-Sum | 34615 | 10 | Component 1 | Without | Planned | n/a |  | 2019-01-01 |  | Aug 31 2019 |  |  | 2019-02-01 | 2019-08-01
MNS |  |  |  | Parenting Consultant - Monthly Workshops |  | Direct Contracting |  | 19-1111d(i) | Lump-Sum | 13385 | 1 | Component 1 | Without | Planned | 2019-04-01 |  | 2019-05-01 |  | 2019-04-01 |  |  | 2019-05-01 | 2019-10-01 |  | Direct Contracting/Single Source is most appropriate as Mrs. Linda Craigie Brown is being recommended base on the continuation of downstream work services
MNS |  |  |  | Parenting Consultant - Manual |  | Direct Contracting |  | 19-1111d(iI) | Lump-Sum | 2696.29 | 1 | Component 2 | Without | Planned | 2019-04-01 |  | 2019-05-01 |  | 2019-04-01 |  |  | 2019-05-01 | 2019-10-01 |  | Direct Contracting/Single Source is most appropriate as Mrs. Linda Craigie Brown is being recommended base on the continuation of downstream work services |  | Newly included
MNS |  |  |  | Youth Ambassdor Progam -Facilitator |  | 3CV |  | 19-1115d | Lump-Sum | 2492 | 1 | Component 1 | Without | Planned | 2019-07-01 |  | 2019-08-01 |  | 2019-08-01 |  |  | 2019-08-01 | 2019-08-01
MNS |  |  |  | Life Skills - Facilitators |  | 3CV |  | 19-1115d(i) | Lump-Sum | 5000 | 2 | Component 1 | Without | Planned | 2019-04-01 |  | 2019-04-01 |  | 2019-04-01 |  |  | 2019-04-01 | 2019-08-01 |  | Consultants to be engaged on an ongoing basis across KMA, Central and Western regions.
MNS |  |  |  | Business Development - Consultant - ornamental fish farm |  | 3CV |  | 19-1223a | Lump-Sum | 2962 | 2 | Component 2 | Without | Planned | 2019-01-01 |  | 2019-01-02 |  | 2019-01-31 |  |  | 2019-01-02 | Jan 31,2019
MNS |  |  |  | Business Development -consultant - to desgin fish farm |  | 3CV |  | 19-1223a(i) | Lump-Sum | 2222 |  | Component 2 | Without | Planned | 2019-02-04 |  | 2019-02-04 |  | 2019-03-01 |  |  | 2019-02-04 | 2019-03-04
MNS |  |  |  | VSD - Resocialization - Facilitators |  | 3CV |  | 19-1311c | Lump-Sum | 1846 |  | Component 3 | Without | Planned | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  |  | 2019-01-01 | 2019-12-01 |  | Consultants to be engaged on an ongoing basis across KMA, Central and Western regions.
MNS |  |  |  | VSD SIP Facilitators |  | 3CV |  | 19-1311c(i) | Lump-Sum | 2462 |  | Component 3 | Without | Planned | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  |  | 2019-01-01 | 2019-12-01 |  | Consultants to be engaged on an ongoing basis across KMA, Central and Western regions.
MNS |  |  |  | VSD Overcomer in Action - Failitator |  | 3CV |  | 19-1311c(ii) | Lump-Sum | 462 |  | Component 3 | Without | Planned | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  |  | 2019-01-01 | 2019-12-01 |  | Consultants to be engaged on an ongoing basis across KMA, Central and Western regions.
MNS |  |  |  | VSD - Training First Responder Facilitator |  | 3CV |  | 19-1311c(iii) | Lump-Sum | 923 |  | Component 3 | Without | Planned | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  |  | 2019-01-01 | 2019-12-01 |  | Consultants to be engaged on an ongoing basis across KMA, Central and Western regions.
MNS |  |  |  | VSD-Stakeholder Facilitators |  | 3CV |  | 19-1311c(iii) | Lump-Sum | 923 |  | Component 3 | Without | Planned | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  |  | 2019-01-01 | 2019-12-01 |  | Consultants to be engaged on an ongoing basis across KMA, Central and Western regions.
MNS |  |  |  | Legal Aid- Facilitators |  | Direct Contracting |  | 19-1312c | Lump-Sum | 2308 |  | Component 3 | With | Planned | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  |  | 2019-01-01 | 2019-12-01 |  | The Bank approved a list of service providers vide CCB/CJA/1353/2016. Each service provider will be selected based on location of client and availability of service provider. Activity will be conducted on an ongoing basis.
MNS |  |  |  | Legal Aid - Drivers |  | 3CV |  | 19-1312c(i) | Lump-Sum | 9692 | 2 | Component 3 | Without | Planned | 2019-02-01 |  | 2019-04-01 |  | 2019-03-01 |  |  | 2019-04-01 | 2019-12-01
MNS |  |  |  | Legal Aid -Legal Officers |  | 3CV |  | 19-1312c(ii) | Lump-Sum | 27506 | 2 | Component 3 | Without | Planned | 2019-02-01 |  | 2019-04-01 |  | 2019-03-01 |  |  | 2019-04-01 | 2019-12-01
MNS |  |  |  | JTI-Consultant to review training manual |  | 3CV |  | 19-1313a | Lump-Sum | 4615 | 1 | Component 3 | Without | Planned | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  |  | 2019-01-01 | 2019-03-01
MNS |  |  |  | JTI - Advance Training Facilitators |  | Direct Contracting |  | 19-1313a(i) | Lump-Sum | 1231 |  | Component 3 | With | Planned | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  |  | 2019-01-01 | 2019-12-01 |  | The Bank approved a list of service providers vide CCB/CJA/682/2016 and CCB/CJA/1291/2016. Each service provider will be selected based on location of client and availability of service provider. Activity will be conducted on an ongoing basis.
MNS |  |  |  | JTI - Qualifying Training Facilitators |  | Direct Contracting |  | 19-1313a(ii) | Lump-Sum | 2385 |  | Component 3 | With | Planned | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  |  | 2019-01-01 | 2019-03-01 |  | The Bank approved a list of service providers vide CCB/CJA/682/2016 and CCB/CJA/1291/2016. Each service provider will be selected based on location of client and availability of service provider. Activity will be conducted on an ongoing basis.
MNS |  |  |  | JTI - Consultant - Mediation Pilot Project |  | Direct Contracting |  | 19-1313a(iii) | Lump-Sum | 43731 | 1 | Component 3 | With | Planned | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  |  | 2019-01-01 | 2019-03-01 |  | Individuals certified by the Dispute Resolution Foundation to conduct mediations sessions. These individuals are the only qualified persons in Jamaica to carry out scope of services. Each service provider will be selected based on location of client and availability of service provider. Activity will be conducted on an ongoing basis. The estimated cost is approximately US $50 per mediator per session.
MNS |  |  |  | RJ Week - Note Takers |  | 3CV |  | 19-1315d | Lump-Sum | 308 | 2 | Component 3 | With | Cancelled | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  |  | 2019-02-01 | 2019-02-01
MNS |  |  |  | RJ Week - Rapporteurs |  | 3CV |  | 19-1315d(i) | Lump-Sum | 231 | 2 | Component 3 | With | Cancelled | 2019-01-01 |  | 2019-01-01 |  | 2019-01-01 |  |  | 2019-02-01 | 2019-02-01
MNS |  |  |  | RJ Conference - International Presenter |  | Direct Contracting |  | 19-1315d(ii) | Lump-Sum | 15385 | 1 | Component 3 | Without |  | 2019-01-01 |  | 2019-01-02 |  | 2019-01-01 |  |  | 2019-02-01 | 2019-02-02 |  | Contract executed
MNS |  |  |  | Community Laision Officer - MOJ |  | 3CV |  | 19-1315d(iii) | Lump-Sum | 8708 | 1 | Component 3 | With |  | 2019-02-01 |  | 2019-03-01 |  | 2019-02-01 |  |  | 2019-02-01 | 2019-12-01 |  | Contract executed
MNS |  |  |  | MOJ- Justice Services Coordinator |  | 3CV |  | 19-1315d(iv) | Lump-Sum | 16.390.59 | 1 | Component 3 | without | Planned | Aug 201 9 |  | 2019-08-01 |  | 2019-08-01 |  |  | 2019-08-01 | 2019-12-01
MNS |  |  |  | Child Diversion Coordinator |  | 3CV |  | 19-1316c | Lump-Sum | 17308 | 1 | Component 3 | without |  | 2019-05-01 |  | 2019-05-01 |  | 2019-05-01 |  |  | 2019-05-01 | 2019-06-01 |  | contract executed
MNS |  |  |  | Child Diversion Pyschologist |  | 3CV |  | 19-1316c(ii) | Lump-Sum | 10404 | 1 | Component 3 | without | Planned | 2019-10-01 |  | 2019-10-01 |  | 2019-10-01 |  |  | 2019-10-01 | 2019-12-01
MNS |  |  |  | Child Diversion - Administrative Assistant |  | 3CV |  | 19-1316c(iii) | Lump-Sum | 10404 | 1 | Component 3 | without | Planned | 2019-10-01 |  | 2019-10-01 |  | 2019-10-01 |  |  | 2019-10-01 | 2019-12-01
MNS |  |  |  | TAT - Change Mgmt. Specialist |  | Direct Contracting |  | TAT | Lump-Sum | 60000 | 1 | TAT | without |  | 2019-01-01 |  | 2019-02-01 |  | 2019-06-01 |  |  | 2019-02-01 | 2019-06-01 |  | contract executed
MNS |  |  |  | Case Mgmt Manual Consultant |  | 3CV |  | 19-1523a(i) | Lump-Sum | 24385 | 1 | Component 5 | Without | Contract in Execution | 2019-04-01 |  | 2019-04-01 |  | 2019-07-01 |  |  | 2019-04-01 | 2019-07-01
MNS |  |  |  | Monitoring and Evaluation Manager |  | 3CV |  | 19-1523a(ii) | Lump-Sum | 21230 | 1 | Component 5 | Without | Contract in Execution | 2019-07-01 |  | 2019-07-01 |  | 2019-07-01 |  |  | 2019-07-01 | 2019-12-01
MNS |  |  |  | Bank Reconcilation Officer |  | 3CV |  | 19-1611b | Lump-Sum | 20326 | 1 | Programme Management | Without | Contract in Execution | 2019-02-01 |  | 2019-03-01 |  | 2019-02-01 |  |  | 2019-03-01 | 2019-12-01
MNS |  |  |  | Accounts Clerk - Payable |  | 3CV |  | 19-1611b(i) | Lump-Sum | 9808 | 2 | Programme Management | Without | Contract in Execution | 2019-06-01 |  | 2019-05-01 |  | n/a |  |  | 2019-05-01 | 2019-06-01
MNS |  |  |  | Office Attendant - Temporary |  | 3CV |  | 19-1611b(ii) | Lump-Sum | 962.22 | 1 | Programme Management | Without | Contract in Execution | 2019-06-01 |  | 2019-06-01 |  | n/a |  |  | 2019-06-01 | 2019-08-01
MNS |  |  |  | Senior Regional Case Mgmt Coordinator |  | Direct Contracting |  | 19-1611b(iii) | Lump-Sum | 42725.06 | 1 | Programme Management | Without | Contract in Execution | 2019-05-01 |  | 2019-06-01 |  | n/a |  |  | 2019-05-01 | 2019-12-01
MNS |  |  |  | Programme Manager |  | Direct Contracting |  | 19-1611b(iv) | Lump-Sum |  | 1 | Programme Management | Without | Contract in Execution | 2019-05-01 |  | 2019-06-01 |  | n/a |  |  | 2019-05-01 | 2019-12-01
MNS |  |  |  | MIS Officer |  | Direct Contracting |  | 19-1611b(v) | Lump-Sum | 9672.72 | 1 | Programme Management | Without | Contract in Execution | 2019-05-01 |  | 2019-06-01 |  | n/a |  |  | 2019-08-01 | 2019-12-01

## 5. Financial Plan
CITIZEN SECURITY AND JUSTICE PROGRAMME 111
SECTION 5: Detailed Financial Plan
PROJECT NUMBER: 3191/OC-JA
1172936.87
WBS Code | Investment Category | Quarter 1 |  |  |  | Quarter 2 |  |  |  | Quarter 3 |  |  |  | WBS Code | Investment Category | Quarter 4 |  |  |  |  | TOTAL PER FUND SOURCE
|  | January | February | March | Total Q1 | April | May | June | Total Q2 | July | August | September | Total Q3 |  |  | October | November | December | Total Q4 | Annual Total | IDB | DFID | GAC | GOJ
1 | Component 1 -Culture change for Peaceful Co-existence and Community Governance | [12 empty] | 1 | Component 1 -Culture change for Peaceful Co-existence and Community Governance
1.1.1.1 | Training courses provided to community members on parenting and healthy gender norms in fami-lies. | 11773.87 | 41028 | 104327.5 | 157129.37 | 4454 | 40563 | 8561 | 53578 | 37322 | 75489 | 86666.86 | 199477.86 | 1.1.1.1 | Training courses provided to community members on parenting and healthy gender norms in fami-lies. | 8281.86 | 67955.86 | 18444.86 | 94682.58 | 504867.81 | 126388.6 | 78115 | 245364.21 | 55000
1.1.1.2 | Counselling/Psycho-Social Support provided to victims/witnesses of violence (including domestic violence) | 2478.8 | 63.11 | 28381.22 | 30923.13 | 418.92 | 14765.65 | 537 | 15721.57 | 67029.63 | 74807.41 | 113877.78 | 255714.82 | 1.1.1.2 | Counselling/Psycho-Social Support provided to victims/witnesses of violence (including domestic violence) | 39716.67 | 2962.96 | 33420.37 | 76100 | 378459.52 | 105367.17 | 62358 | 105367.18 | 105367.18
| Social Workers & Psychologists Consultants | 24796.54 | 23859.37 | 24469.5 | 73125.41 | 24199.73 | 24381.14 | 23642 | 72222.87 | 19405.14 | 19405.14 | 19405 | 58215.28 |  | Social Workers & Psychologists Consultants | 19405 | 19405 | 19405 | 58215 | 261778.56 | 39068 | 152252 | 19960.65 | 50497.91
1.1.1.4 | Violence Interruption Services Provided (e.g. Gang Interruption & Reintegration activities) | 35902 | 59165 | 126192 | 221259 |  | 284082 |  | 284082 | 188146 |  | 185183 | 373329 | 1.1.1.4 | Violence Interruption Services Provided (e.g. Gang Interruption & Reintegration activities) |  |  | 185183 | 185183 | 1063853 | 300536 | 372827 | 195245 | 195245
1.1.1.4 | Violence Prevention and Conflict Resolution Education and Training in Schools | 29244 | 19438.84 | 20297 | 68979.84 | 11926 | 340 |  | 12266 | 19129 | 19129.26 |  | 38258.26 | 1.1.1.4 | Violence Prevention and Conflict Resolution Education and Training in Schools |  |  |  | 0 | 119504.1 | 20681.13 | 48656.33 |  | 50166.64
| Social Marketing Staff Consultants | 12232.52 | 11290.11 | 12378 | 35900.63 | 10601 | 12112 | 6804 | 29517 | 16660.28 | 11709.11 | 11709.11 | 40078.5 |  | Social Marketing Staff Consultants | 11709.11 | 11709.11 | 11709.11 | 35127.33 | 140623.46 | 26376.97 | 47857 |  | 66389.49
1.1.1.5 | Social Marketing for awareness and attitude change to promote 'culture of lawfulness' | 3945.48 | 3098.89 | 57439 | 64483.37 | 4865 | 12015 | 1992 | 18872 | 24689 | 19930.89 | 140740.89 | 185360.78 | 1.1.1.5 | Social Marketing for awareness and attitude change to promote 'culture of lawfulness' | 91851.89 | 38518.89 | 151110.89 | 281481.67 | 550197.82 | 31980 | 131906.79 | 165290 | 221021.03
1.1.1.6 | Community Events to improve citizen-police relations | 0 |  |  | 0 |  |  |  | 0 |  | 2962.96 |  | 2962.96 | 1.1.1.6 | Community Events to improve citizen-police relations |  |  |  | 0 | 2962.96 | 2963
1.1.1.7 | Crisis intervention activities conducted |  | 43915 |  | 43915 |  | 53271 |  | 53271 | 52086 |  |  | 52086 | 1.1.1.7 | Crisis intervention activities conducted | 26043 |  |  | 26043 | 175315 | 72377 | 18366 | 18366 | 66206
1.1.2.1 | Training and technical assistance provided to community leaders and residents | 18535.59 | 18584.49 | 24974.53 | 62094.61 | 4531.14 | 4007.99 | 2665 | 11204.13 | 33204.44 |  |  | 33204.44 | 1.1.2.1 | Training and technical assistance provided to community leaders and residents |  | 33330.37 |  | 33330.37 | 139833.55 |  | 48856 | 90977.55
1.1.2.1 | Community Infrastructure | 7130 | 73687 | 95561 | 176378 | 6864 | 70132 | 8006 | 85002 | 160745 | 199726 | 122239 | 482710 | 1.1.2.1 | Community Infrastructure | 79964 | 7245 | 7245 | 94454 | 838544 | 283049 | 27000 |  | 528495
1.1.2.2 | Community Safety Plans Developed with safety audits for vulnerable groups |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1.1.2.2 | Community Safety Plans Developed with safety audits for vulnerable groups |  | 22596 |  | 22596 | 22596 | 12720 | 9876
1.1.2.3 | Peace Building through cultural and sporting activities | [12 empty] | 1.1.2.3 | Peace Building through cultural and sporting activities |  |  |  |  | 0
1.1.2.4 | Coordination at local level among MDAs & CBOs |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 1.1.2.4 | Coordination at local level among MDAs & CBOs |  |  |  | 0 | 0
| Frontline Service Staff (includes regional Coordinators, CAOs, other frontline staff) | 113595.9 | 7590.12 | 141801.19 | 262987.21 | 118990.17 | 122079.37 | 110428 | 351497.54 | 109687.26 | 109687.26 | 109687.26 | 329061.78 |  | Frontline Service Staff (includes regional Coordinators, CAOs, other frontline staff) | 109687.26 | 109687.26 | 109687.26 | 329061.78 | 1272608.31 | 151430 | 462380 |  | 658798.31
COMPONENT 1: TOTAL |  | 259634.7 | 301719.93 | 635820.94 | 1197175.57 | 186849.96 | 637749.15 | 162635 | 987234.11 | 728103.75 | 532847.03 | 789508.9 | 2050459.68 | COMPONENT 1: TOTAL |  | 386658.79 | 313410.45 | 536205.49 | 1236274.73 | 5471144.09 | 1172936.87 | 1460450.12 | 840570.59 | 1997186.56
2 | 1.1.2.5 | [12 empty] | 2 | 1.1.2.5
WBS Code | Vocational Training provided to targeted beneficiaries | 31076.98 | 116901.73 | 519731.96 | 667710.67 | 101165.46 | 111642.48 | 93913 | 306720.94 | 173876.55 | 173876.55 | 136839.51 | 484592.61 | WBS Code | Vocational Training provided to targeted beneficiaries | 97432.1 | 97432.1 | 91506.13 | 286370.33 | 1745394.55 | 160347.59 | 417396.78 | 793862.48 | 373787
1.2.1.1 | Support to education provided to male/female beneficiaries | 10412.53 | 17811.56 | 38714.51 | 66938.6 | 7589.02 | 11002.04 | 710 | 19301.06 |  |  |  | 0 | 1.2.1.1 | Support to education provided to male/female beneficiaries | 7407.41 | 7407.41 | 7407.41 | 22222.23 | 108461.89 | 102161.89 |  |  | 6300
1.2.1.3a | Remedial education provided in or outside comunities with integrated and life-skills training | 11211.91 | 196304.42 | 448299.61 | 655815.94 | 38009.15 | 49053.97 | 39957 | 127020.12 | 48148.15 | 48148.15 | 48148.15 | 144444.45 | 1.2.1.3a | Remedial education provided in or outside comunities with integrated and life-skills training | 48148.15 | 48148.15 | 48148.15 | 144444.45 | 1071724.96 | 449677.48 | 226579.7 | 238096.39 | 157371.39
1.2.1.3b | Job-seeking, placement, and training services provided to target beneficiaries | 3402.78 | 3247.18 | 3355.75 | 10005.71 | 3285.11 | 3277.34 | 3408 | 9970.45 | 8303.22 | 3858.77 | 3858.77 | 16020.76 | 1.2.1.3b | Job-seeking, placement, and training services provided to target beneficiaries | 3858.77 | 3858.77 | 3858.77 | 11576.31 | 47573.23 |  | 47573
1.2.1.4 | On-the-Job or work orientation apprenticeship/internships provided for male/female youth | 33301.23 | 41739.19 | 65694.32 | 140734.74 | 48735.56 | 42271.64 | 45620 | 136627.2 | 161077.04 | 201077.04 | 94040 | 456194.08 | 1.2.1.4 | On-the-Job or work orientation apprenticeship/internships provided for male/female youth | 90336.3 | 90336.3 | 90336.3 | 271008.9 | 1004564.92 | 140763 | 455878 | 146017 | 261906.92
1.2.2.1 | Business Development services provided for community residents in entrepreneurship | 36.92 | 1695.26 | 5082.67 | 6814.85 | 546.68 | 1642.78 |  | 2189.46 | 111 | 20434 | 474 | 21019 | 1.2.2.1 | Business Development services provided for community residents in entrepreneurship | 474 | 474 | 474 | 1422 | 31445.31 | 5670 | 24493.31 |  | 1282
| Frontline Service delivery staff Consultants including Regional Coordinators | 67.41 | 102523.78 | 3025.45 | 105616.64 | 3987.3 |  |  | 3987.3 |  |  |  | 0 |  | Frontline Service delivery staff Consultants including Regional Coordinators |  |  |  | 0 | 109603.94 | 4054.71 | 47130 | 58419.27
COMPONENT 2: TOTAL |  | 89509.76 | 480223.12 | 1083904.27 | 1653637.15 | 203318.28 | 218890.25 | 183608 | 605816.53 | 391515.96 | 447394.51 | 283360.43 | 1122270.9 | COMPONENT 2: TOTAL |  | 247656.73 | 247656.73 | 241730.76 | 737044.22 | 4118768.8 | 862674.67 | 1219050.79 | 1236395.14 | 800647.31
3 | Community Justice Services | [7 empty] | 0 |  |  |  | 0 | 3 | Community Justice Services |  |  |  | 0
IDB code: 4.2-4.3 | Victim Services expanded and serving new clients in target communities | 8801 | 22421 | 55138 | 86360 | 2421 | 13178 | 1477 | 17076 | 28222 | 85753 | 66000 | 179975 | IDB code: 4.2-4.3 | Victim Services expanded and serving new clients in target communities | 87944 | 66871 | 19308 | 174123 | 457534 | 139464 | 139464 | 139465 | 39141
1.3.1.6c | Technical assistance and resource provided to Legal Aid Council | 3117 | 4605 | 6247 | 13969 | 8887 | 9566 | 9523 | 27976 | 12273 | 22933 | 11939 | 47145 | 1.3.1.6c | Technical assistance and resource provided to Legal Aid Council | 11322 | 15921 | 18063 | 45306 | 134396 |  | 68396 |  | 66000
1.3.1.5d | Technical assistance and resource provided to Justice of the Peace Service Entities | 12874 | 6887 | 11496 | 31257 | 8257 | 7686 | 3293 | 19236 | 33959 | 66560 | 7963 | 108482 | 1.3.1.5d | Technical assistance and resource provided to Justice of the Peace Service Entities | 40353 | 28333 | 16479 | 85165 | 244140 | 35746.29 | 40647 | 65746.71 | 102000
1.3.1.2c | Technical assistance and resources provided to RJ Programme | 36267 | 82836 | 76562 | 195665 | 66216 | 44049 | 35360 | 145625 | 42407 | 58307 | 64815 | 165529 | 1.3.1.2c | Technical assistance and resources provided to RJ Programme | 42407 | 38148 | 46129 | 126684 | 633503 | 1947 | 118790.46 | 166500.93 | 346264.61
1.3.1.3b,c | Technical assistance and resources provided to Child Diversion | 1383 | 1455 | 1484 | 4322 | 1483 | 2793 |  | 4276 | 41591 | 132653 | 72235 | 246479 | 1.3.1.3b,c | Technical assistance and resources provided to Child Diversion | 113309 | 49679 | 50013 | 213001 | 468078 | 2258 | 108549.46 | 106291.46 | 250979.08
1.3.1.5a | Social Justice Consortium | 2540 | 3018 | 2980 | 8538 | 2977 | 2948 | 3069 | 8994 |  | 2729.69 | 2729.69 | 5459.38 | 1.3.1.5a | Social Justice Consortium | 2729.69 | 2729.69 | 2729.69 | 8189.07 | 31180.45 | 8100.45 |  | 20192 | 2888
COMPONENT 3: TOTAL |  | 64982 | 121222 | 153907 | 340111 | 90241 | 80220 | 52722 | 223183 | 158452 | 368935.69 | 225681.69 | 753069.38 | COMPONENT 3: TOTAL |  | 298064.69 | 201681.69 | 152721.69 | 652468.07 | 1968831.45 | 187515.74 | 475846.92 | 498196.1 | 807272.69
4 | Transition Plan | [9 empty] | 14814.81 | 78518.52 | 93333.33 | 4 | Transition Plan | 29629.63 | 66666.67 | 23140 | 119436.3 | 212769.63 | 70923.33 | 70923.33 | 70923.33
4 | Monitoring & Evaluations | [12 empty] | 4 | Monitoring & Evaluations |  |  |  |  | 0
| Victimization Survey |  |  | 70651.14 | 70651.14 |  |  |  | 0 |  | 129383.07 |  | 129383.07 |  | Risk Assement Tools | 64692 |  | 32346 | 97038 | 297072.21 | 148536.11 |  | 148536.11
WBS Code | PEU Client management database Software purchased; staff trained; system implemented | 1396.46 |  | 1360 | 2756.46 |  |  | 690 | 690 | 601.02 | 3193.61 | 6526.94 | 10321.57 | WBS Code | PEU Client management database Software purchased; staff trained; system implemented | 1341.76 | 601.02 | 601.02 | 2543.8 | 16311.83 | 7539 |  | 8772.83
| PEU hardware purchases, software upgrades |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | PEU hardware purchases, software upgrades |  |  |  | 0 | 0
| JCO software, hardware, tech support |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | JCO software, hardware, tech support |  |  |  | 0 | 0
| JCO Equipment & Furniture |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | JCO Equipment & Furniture |  |  |  | 0 | 0
| 4 new staff to aid with secondary data collection by the Jamaica Crime Observatory (JCO) | 2803.92 | 2782.76 | 2772.74 | 8359.42 | 2815.86 | 2844.21 | 2686 | 8346.07 | 2750.48 | 2750.48 | 2750.48 | 8251.44 |  | 4 new staff to aid with secondary data collection by the Jamaica Crime Observatory (JCO) | 2750.48 | 2750.48 | 2750.48 | 8251.44 | 33208.37 | 16658.41 |  | 16549.96
| Technical Assistance for Improving Monitoring Systems & Reporting | 366.25 | 380.96 |  | 747.21 |  |  |  | 0 | 2592.59 |  | 740.74 | 3333.33 |  | Technical Assistance for Improving Monitoring Systems & Reporting |  |  |  | 0 | 4080.54 | 908.23 |  | 3172.31
| Final Evaluation |  |  |  | 0 |  |  |  | 0 | 370.37 |  | 37037.04 | 37407.41 |  | Final Evaluation |  |  | 55555.56 | 55555.56 | 92962.97 | 46481.49 |  | 46481.49
| Impact Evaluation on Parenting Program | 2366.67 | 2251.85 | 2327.15 | 6945.67 | 5810 | 11412.31 |  | 17222.31 | 36719.44 | 34837.16 | 5560.35 | 77116.95 |  | Impact Evaluation on Parenting Program | 9289.72 | 2222.22 | 2222.22 | 13734.16 | 115019.09 | 87968.71 |  | 27050.38
| Impact Evaluation on Vocational Program |  |  |  | 0 | 2208.16 | 2327.99 | 2208 | 6744.15 |  |  |  | 0 |  | Impact Evaluation on Vocational Program |  |  |  | 0 | 6744.15 | 4446.16 |  | 2297.84
| Personnel | 11984.24 | 11948.22 | 12247.4 | 36179.86 | 12014.27 | 11934.1 | 10735 | 34683.37 | 11051.87 | 11051.87 | 11051.87 | 33155.61 |  | Personnel | 11051.87 | 11051.87 | 11051.87 | 33155.61 | 137174.45 | 34693 |  | 102481.45
| Training and technical assistance to establish or improve community governannce structure |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | Training and technical assistance to establish or improve community governannce structure |  |  |  | 0 | 0
| Advocacy campaign developed and implemented for community advocay plans survey |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | Advocacy campaign developed and implemented for community advocay plans survey |  |  |  | 0 | 0
| MONITORING & EVALUATIONS TOTAL | 18917.54 | 17363.79 | 89358.43 | 125639.76 | 22848.29 | 28518.61 | 16319 | 67685.9 | 54085.77 | 181216.19 | 63667.42 | 298969.38 |  | MONITORING & EVALUATIONS TOTAL | 89125.83 | 16625.59 | 104527.15 | 210278.57 | 702573.61 | 347231.11 | 0 | 355342.37 | 0
6 | Programme Management | [12 empty] | 6 | Programme Management
| Stationery and General Administrative Expenses, Furniture & Equipment | 36271.96 | 26417.56 | 40740.72 | 103430.24 | 29042.79 | 36288.45 | 24472 | 89803.24 | 37407.57 | 30481.87 | 36444.83 | 104334.27 |  | Stationery and General Administrative Expenses, Furniture & Equipment | 28148.53 | 34815.2 | 28148.53 | 91112.26 | 388680.01 | 388680.01
| Personnel | 51008.78 | 49859.74 | 48561.28 | 149429.8 | 47697.71 | 40875.54 | 39927 | 128500.25 | 46427.38 | 46427.38 | 46427.38 | 139282.14 |  | Personnel | 46427.38 | 46427.38 | 46427.38 | 139282.14 | 556494.33 | 556494.33
| Audit |  |  |  | 0 |  |  |  | 0 | 16577.78 |  |  | 16577.78 |  | Audit |  |  |  | 0 | 16577.78 | 16577.78
| PROGRAMME MANAGEMENT TOTAL | 87280.74 | 76277.3 | 89302 | 252860.04 | 76740.5 | 77163.99 | 64399 | 218303.49 | 100412.73 | 76909.25 | 82872.21 | 260194.19 |  | PROGRAMME MANAGEMENT TOTAL | 74575.91 | 81242.58 | 74575.91 | 230394.4 | 961752.12 | 961752.12 | 0 | 0 | 0
5 | Technical Advisory Team |  | 4719 | 12000 | 16719 | 5564.2 |  | 12000 | 17564.2 | 19555.56 |  |  | 19555.56 | 5 | Technical Advisory Team |  |  |  | 0 | 53838.76 |  | 53838.76
| Technical Assistant | 4687 | 2252 | 11239 | 18178 | 2379.8 | 2273 | 6751 | 11403.8 | 2222.22 | 17244 | 5689 | 25155.22 |  | Technical Assistant |  |  |  | 0 | 54737.02 |  | 54737.02
PROJECT: TOTAL |  | 525011.74 | 1003777.14 | 2075531.64 | 3604320.52 | 587942.03 | 1044815 | 498434 | 2131191.03 | 1454347.99 | 1639361.48 | 1529298.17 | 4623007.64 | PROJECT: TOTAL |  | 1125711.58 | 927283.71 | 1132901 | 3185896.29 | 13544415.48 | 3603033.84 | 3334846.94 | 3001427.53 | 3605106.56
DISBURSEMENT PROJECTION |  |  |  | 5735511.55 | [6 empty] | 7808903.93 |  |  | DISBURSEMENT PROJECTION | [5 empty] | 13544415.48 | 0 | 0 | 0
Approved By
| Orville Simmonds |  |  |  | Orville Simmonds
| <name> |  |  |  | <name>
| Sponsor / Owner |  |  |  | Project Manager

## 6. Consolidated Financial Plan
CITIZEN SECURITY AND JUSTICE PROGRAMME 111
SECTION 6: Consolidated Financial Plan | [5 empty] | ENTER GOJ ALLOCATION FOR 2019/2020 IN THE BUDGET SECTIO0N
PROJECT NUMBER: 3191/OC-JA
WBS Code | Investment Category | Original Budget in force US$'000 |  |  |  |  | Total Expenditure to Date US$'000-(As December 2018) |  |  |  |  | Available Balance |  |  |  |  | Investment Category | Estimated Budgetary Requirements (January - December 2019) US$ '000 |  |  |  |  | Balance to Commit to the End of the Program US$ '000
|  | IDB | DFID | GAC | GOJ | Total | IDB | DFID | GAC | GOJ | Total | IDB | DFID | GAC | GOJ | Total |  | IDB | DFID | GAC | GOJ | Total | IDB | DFID | GAC | GOJ | Total | NOTES
1 | Component 1 -Culture change for Peaceful Co-existence and Community Governance | 5973916 | 4543379 | 2898288 | 0 | 13415583 | 4992994.25 | 3044295 | 2897119 | 0 | 10934408.25 | 980921.75 | 1499084 | 1169 | 0 | 2481174.75 | Component 1 -Culture change for Peaceful Co-existence and Community Governance | 1172936.87 | 1460450.12 | 840570.59 | 1997186.56 | 5471144.09 | -192015.12 | 38633.88 | -839401.59 | 0 | -992782.83 | Amounts in Credit for the Fund sources are account for via budget transer.
1.1.1.1 | Sub-component 1111: Training courses provided to community members on parenting and healthy gender norms in fami-lies. | 275614 | 217875 | 24027 | 0 | 517516 | 234648.75 | 65243 | 24027 | 0 | 323918.75 | 40965.25 | 152632 | 0 | 0 | 193597.25 | Sub-component 1111: Training courses provided to community members on parenting and healthy gender norms in fami-lies. | 126388.6 | 78115 | 245364.21 | 55000 | 504867.81 | -85423.35 | 74517 | -245364.21 | 0 | -256270.56
1.1.1.2 | Counselling/Psycho-Social Support provided to victims/witnesses of violence (including domestic violence) | 287032 | 233418 | 52598 | 0 | 573048 | 224673.95 | 158371 | 52007 | 0 | 435051.95 | 62358.05 | 75047 | 591 | 0 | 137996.05 | Counselling/Psycho-Social Support provided to victims/witnesses of violence (including domestic violence) | 105367.17 | 62358 | 105367.18 | 105367.18 | 378459.52 | -43009.12 | 12689 | -104776.18 | 0 | -135096.3
1.1.1.1 | Social Workers & Psychologists Consultants | 465209 | 589408 | 375132 | 0 | 1429749 | 426140.96 | 437156 | 375183 | 0 | 1238479.96 | 39068.04 | 152252 | -51 | 0 | 191269.04 | Social Workers & Psychologists Consultants | 39068 | 152252 | 19960.65 | 50497.91 | 261778.56 | 0.04 | 0 | -20011.65 | 0 | -20011.61
1.1.1.3 | Violence Interruption Services Provided (e.g. Gang Interruption & Reintegration activities) | 852579 | 1104535 | 1136143 | 0 | 3093257 | 791965 | 744233 | 1136143 | 0 | 2672341 | 60614 | 360302 | 0 | 0 | 420916 | Violence Interruption Services Provided (e.g. Gang Interruption & Reintegration activities) | 300536 | 372827 | 195245 | 195245 | 1063853 | -239922 | -12525 | -195245 | 0 | -447692
1.1.1.4 | Violence Prevention and Conflict Resolution Education and Training in Schools | 359375 | 430737 | 68857 | 0 | 858969 | 358764.94 | 238789 | 68857 | 0 | 666410.94 | 610.06 | 191948 | 0 | 0 | 192558.06 | Violence Prevention and Conflict Resolution Education and Training in Schools | 20681.13 | 48656.33 | 0 | 50166.64 | 119504.1 | -20071.07 | 143291.67 | 0 | 0 | 123220.6
1.1.1.5 | Social Marketing Staff Consultants | 258803 | 250631 | 193629 | 0 | 703063 | 227136.08 | 202774 | 193629 | 0 | 623539.08 | 31666.92 | 47857 | 0 | 0 | 79523.92 | Social Marketing Staff Consultants | 26376.97 | 47857 | 0 | 66389.49 | 140623.46 | 5289.95 | 0 | 0 | 0 | 5289.95
1.1.1.5 | Social Marketing for awareness and attitude change to promote 'culture of lawfulness' | 309878 | 566750 | 150510 | 0 | 1027138 | 277897.64 | 158050 | 150510 | 0 | 586457.64 | 31980.36 | 408700 | 0 | 0 | 440680.36 | Social Marketing for awareness and attitude change to promote 'culture of lawfulness' | 31980 | 131906.79 | 165290 | 221021.03 | 550197.82 | 0.36 | 276793.21 | -165290 | 0 | 111503.57
1.1.1.6 | Community Events to improve citizen-police relations | 13431 | 3101 |  | 0 | 16532 | 966.33 |  |  | 0 | 966.33 | 12464.67 | 3101 | 0 | 0 | 15565.67 | Community Events to improve citizen-police relations | 2963 | 0 | 0 | 0 | 2962.96 | 9501.67 | 3101 | 0 | 0 | 12602.67
1.1.1.7 | Crisis intervention activities conducted | 159982 | 93870 | 55162 | 0 | 309014 | 87604.6 | 57138 | 55162 | 0 | 199904.6 | 72377.4 | 36732 | 0 | 0 | 109109.4 | Crisis intervention activities conducted | 72377 | 18366 | 18366 | 66206 | 175315 | 0.4 | 18366 | -18366 | 0 | 0.4
1.5.2.4 | Training and technical assistance provided to community leaders and residents | 403860 | 302759 | 193543 | 0 | 900162 | 299659.13 | 253903 | 193543 | 0 | 747105.13 | 104200.87 | 48856 | 0 | 0 | 153056.87 | Training and technical assistance provided to community leaders and residents | 0 | 48856 | 90977.55 | 0 | 139833.55 | 104200.87 | 0 | -90977.55 | 0 | 13223.32
1.1.2.1 | Community Infrastructure | 1727139 | 348866 | 127842 | 0 | 2203847 | 1444089.83 | 347937 | 127842 | 0 | 1919868.83 | 283049.17 | 929 | 0 | 0 | 283978.17 | Community Infrastructure | 283049 | 27000 | 0 | 528495 | 838544 | 0.17 | -26071 | 0 | 0 | -26070.83
1.1.2.2 | Community Safety Plans Developed with safety audits for vulnerable groups | 154746 | 93168 | 146923 | 0 | 394837 | 142026.29 | 73168 | 146923 | 0 | 362117.29 | 12719.71 | 20000 | 0 | 0 | 32719.71 | Community Safety Plans Developed with safety audits for vulnerable groups | 12720 | 9876 | 0 | 0 | 22596 | -0.29 | 10124 | 0 | 0 | 10123.71
1.13 | Peace Building through cultural and sporting activities | 5807 | 3688 | 1305 | 0 | 10800 | 3527.84 | 2960 | 676 | 0 | 7163.84 | 2279.16 | 728 | 629 | 0 | 3636.16 | Peace Building through cultural and sporting activities | 0 | 0 | 0 | 0 | 0 | 2279.16 | 728 | 629 | 0 | 3636.16
1.1.2.4 | Coordination at local level among MDAs & CBOs | 0 | 2221 |  | 0 | 2221 |  | 2221 |  | 0 | 2221 | 0 | 0 | 0 | 0 | 0 | Coordination at local level among MDAs & CBOs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Frontline Service Staff Consultants | 700461 | 302352 | 372617 | 0 | 1375430 | 473892.91 | 302352 | 372617 | 0 | 1148861.91 | 226568.09 | 0 | 0 | 0 | 226568.09 | Frontline Service Staff Consultants | 151430 | 462380 | 0 | 658798.31 | 1272608.31 | 75138.09 | -462380 | 0 | 0 | -387241.91
2 | 1.1.2.5 | 5934552 | 4363882 | 5173663 | 0 | 15472097 | 5403482 | 3154010 | 4908831 | 1219178 | 14685501 | 531070 | 1209872 | 264832 | 0 | 2005774 | 1.1.2.5 | 862674.67 | 1219050.79 | 1236395.14 | 800647.31 | 4118767.91 | -331604.67 | -9178.79 | -971563.14 | 0 | -1312346.6
WBS Code | Vocational Training provided to targeted beneficiaries | 2160810 | 781054 | 1906941 | 0 | 4848805 | 2013930.05 | 464999 | 1906407 | 70477 | 4455813.05 | 146879.95 | 316055 | 534 | 0 | 463468.95 | Vocational Training provided to targeted beneficiaries | 160347.59 | 417396.78 | 793862.48 | 373787 | 1745393.85 | -13467.64 | -101341.78 | -793328.48 |  | -908137.9
1.2.1.1 | Support to education provided to male/female beneficiaries | 966998 | 237266 | 227289 | 0 | 1431553 | 796014.11 | 237266 | 227289 |  | 1260569.11 | 170983.89 | 0 | 0 | 0 | 170983.89 | Support to education provided to male/female beneficiaries | 102161.89 | 0 | 0 | 6300 | 108461.89 | 68822 | 0 | 0 |  | 68822
1.2.1.3a | Remedial education provided in or outside comunities with integrated and life-skills training | 348826 | 259281 | 489970 | 0 | 1098077 | 197211.12 | 185753 | 425924 | 36420 | 845308.12 | 151614.88 | 73528 | 64046 | 0 | 289188.88 | Remedial education provided in or outside comunities with integrated and life-skills training | 449677.48 | 226579.7 | 238096.39 | 157371.39 | 1071724.96 | -298062.6 | -153051.7 | -174050.39 |  | -625164.69
1.2.1.3b | Job-seeking, placement, and training services provided to target beneficiaries | 102257 | 137983 | 63211 | 0 | 303451 | 62821.95 | 86844 | 63211 |  | 212876.95 | 39435.05 | 51139 | 0 | 0 | 90574.05 | Job-seeking, placement, and training services provided to target beneficiaries | 0 | 47573 | 0 | 0 | 47573 | 39435.05 | 3566 | 0 |  | 43001.05
1.2.1.4 | On-the-Job or work orientation apprenticeship/internships provided for male/female youth | 910148 | 605608 | 790290 | 0 | 2306046 | 908995.37 | 286648 | 644273 | 1112281 | 2952197.37 | 1152.63 | 318960 | 146017 | 0 | 466129.63 | On-the-Job or work orientation apprenticeship/internships provided for male/female youth | 140763 | 455878 | 146017 | 261906.92 | 1004564.92 | -139610.37 | -136918 | 0 |  | -276528.37
1.2.2.1 | Business Development services provided for community residents in entrepreneurship | 23751 | 47260 | 15144 | 0 | 86155 | 2987.87 | 3184 |  |  | 6171.87 | 20763.13 | 44076 | 15144 | 0 | 79983.13 | Business Development services provided for community residents in entrepreneurship | 5670 | 24493.31 | 0 | 1282 | 31445.31 | 15093.13 | 19582.69 | 15144 |  | 49819.82
| Crisis intervention activities conducted |  | 25879 |  |  | 25879 |  | 25879 |  |  | 25879 | 0 | 0 | 0 | 0 | 0 | Crisis intervention activities conducted | [5 empty] | 0 | 0 | 0 | 0
| Frontline Service delivery staff Consultants including Regional Coordinators | 1421762 | 2269551 | 1680818 | 0 | 5372131 | 1421521.53 | 1863437 | 1641727 |  | 4926685.53 | 240.47 | 406114 | 39091 | 0 | 445445.47 | Frontline Service delivery staff Consultants including Regional Coordinators | 4054.71 | 47130 | 58419.27 | 0 | 109603.98 | -3814.24 | 358984 | -19328.27 | 0 | 335841.49
| 1.2.2.2 | 1798619 | 1601311 | 4183371 | 0 | 7583301 | 1226611.94 | 1041992 | 1573003 | 0 | 3841606.94 | 572007.06 | 559319 | 2610368 | 0 | 3741694.06 | 1.2.2.2 | 187515.74 | 475846.92 | 498196.1 | 807272.69 | 1968831.45 | 384491.32 | 83472.08 | 2112171.9 |  | 2580135.3
IDB code: 4.2-4.3 | Victim Services expanded and serving new clients in target communities | 425418.42 | 308916 | 474647 | 0 | 1208981.42 | 162919.58 | 129019 | 136832 | 0 | 428770.58 | 262498.84 | 179897 | 337815 | 0 | 780210.84 | Victim Services expanded and serving new clients in target communities | 139464 | 139464 | 139465 | 39141 | 457534 | 123034.84 | 40433 | 198350 |  | 361817.84
1.3.1.6c | Technical assistance and resource provided to Legal Aid Council | 84751 | 147067 | 158772 | 0 | 390590 | 48397.88 | 57042 | 138504 | 0 | 243943.88 | 36353.12 | 90025 | 20268 | 0 | 146646.12 | Technical assistance and resource provided to Legal Aid Council | 0 | 68396 | 0 | 66000 | 134396 | 36353.12 | 21629 | 20268 |  | 78250.12
1.3.1.5d | Technical assistance and resource provided to Justice of the Peace Service Entities | 300254.58 | 128772 | 360156 | 0 | 789182.58 | 185299.81 | 76125 | 215201 | 0 | 476625.81 | 114954.77 | 52647 | 144955 | 0 | 312556.77 | Technical assistance and resource provided to Justice of the Peace Service Entities | 35746.29 | 40647 | 65746.71 | 102000 | 244140 | 79208.48 | 12000 | 79208.29 |  | 170416.77
1.3.1.2c | Technical assistance and resources provided to RJ Programme | 768981 | 806532 | 1511737 | 0 | 3087250 | 767033.77 | 686320 | 998742 | 0 | 2452095.77 | 1947.23 | 120212 | 512995 | 0 | 635154.23 | Technical assistance and resources provided to RJ Programme | 1947 | 118790.46 | 166500.93 | 346264.61 | 633503 | 0.23 | 1421.54 | 346494.07 |  | 347915.84
1.3.1.3b,c | Technical assistance and resources provided to Child Diversion | 36147 | 159072 | 867742 | 0 | 1062961 | 33888.68 | 46867 | 46100 | 0 | 126855.68 | 2258.32 | 112205 | 821642 | 0 | 936105.32 | Technical assistance and resources provided to Child Diversion | 2258 | 108549.46 | 106291.46 | 250979.08 | 468078 | 0.32 | 3655.54 | 715350.54 |  | 719006.4
1.3.1.5a | Social Justice Consortium | 183067 | 50952 | 810317 | 0 | 1044336 | 29072.22 | 46619 | 37624 | 0 | 113315.22 | 153994.78 | 4333 | 772693 | 0 | 931020.78 | Social Justice Consortium | 8100.45 | 0 | 20192 | 2888 | 31180.45 | 145894.33 | 4333 | 752501 |  | 902728.33
4 | Transition Plan | 131215 |  | 114391 | 0 | 245606 | 13438 |  | 14563 | 0 | 28001 | 117777 | 0 | 99828 | 0 | 217605 | Transition Plan | 70923.33 | 70923.33 | 70923.33 |  | 212769.99 | 46853.67 | -70923.33 | 28904.67 | 0 | 4835.01
5 | Component 5 - Monitoring and Evaluation | 1608314 | 179576 | 1402106 | 0 | 3189996 | 939260.06 | 179434 | 978975 | 0 | 2097669.06 | 669053.94 | 142 | 423131 | 0 | 1092326.94 | Component 5 - Monitoring and Evaluation | 347231.11 | 0 | 355342.37 | 0 | 702573.48 | 470358.94 | 142 | 216324.74 | 0 | 686825.68
| Risk Assement Tools | 21614 | 0 | 4784 | 0 | 26398 | 21614 | 0 | 4784 | 0 | 26398 | 0 | 0 | 0 | 0 | 0 | Risk Assement Tools |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS Code | PEU Client management database Software purchased; staff trained; system implemented | 104615 | 1522 | 105633 | 0 | 211770 | 87679.96 | 1522 | 71123 | 0 | 160324.96 | 16935.04 | 0 | 34510 | 0 | 51445.04 | PEU Client management database Software purchased; staff trained; system implemented | 7539 | 0 | 8772.83 | 0 | 16311.83 | 9396.04 | 0 | 25737.17 | 0 | 35133.21
| PEU hardware purchases, software upgrades | 52839 | 0 | 6904 | 0 | 59743 | 39703.75 |  | 6739 | 0 | 46442.75 | 13135.25 | 0 | 165 | 0 | 13300.25 | PEU hardware purchases, software upgrades | 0 | 0 | 0 | 0 | 0 | 13135.25 | 0 | 165 | 0 | 13300.25
| JCO software, hardware, tech support | 7292 | 0 | 34283 | 0 | 41575 |  |  | 10965 | 0 | 10965 | 7292 | 0 | 23318 | 0 | 30610 | JCO software, hardware, tech support | 0 | 0 | 0 | 0 | 0 | 7292 | 0 | 23318 | 0 | 30610
| JCO Equipment & Furniture | 8723 | 0 | 21449 | 0 | 30172 | 8723.31 |  | 15710 | 0 | 24433.31 | -0.31 | 0 | 5739 | 0 | 5738.69 | JCO Equipment & Furniture | 0 | 0 | 0 | 0 | 0 | -0.31 | 0 | 5739 | 0 | 5738.69
| 4 new staff to aid with secondary data collection by the Jamaica Crime Observatory (JCO) | 85389 | 0 | 70809 | 0 | 156198 | 50403.69 |  | 61909 | 0 | 112312.69 | 34985.31 | 0 | 8900 | 0 | 43885.31 | 4 new staff to aid with secondary data collection by the Jamaica Crime Observatory (JCO) | 16658.41 | 0 | 16549.96 | 0 | 33208.37 | 18326.9 | 0 | -7649.96 | 0 | 10676.94
| Technical Assistance for Improving Monitoring Systems & Reporting | 50491 | 107 | 45331 | 0 | 95929 | 21574.06 | 107 | 10976 | 0 | 32657.06 | 28916.94 | 0 | 34355 | 0 | 63271.94 | Technical Assistance for Improving Monitoring Systems & Reporting | 908.23 | 0 | 3172.31 | 0 | 4080.54 | 28008.71 | 0 | 31182.69 | 0 | 59191.4
| Design and conduct CSJP Community Survey data collection, analysis, and report publication. | 306333 | 159198 | 110379 | 0 | 575910 | 238167.2 | 159198 | 110379 | 0 | 507744.2 | 68165.8 | 0 | 0 | 0 | 68165.8 | Design and conduct CSJP Community Survey data collection, analysis, and report publication. | 46481.49 | 0 | 46481.49 | 0 | 92962.98 | 21684.31 | 0 | -46481.49 | 0 | -24797.18
1.5.1.4 | Women’s health survey (to assess prevalence of violence against women) | 136983 | 0 | 34692 | 0 | 171675 | 136982.74 |  | 34692 | 0 | 171674.74 | 0.26 | 0 | 0 | 0 | 0.26 | Women’s health survey (to assess prevalence of violence against women) |  |  |  |  | 0 | 0.26 | 0 | 0 | 0 | 0.26
| Mid-term evaluation report | 32669 | 0 | 182506 | 0 | 215175 |  |  | 181678 | 0 | 181678 | 32669 | 0 | 828 | 0 | 33497 | Mid-term evaluation report |  |  |  |  | 0 | 32669 | 0 | 828 | 0 | 33497
| Impact Evaluation on Parenting Program | 176967 | 134 | 95554 | 0 | 272655 | 54179.17 | 135 | 68503 | 0 | 122817.17 | 122787.83 | -1 | 27051 | 0 | 149837.83 | Impact Evaluation on Parenting Program | 87968.71 | 0 | 27050.38 | 0 | 115019.09 | 34819.12 | -1 | 0.62 | 0 | 34818.74
| Impact Evaluation on Vocational Program | 33963 | 0 | 9483 | 0 | 43446 | 33963 |  | 9483 | 0 | 43446 | 0 | 0 | 0 | 0 | 0 | Impact Evaluation on Vocational Program | 4446.16 | 0 | 2297.84 | 0 | 6744 | -4446.16 | 0 | -2297.84 | 0 | -6744
| Final evaluation | 97087.77 | 0 | 57143 | 0 | 154230.77 |  |  |  | 0 | 0 | 97087.77 | 0 | 57143 | 0 | 154230.77 | Final evaluation | - | - | - | - | 0 | 97087.77 | 0 | 57143 | - | 154230.77
| Dissemination of knowledge and lessons (Social Norm Survey) | 0 | 0 | 49267 | 0 | 49267 |  |  | 49267 | 0 | 49267 | 0 | 0 | 0 | 0 | 0 | Dissemination of knowledge and lessons (Social Norm Survey) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Personnel | 280302 | 18615 | 487664 | 0 | 786581 | 245609.23 | 18472 | 325672 | 0 | 589753.23 | 34692.77 | 143 | 161992 | 0 | 196827.77 | Personnel | 34693 | 0 | 102481.45 | 0 | 137174.45 | -0.23 | 143 | 59510.55 | 0 | 59653.32
1.5.2.2 | Satisfaction Surveys | 120136.23 | 0 | 25911 | 0 | 146047.23 |  |  |  | 0 | 0 | 120136.23 | 0 | 25911 | 0 | 146047.23 | Satisfaction Surveys |  |  |  |  | 0 | 120136.23 | 0 | 25911 | 0 | 146047.23
| Training and technical assistance to establish or improve community governannce structure | 92910 | 0 | 43214 | 0 | 136124 | 659.95 |  |  | 0 | 659.95 | 92250.05 | 0 | 43214 | 0 | 135464.05 | Training and technical assistance to establish or improve community governannce structure | 0 | 0 | 0 | 0 | 0 | 92250.05 | 0 | 43214 | 0 | 135464.05
| Audit | 0 | 0 | 17100 | 0 | 17100 |  |  | 17095 | 0 | 17095 | 0 | 0 | 5 | 0 | 5 | Audit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5
| Advocacy campaign developed and implemented for community advocay plans survey | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Advocacy campaign developed and implemented for community advocay plans survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Victimization Survey | [15 empty] | Victimization Survey | 148536.11 |  | 148536.11 |  | 297072.22 | -148536.11
6 | Programme Management Total | 4353383 | 1076754 | 1179862 | 0 | 6609999 | 2973098.3 | 1076418 | 1179784 | 1151 | 5230451.3 | 1380284.7 | 336 | 78 | 0 | 1380698.7 | Programme Management Total | 961752.12 | 0 | 0 | 0 | 961752.12 | 418532.58 | 336 | 78 | 0 | 418946.58
| Stationery and General Administrative Expenses, Furniture & Equipment | 1781723 | 394966 | 460729 | 0 | 2637418 | 1224091.6 | 394926 | 460729 | 1151 | 2080897.6 | 557631.4 | 40 | 0 | 0 | 557671.4 | Stationery and General Administrative Expenses, Furniture & Equipment | 388680.01 | 0 | 0 |  | 388680.01 | 168951.39 | 40 | 0 | 0 | 168991.39
| Personnel | 2513322 | 681788 | 699567 | 0 | 3894677 | 1718493.25 | 681492 | 699567 | 0 | 3099552.25 | 794828.75 | 296 | 0 | 0 | 795124.75 | Personnel | 556494.33 | 0 | 0 |  | 556494.33 | 238334.42 | 296 | 0 | 0 | 238630.42
| Audit | 58338 | 0 | 19566 | 0 | 77904 | 30513.45 |  | 19488 | 0 | 50001.45 | 27824.55 | 0 | 78 | 0 | 27902.55 | Audit | 16577.78 | 0 | 0 |  | 16577.78 | 11246.77 | 0 | 78 | 0 | 11324.77
0
5 | Technical Advisory Team | 0 | 800000 | 0 | 0 | 800000 | 0 | 539140 | 0 | 13632 | 552772 | 0 | 260860 |  | 0 | 260860 | Technical Advisory Team | 0 | 53838.76 | 0 |  | 53838.76 | 0 | 207021.24 | 0 | 0 | 207021.24
| Technical Assistant | [15 empty] | Technical Assistant |  | 54737.02 |  |  | 54737.02 | 0 | -54737.02 | 0 | 0 | -54737.02
| Contingencies | 200000 | 159120 | 174357 | 0 | 533477 | 0 | 0 | 0 | 0 | 0 | 200000 | 159120 | 174357 | 0 | 533477 | Contingencies | [5 empty] | 200000 | 159120 | 174357 | 0 | 533477
|  | Original Budget in force US$'000 IDB: 0 | [10 empty] | 0
| Administrative Fees | Original Budget in force US$'000 DFID: 837475; Original Budget in force US$'000 GAC: 917670; Original Budget in force US$'000 Total: 1755145; Total Expenditure to Date US$'000-(As December 2018) IDB: 0; Total Expenditure to Date US$'000-(As December 2018) DFID: 837475; Total Expenditure to Date US$'000-(As December 2018) GAC: 917670; Total Expenditure to Date US$'000-(As December 2018) GOJ: 0; Total Expenditure to Date US$'000-(As December 2018) Total: 1755145 | Administrative Fees
| Grand Total | 19999999 | 13561497 | 16043708 | 0 | 49605204 | 15548884.55 | 9872764 | 12469945 | 1233961 | 39125554.55 | 4451114.45 | 3688733 | 3573763 | 0 | 11713610.45 | Grand Total | 3603033.84 | 3334846.94 | 3001427.53 | 3605106.56 | 13544414.82 | 996616.72 | 353886.06 | 720871.58 | 0 | 2071374.36

## 7. Risk Plan
CITIZEN SECURITY AND JUSTICE PROGRAMME 111
Operation Number: 3191/OC-JA
Section 7: RISK MANAGEMENT
Risk ID | WBS Code (Project, Component, Output or Deliverable) | Type of Risk | Risk (Describe potential future opportunities (positive or negative) as well as any threats that caused changes to project work, time, cost and quality.) | Impact (I) | Probability (P) | Risk Rating (IxP) | Risk Classification (use Key below) |  | Risk Response Strategy | Risk Action Plan | Risk Owner
[7 empty] | Value | Level
1 |  | Public Management and Governance | Service delivery by MDAs during/after the transition of services will be hampered due to limited capacity and/or resources within the government to assume CSJP responsibilities and coordination. | 3 | 3 | 9 | 3 | High | Escalate | i. Transfer CSJP staff with the relevant experience and expertise to the government department to maintain/build capacity. ii. Facilitate work exchanges between CSJP and MDAs’ staff to familiarize MDAs with required functions and processes. iii. The Programme will support the implementation of a transition plan with milestones, timelines, to ensure measured transfer of resources, capacity and knowledge. iv. Establish a repository of Programmerelated documents and will share relevant software to support the transition of services to the line ministries. v. Standard reporting formats and training will be provided to all Programme partners to ensure that MDAs can track progress based on GOJ requirements. vi. Organize workshops on planning, training, reporting and networking among partners to share best practices. | MNS
2 |  | Public Management and Governance | The behavior change the Programme seeks to achieve may not materialize due to the high Case loads of Case Managers. The ratio remains prohibitive, and the programme therefore run the risk of not adequately treating each client. | 3 | 2 | 6 | 3 | High | Mitigate | i. Increase staff complement. ii. Implement stricter measures to reviewing of cases for termination inkeeping with established protocals. iii. Reduce active mobilization and focus more on receiving referrals from external sources such as DCS is an attempt to better manage the number of clients engaged by the Programme. | Case Management Coordinators and Programme Manager
3 |  | Public Management and Governance | Case officers are facing increased risk to their safety due to the nature of the communities and clients they engage. | 2 | 2 | 4 | 2 | Medium | Avoid | i.Case officers are fully aware of the safety risks they face and employ a variety of mitigatory measures from avoiding certain areas of the communities at certain times to seeking to engage identified persons in conflict with clients ii.The main concern expressed by case officers is that there is no Programme support should they be harmed and suggests that their compensation includes a risk premium | Case Officers and Regional Case Management Coordinators
4 |  | Public Management and Governance | The Programme is facing the risk of not meeting its targets due to high turnover of critical staff and as the Programme comes to an end it is unable to recruit suitable staff in a timely manner. | 2 | 2 | 4 | 2 | Medium | Mitigate | (i) Seek internally for suitable staff to fill vacant positions. (ii) Utilize selective procurement methodology to hire suitable consultants in a timely manner to fill vacant positions critical to its service delivery. | HR and Programme Management
| Component 1 -1125 | Public Management and Governance | Insufficient coordination among MDAs and donors delivering programmes and services in CSJP ommunities could result in duplication of services or conflicting approaches. | 2 | 2 | 4 | 2 | Medium | Mitigate | (i) Conduct regular stakeholder outreach with community members, the private sector, community service providers and MDAs to provide constant sensitization on CSJP III activities. (ii) Require the CDCs supported by CSJP in each community to demonstrate how they are coordinating with other entities working on similar issues. (iii) Inform and empower members of the Project Steering Committee to take on a communications role. (iv) Identify incentives to encourage more consistent attention from high-level officials (networking opportunities, useful information exchange, and capacity building | Senior Governance Officer
5 |  | Monitoring and Accountability | Programme progress could be hampered due to a lack of functioning programme oversight bodies (Public Order Committee, Technical Working Group and Programme Steering committee) that would hold CSJP accountable for achieving results at the community level. | 2 | 3 | 6 | 3 | High | Mitigate | i. Develop capacity of and strengthen collaboration among key local partners through related training and participation in Programme Steering Committee. ii. Ensure that there is representation from community residents, Community-Based Organizations, and NGOs/civil society on the Programme Steering Committee. iii. Ensure that part of the Technical Advisory Team is dedicated to supporting the design and implementation of oversight mechanisms. | MNS
6 |  | Financial | Fluctuation in exchange rate of international funding sources may impact the Programme’s financial resources | 2 | 3 | 6 |  | HIGH | Escalate | i. GOJ will seek additional source of funding to shore up the financial resources of the Programme. ii. PEU will Implement various cost cutting measures to reduce overall expenditure
7 |  | Financial | The gradual Increase in the number of projects being added to the Capital B Accounts may limit the Fiscal Space available to the Programme. | 2 | 3 | 6 | 3 | High | Accept | i. Reallocate budget to more critical activities. ii. Collaborate with internal units and external agencies such as MDAs to implement activities which the Programme is unable to undertake on its own due to fiscal constraints. | Programme Management
8 |  | Macro-economic and Fiscal Sustainability | Line ministries will be unable to disburse funds on a timely basis due to capacity constraints once responsibilities and budget line items are transferred to them from the Programme Executing Unit. | 2 | 2 | 4 | 2 | Medium | Mitigate | i. Determine component estimates as accurately as possible at the start and review regularly, using key partner staff at the appropriate levels to prioritize and cost activities. ii. Provide technical assistance to strengthen partners’ capacity to plan and budget for Programme activities. iii. Review procurement capacity and requirements of each line ministry ahead of transfer of services and address any discrepancies or gaps. | Accounts and Procurement Units
9 | Component 2 | Macro-economic and Fiscal Sustainability | Macro-economic conditions and fiscal pressures could negatively impact employment prospects and enhanced delivery of government services thereby contributing to adverse security situations at the community level | 3 | 3 | 9 | 3 | High | Mitigate | i. Identify training and work opportunities in nontraditional and high-demand sectors based on recent labour market information and GOJ economic priorities. ii. Implement income-generating activities and business development services, including start-up funding. iii. Integrate entrepreneurial skills into training programmes to increase options for self- employment. iv. Engage the private sector early in Programme development to facilitate their collaboration. | Labour Market Staff
10 | Component 1-1115 | Reputational | Some community residents do not see security and justice as priority issues but rather poverty and unemployment while some policy makers and MDAs do not see social interventions like CSJP as a core andate of the MNS | 2 | 2 | 4 | 2 | Medium | Mitigate | i. Implement Social Marketing campaigns showing how weak security leads to unemployment and poverty ii. Include target communities & MDAs in the planning and implementation process. iii. Ensure proactive engagement with highlevel government officials through the Public Order Committee and keep Minister of MNS informed so he continues his role as a Programme champion. iv.Conduct public awareness campaigns to encourage broader community participation. v.Do more proactive communication of the positive results of CSJP activities and their effects on community safety, including community member testimonials. | Social Marketing Unit and MNS
11 | Component 1 &2 | Reputational | The Programme is not able to provide a variety of services to a range of persons in target communities as they are accustomed to due to its strategic shifts as well as limited resources | 2 | 3 | 6 | 3 | High | Share | i.Continues to establish partnerships with, CBOs, MDAs and other private and public sector organizations such as HEART, MLSS to deliver quality services that it is unable to offer to these individuals. ii.Provide referral kits to individuals who have been risk assessed and deemed low risk and hence not eligible for CSJP services iii.Empower communities through capacity building training to take on management of activities and to seek partnership with public and private entities to continue programmes and management of the centres. | Case Management , Labour Market and Community Governance Staff and Community groups.
|  |  | Key | [5 empty] | Risk Response
|  |  | Risk Rating | Risk Classification |  |  |  |  | Rating | Interpretation
|  |  |  | Value | Level |  |  |  | Escalate | when managing the threat is outside the scope of the PEU’s authority
|  |  | 9 | 3 | High |  |  |  | Avoid | eliminating the threat or protecting the project from its impacts
|  |  | 6 | 3 | High |  |  |  | Transfer | shifting ownership and management to a 3rd party to bear the impact of the risk
|  |  | 4 | 2 | Medium |  |  |  | Mitigate | reducing the probability or impact of the risk by making it a lesser risk
|  |  | 3 | 2 | Medium |  |  |  | Accept | doing nothing (usually for low level threats or when it is not cost-effective to alleviate. For positive risks, acknowledging the opportunity but not taking proactive measures.
|  |  | 2 | 1 | Low |  |  |  | Expoit | (for positive risks) ensuring that the opportunity becomes a reality
|  |  | 1 | 1 | Low |  |  |  | Enhance | (for positive risks) increasing the probability and positive impact
[9 empty] | Share | (for positive risks) sharing the opportunity with a 3rd party
Scale for Probability
|  |  | Rating |  | Interpretation
|  |  | 1 |  | Low
|  |  | 2 |  | Medium
|  |  | 3 |  | High

## AOP Checklist
SECTION 8
ANNUAL OPERATING PLAN CHECKLIST
ITEMS
ANNUAL OPERATING PLAN (AOP)
1 | The AOP includes:
Background and Introduction, including challenges and how they will be addressed
Implementation plan
Procurement Plan
Financial Plan
2 | AOP coverage is for at least 18 months
3 | Alignment:
Procurement plan is aligned with the implementation plan
Financial plan is aligned with the implementation plan
Financial plan is aligned with the procurement plan
IMPLEMENTATION PLAN
4 | Implementation plan broken down according to:
Components
Outputs
Procurement/ Approval steps
Workpackages include WBS code
FINANCIAL PLAN
5 | Financial plan broken down according to:
Months
Source of Funding
Components
Activities
PROCUREMENT PLAN
6 | Procurement Plan:
Plan is approved in SEPA
Plan includes current procurement items
OTHER IMPORTANT CONSIDERATIONS
7 | Content:
Activity level & financial plan consistent with project age
8 | Budget
Financial plan in line with GOJ budget allocation
PEU Financial plan within 20% variance of Bank's disb. projections
9 | AOP preparation process is done in a coordinated manner by PEU project team
Project Coordinator
Project Accountant
Procurement Specialist
Monitoring & Evaluation Specialist
Other: (Specify) _______________
10 | Personnel assigned to update AOPs

## Table of Contents
ANNUAL OPERATING PLAN
TABLE OF CONTENTS
SECTION 1 | Project Overview
SECTION 2 | Results Matrix
SECTION 3 | Implementation Plan
SECTION 4 | Procurement Plan
SECTION 5 | Detailed Financial Plan
SECTION 6 | Consolidated Financial Plan
SECTION 7 | Risk Plan
SECTION 8 | AOP Checklist