## POA-PEP
|  | YEAR 1 - 2017 | [11 empty] | YEAR 2 - 2018 | [11 empty] | YEAR 3 - 2019 | [11 empty] | YEAR 4 - 2020 | [11 empty] | YEAR 5 - 2021 | [11 empty] | YEAR 6 - 2022 | [11 empty] | YEAR 7 - 2023
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Product
Component I. Implementation of the Legal and Institutional Framework for the NIDS
Establishment of NIRA and Improvement of Civil Registration
Establishment of the NIRA Act | bar: YEAR 1 - 2017 Apr to YEAR 1 - 2017 May
Establishment of the NIRA Regulations | bar: YEAR 1 - 2017 Jun to YEAR 1 - 2017 Dec
Establishment of NIRA and Transform the RGD | bar: YEAR 1 - 2017 Apr to YEAR 4 - 2020 Dec
Put in place a Coordinator to Manage all project activities at the RGD | bar: YEAR 1 - 2017 Jun to YEAR 3 - 2019 Jun
Provide mobile tablets for the RGD | bar: YEAR 1 - 2017 Apr to YEAR 2 - 2018 Aug
Put in place officers and digitize RGD records (129 in total) | bar: YEAR 2 - 2018 Jan to YEAR 3 - 2019 Dec
Put in place a programmer to assist with RGD Digitization Systems preparations | bar: YEAR 1 - 2017 Jul to YEAR 3 - 2019 Jul
Training and Documentation for RGD Staff | bar: YEAR 2 - 2018 Jan
Modification of spaces, ICT Infrastructure and resources for the RGD | bar: YEAR 1 - 2017 Jun to YEAR 2 - 2018 Jun
Transportation for RGD Shift Digitization Officers | bar: YEAR 2 - 2018 Jan to YEAR 3 - 2019 Dec
Knowledge Sharing - Study Tour
Communications and Behavior Change
Communications, PR, Behavior Change and Marketing Campaign
Project Coordination, resources for project execution | bar: YEAR 1 - 2017 Jul to YEAR 3 - 2019 Apr
Software Licenses | bar: YEAR 1 - 2017 Jul; YEAR 3 - 2019 Jul
Component II. Implementation of a unique National Identification Number and National Identification Management System:
Put in place hosting for the National Identification System | bar: YEAR 2 - 2018 May to YEAR 7 - 2023 Dec
Put in place ISP Connectivity to link 43 enrollment sites with data center | bar: YEAR 2 - 2018 Jun to YEAR 7 - 2023 Dec
Put in place eGov Project Manager | bar: YEAR 1 - 2017 May to YEAR 4 - 2020 Apr
Put in place eGov Support Staff (2 Officers) | bar: YEAR 2 - 2018 Aug to YEAR 7 - 2023 Dec
Put in place eGov Technical Staff(5 Officers including Application, Database Officers)
Put in place Officers (2 Officers) to Manage and Configure 44 Lanes(1 Production and 43 Enrollment | bar: YEAR 1 - 2017 Sept to YEAR 2 - 2018 Apr
MDA Connectivity, Infrastructure and Data Center Infrastructure for NIDS
Put in place the required MDAs Connectivity and Infrastructure | bar: YEAR 1 - 2017 Aug to YEAR 3 - 2019 Dec
Put in place the required Data Center Infrastructure to accept the NIDS(Power, Data, Cooling etc.) | bar: YEAR 1 - 2017 May to YEAR 3 - 2019 Dec
Technical Training for eGov Support Staff
Technical and Support Training | bar: YEAR 1 - 2017 Jul to YEAR 3 - 2019 Dec
Special Software to Support the NIDS
All software and Backup Tool to support the NIDS and Identity verification services | bar: YEAR 1 - 2017 Jul to YEAR 2 - 2018 Dec
Enrollment and Production Infrastructure
43 Enrollment and 1 Production Site LANs, Equipment and Infrastructure | bar: YEAR 1 - 2017 Sept to YEAR 3 - 2019 May
Consultant Support the installation of Workstations at 43 Enrollment Sites and 1 Production Site 1 | bar: YEAR 1 - 2017 Sept to YEAR 3 - 2019 May
Establishment of Enrollment and Production of Cards
Modification of Spaces at Jamaica Post HQ to facilitate the Production of Cards and NIN | bar: YEAR 1 - 2017 Jul to YEAR 2 - 2018 Mar
Modification of Spaces at 18 Urban Jamaica Post Enrollment Sites to Support Phase 1 | bar: YEAR 1 - 2017 Jul to YEAR 2 - 2018 Mar
Modification of Spaces at 25 Additional(Rural) Jamaica Post Enrollment Sites for Phases 2-4 | bar: YEAR 2 - 2018 Apr to YEAR 3 - 2019 May
Jamaica Post Staff to Facilitate Enrollment of Jamaican in the National Identification System in Phases
Put in place a Task Force and Project Coordinator to drive the preparation activities for the NIDS | bar: YEAR 1 - 2017 Jul to YEAR 4 - 2020 May
Put in place the required enrollment staff(101) and begin Phase 1 Enrollment of Public Sector Employees | bar: YEAR 2 - 2018 Aug to YEAR 7 - 2023 Dec
Put in place the required enrollment staff(50) and begin Phase 2 Enrollment of Students, Parents, Guardians | bar: YEAR 3 - 2019 Jan to YEAR 7 - 2023 Dec
Put in place the required enrollment staff(50) and begin Phase 3 Enrollment of Seniors, College and University Students | bar: YEAR 3 - 2019 Jan to YEAR 7 - 2023 Dec
Put in place the required enrollment staff(25) and begin Phase 4 Enrollment of Private Sector Employees and Special Groups(Persons with Special Needs, Un-documented persons etc.) | bar: YEAR 3 - 2019 Sept to YEAR 7 - 2023 Dec
Jamaica Post Production and Enrollment Sites Provisions
Provisions for Electricity, water, and work spaces during project lifecycle | bar: YEAR 2 - 2018 Aug to YEAR 7 - 2023 Dec
Acquire, Install and Commission the National Identification System
Develop and Publish RFP for NIDS | bar: YEAR 1 - 2017 Apr
Procurement Processes and Award of Contract (Stage 1, Stage 2, Contract Award) | bar: YEAR 1 - 2017 Apr to YEAR 1 - 2017 Dec
Acquire the National Identification System(Servers, Software, Security Devices, Verification System, ABIS etc.) | bar: YEAR 1 - 2017 Dec to YEAR 4 - 2020 Feb
Consultancy - National Identification System - Specialized Areas(ABIS expert, enrollment expert etc.) | bar: YEAR 1 - 2017 Dec to YEAR 4 - 2020 Mar
TOTAL COMPONENT II
Component III. Streamlined identity verification for the public and private sector
Financial Sector Review and Regulations Updates
Put in place a Coordinator to manage the review of financial regulations | bar: YEAR 1 - 2017 Aug to YEAR 2 - 2018 Jul
Financial sector regulations comprehensive review | bar: YEAR 1 - 2017 Sept to YEAR 2 - 2018 May
Training for Supervisory GOJ Organizations(BOJ, FSC, FID) | bar: YEAR 2 - 2018 Apr to YEAR 2 - 2018 Aug
Adoption of NIDS Verification Services and Data Cleaning - Education Sector
Comprehensive Review of Existing Identification Services in Primary, Secondary and Tertiary Institutions; Clean Data in Primary and Secondary Institutions Education Management Information Systems | bar: YEAR 1 - 2017 Sept to YEAR 5 - 2021 Dec
Modification of Existing Systems to use the NIDs Identification Services and Clean Databases | bar: YEAR 2 - 2018 Jan to YEAR 5 - 2021 Feb
Training and deployment of services via project team | bar: YEAR 2 - 2018 Jan to YEAR 5 - 2021 Dec
Adoption of NIDS Verification Services and Data Cleaning - Labour and Social Security, Special Needs
Comprehensive Review of Existing Information Systems in the MLSS and Data Cleaning | bar: YEAR 1 - 2017 Sept to YEAR 5 - 2021 Dec
Modification of Existing Systems in the MLSS to use the NIDs Identity Verification Services(PATH, NIS, Persons with Disabilities/Special Needs etc.) | bar: YEAR 2 - 2018 Jan to YEAR 5 - 2021 Dec
Training and deployment of services via project team | bar: YEAR 1 - 2017 Nov to YEAR 5 - 2021 Dec
Adoption of NIDS Verification Services and Data Cleaning - Ministry of National Security(MNS)
Comprehensive Review of Existing Information Systems in the MNS and Data Cleaning | bar: YEAR 1 - 2017 Nov to YEAR 6 - 2022 Dec
Modification of Existing Systems in the MNS to use the NIDs Identity Verification Services | bar: YEAR 2 - 2018 Jul to YEAR 5 - 2021 Dec
Provide Workstations and Fingerprint Scanners for selected Police Stations | bar: YEAR 3 - 2019 Feb to YEAR 6 - 2022 Dec
Local Project Execution Team - Implement Modified System in the MNS | bar: YEAR 1 - 2017 Nov to YEAR 6 - 2022 Dec
Adoption of NIDS Verification Services and Data Cleaning - National Housing and Training Agencies
Comprehensive Review of Existing Information Systems in the HEART Trust/NTA and National Housing Trust; Data Cleaning | bar: YEAR 2 - 2018 Jan to YEAR 6 - 2022 Dec
Modification of Existing Systems in the HEART Trust/NTA and the National Housing Trust to use the NIDs Identity Verification Services | bar: YEAR 3 - 2019 Jan to YEAR 6 - 2022 Dec
Provide Fingerprint Scanners for the National Housing Trust and HEART Trust/NTA Regional Offices | bar: YEAR 3 - 2019 Jan to YEAR 6 - 2022 Dec
Local Project Execution Team - Implement Modified System national agencies | bar: YEAR 1 - 2017 Dec to YEAR 6 - 2022 Dec
Adoption of NIDS Verification Services and Data Cleaning - Tax Administration Systems
Comprehensive Review of Existing Information Systems in the Tax Services and Data Cleaning(RAiS, Drivers License, TRN etc.) | bar: YEAR 1 - 2017 Nov to YEAR 6 - 2022 Dec
Modification of Existing Systems in the Tax Services to use the NIDs Identity Verification Services | bar: YEAR 3 - 2019 Jan to YEAR 6 - 2022 Dec
Local Project Execution Team - Implement Modified System in the Tax Services and Training | bar: YEAR 1 - 2017 Oct to YEAR 7 - 2023 May
Adoption of Statistics Extraction Tools - PIOJ
Data Extraction Training for GOJ Decision Making | bar: YEAR 3 - 2019 Jan to YEAR 3 - 2019 Mar
TOTAL COMPONENT III | bar: YEAR 3 - 2019 Jan to YEAR 3 - 2019 Mar
Audit, Monitoring and Evaluation
Facilitate Project Audits and Evaluations | bar: YEAR 2 - 2018 Mar to YEAR 7 - 2023 Mar
Contingency | bar: YEAR 6 - 2022 Jan to YEAR 7 - 2023 May
NIDS Project Execution Plan Grand Total

## Consolidated Financial Plan
SECTION 4
CONSOLIDATED FINANCIAL PLAN
Suggested model
| Programme Components (1) | April 2017-December 2017 |  |  |  | Jan 2018 - Dec 2018 |  |  |  | Jan 2019 - Dec 2019 |  |  |  | Jan 2020 - Dec 2020 |  |  |  | Jan 2021 - Dec 2021 |  |  |  | Jan 2022 - Dec 2022 |  |  |  | Jan 2023 - June 2023 |  |  |  | PROJECT TOTAL |  |  |  | Balance Test
|  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000)
|  | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total
| COMPONENT I: Implemenation of the Legal and Institutional Framework for the NIDS |  |  |  | (as per approved amount)
| ESTABLISHMENT OF THE NIRA | 740734.915 | 0 | 0 | 740734.915 | 1370642.22 | 0 | 0 | 1370642.22 | 1602790.22 | 0 | 0 | 1602790.22 | 1595490.22 | 0 | 0 | 1595490.22 | 1595490.22 | 0 | 0 | 1595490.22 | 1518657.22 | 0 | 0 | 1518657.22 | 912928.61 | 0 | 0 | 912928.61 | 9336733.625 | 0 | 0 | 9336733.625
| IMPROVEMENT OF THE CIVIL REGISTRY | 848421.7949 | 0 | 0 | 848421.7949 | 1233368.2051 | 0 | 0 | 1233368.2051 | 1169378.4615 | 0 | 0 | 1169378.4615 | 81000 | 0 | 0 | 81000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3332168.4615 | 0 | 0 | 3332168.4615
| COMMUNICATION AND BEHAVIOUR CHANGE | 90153.8462 | 0 | 0 | 90153.8462 | 315538.4615 | 0 | 0 | 315538.4615 | 369630.7692 | 0 | 0 | 369630.7692 | 369630.7692 | 0 | 0 | 369630.7692 | 369630.7692 | 0 | 0 | 369630.7692 | 369630.7692 | 0 | 0 | 369630.7692 | 369630.7692 | 0 | 0 | 369630.7692 | 2253846.1538 | 0 | 0 | 2253846.1538
| Sub Total COMPONENT I: Implemenation of the Legal and Institutional Framework for the NIDS | 1679310.556 | 0 | 0 | 1679310.556 | 2919548.8867 | 0 | 0 | 2919548.8867 | 3141799.4508 | 0 | 0 | 3141799.4508 | 2046120.9892 | 0 | 0 | 2046120.9892 | 1965120.9892 | 0 | 0 | 1965120.9892 | 1888287.9892 | 0 | 0 | 1888287.9892 | 1282559.3792 | 0 | 0 | 1282559.3792 | 14922748.2404 | 0 | 0 | 14922748.2404 | -268
| COMPONENT II: Implementation of a unique National Identification Number and National Identification Management System: |  |  |  | (as per approved amount)
| DATA CENTER AND CONNECTIVITY | 1171623.2562 | 0 | 0 | 1171623.2562 | 4729998.0898 | 0 | 0 | 4729998.0898 | 2482995.1188 | 0 | 0 | 2482995.1188 | 710620.3157 | 0 | 0 | 710620.3157 | 668925.7486 | 0 | 0 | 668925.7486 | 668925.7486 | 0 | 0 | 668925.7486 | 390517.1034 | 0 | 0 | 390517.1034 | 10823605.381 | 0 | 0 | 10823605.381
| ESTABLISHMENT OF PRODUCTION SITE | 197780 | 0 | 0 | 197780 | 361620 | 0 | 0 | 361620 | 216250 | 0 | 0 | 216250 | 91250 | 0 | 0 | 91250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 866900 | 0 | 0 | 866900
| ESTABLISHMENT OF ENROLLMENT SITES | 423418.8462 | 0 | 0 | 423418.8462 | 699346.3782 | 0 | 0 | 699346.3782 | 910594.9038 | 0 | 0 | 910594.9038 | 721968.4615 | 0 | 0 | 721968.4615 | 706568.4615 | 0 | 0 | 706568.4615 | 706568.4615 | 0 | 0 | 706568.4615 | 416164.9359 | 0 | 0 | 416164.9359 | 4584630.4487 | 0 | 0 | 4584630.4487
| NIDS SOLUTION | 5923678.6 | 0 | 0 | 5923678.6 | 8885517.9 | 0 | 0 | 8885517.9 | 8885517.9 | 0 | 0 | 8885517.9 | 5923678.6 | 0 | 0 | 5923678.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29618393 | 0 | 0 | 29618393
| Sub Total: COMPONENT II Implemenation of a National Identification System and Infrastructure | 7716500.7023 | 0 | 0 | 7716500.7023 | 14676482.368 | 0 | 0 | 14676482.368 | 12495357.9226 | 0 | 0 | 12495357.9226 | 7447517.3772 | 0 | 0 | 7447517.3772 | 1375494.2102 | 0 | 0 | 1375494.2102 | 1375494.2102 | 0 | 0 | 1375494.2102 | 806682.0393 | 0 | 0 | 806682.0393 | 45893528.8297 | 0 | 0 | 45893528.8297 | 0.0084615
| COMPONENT III: Streamlined idenitity verification for the public and prive sector: |  |  |  | (as per approved amount)
| IMPLEMENTATION OF IDENTITY VERFICATION IN MDAs | 309722.2222 |  |  | 309722.2222 | 1121944.4444 |  |  | 1121944.4444 | 707499.9992 |  |  | 707499.9992 | 744999.9992 |  |  | 744999.9992 | 682499.9992 |  |  | 682499.9992 | 483333.3325 |  |  | 483333.3325 | 10000 |  |  | 10000 | 4059999.9967 |  |  | 4059999.9967
| Sub Total: COMPONENT III Streamlined idenitity verification for the public and prive sector: | 309722.2222 | 0 | 0 | 309722.2222 | 1121944.4444 | 0 | 0 | 1121944.4444 | 707499.9992 | 0 | 0 | 707499.9992 | 744999.9992 | 0 | 0 | 744999.9992 | 682499.9992 | 0 | 0 | 682499.9992 | 483333.3325 | 0 | 0 | 483333.3325 | 10000 | 0 | 0 | 10000 | 4059999.9967 | 0 | 0 | 4059999.9967 | -0.0033333
| CATEGORY 10: PROJECT M & E | Year 1 April 2017-December 2017 |  |  |  | Year 2 Jan 2018 - Dec 2018 |  |  |  | Year 3 Jan 2019 - Dec 2019 |  |  |  | Year 4 Jan 2020 - Dec 2020 |  |  |  | Year 5 Jan 2021 - Dec 2021 |  |  |  | Year 6 Jan 2022 - Dec 2022 |  |  |  | Year 7 Jan 2023 - June 2023 |  |  |  | PROJECT TOTAL
|  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000)
|  | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total
| CATEGORY 10: PROJECT MONITORING & EVALUATION |  |  |  | (as per approved amount)
| Provisions for project lifecycle monitoring and evaluation; Business Impact Study | 0 | 0 | 0 |  | 87000 |  |  | 87000 | 137000 |  |  | 137000 | 20000 |  |  | 20000 | 20000 |  |  | 20000 | 20000 |  |  | 20000 | 170000 |  |  | 170000 | 454000 | 0 | 0 | 454000
| Sub Total: TOTAL CATEGORY 10: PROJECT M & E | 0 | 0 | 0 | 0 | 87000 | 0 | 0 | 87000 | 137000 | 0 | 0 | 137000 | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0 | 20000 | 170000 | 0 | 0 | 170000 | 454000 | 0 | 0 | 454000 | 0
| Total | 0 | 0 | 0 | 0 | 87000 | 0 | 0 | 87000 | 137000 | 0 | 0 | 137000 | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0 | 20000 | 20000 | 0 | 0 | 20000 | 170000 | 0 | 0 | 170000 | 454000 | 0 | 0 | 454000
| CATEGORY 11: CONTINGENCY PROVISIONS: |  |  |  | (as per approved amount)
| Provisions for Contingency | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 1334727.4692 |  |  | 1334727.4692 | 1334727.4692 |  |  | 1334727.4692 | 2669454.9383 |  |  | 2669454.9383
| Subtotal : TOTAL:CATEGORY 11: CONTINGENCY PROVISIONS: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1334727.4692 | 0 | 0 | 1334727.4692 | 1334727.4692 | 0 | 0 | 1334727.4692 | 2669454.9383 | 0 | 0 | 2669454.9383
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1334727.4692 | 0 | 0 | 1334727.4692 | 1334727.4692 | 0 | 0 | 1334727.4692 | 2669454.9383 | 0 | 0 | 2669454.9383
| Grand Total | 9705533.4806 | 0 | 0 | 9705533.4806 | 18804975.6991 | 0 | 0 | 18804975.6991 | 16481657.3726 | 0 | 0 | 16481657.3726 | 10258638.3656 | 0 | 0 | 10258638.3656 | 4043115.1986 | 0 | 0 | 4043115.1986 | 5101843.0011 | 0 | 0 | 5101843.0011 | 3603968.8877 | 0 | 0 | 3603968.8877 | 67999732.0051 | 0 | 0 | 67999732.0051
Note on AH9: Warren Vernon: Project Executing Unit and Production Staff
Note on AE12: Warren Vernon: Total Component I
Note on AE18: Warren Vernon: Total Component II
Note on AE21: Warren Vernon: Total Component III
Note on B30: Warren Vernon: Provision for M & E
Note on AH40: Warren Vernon: Total Project Budget Year 1-7

## Detailed Financial plan
SECTION 5 | [18 empty] | F/X Rate |  |  | 130
DETAILED FINANCIAL PLAN: ENTIRE PROJECT
[10 empty] | Year 2017 | [35 empty] | 2018
|  |  |  | Category Details | Unit Cost US$ | Qty | Total US$ (2017 - 2023) |  | Comments | January |  |  | February |  |  | March |  |  | 2017-04-01 |  |  | 2017-05-01 |  |  | 2017-06-01 |  |  | 2017-07-01 |  |  | 2017-08-01 |  |  | 2017-09-01 |  |  | 2017-10-01 |  |  | 2017-11-01 |  |  | 2017-12-01 |  |  | 2018-01-01 |  |  | 2018-02-01 |  |  | 2018-03-01 |  |  | 2018-04-01 |  |  | 2018-05-01 |  |  | 2018-06-01 |  |  | 2018-07-01 |  |  | 2018-08-01 |  |  | 2018-09-01 |  |  | YEAR 1 April 2017 - December 2017 |  |  | YEAR 2 January 2018 - December 2018 |  |  | YEAR 3 January 2019 - December 2019 |  |  | YEAR 4 January 2020 - December 2020 |  |  | YEAR 5 January 2021 - December 2021 |  |  | YEAR 6 January 2022 - December 2022 |  |  | YEAR 7 January 2023 -June 2023 |  |  | YEAR 1 - 7 Total Costs |  |  | How much will it cost NIRA to maintain the NIDS post implementation? | Budget Balance Test
Item no. | Pro. Group | Source of Financing | Obj. | [6 empty] | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance
COMPONENT I
|  |  |  | ESTABLISHMENT OF NIRA | [71 empty] | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS122 | PROJ-CORD1 | IDBFunded | 25 | Project Staff equipment (Laptop, Monitors) | 18000 | 1 | 18000 |  | Project Coordination | [18 empty] | 18000 | [44 empty] | 18000 |  |  | 0 | [17 empty] | 18000 |  |  | #REF! | 0
NIDS123 | PROJ-CORD2 | IDBFunded | 25 | Furniture & Supplies (Project Team) | 10000 | 1 | 10000 |  | Project Coordination | [18 empty] | 10000 | [44 empty] | 10000 |  |  | 0 | [17 empty] | 10000 |  |  | #REF! | 0
NIDS124 | PROJ-CORD3 | IDBFunded | 25 | Furniture & Supplies (Production & Vetting staff) | 13000 | 1 | 13000 |  | Project Coordination | [18 empty] | 13000 | [44 empty] | 13000 |  |  | 0 | [17 empty] | 13000 |  |  | #REF! | 0
NIDS125 | PROJ-CORD4 | IDBFunded | 25 | ACCPAC Software license | 9000 | 1 | 9000 |  | Project Coordination | [18 empty] | 4500 | [44 empty] | 4500 |  |  | 0 |  |  | 4500 | [14 empty] | 9000 |  |  | #REF! | 0
NIDS126 | PROJ-CORD5 | IDBFunded | 25 | ACCPAC Software | 10000 | 1 | 10000 |  | Project Coordination | [18 empty] | 10000 | [44 empty] | 10000 |  |  | 0 | [17 empty] | 10000 |  |  | #REF! | 0
NIDS127 | PROJ-CORD6 | IDBFunded | 25 | Servers to host accounting software | 6000 | 1 | 6000 |  | Project Coordination | [18 empty] | 6000 | [44 empty] | 6000 |  |  | 0 | [17 empty] | 6000 |  |  | #REF! | 0
NIDS128 | PROJ-CORD7 | IDBFunded | 25 | SPSS -One license | 6000 | 1 | 6000 |  | Project Coordination | [18 empty] | 6000 | [44 empty] | 6000 |  |  | 0 | [17 empty] | 6000 |  |  | #REF! | 0
NIDS129 | PROJ-CORD8 | IDBFunded | 25 | Office productivity software (MS Project, | 11000 | 1 | 11000 |  | Project Coordination | [18 empty] | 11000 | [44 empty] | 11000 |  |  | 0 | [17 empty] | 11000 |  |  | #REF! | 0
NIDS130 | PROJ-CORD9 | IDBFunded | 25 | Printer | 4000 | 1 | 4000 |  | Project Coordination | [18 empty] | 4000 | [44 empty] | 4000 |  |  | 0 | [17 empty] | 4000 |  |  | #REF! | 0
NIDS131 | PROJ-CORD10 | IDBFunded | 25 | Use of Goods & Services | 28000 | 1 | 28000 |  | Project Coordination | [18 empty] | 5600 | [44 empty] | 5600 |  |  | 5600 |  |  | 5600 |  |  | 2800 |  |  | 2800 |  |  | 2800 |  |  | 2800 |  |  | 28000 |  |  | #REF! | 0
NIDS132 | PROJ-CORD11 | IDBFunded | 25 | Administrative Charges | 505000 | 1 | 505000 |  | Project Coordination | [18 empty] | 10100 |  |  | 10100 |  |  | 10100 |  |  | 10100 |  |  | 10100 |  |  | 10100 |  |  | 10100 |  |  | 10100 |  |  | 10100 |  |  | 10100 |  |  | 10100 |  |  | 10100 |  |  | 10100 |  |  | 10100 |  |  | 10100 |  |  | 60600 |  |  | 74033 |  |  | 74033 |  |  | 74033 |  |  | 74033 |  |  | 74033 |  |  | 74235 |  |  | 505000 |  |  | #REF! | 0
NIDS002 | NIDSPEU1 | IDBFunded | 25 | Project Director | 105846.15 | 1 | 661538.4375 |  | Remuneration from Technical Grant and Loan funds | [9 empty] | 8820.5125 |  |  | 8820.5125 |  |  | 8820.5125 |  |  | 8820.5125 |  |  | 8820.5125 |  |  | 8820.5125 |  |  | 8820.5125 |  |  | 8820.5125 |  |  | 8820.5125 |  |  | 8820.5125 |  |  | 8820.5125 |  |  | 8820.5125 |  |  | 8820.5125 |  |  | 8820.5125 |  |  | 8820.5125 |  |  | 8820.5125 |  |  | 8820.5125 |  |  | 8820.5125 |  |  | 79384.6125 |  |  | 105846.15 |  |  | 105846.15 |  |  | 105846.15 |  |  | 105846.15 |  |  | 105846.15 |  |  | 52923.075 |  |  | 661538.4375 |  |  | #REF! | 0
NIDS003 | NIDSPEU2 | IDBFunded | 25 | Project Coordinator | 60000 | 1 | 375000 |  | Remuneration from Technical Grant and Loan funds | [9 empty] | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 45000 |  |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 30000 |  |  | 375000 |  |  | #REF! | 0
NIDS004 | NIDSPEU3 | IDBFunded | 25 | Procurement Manager | 90923.07 | 1 | 568269.1875 |  | Remuneration from Technical Grant and Loan funds | [9 empty] | 7576.9225 |  |  | 7576.9225 |  |  | 7576.9225 |  |  | 7576.9225 |  |  | 7576.9225 |  |  | 7576.9225 |  |  | 7576.9225 |  |  | 7576.9225 |  |  | 7576.9225 |  |  | 7576.9225 |  |  | 7576.9225 |  |  | 7576.9225 |  |  | 7576.9225 |  |  | 7576.9225 |  |  | 7576.9225 |  |  | 7576.9225 |  |  | 7576.9225 |  |  | 7576.9225 |  |  | 68192.3025 |  |  | 90923.07 |  |  | 90923.07 |  |  | 90923.07 |  |  | 90923.07 |  |  | 90923.07 |  |  | 45461.535 |  |  | 568269.1875 |  |  | #REF! | 0
NIDS005 | NIDSPEU4 | IDBFunded | 25 | Financial Manager | 60000 | 1 | 375000 |  | Recruitment of Financial Manager | [9 empty] | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 45000 |  |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 30000 |  |  | 375000 |  |  | #REF! | 0
NIDS006 | NIDSPEU5 | IDBFunded | 25 | Project Accountant | 40000 | 1 | 250000 |  | Recruitment of a Project Accountant. Individual will manage the Financial requirements and reporting format for all financial transactions. | [9 empty] | 3333.3333 |  |  | 3333.3333 |  |  | 3333.3333 |  |  | 3333.3333 |  |  | 3333.3333 |  |  | 3333.3333 |  |  | 3333.3333 |  |  | 3333.3333 |  |  | 3333.3333 |  |  | 3333.3333 |  |  | 3333.3333 |  |  | 3333.3333 |  |  | 3333.3333 |  |  | 3333.3333 |  |  | 3333.3333 |  |  | 3333.3333 |  |  | 3333.3333 |  |  | 3333.3333 |  |  | 30000 |  |  | 40000 |  |  | 40000 |  |  | 40000 |  |  | 40000 |  |  | 40000 |  |  | 20000 |  |  | 250000 |  |  | #REF! | 0
NIDS007 | NIDSPEU6 | IDBFunded | 25 | Legal Specialist | 45000 | 1 | 281250 |  | Recruitment of a Legal Expert to ensure the speedy submission and approval of the drafting instruction to CPC. | [9 empty] | 3750 |  |  | 3750 |  |  | 3750 |  |  | 3750 |  |  | 3750 |  |  | 3750 |  |  | 3750 |  |  | 3750 |  |  | 3750 |  |  | 3750 |  |  | 3750 |  |  | 3750 |  |  | 3750 |  |  | 3750 |  |  | 3750 |  |  | 3750 |  |  | 3750 |  |  | 3750 |  |  | 33750 |  |  | 45000 |  |  | 45000 |  |  | 45000 |  |  | 45000 |  |  | 45000 |  |  | 22500 |  |  | 281250 |  |  | #REF! | 0
NIDS008 | NIDSPEU7 | IDBFunded | 25 | Systems Support Manager | 60000 | 1 | 365000 |  | In addition to the technical support eGov will provide , additional ICT skills required in specialized areas such as the ABIS, Identity assurance and vetting. | [15 empty] | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 35000 |  |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 30000 |  |  | 365000 |  |  | #REF! | 0
NIDS009 | NIDSPEU8 | IDBFunded | 25 | ICT Coordinator | 46000 | 1 | 287500 |  | In addition to the technical support eGov will provide , additional ICT skills required in specialized areas such as the ABIS, Identity assurance and vetting. | [9 empty] | 3833.3333 |  |  | 3833.3333 |  |  | 3833.3333 |  |  | 3833.3333 |  |  | 3833.3333 |  |  | 3833.3333 |  |  | 3833.3333 |  |  | 3833.3333 |  |  | 3833.3333 |  |  | 3833.3333 |  |  | 3833.3333 |  |  | 3833.3333 |  |  | 3833.3333 |  |  | 3833.3333 |  |  | 3833.3333 |  |  | 3833.3333 |  |  | 3833.3333 |  |  | 3833.3333 |  |  | 34500 |  |  | 46000 |  |  | 46000 |  |  | 46000 |  |  | 46000 |  |  | 46000 |  |  | 23000 |  |  | 287500 |  |  | #REF! | 0
NIDS010 | NIDSPEU9 | IDBFunded | 25 | Research &Development Officer | 44472 | 1 | 277950 |  | Ensures Project operations. | [9 empty] | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 33354 |  |  | 44472 |  |  | 44472 |  |  | 44472 |  |  | 44472 |  |  | 44472 |  |  | 22236 |  |  | 277950 |  |  | #REF! | 0
NIDS011 | NIDSPEU10 | IDBFunded | 25 | Business Process and Documentation | 44472 | 1 | 277950 |  | Please see Organizational Chart. | [9 empty] | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 33354 |  |  | 44472 |  |  | 44472 |  |  | 44472 |  |  | 44472 |  |  | 44472 |  |  | 22236 |  |  | 277950 |  |  | #REF! | 0
NIDS012 | NIDSPEU11 | IDBFunded | 25 | Marketing, PR & Communication | 60000 | 1 | 375000 |  | Please see Organizational Chart. | [9 empty] | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 45000 |  |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 30000 |  |  | 375000 |  |  | #REF! | 0
NIDS013 | NIDSPEU12 | IDBFunded | 25 | Procurement Assistant | 29000 | 2 | 362500 |  | Remuneration from Technical Grant and Loan funds starting at the end of current contract | [9 empty] | 4833.3333 |  |  | 4833.3333 |  |  | 4833.3333 |  |  | 4833.3333 |  |  | 4833.3333 |  |  | 4833.3333 |  |  | 4833.3333 |  |  | 4833.3333 |  |  | 4833.3333 |  |  | 4833.3333 |  |  | 4833.3333 |  |  | 4833.3333 |  |  | 4833.3333 |  |  | 4833.3333 |  |  | 4833.3333 |  |  | 4833.3333 |  |  | 4833.3333 |  |  | 4833.3333 |  |  | 43500 |  |  | 58000 |  |  | 58000 |  |  | 58000 |  |  | 58000 |  |  | 58000 |  |  | 29000 |  |  | 362500 |  |  | #REF! | 0
NIDS014 | NIDSPEU13 | IDBFunded | 25 | Administrative Assistant | 28000 | 1 | 175000 |  | Project Support Staff | [9 empty] | 2333.3333 |  |  | 2333.3333 |  |  | 2333.3333 |  |  | 2333.3333 |  |  | 2333.3333 |  |  | 2333.3333 |  |  | 2333.3333 |  |  | 2333.3333 |  |  | 2333.3333 |  |  | 2333.3333 |  |  | 2333.3333 |  |  | 2333.3333 |  |  | 2333.3333 |  |  | 2333.3333 |  |  | 2333.3333 |  |  | 2333.3333 |  |  | 2333.3333 |  |  | 2333.3333 |  |  | 21000 |  |  | 28000 |  |  | 28000 |  |  | 28000 |  |  | 28000 |  |  | 28000 |  |  | 14000 |  |  | 175000 |  |  | #REF! | 0
NIDS015 | NIDSPEU14 | IDBFunded | 25 | Monitoring and Evaluation Officer | 60000 | 1 | 375000 |  | Project Support Staff | [9 empty] | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 45000 |  |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 30000 |  |  | 375000 |  |  | #REF! | 0
NIDS016 | NIDSPEU15 | IDBFunded | 25 | ICT - Deployment and Support Personnel | 33000 | 4 | 693000 |  | Project Support Staff | [45 empty] | 11000 |  |  | 11000 |  |  | 11000 |  |  | 11000 |  |  | 11000 |  |  | 11000 |  |  | 0 |  |  | 99000 |  |  | 132000 |  |  | 132000 |  |  | 132000 |  |  | 132000 |  |  | 66000 |  |  | 693000 |  |  | #REF! | 0
|  |  |  | PRODUCTION PROJECT STAFF: | [53 empty] | 0 | [14 empty] | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | #REF! | 0
NIDS018 | NIDSPEU17 | IDBFunded | 25 | Senior Manager, Card & NIN Services | 60000 | 1 | 310000 |  | Production Staff | [48 empty] | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 0 |  |  | 40000 |  |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 30000 |  |  | 310000 |  |  | #REF! | 0
NIDS019 | NIDSPEU18 | IDBFunded | 25 | Production and Distribution Manager | 44472 | 1 | 229772 |  | Production Staff | [48 empty] | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 0 |  |  | 29648 |  |  | 44472 |  |  | 44472 |  |  | 44472 |  |  | 44472 |  |  | 22236 |  |  | 229772 |  |  | #REF! | 0
NIDS020 | NIDSPEU19 | IDBFunded | 25 | Vetting Manager | 44472 | 1 | 229772 |  | Production Staff | [48 empty] | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 3706 |  |  | 0 |  |  | 29648 |  |  | 44472 |  |  | 44472 |  |  | 44472 |  |  | 44472 |  |  | 22236 |  |  | 229772 |  |  | #REF! | 0
NIDS021 | NIDSPEU20 | IDBFunded | 25 | Machine Operators - Printers | 22000 | 2 | 227333.3333 |  | Production Staff | [48 empty] | 3666.6667 |  |  | 3666.6667 |  |  | 3666.6667 |  |  | 3666.6667 |  |  | 3666.6667 |  |  | 0 |  |  | 29333.3333 |  |  | 44000 |  |  | 44000 |  |  | 44000 |  |  | 44000 |  |  | 22000 |  |  | 227333.3333 |  |  | #REF! | 0
NIDS022 | NIDSPEU21 | IDBFunded | 25 | Vetting Officers - QC Vetting Section | 23000 | 8 | 950666.6667 |  | Production Staff | [48 empty] | 15333.3333 |  |  | 15333.3333 |  |  | 15333.3333 |  |  | 15333.3333 |  |  | 15333.3333 |  |  | 0 |  |  | 122666.6667 |  |  | 184000 |  |  | 184000 |  |  | 184000 |  |  | 184000 |  |  | 92000 |  |  | 950666.6667 |  |  | #REF! | 0
NIDS023 | NIDSPEU22 | IDBFunded | 25 | Quality Control Officers - Printing Room | 23000 | 8 | 950666.6667 |  | Production Staff | [48 empty] | 15333.3333 |  |  | 15333.3333 |  |  | 15333.3333 |  |  | 15333.3333 |  |  | 15333.3333 |  |  | 0 |  |  | 122666.6667 |  |  | 184000 |  |  | 184000 |  |  | 184000 |  |  | 184000 |  |  | 92000 |  |  | 950666.6667 |  |  | #REF! | 0
NIDS024 | NIDSPEU23 | IDBFunded | 25 | Store Room and Distribution Officer | 23000 | 1 | 118833.3333 |  | Production Staff | [48 empty] | 1916.6667 |  |  | 1916.6667 |  |  | 1916.6667 |  |  | 1916.6667 |  |  | 1916.6667 |  |  | 0 |  |  | 15333.3333 |  |  | 23000 |  |  | 23000 |  |  | 23000 |  |  | 23000 |  |  | 11500 |  |  | 118833.3333 |  |  | #REF! | 0
|  |  |  | SUB TOTAL ESTABLISHMENT OF NIRA |  |  | 9337001.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61892.7683 | 0 | 0 | 61892.7683 | 0 | 0 | 66892.7683 | 0 | 0 | 165092.7683 | 0 | 0 | 76992.7683 | 0 | 0 | 76992.7683 | 0 | 0 | 76992.7683 | 0 | 0 | 76992.7683 | 0 | 0 | 76992.7683 | 0 | 0 | 76992.7683 | 0 | 0 | 76992.7683 | 0 | 0 | 76992.7683 | 0 | 0 | 87992.7683 | 0 | 0 | 136654.7683 | 0 | 0 | 136654.7683 | 0 | 0 | 136654.7683 | 0 | 0 | 136654.7683 | 0 | 0 | 136654.7683 | 0 | 0 | 740734.915 | 0 | 0 | 1370642.22 | 0 | 0 | 1602790.22 | 0 | 0 | 1595490.22 | 0 | 0 | 1595490.22 | 0 | 0 | 1595490.22 | 0 | 0 | 836363.61 | 0 | 0 | 8717001.625 | 0 | 0 | #REF! | 620000
|  |  |  | IMPROVEMENT OF THE CIVIL REGISTRY | [68 empty] | 0 | [20 empty] | 0 |  |  | #REF! | 0
NIDS028 | NIRA1 | IDBFunded | 25 | Establish a Business Model for the NIRA: Establish Structure for NIRA Governance, Resources and Staff Develop Job Descriptions Design Revenue Model for NIRA Develop Decisions Making Processes Mechanism for Accountability | 405000 | 1 | 405000 |  | Consultancy to define business model for the JNIA | [45 empty] | 81000 | [14 empty] | 81000 |  |  | 0 |  |  | 162000 |  |  | 162000 |  |  | 81000 | [11 empty] | 405000 |  |  | #REF! | 0
NIDS028B | NIRA2 | IDBFunded | 26 | Project Coordinator - RGD Activities | 48000 | 2 | 96000 |  | Manage, Track and Report on All RGD Targets | [15 empty] | 4000 |  |  | 4000 |  |  | 4000 |  |  | 4000 |  |  | 4000 |  |  | 4000 |  |  | 4000 |  |  | 4000 |  |  | 4000 |  |  | 4000 |  |  | 4000 |  |  | 4000 |  |  | 4000 |  |  | 4000 |  |  | 4000 |  |  | 4000 |  |  | 28000 |  |  | 48000 |  |  | 20000 | [14 empty] | 96000 |  |  | #REF! | 0
NIDS029 | NIRA2 | IDBFunded | 25 | Knowledge Sharing Strategy (Study Tour) | 8615.3846 | 10 | 86153.8462 |  | Training Sessions to be conducted in South Korea | [27 empty] | 86153.8462 | [35 empty] | 86153.8462 | [20 empty] | 86153.8462 |  |  | #REF! | 0
|  |  |  | Mobile Enrollment Stations - For New Born and Mother Verification: | [68 empty] | 0 | [20 empty] | 0 |  |  | #REF! | 0
NIDS031 | IDMS_SOL1 | IDBFunded | 32 | Mobile Enrolment Tablets for RGD New Born | 400 | 160 | 64000 | [35 empty] | 12800 | [11 empty] | 12800 | [11 empty] | 19200 | [5 empty] | 12800 |  |  | 32000 |  |  | 19200 | [14 empty] | 64000 |  |  | #REF! | 0
NIDS032 | IDMS_SOL1 | IDBFunded | 32 | Mobile Enrolment Tablets Shoulder Bag for RGD | 50 | 160 | 8000 | [35 empty] | 1600 | [11 empty] | 1600 | [11 empty] | 2400 | [5 empty] | 1600 |  |  | 4000 |  |  | 2400 | [14 empty] | 8000 |  |  | #REF! | 0
|  |  |  | DIGITIZATION OF RGD RECORDS: | [38 empty] | 0 | [32 empty] | 0 | [17 empty] | 0 |  |  | #REF! | 0
|  |  |  | PERSONNEL: | [38 empty] | 0 | [50 empty] | 0 |  |  | #REF! | 0
NIDS035 | RGDPEU1 | IDBFunded | 25 | Scanning Officers | 6923.0769 | 30 | 415384.6154 |  | RGD Transformation and NIRA | [36 empty] | 17307.6923 |  |  | 17307.6923 |  |  | 17307.6923 |  |  | 17307.6923 |  |  | 17307.6923 |  |  | 17307.6923 |  |  | 17307.6923 |  |  | 17307.6923 |  |  | 17307.6923 |  |  | 0 |  |  | 207692.3077 |  |  | 207692.3077 | [14 empty] | 415384.6154 |  |  | #REF! | 0
NIDS036 | RGDPEU2 | IDBFunded | 25 | Data Entry Officer | 6923.0769 | 90 | 1246153.8462 |  | RGD Transformation and NIRA | [36 empty] | 51923.0769 |  |  | 51923.0769 |  |  | 51923.0769 |  |  | 51923.0769 |  |  | 51923.0769 |  |  | 51923.0769 |  |  | 51923.0769 |  |  | 51923.0769 |  |  | 51923.0769 |  |  | 0 |  |  | 623076.9231 |  |  | 623076.9231 | [14 empty] | 1246153.8462 |  |  | #REF! | 0
NIDS037 | RGDPEU3 | IDBFunded | 25 | Supervisors | 9230.7692 | 5 | 92307.6923 |  | RGD Transformation and NIRA | [36 empty] | 3846.1538 |  |  | 3846.1538 |  |  | 3846.1538 |  |  | 3846.1538 |  |  | 3846.1538 |  |  | 3846.1538 |  |  | 3846.1538 |  |  | 3846.1538 |  |  | 3846.1538 |  |  | 0 |  |  | 46153.8462 |  |  | 46153.8462 | [14 empty] | 92307.6923 |  |  | #REF! | 0
NIDS038 | RGDPEU4 | IDBFunded | 25 | Programmers | 20000 | 2 | 40000 |  | RGD Transformation and NIRA | [18 empty] | 1666.6667 |  |  | 1666.6667 |  |  | 1666.6667 |  |  | 1666.6667 |  |  | 1666.6667 |  |  | 1666.6667 |  |  | 1666.6667 |  |  | 1666.6667 |  |  | 1666.6667 |  |  | 1666.6667 |  |  | 1666.6667 |  |  | 1666.6667 |  |  | 1666.6667 |  |  | 1666.6667 |  |  | 1666.6667 |  |  | 10000 |  |  | 20000 |  |  | 10000 | [14 empty] | 40000 |  |  | #REF! | 0
NIDS039 | RGDPEU5 | IDBFunded | 25 | IT Technicians | 11538.4615 | 2 | 23076.9231 | [32 empty] | 961.5385 |  |  | 961.5385 |  |  | 961.5385 |  |  | 961.5385 |  |  | 961.5385 |  |  | 961.5385 |  |  | 961.5385 |  |  | 961.5385 |  |  | 961.5385 |  |  | 961.5385 |  |  | 961.5385 |  |  | 1923.0769 |  |  | 11538.4615 |  |  | 9615.3846 | [14 empty] | 23076.9231 |  |  | #REF! | 0
|  |  |  | TRAINING: |  |  |  |  | RGD Transformation and NIRA | [63 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS041 | RGDTR1 | IDBFunded | 25 | Classes | 769.2308 | 6 | 4615.3846 |  | RGD Transformation and NIRA | [36 empty] | 4615.3846 | [26 empty] | 0 |  |  | 4615.3846 | [17 empty] | 4615.3846 |  |  | #REF! | 0
NIDS042 | RGDTR1 | IDBFunded | 25 | Documentation Manual | 384.6154 | 2 | 769.2308 |  | RGD Transformation and NIRA | [36 empty] | 769.2308 | [26 empty] | 0 |  |  | 769.2308 | [17 empty] | 769.2308 |  |  | #REF! | 0
NIDS043 | RGDTR1 | IDBFunded | 25 | Trainer | 1153.8462 | 2 | 2307.6923 |  | RGD Transformation and NIRA | [36 empty] | 2307.6923 | [26 empty] | 0 |  |  | 2307.6923 | [17 empty] | 2307.6923 |  |  | #REF! | 0
|  |  |  | MAINTENANCE & SUPPORT: |  |  | 0 |  | RGD Transformation and NIRA | [63 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS045 | RGDPR1 | IDBFunded | 25 | Printing | 1692.3077 | 2 | 3384.6154 |  | RGD Transformation and NIRA | [21 empty] | 282.0513 |  |  | 282.0513 |  |  | 282.0513 |  |  | 282.0513 |  |  | 282.0513 |  |  | 282.0513 |  |  | 282.0513 |  |  | 282.0513 |  |  | 282.0513 |  |  | 282.0513 |  |  | 282.0513 |  |  | 282.0513 | [8 empty] | 1410.2564 |  |  | 1974.359 | [17 empty] | 3384.6154 |  |  | #REF! | 0 | #REF!
|  |  |  | STRUCTURAL: |  |  |  |  | RGD Transformation and NIRA | [63 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS047 | RGDMODSPC1 | IDBFunded | 25 | Site power & Cooling | 3076.9231 | 6 | 18461.5385 |  | RGD Transformation and NIRA | [21 empty] | 3692.3077 |  |  | 3692.3077 |  |  | 3692.3077 |  |  | 3692.3077 |  |  | 3692.3077 | [29 empty] | 18461.5385 |  |  | 0 | [17 empty] | 18461.5385 |  |  | #REF! | 0
NIDS048 | RGDMODSPC1 | IDBFunded | 25 | Modification of spaces for the Digitization of records and operation of NIDS | 246584.6154 | 1 | 246584.6154 |  | RGD Transformation and NIRA | [21 empty] | 49316.9231 |  |  | 49316.9231 |  |  | 49316.9231 |  |  | 49316.9231 |  |  | 49316.9231 | [29 empty] | 246584.6154 |  |  | 0 | [17 empty] | 246584.6154 |  |  | #REF! | 0
NIDS049 | RGDMODSPC1 | IDBFunded | 25 | Architecture, Engineer and Quantity Surveyor services | 11076.9231 | 1 | 11076.9231 |  | RGD Transformation and NIRA | [9 empty] | 2215.3846 |  |  | 4430.7692 |  |  | 4430.7692 | [47 empty] | 11076.9231 |  |  | 0 | [17 empty] | 11076.9231 |  |  | #REF! | 0
NIDS050 | RGDMODSPC1 | IDBFunded | 25 | Electrical Works | 16153.8462 | 1 | 16153.8462 |  | RGD Transformation and NIRA | [21 empty] | 3230.7692 |  |  | 3230.7692 |  |  | 3230.7692 |  |  | 3230.7692 |  |  | 3230.7692 | [29 empty] | 16153.8462 |  |  | 0 | [17 empty] | 16153.8462 |  |  | #REF! | 0
NIDS051 | RGDMODSPC1 | IDBFunded | 25 | Relocation of Generator room | 23076.9231 | 1 | 23076.9231 |  | RGD Transformation and NIRA | [21 empty] | 4615.3846 |  |  | 4615.3846 |  |  | 4615.3846 |  |  | 4615.3846 |  |  | 4615.3846 | [29 empty] | 23076.9231 |  |  | 0 | [17 empty] | 23076.9231 |  |  | #REF! | 0
|  |  |  | FURNITURE: |  |  | 0 |  | RGD Transformation and NIRA | [63 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS053 | RGDDSKCHR1 | IDBFunded | 25 | Desks | 192.3077 | 67 | 12884.6154 |  | RGD Transformation and NIRA | [33 empty] | 12884.6154 | [29 empty] | 12884.6154 |  |  | 0 | [17 empty] | 12884.6154 |  |  | #REF! | 0
NIDS054 | RGDDSKCHR1 | IDBFunded | 25 | Chairs | 96.1538 | 67 | 6442.3077 |  | RGD Transformation and NIRA | [33 empty] | 6442.3077 | [29 empty] | 6442.3077 |  |  | 0 | [17 empty] | 6442.3077 |  |  | #REF! | 0
|  |  |  | WORKSTATION SOFTWARE: |  |  | 0 |  | RGD Transformation and NIRA | [63 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS056 | RGDSTR1 | IDBFunded | 25 | MS Office | 346.1538 | 4 | 1384.6154 |  | RGD Transformation and NIRA | [33 empty] | 1384.6154 | [29 empty] | 1384.6154 |  |  | 0 | [17 empty] | 1384.6154 |  |  | #REF! | 0
|  |  |  | SERVER SOFTWARE: |  |  | 0 |  | RGD Transformation and NIRA | [63 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS058 | RGDSOF1 | IDBFunded | 25 | MS 2016 Data Center Server Edition | 15384.6154 | 1 | 15384.6154 |  | RGD Transformation and NIRA | [33 empty] | 15384.6154 | [29 empty] | 15384.6154 |  |  | 0 | [17 empty] | 15384.6154 |  |  | #REF! | 0
NIDS059 | RGDSOF1 | IDBFunded | 25 | MS 2016 CALs License | 4615.3846 | 1 | 4615.3846 |  | RGD Transformation and NIRA | [33 empty] | 4615.3846 | [29 empty] | 4615.3846 |  |  | 0 | [17 empty] | 4615.3846 |  |  | #REF! | 0
NIDS060 | RGDSOF1 | IDBFunded |  | Paper Scan Version 1.7 50 license | 1000 | 1 | 1000 |  | RGD Transformation and NIRA | [33 empty] | 1000 | [29 empty] | 1000 |  |  | 0 | [17 empty] | 1000 |  |  | #REF! | 0
NIDS061 | RGDSOF1 | IDBFunded | 32 | SQL License Server | 7692.3077 | 1 | 7692.3077 |  | RGD Transformation and NIRA | [33 empty] | 7692.3077 | [29 empty] | 7692.3077 |  |  | 0 | [17 empty] | 7692.3077 |  |  | #REF! | 0
|  |  |  | SECURITY SOFTWARE: |  |  | 0 |  | RGD Transformation and NIRA | [63 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS063 | RGDSOF1 | IDBFunded | 25 | Anti-virus | 11538.4615 | 1 | 11538.4615 |  | RGD Transformation and NIRA | [33 empty] | 11538.4615 | [29 empty] | 11538.4615 |  |  | 0 | [17 empty] | 11538.4615 |  |  | #REF! | 0
|  |  |  | DESKTOP HARDWARE: |  |  | 0 |  | RGD Transformation and NIRA | [63 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS065 | RGDHRD1 | IDBFunded | 32 | Computer (Micro Desktop) | 846.1538 | 68 | 57538.4615 |  | RGD Transformation and NIRA | [30 empty] | 57538.4615 | [32 empty] | 57538.4615 |  |  | 0 | [17 empty] | 57538.4615 |  |  | #REF! | 0
NIDS066 | RGDHRD1 | IDBFunded | 32 | Laptop | 1230.7692 | 2 | 2461.5385 |  | RGD Transformation and NIRA | [18 empty] | 2461.5385 | [44 empty] | 2461.5385 |  |  | 0 | [17 empty] | 2461.5385 |  |  | #REF! | 0
|  |  |  | NETWORKING: |  |  | 0 |  | RGD Transformation and NIRA | [63 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS068 | RGDNET1 | IDBFunded | 32 | Ports (labour) | 65.3846 | 100 | 6538.4615 |  | RGD Transformation and NIRA | [33 empty] | 6538.4615 | [29 empty] | 6538.4615 |  |  | 0 | [17 empty] | 6538.4615 |  |  | #REF! | 0
NIDS069 | RGDNET1 | IDBFunded | 32 | Racks | 1153.8462 | 1 | 1153.8462 |  | RGD Transformation and NIRA | [33 empty] | 1153.8462 | [29 empty] | 1153.8462 |  |  | 0 | [17 empty] | 1153.8462 |  |  | #REF! | 0
NIDS070 | RGDNET1 | IDBFunded | 32 | Patch Panel 48 Port | 192.3077 | 3 | 576.9231 |  | RGD Transformation and NIRA | [33 empty] | 576.9231 | [29 empty] | 576.9231 |  |  | 0 | [17 empty] | 576.9231 |  |  | #REF! | 0
NIDS071 | RGDNET1 | IDBFunded | 32 | Network Cable Cat6 (box) | 100 | 12 | 1200 |  | RGD Transformation and NIRA | [33 empty] | 1200 | [29 empty] | 1200 |  |  | 0 | [17 empty] | 1200 |  |  | #REF! | 0
NIDS072 | RGDNET1 | IDBFunded |  | Switch -1 GB layer 2 | 3076.9231 | 3 | 9230.7692 |  | RGD Transformation and NIRA | [33 empty] | 9230.7692 | [29 empty] | 9230.7692 |  |  | 0 | [17 empty] | 9230.7692 |  |  | #REF! | 0
|  |  |  | SERVERS |  |  | 0 |  | RGD Transformation and NIRA | [33 empty] | 0 | [29 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS074 | RGDSERV1 | IDBFunded | 32 | Virtual Host Server | 7692.3077 | 2 | 15384.6154 |  | RGD Transformation and NIRA | [33 empty] | 15384.6154 | [29 empty] | 15384.6154 |  |  | 0 | [17 empty] | 15384.6154 |  |  | #REF! | 0
NIDS075 | RGDSERV1 | IDBFunded | 32 | Verification Server | 7692.3077 | 1 | 7692.3077 |  | RGD Transformation and NIRA | [33 empty] | 7692.3077 | [29 empty] | 7692.3077 |  |  | 0 | [17 empty] | 7692.3077 |  |  | #REF! | 0
|  |  |  | STORAGE |  |  | 0 |  | RGD Transformation and NIRA | [63 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS077 | RGDSTOR1 | IDBFunded | 32 | NAS Drives (72 TB) | 9230.7692 | 2 | 18461.5385 |  | RGD Transformation and NIRA | [33 empty] | 18461.5385 | [29 empty] | 18461.5385 |  |  | 0 | [17 empty] | 18461.5385 |  |  | #REF! | 0
|  |  |  | MISC |  |  | 0 |  | RGD Transformation and NIRA | [63 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS079 | RGDHRD1 | IDBFunded | 32 | Scanner Flat Bed | 7307.6923 | 16 | 116923.0769 |  | RGD Transformation and NIRA | [33 empty] | 116923.0769 | [29 empty] | 116923.0769 |  |  | 0 | [17 empty] | 116923.0769 |  |  | #REF! | 0
NIDS080 | RGDHRD1 | IDBFunded | 32 | Scanners Roller Feed | 3846.1538 | 16 | 61538.4615 |  | RGD Transformation and NIRA | [33 empty] | 61538.4615 | [29 empty] | 61538.4615 |  |  | 0 | [17 empty] | 61538.4615 |  |  | #REF! | 0
NIDS081 | RGDHRD1 | IDBFunded |  | Rollers for Scanner | 38.4615 | 64 | 2461.5385 |  | RGD Transformation and NIRA | [33 empty] | 2461.5385 | [29 empty] | 2461.5385 |  |  | 0 | [17 empty] | 2461.5385 |  |  | #REF! | 0
NIDS082 | RGDHRD1 | IDBFunded | 32 | 18KVA UPS | 13076.9231 | 1 | 13076.9231 |  | RGD Transformation and NIRA | [33 empty] | 13076.9231 | [29 empty] | 13076.9231 |  |  | 0 | [17 empty] | 13076.9231 |  |  | #REF! | 0
NIDS083 | RGDHRD2 | IDBFunded |  | Tape Library | 16000 | 1 | 16000 |  | RGD Transformation and NIRA | [33 empty] | 16000 | [29 empty] | 16000 |  |  | 0 | [17 empty] | 16000 |  |  | #REF! | 0
|  |  |  | TRANSPORTATION |  |  | 0 |  | RGD Transformation and NIRA | [63 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS085 | RGDTRAN1 | IDBFunded | 23 | Transport of staff for digitization | 69240 | 2 | 138480 |  | RGD Transformation and NIRA | [36 empty] | 5770 |  |  | 5770 |  |  | 5770 |  |  | 5770 |  |  | 5770 |  |  | 5770 |  |  | 5770 |  |  | 5770 |  |  | 5770 |  |  | 0 |  |  | 69240 |  |  | 69240 | [14 empty] | 138480 |  |  | #REF! | 0
|  |  |  | SUBTOTAL TRANSFORMATION OF THE CIVIL REGISTRY |  |  | 3332168.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2215.3846 | 0 | 0 | 4430.7692 | 0 | 0 | 8430.7692 | 0 | 0 | 8128.2051 | 0 | 0 | 66804.1026 | 0 | 0 | 66804.1026 | 0 | 0 | 152957.9487 | 0 | 0 | 125304.1026 | 0 | 0 | 413346.4103 | 0 | 0 | 93449.4872 | 0 | 0 | 85757.1795 | 0 | 0 | 85757.1795 | 0 | 0 | 181157.1795 | 0 | 0 | 85757.1795 | 0 | 0 | 85757.1795 | 0 | 0 | 85757.1795 | 0 | 0 | 107075.1282 | 0 | 0 | 166475.1282 | 0 | 0 | 848421.7949 | 0 | 0 | 1233368.2051 | 0 | 0 | 1169378.4615 | 0 | 0 | 81000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3332168.4615 | 0 | 0 | #REF! | 0
|  |  |  | COMMUNICATIONS AND BEHAVIOUR CHANGE | [89 empty] | 0 |  |  | #REF! | 0
|  |  |  | PR AND MEDIA VISIBILITY: | [89 empty] | 0 |  |  | #REF! | 0
NIDS089 | COMPR1 | IDBFunded | 25 | PR Support for NIDS Activities (e.g. Presentations, speeches, press releases,) | 61538.4615 | 1 | 61538.4615 |  | 10 % of budget in April 2017; to support bill debate and passing 20% of budget in August 2017; to support contract approval in November 2017 20 % of budget in April 2018 to support pilot in July 2018 -September 2018 50 % of budget in December 2018 to support national rollout in Jan 2019 | [15 empty] | 1230.7692 | [14 empty] | 1230.7692 | [20 empty] | 1230.7692 |  |  | 1230.7692 |  |  | 1230.7692 |  |  | 1230.7692 |  |  | 2461.5385 |  |  | 8615.3846 |  |  | 10092.3077 |  |  | 10092.3077 |  |  | 10092.3077 |  |  | 10092.3077 |  |  | 10092.3077 |  |  | 61538.4615 |  |  | #REF! | 0
NIDS090 | COMPR1 | IDBFunded | 25 | PR Consultant Support - Writers, Execution Agency, Co-coordinator, Facilitator etc. | 123076.9231 | 1 | 123076.9231 | [17 empty] | 2461.5385 | [14 empty] | 2461.5385 | [20 empty] | 2461.5385 |  |  | 2461.5385 |  |  | 2461.5385 |  |  | 2461.5385 |  |  | 4923.0769 |  |  | 17230.7692 |  |  | 20184.6154 |  |  | 20184.6154 |  |  | 20184.6154 |  |  | 20184.6154 |  |  | 20184.6154 |  |  | 123076.9231 |  |  | #REF! | 0
NIDS091 | COMPR1 | IDBFunded | 25 | External Engagement Island wide - Assocs. Advocate Group, Media etc. | 53846.1538 | 1 | 53846.1538 | [17 empty] | 1076.9231 | [14 empty] | 1076.9231 | [20 empty] | 1076.9231 |  |  | 1076.9231 |  |  | 1076.9231 |  |  | 1076.9231 |  |  | 2153.8462 |  |  | 7538.4615 |  |  | 8830.7692 |  |  | 8830.7692 |  |  | 8830.7692 |  |  | 8830.7692 |  |  | 8830.7692 |  |  | 53846.1538 |  |  | #REF! | 0
NIDS092 | COMPR1 | IDBFunded | 25 | Employee Engagement/Internal Communications across Agencies | 23076.9231 | 1 | 23076.9231 | [17 empty] | 461.5385 | [14 empty] | 461.5385 | [20 empty] | 461.5385 |  |  | 461.5385 |  |  | 461.5385 |  |  | 461.5385 |  |  | 923.0769 |  |  | 3230.7692 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 23076.9231 |  |  | #REF! | 0
|  |  |  | ADVERTISING AND PROMOTION: | [56 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | #REF! | 0
NIDS094 | COMADV1 | IDBFunded | 25 | PRODUCTION COSTS |  |  | 0 | [53 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | #REF! | 0
NIDS095 | COMADV1 | IDBFunded | 25 | Television | 192307.6923 | 1 | 192307.6923 | [17 empty] | 3846.1538 | [14 empty] | 3846.1538 | [20 empty] | 3846.1538 |  |  | 3846.1538 |  |  | 3846.1538 |  |  | 3846.1538 |  |  | 7692.3077 |  |  | 26923.0769 |  |  | 31538.4615 |  |  | 31538.4615 |  |  | 31538.4615 |  |  | 31538.4615 |  |  | 31538.4615 |  |  | 192307.6923 |  |  | #REF! | 0
NIDS096 | COMADV1 | IDBFunded | 25 | Radio Ads & Programmes | 30769.2308 | 1 | 30769.2308 | [17 empty] | 615.3846 | [14 empty] | 615.3846 | [20 empty] | 615.3846 |  |  | 615.3846 |  |  | 615.3846 |  |  | 615.3846 |  |  | 1230.7692 |  |  | 4307.6923 |  |  | 5046.1538 |  |  | 5046.1538 |  |  | 5046.1538 |  |  | 5046.1538 |  |  | 5046.1538 |  |  | 30769.2308 |  |  | #REF! | 0
NIDS097 | COMADV1 | IDBFunded | 25 | Outdoor (billboards, video boards, supermarket screens, bus sheds, bus sides etc. | 153846.1538 | 1 | 153846.1538 | [17 empty] | 3076.9231 | [14 empty] | 3076.9231 | [20 empty] | 3076.9231 |  |  | 3076.9231 |  |  | 3076.9231 |  |  | 3076.9231 |  |  | 6153.8462 |  |  | 21538.4615 |  |  | 25230.7692 |  |  | 25230.7692 |  |  | 25230.7692 |  |  | 25230.7692 |  |  | 25230.7692 |  |  | 153846.1538 |  |  | #REF! | 0
NIDS098 | COMADV1 | IDBFunded | 25 | Print Ads & Advertorials | 46153.8462 | 1 | 46153.8462 | [17 empty] | 923.0769 | [14 empty] | 923.0769 | [20 empty] | 923.0769 |  |  | 923.0769 |  |  | 923.0769 |  |  | 923.0769 |  |  | 1846.1538 |  |  | 6461.5385 |  |  | 7569.2308 |  |  | 7569.2308 |  |  | 7569.2308 |  |  | 7569.2308 |  |  | 7569.2308 |  |  | 46153.8462 |  |  | #REF! | 0
NIDS099 | COMADV1 | IDBFunded | 25 | Newsletters, Brochures, Leaflets, Posters, Flyers, Fact Sheets other collateral material | 30769.2308 | 1 | 30769.2308 | [17 empty] | 615.3846 | [14 empty] | 615.3846 | [20 empty] | 615.3846 |  |  | 615.3846 |  |  | 615.3846 |  |  | 615.3846 |  |  | 1230.7692 |  |  | 4307.6923 |  |  | 5046.1538 |  |  | 5046.1538 |  |  | 5046.1538 |  |  | 5046.1538 |  |  | 5046.1538 |  |  | 30769.2308 |  |  | #REF! | 0
NIDS100 | COMADV1 | IDBFunded | 25 | Promotional Material e.g. t-shirts, cups, pens etc. | 23076.9231 | 1 | 23076.9231 | [17 empty] | 461.5385 | [14 empty] | 461.5385 | [20 empty] | 461.5385 |  |  | 461.5385 |  |  | 461.5385 |  |  | 461.5385 |  |  | 923.0769 |  |  | 3230.7692 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 23076.9231 |  |  | #REF! | 0
NIDS101 | COMADV1 | IDBFunded | 25 | Digital Media (including Google Ads) | 15384.6154 | 1 | 15384.6154 | [17 empty] | 307.6923 | [14 empty] | 307.6923 | [20 empty] | 307.6923 |  |  | 307.6923 |  |  | 307.6923 |  |  | 307.6923 |  |  | 615.3846 |  |  | 2153.8462 |  |  | 2523.0769 |  |  | 2523.0769 |  |  | 2523.0769 |  |  | 2523.0769 |  |  | 2523.0769 |  |  | 15384.6154 |  |  | #REF! | 0
|  |  |  | PLACEMENT/ RENTAL/ POSTERING COSTS |  | 1 | 0 | [53 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | #REF! | 0
NIDS103 | COMPLAC1 | IDBFunded | 25 | Television | 461538.4615 | 1 | 461538.4615 | [17 empty] | 9230.7692 | [14 empty] | 9230.7692 | [20 empty] | 9230.7692 |  |  | 9230.7692 |  |  | 9230.7692 |  |  | 9230.7692 |  |  | 18461.5385 |  |  | 64615.3846 |  |  | 75692.3077 |  |  | 75692.3077 |  |  | 75692.3077 |  |  | 75692.3077 |  |  | 75692.3077 |  |  | 461538.4615 |  |  | #REF! | 0
NIDS104 | COMPLAC1 | IDBFunded | 25 | Radio | 38461.5385 | 1 | 38461.5385 | [17 empty] | 769.2308 | [14 empty] | 769.2308 | [20 empty] | 769.2308 |  |  | 769.2308 |  |  | 769.2308 |  |  | 769.2308 |  |  | 1538.4615 |  |  | 5384.6154 |  |  | 6307.6923 |  |  | 6307.6923 |  |  | 6307.6923 |  |  | 6307.6923 |  |  | 6307.6923 |  |  | 38461.5385 |  |  | #REF! | 0
NIDS105 | COMPLAC1 | IDBFunded | 25 | Outdoor Rentals/Postering & Transport (billboards, video boards, supermarket screens, bus sheds, bus sides etc. | 215384.6154 | 1 | 215384.6154 | [17 empty] | 4307.6923 | [14 empty] | 4307.6923 | [20 empty] | 4307.6923 |  |  | 4307.6923 |  |  | 4307.6923 |  |  | 4307.6923 |  |  | 8615.3846 |  |  | 30153.8462 |  |  | 35323.0769 |  |  | 35323.0769 |  |  | 35323.0769 |  |  | 35323.0769 |  |  | 35323.0769 |  |  | 215384.6154 |  |  | #REF! | 0
NIDS106 | COMPLAC1 | IDBFunded | 25 | Print | 269230.7692 | 1 | 269230.7692 | [17 empty] | 5384.6154 | [14 empty] | 5384.6154 | [20 empty] | 5384.6154 |  |  | 5384.6154 |  |  | 5384.6154 |  |  | 5384.6154 |  |  | 10769.2308 |  |  | 37692.3077 |  |  | 44153.8462 |  |  | 44153.8462 |  |  | 44153.8462 |  |  | 44153.8462 |  |  | 44153.8462 |  |  | 269230.7692 |  |  | #REF! | 0
NIDS107 | COMPLAC1 | IDBFunded |  | Digital Media | 30769.2308 | 1 | 30769.2308 | [17 empty] | 615.3846 | [14 empty] | 615.3846 | [20 empty] | 615.3846 |  |  | 615.3846 |  |  | 615.3846 |  |  | 615.3846 |  |  | 1230.7692 |  |  | 4307.6923 |  |  | 5046.1538 |  |  | 5046.1538 |  |  | 5046.1538 |  |  | 5046.1538 |  |  | 5046.1538 |  |  | 30769.2308 |  |  | #REF! | 0
NIDS108 | COMPLAC1 | IDBFunded | 25 | Outside Broadcasts (Radio & Television) | 46153.8462 | 1 | 46153.8462 | [17 empty] | 923.0769 | [14 empty] | 923.0769 | [20 empty] | 923.0769 |  |  | 923.0769 |  |  | 923.0769 |  |  | 923.0769 |  |  | 1846.1538 |  |  | 6461.5385 |  |  | 7569.2308 |  |  | 7569.2308 |  |  | 7569.2308 |  |  | 7569.2308 |  |  | 7569.2308 |  |  | 46153.8462 |  |  | #REF! | 0
NIDS109 | COMPLAC1 | IDBFunded | 25 | Promotional Material e.g. t-shirts, cups, pens etc. | 230769.2308 | 1 | 230769.2308 | [17 empty] | 4615.3846 | [14 empty] | 4615.3846 | [20 empty] | 4615.3846 |  |  | 4615.3846 |  |  | 4615.3846 |  |  | 4615.3846 |  |  | 9230.7692 |  |  | 32307.6923 |  |  | 37846.1538 |  |  | 37846.1538 |  |  | 37846.1538 |  |  | 37846.1538 |  |  | 37846.1538 |  |  | 230769.2308 |  |  | #REF! | 0
|  |  |  | EVENTS (COMMUNITY, NATIONAL & DIASPORA) | [20 empty] | 0 | [14 empty] | 0 | [20 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | #REF! | 0
|  |  |  | Community | [56 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | #REF! | 0
NIDS112 | COMEVENTS2 | IDBFunded | 25 | Town Hall Meetings | 38461.5385 | 1 | 38461.5385 | [17 empty] | 769.2308 | [14 empty] | 769.2308 | [20 empty] | 769.2308 |  |  | 769.2308 |  |  | 769.2308 |  |  | 769.2308 |  |  | 1538.4615 |  |  | 5384.6154 |  |  | 6307.6923 |  |  | 6307.6923 |  |  | 6307.6923 |  |  | 6307.6923 |  |  | 6307.6923 |  |  | 38461.5385 |  |  | #REF! | 0
NIDS113 | COMEVENTS3 | IDBFunded | 25 | Focus Groups | 23076.9231 | 1 | 23076.9231 | [17 empty] | 461.5385 | [14 empty] | 461.5385 | [20 empty] | 461.5385 |  |  | 461.5385 |  |  | 461.5385 |  |  | 461.5385 |  |  | 923.0769 |  |  | 3230.7692 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 23076.9231 |  |  | #REF! | 0
NIDS114 | COMEVENTS4 | IDBFunded | 25 | Community Engagement/ Roll Out in New Areas e.g. Town Criers & Promotional Incentive events | 23076.9231 | 1 | 23076.9231 | [17 empty] | 461.5385 | [14 empty] | 461.5385 | [20 empty] | 461.5385 |  |  | 461.5385 |  |  | 461.5385 |  |  | 461.5385 |  |  | 923.0769 |  |  | 3230.7692 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 23076.9231 |  |  | #REF! | 0
NIDS115 | COMEVENTS5 | IDBFunded | 25 | School Engagement activities | 23076.9231 | 1 | 23076.9231 | [17 empty] | 461.5385 | [14 empty] | 461.5385 | [20 empty] | 461.5385 |  |  | 461.5385 |  |  | 461.5385 |  |  | 461.5385 |  |  | 923.0769 |  |  | 3230.7692 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 23076.9231 |  |  | #REF! | 0
NIDS116 | COMEVENTS6 | IDBFunded | 25 | Media Sponsorships/Partnerships | 46153.8462 | 1 | 46153.8462 | [17 empty] | 923.0769 | [14 empty] | 923.0769 | [20 empty] | 923.0769 |  |  | 923.0769 |  |  | 923.0769 |  |  | 923.0769 |  |  | 1846.1538 |  |  | 6461.5385 |  |  | 7569.2308 |  |  | 7569.2308 |  |  | 7569.2308 |  |  | 7569.2308 |  |  | 7569.2308 |  |  | 46153.8462 |  |  | #REF! | 0
NIDS117 | COMEVENTS7 | IDBFunded | 25 | Ambassadors & Celebrity Endorsements/ Activities | 23076.9231 | 1 | 23076.9231 | [17 empty] | 461.5385 | [14 empty] | 461.5385 | [20 empty] | 461.5385 |  |  | 461.5385 |  |  | 461.5385 |  |  | 461.5385 |  |  | 923.0769 |  |  | 3230.7692 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 3784.6154 |  |  | 23076.9231 |  |  | #REF! | 0
|  |  |  | COMPETITIONS | [56 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | #REF! | 0
NIDS119 | COMCOMP1 | IDBFunded | 25 | Local Competitions, Promotions & Prizes | 30769.2308 | 1 | 30769.2308 | [17 empty] | 615.3846 | [14 empty] | 615.3846 | [20 empty] | 615.3846 |  |  | 615.3846 |  |  | 615.3846 |  |  | 615.3846 |  |  | 1230.7692 |  |  | 4307.6923 |  |  | 5046.1538 |  |  | 5046.1538 |  |  | 5046.1538 |  |  | 5046.1538 |  |  | 5046.1538 |  |  | 30769.2308 |  |  | #REF! | 0
|  |  |  | COMMUNICATIONS AND BEHAVIOUR CHANGE |  |  | 2253846.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45076.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45076.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45076.9231 | 0 | 0 | 45076.9231 | 0 | 0 | 45076.9231 | 0 | 0 | 45076.9231 | 0 | 0 | 90153.8462 | 0 | 0 | 315538.4615 | 0 | 0 | 369630.7692 | 0 | 0 | 369630.7692 | 0 | 0 | 369630.7692 | 0 | 0 | 369630.7692 | 0 | 0 | 369630.7692 | 0 | 0 | 2253846.1538 | 0 | 0 | #REF! | 0
TOTAL FOR COMPONENT I | [6 empty] | 14923016.2404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64108.1529 | 0 | 0 | 66323.5376 | 0 | 0 | 120400.4606 | 0 | 0 | 173220.9735 | 0 | 0 | 143796.8709 | 0 | 0 | 143796.8709 | 0 | 0 | 229950.7171 | 0 | 0 | 247373.794 | 0 | 0 | 490339.1786 | 0 | 0 | 170442.2555 | 0 | 0 | 162749.9478 | 0 | 0 | 162749.9478 | 0 | 0 | 269149.9478 | 0 | 0 | 222411.9478 | 0 | 0 | 267488.8709 | 0 | 0 | 267488.8709 | 0 | 0 | 288806.8196 | 0 | 0 | 348206.8196 | 0 | 0 | 1679310.556 | 0 | 0 | 2919548.8867 | 0 | 0 | 3141799.4508 | 0 | 0 | 2046120.9892 | 0 | 0 | 1965120.9892 | 0 | 0 | 1965120.9892 | 0 | 0 | 1205994.3792 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
COMPONENT II | [93 empty] | 0 |  |  | #REF! | 0
|  |  |  | DATA CENTER AND CONNECTIVITY | [89 empty] | 0 |  |  | #REF! | 0
|  |  |  | Hosting for NIDS Racks a eGov Data Center | [89 empty] | 0 |  |  | #REF! | 0
NIDS146 | eGovHOST1 | IDBFunded | 23 | Hosting for NIDS Racks at eGov Data Center | 971.5 | 63 | 61204.5 | [50 empty] | 971.5 |  |  | 971.5 |  |  | 971.5 |  |  | 971.5 |  |  | 971.5 |  |  | 0 |  |  | 7772 |  |  | 11658 |  |  | 11658 |  |  | 11658 |  |  | 11658 |  |  | 6800.5 |  |  | 61204.5 |  |  | #REF! | 0
NIDS147 | eGovHOST2 | IDBFunded | 23 | DR Site Hosting | 1500 | 62 | 93000 | [53 empty] | 1500 |  |  | 1500 |  |  | 1500 |  |  | 1500 |  |  | 0 |  |  | 10500 |  |  | 18000 |  |  | 18000 |  |  | 18000 |  |  | 18000 |  |  | 10500 |  |  | 93000 |  |  | #REF! | 0
NIDS148 | eGovHOST3 | IDBFunded | 23 | Digital Certificate | 745 | 6 | 4470 | [50 empty] | 745 | [14 empty] | 0 |  |  | 745 |  |  | 745 |  |  | 745 |  |  | 745 |  |  | 745 |  |  | 745 |  |  | 4470 |  |  | #REF! | 0
|  |  |  | SECURE CONNECTIVITY TO SITES (DR & ENROLMENT): | [68 empty] | 0 | [20 empty] | 0 |  |  | #REF! | 0
NIDS150 | eGovHOST4 | IDBFunded | 23 | Link to Facilitate Accredited Organizations and Connectivity from Public Networks - 100MB | 1260 | 62 | 78120 | [53 empty] | 1260 |  |  | 1260 |  |  | 1260 |  |  | 1260 |  |  | 0 |  |  | 8820 |  |  | 15120 |  |  | 15120 |  |  | 15120 |  |  | 15120 |  |  | 8820 |  |  | 78120 |  |  | #REF! | 0
NIDS151 | eGovHOST5 | IDBFunded | 23 | 10 mb DIA from Central to Urban Enrolment Sites (18 Parish Capital Sites) | 13440 | 62 | 833280 | [53 empty] | 13440 |  |  | 13440 |  |  | 13440 |  |  | 13440 |  |  | 0 |  |  | 94080 |  |  | 161280 |  |  | 161280 |  |  | 161280 |  |  | 161280 |  |  | 94080 |  |  | 833280 |  |  | #REF! | 0
NIDS152 | eGovHOST6 | IDBFunded | 23 | 10mb DIA from Central to Rural Enrolment Sites (25 Sites Rural Sites) | 24000 | 55 | 1320000 | [65 empty] | 0 |  |  | 0 |  |  | 288000 |  |  | 288000 |  |  | 288000 |  |  | 288000 |  |  | 168000 |  |  | 1320000 |  |  | #REF! | 0
NIDS153 | eGovHOST7 | IDBFunded | 23 | Central to DR Site 50mb link (private) | 1085 | 60 | 65100 | [59 empty] | 1085 |  |  | 1085 |  |  | 0 |  |  | 5425 |  |  | 13020 |  |  | 13020 |  |  | 13020 |  |  | 13020 |  |  | 7595 |  |  | 65100 |  |  | #REF! | 0
NIDS154 | eGovHOST8 | IDBFunded | 32 | Installation one time cost per site (43) | 2000 | 43 | 86000 | [47 empty] | 36000 | [17 empty] | 0 |  |  | 36000 |  |  | 50000 | [14 empty] | 86000 |  |  | #REF! | 0
|  |  |  | Sub Total: Hosting for NIDS Racks a eGov Data Center |  |  | 2541174.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 0 | 0 | 1716.5 | 0 | 0 | 17171.5 | 0 | 0 | 17171.5 | 0 | 0 | 18256.5 | 0 | 0 | 18256.5 | 0 | 0 | 0 | 0 | 0 | 163342 | 0 | 0 | 557823 | 0 | 0 | 507823 | 0 | 0 | 507823 | 0 | 0 | 507823 | 0 | 0 | 296540.5 | 0 | 0 | 2541174.5 | 0 | 0 | #REF! | 0
|  |  |  | SUPPORT SERVICES: | [68 empty] | 0 | [20 empty] | 0 |  |  | #REF! | 0
NIDS157 | eGovSUPPORT1 | IDBFunded | 25 | Customer Service officer | 11538.4615 | 1 | 57692.3077 | [59 empty] | 961.5385 |  |  | 961.5385 |  |  | 0 |  |  | 4807.6923 |  |  | 11538.4615 |  |  | 11538.4615 |  |  | 11538.4615 |  |  | 11538.4615 |  |  | 6730.7692 |  |  | 57692.3077 |  |  | #REF! | 0
NIDS158 | eGovSUPPORT2 | IDBFunded | 25 | System Administrator | 24271 | 1 | 121355 | [59 empty] | 2022.5833 |  |  | 2022.5833 |  |  | 0 |  |  | 10112.9167 |  |  | 24271 |  |  | 24271 |  |  | 24271 |  |  | 24271 |  |  | 14158.0833 |  |  | 121355 |  |  | #REF! | 0
NIDS159 | eGovSUPPORT3 | IDBFunded | 25 | Subsistence (Support Staff) | 1153.8462 | 1 | 5769.2308 | [59 empty] | 96.1538 |  |  | 96.1538 |  |  | 0 |  |  | 480.7692 |  |  | 1153.8462 |  |  | 1153.8462 |  |  | 1153.8462 |  |  | 1153.8462 |  |  | 673.0769 |  |  | 5769.2308 |  |  | #REF! | 0
|  |  |  | TECHNICAL STAFF COSTS: | [68 empty] | 0 | [20 empty] | 0 |  |  | #REF! | 0
NIDS161 | eGovTECHN1 | IDBFunded | 25 | Snr Database Administrator | 54387.2809 | 1 | 290065.4983 | [47 empty] | 4532.2734 |  |  | 4532.2734 |  |  | 4532.2734 |  |  | 4532.2734 |  |  | 4532.2734 |  |  | 4532.2734 |  |  | 0 |  |  | 40790.4607 |  |  | 54387.2809 |  |  | 54387.2809 |  |  | 54387.2809 |  |  | 54387.2809 |  |  | 31725.9139 |  |  | 290065.4983 |  |  | #REF! | 0
NIDS162 | eGovTECHN2 | IDBFunded | 25 | Application Administrator/Manager | 32376.08 | 2 | 345344.8533 | [47 empty] | 5396.0133 |  |  | 5396.0133 |  |  | 5396.0133 |  |  | 5396.0133 |  |  | 5396.0133 |  |  | 5396.0133 |  |  | 0 |  |  | 48564.12 |  |  | 64752.16 |  |  | 64752.16 |  |  | 64752.16 |  |  | 64752.16 |  |  | 37772.0933 |  |  | 345344.8533 |  |  | #REF! | 0
NIDS163 | eGovTECHN3 | IDBFunded |  | Project Manager | 40134.8577 | 1 | 120404.5731 | [14 empty] | 3344.5715 |  |  | 3344.5715 |  |  | 3344.5715 |  |  | 3344.5715 |  |  | 3344.5715 |  |  | 3344.5715 |  |  | 3344.5715 |  |  | 3344.5715 |  |  | 3344.5715 |  |  | 3344.5715 |  |  | 3344.5715 |  |  | 3344.5715 |  |  | 3344.5715 |  |  | 3344.5715 |  |  | 3344.5715 |  |  | 3344.5715 |  |  | 3344.5715 |  |  | 26756.5718 |  |  | 40134.8577 |  |  | 40134.8577 |  |  | 13378.2859 | [11 empty] | 120404.5731 |  |  | #REF! | 0
NIDS164 | eGovTECHN4 | IDBFunded | 25 | Developers | 24271.0982 | 2 | 145626.5889 | [23 empty] | 4045.183 |  |  | 4045.183 |  |  | 4045.183 |  |  | 4045.183 |  |  | 4045.183 |  |  | 4045.183 |  |  | 4045.183 |  |  | 4045.183 |  |  | 4045.183 |  |  | 4045.183 |  |  | 4045.183 |  |  | 4045.183 |  |  | 4045.183 |  |  | 4045.183 |  |  | 20225.9151 |  |  | 48542.1963 |  |  | 48542.1963 |  |  | 28316.2812 | [11 empty] | 145626.5889 |  |  | #REF! | 0
NIDS165 | eGovTECHN5 | IDBFunded | 25 | Subsistence (technical Staff) | 5000 | 1 | 26666.6667 | [47 empty] | 416.6667 |  |  | 416.6667 |  |  | 416.6667 |  |  | 416.6667 |  |  | 416.6667 |  |  | 416.6667 |  |  | 0 |  |  | 3750 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 2916.6667 |  |  | 26666.6667 |  |  | #REF! | 0
NIDS166 | eGovTECHN6 | IDBFunded | 25 | Consultant to Design LANs, Manage Installation of 43 LANs | 76923.0769 | 1 | 76923.0769 | [23 empty] | 15384.6154 | [5 empty] | 15384.6154 | [8 empty] | 15384.6154 | [14 empty] | 30769.2308 | [11 empty] | 30769.2308 |  |  | 46153.8462 | [17 empty] | 76923.0769 |  |  | #REF! | 0
NIDS167 | eGovTECHN7 | IDBFunded | 25 | Consultant to configure Switches, Routers, VLANs , Access Lists etc. | 76923.0769 | 1 | 76923.0769 | [47 empty] | 15384.6154 | [8 empty] | 15384.6154 | [8 empty] | 0 |  |  | 30769.2308 |  |  | 46153.8462 | [14 empty] | 76923.0769 |  |  | #REF! | 0
NIDS168 |  | IDBFunded |  | Sub Total Staff and ISP Links |  |  | 1266770.8726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3344.5715 | 0 | 0 | 3344.5715 | 0 | 0 | 3344.5715 | 0 | 0 | 22774.3699 | 0 | 0 | 7389.7545 | 0 | 0 | 22774.3699 | 0 | 0 | 7389.7545 | 0 | 0 | 7389.7545 | 0 | 0 | 22774.3699 | 0 | 0 | 7389.7545 | 0 | 0 | 7389.7545 | 0 | 0 | 33119.3233 | 0 | 0 | 17734.7079 | 0 | 0 | 48503.9387 | 0 | 0 | 33119.3233 | 0 | 0 | 20814.9836 | 0 | 0 | 20814.9836 | 0 | 0 | 77751.7177 | 0 | 0 | 274106.0898 | 0 | 0 | 295933.6488 | 0 | 0 | 202797.3157 | 0 | 0 | 161102.7486 | 0 | 0 | 161102.7486 | 0 | 0 | 93976.6034 | 0 | 0 | 1266770.8726 | 0 | 0 | #REF! | 0
|  |  |  | MDAs Connectivity and Data Center Infrastructure | [68 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
|  |  |  | MDAs Connectivity : | [68 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS171 | eGovMDA1 | IDBFunded | 32 | Infrastructure | 410000 | 1 | 410000 | [56 empty] | 170000 | [8 empty] | 0 |  |  | 170000 |  |  | 240000 | [14 empty] | 410000 |  |  | #REF! | 0
NIDS172 | eGovMDA2 | IDBFunded | 32 | Equipment | 1900000 | 1 | 1900000 | [23 empty] | 234307.6923 | [23 empty] | 484000 | [17 empty] | 234307.6923 |  |  | 484000 |  |  | 1181692.31 | [14 empty] | 1900000.0023 |  |  | #REF! | -0.0023077
NIDS173 | eGovMDA3 | IDBFunded | 32 | Tools to Support the NIDS | 110000 | 1 | 110000 | [56 empty] | 80000 | [8 empty] | 0 |  |  | 80000 |  |  | 30000 | [14 empty] | 110000 |  |  | #REF! | 0
|  |  |  | Data Center Infrastructure to Support the NIDS: | [68 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS175 | eGovMDA4 | IDBFunded | 32 | Redundant emergency power for NIDS hosting site (Replacement of both generators & ATS) | 600000 | 1 | 600000 |  | Cabinet approval required if done as a single lot | [36 empty] | 120000 |  |  | 240000 |  |  | 180000 |  |  | 60000 | [17 empty] | 0 |  |  | 600000 | [17 empty] | 600000 |  |  | #REF! | 0
NIDS176 | eGovMDA5 | IDBFunded | 32 | Addition of redundant 24KVA feed from substation to support higher uptime objective for NIDS hosting site | 54260 | 1 | 54260 | [32 empty] | 48834 |  |  | 5426 | [29 empty] | 54260 |  |  | 0 | [17 empty] | 54260 |  |  | #REF! | 0
NIDS177 | eGovMDA6 | IDBFunded | 32 | Replacement of redundant UPS system to improve power uptime for NIDS and supporting ICT systems hosted at eGovJa | 117500 | 1 | 117500 | [50 empty] | 23500 |  |  | 82250 |  |  | 11750 | [8 empty] | 0 |  |  | 117500 | [17 empty] | 117500 |  |  | #REF! | 0
NIDS178 | eGovMDA7 | IDBFunded | 32 | In-Suite power distribution & management system to improve redundancy & cooling efficiency at NIDS hosting site | 80000 | 1 | 80000 |  | Implementation of true A & B path UPS power for NIDS hosting site; increased cooling efficiency via removal of excess under floor cable runs | [30 empty] | 72000 |  |  | 8000 | [29 empty] | 80000 |  |  | 0 | [17 empty] | 80000 |  |  | #REF! | 0
NIDS179 | eGovMDA8 | IDBFunded | 32 | Specialized electrical tools for the eGovJa Power Team to support new infrastructure | 9000 | 1 | 9000 |  | Tools are needed to support the new infrastructure & improve responsiveness to faults, capacity management | [12 empty] | 9000 | [50 empty] | 9000 |  |  | 0 | [17 empty] | 9000 |  |  | #REF! | 0
NIDS180 | eGovMDA9 | IDBFunded |  | Populated core services rack to provide onsite redundancy for NIDS and supporting systems | 150000 | 1 | 150000 |  | Required to support shared core services for NIDS and supporting validation web services framework: DNS/DHCP/LDAP/email/ADS | [30 empty] | 150000 | [32 empty] | 150000 |  |  | 0 | [17 empty] | 150000 |  |  | #REF! | 0
NIDS181 | eGovMDA10 | IDBFunded |  | Mid-level SAN to host storage for core services to support onsite redundancy | 75000 | 1 | 75000 |  | Required to support core services | [30 empty] | 75000 | [32 empty] | 75000 |  |  | 0 | [17 empty] | 75000 |  |  | #REF! | 0
NIDS182 | eGovMDA11 | IDBFunded |  | Additional LTO tape drives to facilitate backup regime of the NIDS solution | 14000 | 1 | 14000 |  | 4 LTO-6 drives to expand existing tape libraries in the Enterprise Backup System (EBS) | [15 empty] | 14000 | [47 empty] | 14000 |  |  | 0 | [17 empty] | 14000 |  |  | #REF! | 0
NIDS183 | eGovMDA12 | IDBFunded |  | Replacement of second CRAC unit to support onsite redundancy | 77800 | 1 | 77800 | [50 empty] | 7780 |  |  | 58350 |  |  | 11670 | [8 empty] | 0 |  |  | 77800 | [17 empty] | 77800 |  |  | #REF! | 0
NIDS184 | eGovMDA13 | IDBFunded |  | Consultancy to facilitate the replacement of second CRAC unit to support onsite redundancy | 14200 | 1 | 14200 | [44 empty] | 4260 | [5 empty] | 4260 |  |  | 2840 |  |  | 2840 | [8 empty] | 0 |  |  | 14200 | [17 empty] | 14200 |  |  | #REF! | 0
NIDS185 | eGovMDA14 | IDBFunded |  | LTM Load Balancer Cluster Solution | 328700 | 1 | 328700 | [35 empty] | 26153.8462 | [11 empty] | 103076.9231 | [8 empty] | 103076.9231 | [8 empty] | 26153.8462 |  |  | 206153.8462 |  |  | 96392.31 | [14 empty] | 328700.0023 |  |  | #REF! | -0.0023077
NIDS186 | eGovMDA15 | IDBFunded |  | Global load balancer service from ISP | 30000 | 1 | 180000 | [35 empty] | 90000 | [5 empty] | 30000 | [23 empty] | 90000 |  |  | 30000 |  |  | 60000 | [14 empty] | 180000 |  |  | #REF! | 0
NIDS187 | eGovMDA16 | IDBFunded |  | Network Management Software Solution to support the NIDS | 115000 | 1 | 115000 | [41 empty] | 93846.1538 | [23 empty] | 0 |  |  | 93846.1538 |  |  | 21153.85 | [14 empty] | 115000.0038 |  |  | #REF! | -0.0038462
NIDS188 | eGovMDA17 | IDBFunded |  | Network Equipment to create High Availability Environment for NIDS servers and to connect GoJ MDAs | 239000 | 1 | 239000 | [26 empty] | 23900 | [11 empty] | 86040 | [8 empty] | 107550 |  |  | 21510 | [14 empty] | 23900 |  |  | 215100 | [17 empty] | 239000 |  |  | #REF! | 0
NIDS189 | eGovMDA18 | IDBFunded |  | Replacement of ACs for UPS Room | 22000 | 1 | 22000 | [41 empty] | 19800 |  |  | 2200 | [20 empty] | 0 |  |  | 22000 | [17 empty] | 22000 |  |  | #REF! | 0
NIDS190 | eGovMDA19 | IDBFunded |  | Installation of overhead cable tray for networking and storage | 11000 | 1 | 11000 | [11 empty] | 6923.0769 |  |  | 4076.9231 | [50 empty] | 11000 |  |  | 0 | [17 empty] | 11000 |  |  | #REF! | 0
NIDS191 | eGovMDA20 | IDBFunded |  | 2 new firewall servers for upgrade of cluster capacity (merge w/10 GB transceivers) - Increased interface throughput (10GB interfaces) | 31000 | 1 | 31000 | [20 empty] | 0 | [20 empty] | 31000 | [23 empty] | 0 |  |  | 31000 | [17 empty] | 31000 |  |  | #REF! | 0
NIDS192 | eGovMDA21 | IDBFunded |  | High availability local storage for SIEM (log analysis & incident correlation engine) to facilitate inclusion of NIDS logs | 15000 | 1 | 15000 | [50 empty] | 15000 | [14 empty] | 0 |  |  | 15000 | [17 empty] | 15000 |  |  | #REF! | 0
NIDS193 | eGovMDA22 | IDBFunded |  | Capacity upgrade / replacement of blade infrastructure hosting validation web services and supporting applications: - Replacement of Gen 1 HP Blades with current servers - Replacement of Virtual Connect modules on older blade enclosures - Additional blade enclosures for eGovJa DC - 2 enclosures | 876000 | 1 | 876000 |  | Facilitate the streamlining and adoption of NIDS by existing and upcoming GoJ applications. Cabinet approval required | [36 empty] | 876000 | [26 empty] | 0 |  |  | 876000 | [17 empty] | 876000 |  |  | #REF! | 0
NIDS194 | eGovDRSITE1 | IDBFunded |  | Provision of DR co-location facility | 228000 | 1 | 228000 |  | Colocation of 2 racks @ DR site; preparatory work will begin in advance | [39 empty] | 68400 | [8 empty] | 68400 | [5 empty] | 91200 | [8 empty] | 0 |  |  | 228000 | [17 empty] | 228000 |  |  | #REF! | 0
|  |  |  | CONSULTANCY & TRAINING | [68 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS196 | eGovCONSULT1 | IDBFunded |  | Tier III Gap Analysis & Design | 40000 | 1 | 40000 | [17 empty] | 40000 | [47 empty] | 40000 |  |  | 0 | [17 empty] | 40000 |  |  | #REF! | 0
NIDS197 | eGovCONSULT2 | IDBFunded |  | Data Centre Management training | 20000 | 1 | 20000 |  | To be placed in RFP. Cabinet approval required | [39 empty] | 20000 | [23 empty] | 0 |  |  | 20000 | [17 empty] | 20000 |  |  | #REF! | 0
NIDS198 | eGovCONSULT3 | IDBFunded |  | UPS manufacturer training | 18000 | 1 | 18000 |  | Items in this section are required to prepare the human resources for efficient usage of the systems under management and address any gaps in skill set & knowledge required to support the upgraded NIDS hosting site. | [48 empty] | 18000 | [14 empty] | 0 |  |  | 18000 | [17 empty] | 18000 |  |  | #REF! | 0
NIDS199 | eGovCONSULT4 | IDBFunded |  | Generator maintenance training | 12000 | 1 | 12000 | [53 empty] | 12000 | [11 empty] | 0 |  |  | 12000 | [17 empty] | 12000 |  |  | #REF! | 0
NIDS200 | eGovCONSULT5 | IDBFunded |  | HP One View | 10000 | 1 | 10000 | [32 empty] | 10000 | [32 empty] | 10000 |  |  | 0 | [17 empty] | 10000 |  |  | #REF! | 0
NIDS201 | eGovCONSULT6 | IDBFunded |  | HP Virtual Connect | 10000 | 1 | 10000 | [32 empty] | 10000 | [32 empty] | 10000 |  |  | 0 | [17 empty] | 10000 |  |  | #REF! | 0
NIDS202 | eGovCONSULT7 | IDBFunded |  | Occupational Health & Safety | 9600 | 0 | 0 | [53 empty] | 0 | [11 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS203 | eGovCONSULT8 | IDBFunded |  | Data Power Administration training | 16800 | 1 | 16800 | [38 empty] | 16800 | [26 empty] | 0 |  |  | 16800 | [17 empty] | 16800 |  |  | #REF! | 0
NIDS204 | eGovCONSULT9 | IDBFunded |  | Zimbra email training | 6000 | 1 | 6000 | [32 empty] | 6000 | [32 empty] | 6000 |  |  | 0 | [17 empty] | 6000 |  |  | #REF! | 0
NIDS205 | eGovCONSULT10 | IDBFunded |  | Hyper-V System Centre training | 22400 | 1 | 22400 | [38 empty] | 22400 | [26 empty] | 0 |  |  | 22400 | [17 empty] | 22400 |  |  | #REF! | 0
NIDS206 | eGovCONSULT11 | IDBFunded |  | Windows Server training | 30000 | 1 | 30000 | [32 empty] | 30000 | [32 empty] | 30000 |  |  | 0 | [17 empty] | 30000 |  |  | #REF! | 0
NIDS207 | eGovCONSULT12 | IDBFunded |  | Red Hat Enterprise Linux (RHCE) Training | 22400 | 1 | 22400 | [41 empty] | 22400 | [23 empty] | 0 |  |  | 22400 | [17 empty] | 22400 |  |  | #REF! | 0
NIDS208 | eGovCONSULT13 | IDBFunded |  | Database & Application Server platform training |  |  | 0 | [65 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
|  |  |  | SOFTWARE | [68 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS210 | eGovSOF1 | IDBFunded |  | Expansion / replacement of backup solution to facilitate the inclusion of NIDS in the backup schedule | 55000 | 1 | 55000 |  | Infrastructure to support delivery of Validation Web Services framework to facilitate government to government and business verification services | [33 empty] | 55000 | [29 empty] | 55000 |  |  | 0 | [17 empty] | 55000 |  |  | #REF! | 0
NIDS211 | eGovSOF2 | IDBFunded |  | Expansion of VMware virtualization platform to include provision of cloud services to validation web services and supporting applications | 610000 | 1 | 610000 |  | Infrastructure to support delivery of Validation Web Services framework and application availability. Cabinet approval required | [36 empty] | 610000 | [26 empty] | 0 |  |  | 610000 | [17 empty] | 610000 |  |  | #REF! | 0
NIDS212 | eGovSOF3 | IDBFunded |  | Data Centre monitoring tool - support renewal & expansion | 53000 | 1 | 53000 |  | To ensure monitoring of service availability and measurement of KPIs across NIDS and supporting systems / infrastructure | [45 empty] | 53000 | [17 empty] | 0 |  |  | 53000 | [17 empty] | 53000 |  |  | #REF! | 0
NIDS213 | eGovSOF4 | IDBFunded |  | LDAP replacement (clustered w/migration effort) | 85000 | 1 | 85000 |  | Infrastructure to support delivery of Validation Web Services framework and application integration | [30 empty] | 85000 | [32 empty] | 85000 |  |  | 0 | [17 empty] | 85000 |  |  | #REF! | 0
NIDS214 | eGovSOF5 | IDBFunded |  | Firewall - Additional VPN (user) licenses (unlimited) - merged with CPU cores | 93000 | 1 | 93000 |  | Merged with CPU Cores to be one Lot (Direct Contracting) | [54 empty] | 93000 | [8 empty] | 0 |  |  | 93000 | [17 empty] | 93000 |  |  | #REF! | 0
NIDS215 | eGovSOF6 | IDBFunded |  | Provision of centralized Windows Management platform to streamline integration of supporting applications with NIDS [Windows System Centre (Hyper-V), Windows Server - Data Centre Edition] | 36000 | 1 | 36000 |  | Infrastructure to support delivery of Validation Web Services framework and application availability. | [30 empty] | 36000 | [32 empty] | 36000 |  |  | 0 | [17 empty] | 36000 |  |  | #REF! | 0
NIDS216 | eGovSOF7 | IDBFunded |  | Provision of support for enterprise-class open source email solution to facilitate application email notification management for NIDS and related applications [Zimbra CS Email - Perpetual User License] | 14250 | 1 | 14250 | [32 empty] | 14250 | [32 empty] | 14250 |  |  | 0 | [17 empty] | 14250 |  |  | #REF! | 0
NIDS217 | eGovSOF8 | IDBFunded |  | Web Filtering Security Application ( 2 devices) | 20000 | 1 | 20000 | [23 empty] | 20000 | [41 empty] | 20000 |  |  | 0 | [17 empty] | 20000 |  |  | #REF! | 0
NIDS218 | eGovSOF9 | IDBFunded |  | Vulnerability Management Tool | 20000 | 1 | 20000 | [32 empty] | 20000 | [32 empty] | 20000 |  |  | 0 | [17 empty] | 20000 |  |  | #REF! | 0
NIDS219 | eGovSOF10 | IDBFunded |  | Automated service recovery / availability tool for virtualized environments | 164350 | 1 | 164350 |  | To ensure the ability to failover / recover NIDS and supporting systems across the primary and DR sites | [36 empty] | 164350 | [26 empty] | 0 |  |  | 164350 | [17 empty] | 164350 |  |  | #REF! | 0
NIDS220 |  | IDBFunded |  | Sub-Total MDAs Connectivity and Data Center Infrastructure |  |  | 7015660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6923.0769 | 0 | 0 | 13076.9231 | 0 | 0 | 54000 | 0 | 0 | 0 | 0 | 0 | 254307.6923 | 0 | 0 | 23900 | 0 | 0 | 0 | 0 | 0 | 557084 | 0 | 0 | 184579.8462 | 0 | 0 | 1895590 | 0 | 0 | 525446.1538 | 0 | 0 | 186460 | 0 | 0 | 807626.9231 | 0 | 0 | 158450 | 0 | 0 | 155440 | 0 | 0 | 563536.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1093871.5385 | 0 | 0 | 4292550 | 0 | 0 | 1629238.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7015660.0085 | 0 | 0 | #REF! | -0.0084615
|  |  |  | SUB TOTAL DATA CENTER AND CONNECTIVITY |  |  | 10823605.3726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6923.0769 | 0 | 0 | 16421.4946 | 0 | 0 | 57344.5715 | 0 | 0 | 3344.5715 | 0 | 0 | 277082.0622 | 0 | 0 | 31289.7545 | 0 | 0 | 22774.3699 | 0 | 0 | 564473.7545 | 0 | 0 | 191969.6007 | 0 | 0 | 1918364.3699 | 0 | 0 | 532835.9083 | 0 | 0 | 193849.7545 | 0 | 0 | 876746.2464 | 0 | 0 | 177901.2079 | 0 | 0 | 221115.4387 | 0 | 0 | 613827.7464 | 0 | 0 | 39071.4836 | 0 | 0 | 39071.4836 | 0 | 0 | 1171623.2562 | 0 | 0 | 4729998.0898 | 0 | 0 | 2482995.1188 | 0 | 0 | 710620.3157 | 0 | 0 | 668925.7486 | 0 | 0 | 668925.7486 | 0 | 0 | 390517.1034 | 0 | 0 | 10823605.381 | 0 | 0 | #REF! | -0.0084615
|  |  |  | ESTABLISHMENT OF PRODUCTION SITE | [68 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
|  |  |  | PRODUCTION/CARD PRINTING AND DISTRIBUTION SITE: | [68 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS224 | ENROL-LAN1 | IDBFunded | 25 | LAN Installation | 5000 | 1 | 5000 | [20 empty] | 2500 |  |  | 2500 | [41 empty] | 5000 |  |  | 0 | [17 empty] | 5000 |  |  | #REF! | 0
NIDS225 | ENROL-LAN1 | IDBFunded |  | 1000VA UPS (Workstations) | 300 | 10 | 3000 | [20 empty] | 1500 |  |  | 1500 | [41 empty] | 3000 |  |  | 0 | [17 empty] | 3000 |  |  | #REF! | 0
NIDS226 | ENROL-LAN1 | IDBFunded |  | 24 port POE switch | 2000 | 1 | 2000 | [20 empty] | 1000 |  |  | 1000 | [41 empty] | 2000 |  |  | 0 | [17 empty] | 2000 |  |  | #REF! | 0
|  |  |  | ENROLMENT SITES: | [68 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS228 | ENROL-LAN1 | IDBFunded | 32 | LAN Installation for 18 Parish Capitals Enrollment Sites | 6000 | 18 | 108000 | [20 empty] | 21600 |  |  | 21600 |  |  | 21600 |  |  | 21600 |  |  | 21600 | [32 empty] | 108000 |  |  | 0 | [17 empty] | 108000 |  |  | #REF! | 0
NIDS229 | ENROL-LAN1 | IDBFunded | 32 | LAN Installation for 25 Rural Enrollment Sites | 5000 | 25 | 125000 | [65 empty] | 0 |  |  | 0 |  |  | 125000 | [14 empty] | 125000 |  |  | #REF! | 0
NIDS230 | ENROL-LAN1 | IDBFunded |  | 1000VA UPS(Enrollment Sites Racks) | 300 | 43 | 12900 | [32 empty] | 2580 | [5 empty] | 2580 | [5 empty] | 7740 | [20 empty] | 2580 |  |  | 10320 | [17 empty] | 12900 |  |  | #REF! | 0
NIDS231 | ENROL-LAN1 | IDBFunded | 25 | 24 Port POE switch | 2000 | 43 | 86000 | [32 empty] | 17200 | [5 empty] | 17200 | [5 empty] | 51600 | [20 empty] | 17200 |  |  | 68800 | [17 empty] | 86000 |  |  | #REF! | 0
NIDS232 | WAN-ENROL1 | IDBFunded | 32 | ASA 5555-X Firewall Central(DR, Central and Standby) and Configurations | 30000 | 2 | 60000 | [32 empty] | 12000 | [5 empty] | 12000 | [5 empty] | 36000 | [20 empty] | 12000 |  |  | 48000 | [17 empty] | 60000 |  |  | #REF! | 0
NIDS233 | WAN-ENROL1 | IDBFunded | 32 | ASA 5510 or more advanced Firewall - For Branch Offices or Enrollment Sites and Configurations | 5000 | 43 | 215000 | [32 empty] | 43000 | [5 empty] | 43000 | [5 empty] | 129000 | [20 empty] | 43000 |  |  | 172000 | [17 empty] | 215000 |  |  | #REF! | 0
NIDS234 | ENROL-CONSUL1 | IDBFunded | 32 | Consultant to manage workstations installation at all sites | 250000 | 1 | 250000 | [20 empty] | 5000 | [26 empty] | 10416.6667 |  |  | 10416.6667 |  |  | 10416.6667 |  |  | 10416.6667 |  |  | 10416.6667 |  |  | 10416.6667 |  |  | 5000 |  |  | 62500 |  |  | 91250 |  |  | 91250 | [11 empty] | 250000 |  |  | #REF! | 0
|  |  |  | SUB TOTAL ESTABLISHMENT OF PRODUCTION SITE |  |  | 866900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31600 | 0 | 0 | 26600 | 0 | 0 | 21600 | 0 | 0 | 21600 | 0 | 0 | 96380 | 0 | 0 | 0 | 0 | 0 | 74780 | 0 | 0 | 0 | 0 | 0 | 224340 | 0 | 0 | 10416.6667 | 0 | 0 | 10416.6667 | 0 | 0 | 10416.6667 | 0 | 0 | 10416.6667 | 0 | 0 | 10416.6667 | 0 | 0 | 10416.6667 | 0 | 0 | 197780 | 0 | 0 | 361620 | 0 | 0 | 216250 | 0 | 0 | 91250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 866900 | 0 | 0 | #REF! | 0
|  |  |  | ESTABLISHMENT OF ENROLLMENT SITES | [68 empty] | 0 | [20 empty] | 0 |  |  | #REF! | 0
|  |  |  | ENROLMENT PROJECT STAFF: | [68 empty] | 0 | [20 empty] | 0 |  |  | #REF! | 0
NIDS238 | JAMPOST1 | IDBFunded |  | Jamaica Post Implementation Task Force | 800 | 24 | 19200 |  | Manage and govern the enrolment sites | [18 empty] | 800 |  |  | 800 |  |  | 800 |  |  | 800 |  |  | 800 |  |  | 800 |  |  | 800 |  |  | 800 |  |  | 800 |  |  | 800 |  |  | 800 |  |  | 800 |  |  | 800 |  |  | 800 |  |  | 800 |  |  | 4800 |  |  | 9600 |  |  | 4800 | [14 empty] | 19200 |  |  | #REF! | 0
|  |  |  | Project Coordinator | 30800 | 3 | 92400 |  | Manage track and report on Jamaica Post Targets | [18 empty] | 2566.6667 |  |  | 2566.6667 |  |  | 2566.6667 |  |  | 2566.6667 |  |  | 2566.6667 |  |  | 2566.6667 |  |  | 2566.6667 |  |  | 2566.6667 |  |  | 2566.6667 |  |  | 2566.6667 |  |  | 2566.6667 |  |  | 2566.6667 |  |  | 2566.6667 |  |  | 2566.6667 |  |  | 2566.6667 |  |  | 15400 |  |  | 30800 |  |  | 30800 |  |  | 15400 | [11 empty] | 92400 |  |  | #REF! | 0
|  |  |  | PHASE 1: Public Sector and Focus Group Sites (18): |  |  | 0 | [65 empty] | 0 | [20 empty] | 0 |  |  | #REF! | 0
NIDS240 | JAMPOST1 | IDBFunded |  | Regional Manager | 3230 | 11 | 177650 |  | Supervisor for the regions | [57 empty] | 2960.8333 |  |  | 2960.8333 |  |  | 0 |  |  | 14804.1667 |  |  | 35530 |  |  | 35530 |  |  | 35530 |  |  | 35530 |  |  | 20725.8333 |  |  | 177650 |  |  | #REF! | 0
NIDS241 | JAMPOST1 | IDBFunded |  | Enrollment Supervisor | 2770 | 18 | 249300 |  | Supervisor for the sites | [57 empty] | 4155 |  |  | 4155 |  |  | 0 |  |  | 20775 |  |  | 49860 |  |  | 49860 |  |  | 49860 |  |  | 49860 |  |  | 29085 |  |  | 249300 |  |  | #REF! | 0
NIDS242 | JAMPOST1 | IDBFunded |  | Enrollment Officers | 2400 | 72 | 864000 |  | Enrollment Site Staff | [57 empty] | 14400 |  |  | 14400 |  |  | 0 |  |  | 72000 |  |  | 172800 |  |  | 172800 |  |  | 172800 |  |  | 172800 |  |  | 100800 |  |  | 864000 |  |  | #REF! | 0
|  |  |  | PHASE 2: Students, Parents and Guardians Sites(10 Additional): |  |  |  |  | Enrollment Site Staff | [63 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS244 | JAMPOST1 | IDBFunded |  | Enrollment Supervisor | 2770 | 10 | 120033.3333 |  | Enrollment Site Staff | [63 empty] | 0 |  |  | 0 |  |  | 20775 |  |  | 27700 |  |  | 27700 |  |  | 27700 |  |  | 16158.3333 |  |  | 120033.3333 |  |  | #REF! | 0
NIDS245 | JAMPOST1 | IDBFunded |  | Enrollment Officers | 2400 | 40 | 416000 |  | Enrollment Site Staff | [63 empty] | 0 |  |  | 0 |  |  | 72000 |  |  | 96000 |  |  | 96000 |  |  | 96000 |  |  | 56000 |  |  | 416000 |  |  | #REF! | 0
|  |  |  | PHASE 3: Seniors, College and University Students(10 Additional): | [68 empty] | 0 |  |  | 0 | [17 empty] | 0
NIDS247 | JAMPOST1 | IDBFunded |  | Enrollment Supervisor | 2770 | 10 | 108491.6667 |  | Enrollment Site Staff | [63 empty] | 0 |  |  | 0 |  |  | 9233.3333 |  |  | 27700 |  |  | 27700 |  |  | 27700 |  |  | 16158.3333 |  |  | 108491.6667 |  |  | #REF! | 0
NIDS248 | JAMPOST1 | IDBFunded |  | Enrollment Officers | 2400 | 40 | 376000 |  | Enrollment Site Staff | [63 empty] | 0 |  |  | 0 |  |  | 32000 |  |  | 96000 |  |  | 96000 |  |  | 96000 |  |  | 56000 |  |  | 376000 |  |  | #REF! | 0
|  |  |  | PHASE 4: Private Sector Employees Sites(5 Additional): | [68 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS250 | JAMPOST1 | IDBFunded |  | Enrollment Supervisor | 4000 | 5 | 78333.3333 |  | Enrollment Site Staff | [63 empty] | 0 |  |  | 0 |  |  | 6666.6667 |  |  | 20000 |  |  | 20000 |  |  | 20000 |  |  | 11666.6667 |  |  | 78333.3333 |  |  | #REF! | 0
NIDS251 | JAMPOST1 | IDBFunded |  | Enrollment Officers | 2400 | 20 | 188000 |  | Enrollment Site Staff | [63 empty] | 0 |  |  | 0 |  |  | 16000 |  |  | 48000 |  |  | 48000 |  |  | 48000 |  |  | 28000 |  |  | 188000 |  |  | #REF! | 0
NIDS252 | JAMPOST1 | IDBFunded |  | Taxi and Supper allowances | 800 | 60 | 48000 | [65 empty] | 0 |  |  | 0 |  |  | 9600 |  |  | 9600 |  |  | 9600 |  |  | 9600 |  |  | 9600 |  |  | 48000 |  |  | #REF! | 0
|  |  |  | Enrollment Sites - Modification of Spaces: | [68 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF!
NIDS254 | JAMPOST1 | IDBFunded |  | Production Center Modification of Spaces | 32738.4615 | 1 | 32738.4615 | [20 empty] | 6547.6923 | [5 empty] | 9821.5385 | [8 empty] | 6547.6923 | [5 empty] | 9821.5385 | [23 empty] | 22916.9231 |  |  | 9821.5385 | [17 empty] | 32738.4615 |  |  | #REF! | 0
NIDS255 | JAMPOST1 | IDBFunded |  | Enrollment Sites - Modification of Spaces - Urban | 30182.6923 | 18 | 543288.4615 | [20 empty] | 108657.6923 | [5 empty] | 162986.5385 | [8 empty] | 108657.6923 | [5 empty] | 162986.5385 | [23 empty] | 380301.9231 |  |  | 162986.5385 | [17 empty] | 543288.4615 |  |  | #REF! | 0
NIDS256 | JAMPOST1 | IDBFunded |  | Enrollment Sites - Modification of Spaces - Rural | 26172.1154 | 25 | 654302.8846 | [47 empty] | 130860.5769 | [14 empty] | 196290.8654 |  |  | 0 |  |  | 327151.4423 |  |  | 327151.4423 | [14 empty] | 654302.8846 |  |  | #REF! | 0
|  |  |  | Rent and Utilities | [68 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS258 | JAMPOST1 | IDBFunded |  | Production Site Rent | 45600 | 1 | 228000 | [59 empty] | 3800 |  |  | 3800 |  |  | 0 |  |  | 19000 |  |  | 45600 |  |  | 45600 |  |  | 45600 |  |  | 45600 |  |  | 26600 |  |  | 228000 |  |  | #REF! | 0
NIDS259 | JAMPOST1 | IDBFunded |  | Electricity - Production Site | 9240 | 1 | 46200 | [59 empty] | 770 |  |  | 770 |  |  | 0 |  |  | 3850 |  |  | 9240 |  |  | 9240 |  |  | 9240 |  |  | 9240 |  |  | 5390 |  |  | 46200 |  |  | #REF! | 0
NIDS260 | JAMPOST1 | IDBFunded |  | Electricity -Enrollment Sites | 63000 | 1 | 315000 | [59 empty] | 5250 |  |  | 5250 |  |  | 0 |  |  | 26250 |  |  | 63000 |  |  | 63000 |  |  | 63000 |  |  | 63000 |  |  | 36750 |  |  | 315000 |  |  | #REF! | 0
NIDS261 | JAMPOST1 | IDBFunded |  | Water & Sewage - Production Site | 5538.4615 | 1 | 27692.3077 | [59 empty] | 461.5385 |  |  | 461.5385 |  |  | 0 |  |  | 2307.6923 |  |  | 5538.4615 |  |  | 5538.4615 |  |  | 5538.4615 |  |  | 5538.4615 |  |  | 3230.7692 |  |  | 27692.3077 |  |  | #REF! | 0
|  |  |  | SUB TOTAL ESTABLISHMENT OF ENROLLMENT SITES |  |  | 4584630.4487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118572.0513 | 0 | 0 | 3366.6667 | 0 | 0 | 176174.7436 | 0 | 0 | 3366.6667 | 0 | 0 | 3366.6667 | 0 | 0 | 118572.0513 | 0 | 0 | 3366.6667 | 0 | 0 | 176174.7436 | 0 | 0 | 3366.6667 | 0 | 0 | 134227.2436 | 0 | 0 | 3366.6667 | 0 | 0 | 3366.6667 | 0 | 0 | 3366.6667 | 0 | 0 | 35164.0385 | 0 | 0 | 231454.9038 | 0 | 0 | 423418.8462 | 0 | 0 | 699346.3782 | 0 | 0 | 910594.9038 | 0 | 0 | 721968.4615 | 0 | 0 | 706568.4615 | 0 | 0 | 706568.4615 | 0 | 0 | 416164.9359 | 0 | 0 | 4584630.4487 | 0 | 0 | #REF! | 0
|  |  |  | IMPLEMENTATION OF A NATIONAL IDENTIFICATION MANAGEMENT SYSTEM | [68 empty] | 0 | [20 empty] | 0 |  |  | #REF! | 0
|  |  |  | IDENTIFICATION MANAGEMENT SYSTEM (IDMS): | [68 empty] | 0 | [20 empty] | 0 |  |  | #REF! | 0
NIDS265 | IDMS_SOL1 | IDBFunded |  | All Servers, Racks, PDUs Blade Enclosures, SANs, Load Balancers, Other Appliances, Physical Backup Devices to host the NIDS Solution - Supply and Install | 2500000 | 1 | 2500000 | [35 empty] | 500000 | [20 empty] | 750000 | [8 empty] | 500000 |  |  | 750000 |  |  | 750000 |  |  | 500000 | [11 empty] | 2500000 |  |  | #REF! | 0
NIDS266 | IDMS_SOL1 | IDBFunded |  | Core System Software and modifications (customization of off-the-shelf software; supply and install software) Plus Operation System and Database Software | 1900000 | 1 | 1900000 | [35 empty] | 380000 | [20 empty] | 570000 | [8 empty] | 380000 |  |  | 570000 |  |  | 570000 |  |  | 380000 | [11 empty] | 1900000 |  |  | #REF! | 0
NIDS267 | IDMS_SOL1 | IDBFunded | 32 | Verification System (web portal and API/Web Services) | 1200000 | 1 | 1200000 | [35 empty] | 240000 | [20 empty] | 360000 | [8 empty] | 240000 |  |  | 360000 |  |  | 360000 |  |  | 240000 | [11 empty] | 1200000 |  |  | #REF! | 0
NIDS268 | IDMS_SOL1 | IDBFunded | 32 | ABIS Biometrics System - (fingerprint and facial recognition software) | 8000000 | 1 | 8000000 | [35 empty] | 1600000 | [20 empty] | 2400000 | [8 empty] | 1600000 |  |  | 2400000 |  |  | 2400000 |  |  | 1600000 | [11 empty] | 8000000 |  |  | #REF! | 0
NIDS269 | IDMS_SOL1 | IDBFunded | 32 | Backup / Failover / Disaster Recovery (Supply and install software & hardware for the DR Site) | 2000000 | 1 | 2000000 | [35 empty] | 400000 | [20 empty] | 600000 | [8 empty] | 400000 |  |  | 600000 |  |  | 600000 |  |  | 400000 | [11 empty] | 2000000 |  |  | #REF! | 0
NIDS270 | IDMS_SOL1 | IDBFunded | 32 | Technical and End Users Training / Documentation, Vendor PM Services | 500000 | 1 | 500000 | [35 empty] | 100000 | [20 empty] | 150000 | [8 empty] | 100000 |  |  | 150000 |  |  | 150000 |  |  | 100000 | [11 empty] | 500000 |  |  | #REF! | 0
NIDS271 | IDMS_SOL1 | IDBFunded | 32 | Hardware and Software Maintenance & Warranty | 2200000 | 1 | 2200000 | [35 empty] | 440000 | [20 empty] | 660000 | [8 empty] | 440000 |  |  | 660000 |  |  | 660000 |  |  | 440000 | [11 empty] | 2200000 |  |  | #REF! | 0
NIDS272 | IDMS_SOL1 | IDBFunded | 25 | 3 Racks | 1250 | 3 | 3750 |  | Estimated cost for Data Center preparation at eGov | [33 empty] | 750 | [20 empty] | 1125 | [8 empty] | 750 |  |  | 1125 |  |  | 1125 |  |  | 750 | [11 empty] | 3750 |  |  | #REF! | 0
|  |  |  | PRODUCTION & ENROLMENT SITES EQUIPMENT: | [38 empty] | 0 | [20 empty] | 0 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [11 empty] | 0 |  |  | #REF! | 0
|  |  |  | ENROLMENT WORKSTATIONS: | [38 empty] | 0 | [20 empty] | 0 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [11 empty] | 0 |  |  | #REF! | 0
NIDS275 | IDMS_SOL1 | IDBFunded |  | Enrolment Workstation(Fixed Computer) | 1500 | 172 | 258000 | [35 empty] | 51600 | [20 empty] | 77400 | [8 empty] | 51600 |  |  | 77400 |  |  | 77400 |  |  | 51600 | [11 empty] | 258000 |  |  | #REF! | 0
NIDS276 |  | IDBFunded |  | Cameras | 600 | 129 | 77400 | [35 empty] | 15480 | [20 empty] | 23220 | [8 empty] | 15480 |  |  | 23220 |  |  | 23220 |  |  | 15480 | [11 empty] | 77400 |  |  | #REF! | 0
NIDS277 | IDMS_SOL1 | IDBFunded | 32 | Fingerprint Scanners | 2500 | 129 | 322500 | [35 empty] | 64500 | [20 empty] | 96750 | [8 empty] | 64500 |  |  | 96750 |  |  | 96750 |  |  | 64500 | [11 empty] | 322500 |  |  | #REF! | 0
NIDS278 | IDMS_SOL1 | IDBFunded | 32 | Document Scanners | 150 | 172 | 25800 | [35 empty] | 5160 | [20 empty] | 7740 | [8 empty] | 5160 |  |  | 7740 |  |  | 7740 |  |  | 5160 | [11 empty] | 25800 |  |  | #REF! | 0
NIDS279 | IDMS_SOL1 | IDBFunded | 32 | Signature Capture Devices | 300 | 129 | 38700 | [35 empty] | 7740 | [20 empty] | 11610 | [8 empty] | 7740 |  |  | 11610 |  |  | 11610 |  |  | 7740 | [11 empty] | 38700 |  |  | #REF! | 0
NIDS280 | IDMS_SOL1 | IDBFunded | 32 | Receipt Printers at Enrolment sites | 235 | 129 | 30315 | [35 empty] | 6063 | [20 empty] | 9094.5 | [8 empty] | 6063 |  |  | 9094.5 |  |  | 9094.5 |  |  | 6063 | [11 empty] | 30315 |  |  | #REF! | 0
NIDS281 | IDMS_SOL1 | IDBFunded | 32 | Receipt Printers - Thermal Printing Roll | 2 | 189 | 378 | [35 empty] | 75.6 | [20 empty] | 113.4 | [8 empty] | 75.6 |  |  | 113.4 |  |  | 113.4 |  |  | 75.6 | [11 empty] | 378 |  |  | #REF! | 0
|  |  |  | MOBILE WORKSTATIONS -NIDS Mobile Team: | [38 empty] | 0 | [20 empty] | 0 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [11 empty] | 0 |  |  | #REF! | 0
NIDS283 | IDMS_SOL1 | IDBFunded | 32 | Mobile Enrolment Devices - For General Mobile Enrolment + Bags | 1200 | 30 | 36000 | [35 empty] | 7200 | [20 empty] | 10800 | [8 empty] | 7200 |  |  | 10800 |  |  | 10800 |  |  | 7200 | [11 empty] | 36000 |  |  | #REF! | 0
NIDS284 | IDMS_SOL1 | IDBFunded | 32 | Mobile Fingerprint Scanners | 2500 | 30 | 75000 | [35 empty] | 15000 | [20 empty] | 22500 | [8 empty] | 15000 |  |  | 22500 |  |  | 22500 |  |  | 15000 | [11 empty] | 75000 |  |  | #REF! | 0
NIDS285 | IDMS_SOL1 | IDBFunded | 32 | Mobile Hot Spot - VPN Back to Central Site | 200 | 20 | 4000 | [35 empty] | 800 | [20 empty] | 1200 | [8 empty] | 800 |  |  | 1200 |  |  | 1200 |  |  | 800 | [11 empty] | 4000 |  |  | #REF! | 0
|  |  |  | ISSURANCE WORKSTATIONS: | [38 empty] | 0 | [20 empty] | 0 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [11 empty] | 0 |  |  | #REF! | 0
NIDS287 | IDMS_SOL1 | IDBFunded | 32 | Workstation(Fixed Computer) | 1500 | 43 | 64500 | [35 empty] | 12900 | [20 empty] | 19350 | [8 empty] | 12900 |  |  | 19350 |  |  | 19350 |  |  | 12900 | [11 empty] | 64500 |  |  | #REF! | 0
NIDS288 | IDMS_SOL1 | IDBFunded |  | Fingerprint Scanners(Single Finger) | 400 | 43 | 17200 | [35 empty] | 3440 | [20 empty] | 5160 | [8 empty] | 3440 |  |  | 5160 |  |  | 5160 |  |  | 3440 | [11 empty] | 17200 |  |  | #REF! | 0
NIDS289 | IDMS_SOL1 | IDBFunded | 32 | Contactless Card Readers | 350 | 43 | 15050 | [35 empty] | 3010 | [20 empty] | 4515 | [8 empty] | 3010 |  |  | 4515 |  |  | 4515 |  |  | 3010 | [11 empty] | 15050 |  |  | #REF! | 0
|  |  |  | VETTING WORKSTATIONS - PRODUCTION AT SITE: | [38 empty] | 0 | [20 empty] | 0 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [11 empty] | 0 |  |  | #REF! | 0
NIDS291 | IDMS_SOL1 | IDBFunded | 32 | Production Workstation(Fixed Computer) | 1500 | 8 | 12000 | [35 empty] | 2400 | [20 empty] | 3600 | [8 empty] | 2400 |  |  | 3600 |  |  | 3600 |  |  | 2400 | [11 empty] | 12000 |  |  | #REF! | 0
|  |  |  | QUALITY CONTROL AND MACHINE OPERATORS WORKSTATIONS: | [38 empty] | 0 | [20 empty] | 0 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [11 empty] | 0 |  |  | #REF! | 0
NIDS293 | IDMS_SOL1 | IDBFunded | 32 | Machine Operators - Printers | 1500 | 2 | 3000 | [35 empty] | 600 | [20 empty] | 900 | [8 empty] | 600 |  |  | 900 |  |  | 900 |  |  | 600 | [11 empty] | 3000 |  |  | #REF! | 0
NIDS294 |  | IDBFunded |  | Quality Control Officers - Fixed Workstations | 1500 | 8 | 12000 | [35 empty] | 2400 | [20 empty] | 3600 | [8 empty] | 2400 |  |  | 3600 |  |  | 3600 |  |  | 2400 | [11 empty] | 12000 |  |  | #REF! | 0
NIDS295 | IDMS_SOL1 | IDBFunded | 32 | Contactless Card Readers | 350 | 8 | 2800 | [35 empty] | 560 | [20 empty] | 840 | [8 empty] | 560 |  |  | 840 |  |  | 840 |  |  | 560 | [11 empty] | 2800 |  |  | #REF! | 0
|  |  |  | PRODUCTION PRINTERS AND CARDS: | [38 empty] | 0 | [20 empty] | 0 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [11 empty] | 0 |  |  | #REF! | 0
NIDS297 | IDMS_SOL1 | IDBFunded | 32 | Card Printers | 800000 | 2 | 1600000 | [35 empty] | 320000 | [20 empty] | 480000 | [8 empty] | 320000 |  |  | 480000 |  |  | 480000 |  |  | 320000 | [11 empty] | 1600000 |  |  | #REF! | 0
NIDS298 | IDMS_SOL1 | IDBFunded | 32 | Cards | 2.5 | 3000000 | 7500000 | [35 empty] | 1500000 | [20 empty] | 2250000 | [8 empty] | 1500000 |  |  | 2250000 |  |  | 2250000 |  |  | 1500000 | [11 empty] | 7500000 |  |  | #REF! | 0
NIDS299 | IDMS_SOL1 | IDBFunded | 32 | ID Cards personalization and production software | 500000 | 1 | 500000 | [35 empty] | 100000 | [20 empty] | 150000 | [8 empty] | 100000 |  |  | 150000 |  |  | 150000 |  |  | 100000 | [11 empty] | 500000 |  |  | #REF! | 0
NIDS300 | IDMS_SOL1 | IDBFunded | 25 | Maintenance - Printers and Software | 420000 | 1 | 420000 | [35 empty] | 84000 | [20 empty] | 126000 | [8 empty] | 84000 |  |  | 126000 |  |  | 126000 |  |  | 84000 | [11 empty] | 420000 |  |  | #REF! | 0
NIDS301 | IDMS_SOL1 | IDBFunded | 25 | Consultancy - National Identification Systems | 300000 | 1 | 300000 | [35 empty] | 60000 | [20 empty] | 90000 | [8 empty] | 60000 |  |  | 90000 |  |  | 90000 |  |  | 60000 | [11 empty] | 300000 |  |  | #REF! | 0
|  |  |  | SUB TOTAL IMPLEMENTATION OF A NATIONAL IDENTIFICATION MANAGEMENT SYSTEM |  |  | 29618393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5923678.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8885517.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5923678.6 | 0 | 0 | 8885517.9 | 0 | 0 | 8885517.9 | 0 | 0 | 5923678.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29618393 | 0 | 0 | #REF! | 0
TOTAL FOR COMPONENT II | [6 empty] | 45893528.8213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6923.0769 | 0 | 0 | 16421.4946 | 0 | 0 | 57344.5715 | 0 | 0 | 153516.6228 | 0 | 0 | 307048.7289 | 0 | 0 | 229064.4981 | 0 | 0 | 47741.0366 | 0 | 0 | 664220.4212 | 0 | 0 | 6234220.2519 | 0 | 0 | 1996511.0366 | 0 | 0 | 709010.6519 | 0 | 0 | 421556.4212 | 0 | 0 | 1021390.1566 | 0 | 0 | 191684.5412 | 0 | 0 | 234898.772 | 0 | 0 | 9513128.9797 | 0 | 0 | 84652.1887 | 0 | 0 | 280943.0541 | 0 | 0 | 7716500.7023 | 0 | 0 | 14676482.368 | 0 | 0 | 12495357.9226 | 0 | 0 | 7447517.3772 | 0 | 0 | 1375494.2102 | 0 | 0 | 1375494.2102 | 0 | 0 | 806682.0393 | 0 | 0 | 45893528.8297 | 0 | 0 | #REF!
COMPONENT III | [93 empty] | 0 |  |  | #REF! | 0
|  |  |  | IMPLEMENTATION OF ID VERIFICATION IN MDAS | [89 empty] | 0 |  |  | #REF! | 0
|  |  |  | Regulatory Review and Training: | [89 empty] | 0 |  |  | #REF! | 0
NIDS308 | FINSEC1 | IDBFunded | 25 | Financial Sector Comprehensive Review Consultancy | 300000 | 1 | 300000 | [26 empty] | 30000 | [5 empty] | 60000 | [5 empty] | 60000 |  |  | 60000 | [8 empty] | 90000 | [14 empty] | 90000 |  |  | 210000 | [17 empty] | 300000 |  |  | #REF! | 0
NIDS309 | FINSEC1 | IDBFunded | 25 | Training- Supervisory Agencies (BOJ, FSC, FID) | 35000 | 1 | 35000 | [47 empty] | 7000 |  |  | 7000 |  |  | 7000 |  |  | 7000 |  |  | 7000 | [5 empty] | 0 |  |  | 35000 | [17 empty] | 35000 |  |  | #REF! | 0
NIDS310 | FINSEC1 | IDBFunded | 25 | Training for - Train the Trainer | 60000 | 1 | 60000 | [47 empty] | 12000 |  |  | 12000 |  |  | 12000 |  |  | 12000 |  |  | 12000 | [5 empty] | 0 |  |  | 60000 | [17 empty] | 60000 |  |  | #REF! | 0
NIDS311 | FINSEC1 | IDBFunded | 25 | Consultant-Financial Sector Activities Coordinator | 65000 | 1 | 65000 | [23 empty] | 5416.6667 |  |  | 5416.6667 |  |  | 5416.6667 |  |  | 5416.6667 |  |  | 5416.6667 |  |  | 5416.6667 |  |  | 5416.6667 |  |  | 5416.6667 |  |  | 5416.6667 |  |  | 5416.6667 |  |  | 5416.6667 |  |  | 5416.6667 | [8 empty] | 27083.3333 |  |  | 37916.6667 | [17 empty] | 65000 |  |  | #REF! | 0
|  |  |  | Subtotal: Regulatory Review and Training: |  |  | 460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5416.6667 | 0 | 0 | 35416.6667 | 0 | 0 | 5416.6667 | 0 | 0 | 65416.6667 | 0 | 0 | 5416.6667 | 0 | 0 | 65416.6667 | 0 | 0 | 65416.6667 | 0 | 0 | 5416.6667 | 0 | 0 | 24416.6667 | 0 | 0 | 114416.6667 | 0 | 0 | 24416.6667 | 0 | 0 | 24416.6667 | 0 | 0 | 19000 | 0 | 0 | 0 | 0 | 0 | 117083.3333 | 0 | 0 | 342916.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460000 | 0 | 0 | #REF! | 0
|  |  |  | Education Sector- Identity Verification Services Implementation: | [68 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS314 | EDUSEC1 | IDBFunded | 25 | Comprehensive Review of Existing Identification Services in Primary, Secondary and Tertiary Institutions; Clean Data in Primary and Secondary Institutions Education Management Information Systems | 150000 | 1 | 150000 | [23 empty] | 15000 |  |  | 15000 |  |  | 22500 | [5 empty] | 22500 | [29 empty] | 75000 |  |  | 0 | [5 empty] | 37500 |  |  | 37500 | [8 empty] | 150000 |  |  | #REF! | 0
NIDS315 | EDUSEC1 | IDBFunded | 25 | Modification of Existing Systems to use the NIDs Identification Services and Clean Databases | 250000 | 1 | 250000 | [41 empty] | 25000 | [8 empty] | 50000 | [5 empty] | 50000 | [5 empty] | 50000 |  |  | 0 |  |  | 175000 |  |  | 37500 |  |  | 37500 | [11 empty] | 250000 |  |  | #REF! | 0
NIDS316 | EDUSEC1 | IDBFunded | 25 | Training -for Trainers | 40000 | 1 | 40000 | [65 empty] | 0 |  |  | 0 |  |  | 13333.3333 |  |  | 13333.3333 |  |  | 13333.3333 | [8 empty] | 40000 |  |  | #REF! | 0
NIDS317 | EDUSEC1 | IDBFunded | 25 | Local Project Execution Team - Implement Modified System in Primary and Secondary Schools | 100000 | 1 | 100000 | [65 empty] | 0 |  |  | 25000 |  |  | 25000 |  |  | 25000 |  |  | 25000 | [8 empty] | 100000 |  |  | #REF! | 0
|  |  |  | Subtotal : Education Sector- Identity Verification Services Implementation |  |  | 540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 15000 | 0 | 0 | 22500 | 0 | 0 | 0 | 0 | 0 | 22500 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 75000 | 0 | 0 | 200000 | 0 | 0 | 75833.3333 | 0 | 0 | 113333.3333 | 0 | 0 | 75833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540000 | 0 | 0 | #REF! | 0
|  |  |  | Review of the MLSS Systems -Data Cleaning and Software Upgrade to Verify Beneficiaries and Workers using NIDS | [68 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS320 | SOCSEC1 | IDBFunded | 25 | Comprehensive Review of Existing Information Systems in the MLSS and Data Cleaning | 200000 | 1 | 200000 | [29 empty] | 10000 | [5 empty] | 20000 | [5 empty] | 20000 | [5 empty] | 40000 | [5 empty] | 10000 | [11 empty] | 30000 |  |  | 70000 |  |  | 33333.3333 |  |  | 33333.3333 |  |  | 33333.3333 | [8 empty] | 200000 |  |  | #REF! | 0
NIDS321 | SOCSEC1 | IDBFunded | 25 | Modification of Existing Systems in the MLSS to use the NIDs Identity Verification Services(PATH, NIS etc.) | 200000 | 1 | 200000 | [65 empty] | 0 |  |  | 50000 |  |  | 50000 |  |  | 50000 |  |  | 50000 | [8 empty] | 200000 |  |  | #REF! | 0
NIDS322 | SOCSEC1 | IDBFunded | 25 | Local Project Execution Team - Implement Modified System in the MLSS | 100000 | 1 | 100000 | [29 empty] | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 12500 |  |  | 37500 |  |  | 25000 |  |  | 25000 | [11 empty] | 100000 |  |  | #REF! | 0
NIDS323 | SOCSEC1 | IDBFunded | 25 | Training -for Trainers | 40000 | 1 | 40000 | [65 empty] | 0 |  |  | 0 |  |  | 10000 |  |  | 10000 |  |  | 10000 |  |  | 10000 | [5 empty] | 40000 |  |  | #REF! | 0
NIDS324 |  | IDBFunded |  | Subtotal : Review of the MLSS Systems -Data Cleaning and Software Upgrade to Verify Beneficiaries and Workers using NIDS |  | 1 | 540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14166.6667 | 0 | 0 | 4166.6667 | 0 | 0 | 24166.6667 | 0 | 0 | 4166.6667 | 0 | 0 | 24166.6667 | 0 | 0 | 4166.6667 | 0 | 0 | 44166.6667 | 0 | 0 | 4166.6667 | 0 | 0 | 14166.6667 | 0 | 0 | 4166.6667 | 0 | 0 | 4166.6667 | 0 | 0 | 4166.6667 | 0 | 0 | 42500 | 0 | 0 | 157500 | 0 | 0 | 118333.3333 | 0 | 0 | 118333.3333 | 0 | 0 | 93333.3333 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 540000 | 0 | 0 | #REF! | 0
NIDS325 |  | IDBFunded |  | Review of the Ministry of National Security(MNS) Information Systems-Data Cleaning and Software Upgrade to Verify persons identity using NIDS | [68 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS326 | SECURSEC1 | IDBFunded | 25 | Comprehensive Review of Existing Information Systems in the MNS and Data Cleaning | 200000 | 1 | 200000 | [32 empty] | 11111.1111 |  |  | 11111.1111 |  |  | 11111.1111 |  |  | 11111.1111 |  |  | 11111.1111 |  |  | 11111.1111 |  |  | 11111.1111 |  |  | 11111.1111 |  |  | 11111.1111 | [8 empty] | 22222.2222 |  |  | 77777.7778 |  |  | 25000 |  |  | 25000 |  |  | 25000 |  |  | 25000 | [5 empty] | 200000 |  |  | #REF! | 0
NIDS327 | SECURSEC1 | IDBFunded | 25 | Modification of Existing Systems in the MNS to use the NIDs Identity Verification Services | 200000 | 1 | 200000 | [53 empty] | 40000 | [5 empty] | 40000 | [5 empty] | 0 |  |  | 80000 |  |  | 40000 |  |  | 40000 |  |  | 40000 | [8 empty] | 200000 |  |  | #REF! | 0
NIDS328 | SECURSEC1 | IDBFunded | 25 | Provide Workstations and Fingerprint Scanners for selected Police Stations | 3500 | 210 | 735000 | [65 empty] | 0 |  |  | 0 |  |  | 183750 |  |  | 183750 |  |  | 183750 |  |  | 183750 | [5 empty] | 735000 |  |  | #REF! | 0
NIDS329 | SECURSEC1 | IDBFunded | 25 | Local Project Execution Team - Implement Modified System in the MNS | 100000 | 1 | 100000 | [29 empty] | 2083.3333 |  |  | 2083.3333 |  |  | 2083.3333 |  |  | 2083.3333 |  |  | 2083.3333 |  |  | 2083.3333 |  |  | 2083.3333 |  |  | 2083.3333 |  |  | 2083.3333 |  |  | 2083.3333 |  |  | 2083.3333 |  |  | 2083.3333 |  |  | 6250 |  |  | 18750 |  |  | 18750 |  |  | 18750 |  |  | 18750 |  |  | 18750 | [5 empty] | 100000 |  |  | #REF! | 0
NIDS330 | SECURSEC1 | IDBFunded | 25 | Training -for Trainers | 40000 | 1 | 40000 | [65 empty] | 0 |  |  | 0 |  |  | 10000 |  |  | 10000 |  |  | 10000 |  |  | 10000 | [5 empty] | 40000 |  |  | #REF! | 0
|  |  |  | Subtotal : Review of the Ministry of National Security(MNS) Information Systems-Data Cleaning and Software Upgrade to Verify persons identity using NIDS |  |  | 1275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2083.3333 | 0 | 0 | 13194.4444 | 0 | 0 | 13194.4444 | 0 | 0 | 13194.4444 | 0 | 0 | 13194.4444 | 0 | 0 | 13194.4444 | 0 | 0 | 13194.4444 | 0 | 0 | 13194.4444 | 0 | 0 | 53194.4444 | 0 | 0 | 13194.4444 | 0 | 0 | 42083.3333 | 0 | 0 | 2083.3333 | 0 | 0 | 28472.2222 | 0 | 0 | 176527.7778 | 0 | 0 | 277500 | 0 | 0 | 277500 | 0 | 0 | 277500 | 0 | 0 | 237500 | 0 | 0 | 0 | 0 | 0 | 1275000 | 0 | 0 | #REF! | 0
|  | IDBFunded |  | Review of the National Training Agency and Housing Agency Information Systems-Data Cleaning and Software Upgrade to Verify persons identity using NIDS | [68 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS333 | HOUSINGSEC1 | IDBFunded | 25 | Comprehensive Review of Existing Information Systems in the HEART Trust/NTA and National Housing Trust; Data Cleaning | 200000 | 1 | 200000 | [38 empty] | 11111.1111 |  |  | 11111.1111 |  |  | 11111.1111 |  |  | 11111.1111 |  |  | 11111.1111 |  |  | 11111.1111 |  |  | 11111.1111 |  |  | 11111.1111 |  |  | 11111.1111 |  |  | 0 |  |  | 100000 |  |  | 25000 |  |  | 25000 |  |  | 25000 |  |  | 25000 | [5 empty] | 200000 |  |  | #REF! | 0
NIDS334 | HOUSINGSEC1 | IDBFunded | 25 | Modification of Existing Systems in the HEART Trust/NTA and the National Housing Trust to use the NIDs Identity Verification Services | 280000 | 1 | 280000 | [65 empty] | 0 |  |  | 0 |  |  | 70000 |  |  | 70000 |  |  | 70000 |  |  | 70000 | [5 empty] | 280000 |  |  | #REF! | 0
NIDS335 | HOUSINGSEC1 | IDBFunded | 25 | Provide Fingerprint Scanners for the National Housing Trust and HEART Trust/NTA Regional Offices | 2500 | 30 | 75000 | [65 empty] | 0 |  |  | 0 |  |  | 18750 |  |  | 18750 |  |  | 18750 |  |  | 18750 | [5 empty] | 75000 |  |  | #REF! | 0
NIDS336 | HOUSINGSEC1 | IDBFunded | 25 | Local Project Execution Teams - Implement Modified System in the MLSS | 100000 | 1 | 100000 | [35 empty] | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 37500 |  |  | 14583.3325 |  |  | 14583.3325 |  |  | 14583.3325 |  |  | 14583.3325 | [5 empty] | 99999.9967 |  |  | #REF! | 0.0033333
NIDS337 | HOUSINGSEC1 | IDBFunded | 25 | Training -for Trainers | 30000 | 1 | 30000 | [65 empty] | 0 |  |  | 0 | [5 empty] | 10000 |  |  | 10000 |  |  | 10000 | [5 empty] | 30000 |  |  | #REF! | 0
|  |  |  | Subtotal : Review of the National Training Agency and Housing Agency Information Systems-Data Cleaning and Software Upgrade to Verify persons identity using NIDS |  | 1 | 685000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 0 | 0 | 15277.7778 | 0 | 0 | 15277.7778 | 0 | 0 | 15277.7778 | 0 | 0 | 15277.7778 | 0 | 0 | 15277.7778 | 0 | 0 | 15277.7778 | 0 | 0 | 15277.7778 | 0 | 0 | 15277.7778 | 0 | 0 | 15277.7778 | 0 | 0 | 4166.6667 | 0 | 0 | 137500 | 0 | 0 | 128333.3325 | 0 | 0 | 138333.3325 | 0 | 0 | 138333.3325 | 0 | 0 | 138333.3325 | 0 | 0 | 0 | 0 | 0 | 684999.9967 | 0 | 0 | #REF! | 0.0033333
|  |  |  | Review of the Tax Administration Systems -Data Cleaning and Software Upgrade to Verify Tax Payers (RAiS, Drivers License, TRN) | [68 empty] | 0 | [20 empty] | 0 |  |  | #REF! | 0
NIDS340 | TAXSEC1 | IDBFunded |  | Comprehensive Review of Existing Information Systems in the Tax Services and Data Cleaning | 200000 | 1 | 200000 | [29 empty] | 10000 | [5 empty] | 20000 | [5 empty] | 20000 | [5 empty] | 40000 | [5 empty] | 10000 | [11 empty] | 30000 |  |  | 70000 |  |  | 25000 |  |  | 25000 |  |  | 25000 |  |  | 25000 | [5 empty] | 200000 |  |  | #REF! | 0
NIDS341 | TAXSEC1 | IDBFunded |  | Modification of Existing Systems in the Tax Services to use the NIDs Identity Verification Services | 200000 | 1 | 200000 | [65 empty] | 0 |  |  | 0 |  |  | 50000 |  |  | 50000 |  |  | 50000 |  |  | 50000 | [5 empty] | 200000 |  |  | #REF! | 0
NIDS342 | TAXSEC1 | IDBFunded |  | Local Project Execution Team - Implement Modified System in the Tax Services | 100000 | 1 | 100000 | [29 empty] | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 4166.6667 |  |  | 12500 |  |  | 37500 |  |  | 12500 |  |  | 12500 |  |  | 12500 |  |  | 12500 | [5 empty] | 100000 |  |  | #REF! | 0
NIDS343 | TAXSEC1 | IDBFunded |  | Training -for Trainers | 40000 | 1 | 40000 | [65 empty] | 0 |  |  | 0 | [5 empty] | 10000 |  |  | 10000 |  |  | 10000 |  |  | 10000 |  |  | 40000 |  |  | #REF! | 0
|  |  |  | Subtotal : Review of the Tax Administration Systems -Data Cleaning and Software Upgrade to Verify Tax Payers (RAiS, Drivers License, TRN) |  | 1 | 540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14166.6667 | 0 | 0 | 4166.6667 | 0 | 0 | 24166.6667 | 0 | 0 | 4166.6667 | 0 | 0 | 24166.6667 | 0 | 0 | 4166.6667 | 0 | 0 | 44166.6667 | 0 | 0 | 4166.6667 | 0 | 0 | 14166.6667 | 0 | 0 | 4166.6667 | 0 | 0 | 4166.6667 | 0 | 0 | 4166.6667 | 0 | 0 | 42500 | 0 | 0 | 107500 | 0 | 0 | 87500 | 0 | 0 | 97500 | 0 | 0 | 97500 | 0 | 0 | 97500 | 0 | 0 | 10000 | 0 | 0 | 540000 | 0 | 0 | #REF! | 0
|  |  |  | Data Extraction Training - PIOJ Staff(Training for Trainers) | 20000 | 1 | 20000 | [65 empty] | 0 |  |  | 0 |  |  | 20000 | [14 empty] | 20000 |  |  | #REF! | 0
|  |  |  | SUB TOTAL IMPLEMENTATION OF ID VERIFICATION IN MDAS |  |  | 4060000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20416.6667 | 0 | 0 | 50416.6667 | 0 | 0 | 58333.3333 | 0 | 0 | 86944.4444 | 0 | 0 | 93611.1111 | 0 | 0 | 102222.2222 | 0 | 0 | 167222.2222 | 0 | 0 | 42222.2222 | 0 | 0 | 141222.2222 | 0 | 0 | 201222.2222 | 0 | 0 | 121222.2222 | 0 | 0 | 111222.2222 | 0 | 0 | 84694.4444 | 0 | 0 | 75694.4444 | 0 | 0 | 309722.2222 | 0 | 0 | 1121944.4444 | 0 | 0 | 707499.9992 | 0 | 0 | 744999.9992 | 0 | 0 | 682499.9992 | 0 | 0 | 483333.3325 | 0 | 0 | 10000 | 0 | 0 | 4059999.9967 | 0 | 0 | #REF! | 0.0033333
TOTAL FOR COMPONENT III | [6 empty] | 4060000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20416.6667 | 0 | 0 | 50416.6667 | 0 | 0 | 58333.3333 | 0 | 0 | 86944.4444 | 0 | 0 | 93611.1111 | 0 | 0 | 102222.2222 | 0 | 0 | 167222.2222 | 0 | 0 | 42222.2222 | 0 | 0 | 141222.2222 | 0 | 0 | 201222.2222 | 0 | 0 | 121222.2222 | 0 | 0 | 111222.2222 | 0 | 0 | 84694.4444 | 0 | 0 | 75694.4444 | 0 | 0 | 309722.2222 | 0 | 0 | 1121944.4444 | 0 | 0 | 707499.9992 | 0 | 0 | 744999.9992 | 0 | 0 | 682499.9992 | 0 | 0 | 483333.3325 | 0 | 0 | 10000 | 0 | 0 | 4059999.9967 | 0 | 0 | #REF! | 0.0033333
[73 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
|  |  |  | PROJECT M & E | [68 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
|  |  |  | AUDIT, MONITORING AND EVALUATION: | [68 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
NIDS347 | M&E1 | IDBFunded |  | Financial Audits | 20000 | 6 | 120000 | [44 empty] | 20000 | [20 empty] | 0 |  |  | 20000 |  |  | 20000 |  |  | 20000 |  |  | 20000 |  |  | 20000 |  |  | 20000 |  |  | 120000 |  |  | #REF! | 0
NIDS348 | M&E1 | IDBFunded |  | Technical Evaluation | 17000 | 2 | 34000 | [44 empty] | 17000 | [20 empty] | 0 |  |  | 17000 |  |  | 17000 | [14 empty] | 34000 |  |  | #REF! | 0
NIDS349 | M&E1 | IDBFunded |  | Monitoring and Evaluation | 300000 | 1 | 300000 | [47 empty] | 50000 | [17 empty] | 0 |  |  | 50000 |  |  | 100000 | [11 empty] | 150000 |  |  | 300000 |  |  | #REF! | 0
|  |  |  | PROJECT M & E | 337000 |  | 454000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87000 | 0 | 0 | 137000 | 0 | 0 | 20000 | 0 | 0 | 20000 | 0 | 0 | 20000 | 0 | 0 | 170000 | 0 | 0 | 454000 | 0 | 0 | #REF! | 0
[73 empty] | 0 |  |  | 0 | [17 empty] | 0 |  |  | #REF! | 0
|  |  |  | Total |  |  | 65330545.0617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71031.2299 | 0 | 0 | 82745.0321 | 0 | 0 | 177745.0321 | 0 | 0 | 326737.5962 | 0 | 0 | 471262.2664 | 0 | 0 | 423278.0357 | 0 | 0 | 336025.0869 | 0 | 0 | 998538.6596 | 0 | 0 | 6818170.5416 | 0 | 0 | 2269175.5143 | 0 | 0 | 1038982.822 | 0 | 0 | 663528.5912 | 0 | 0 | 1481762.3267 | 0 | 0 | 615318.7113 | 0 | 0 | 623609.8651 | 0 | 0 | 9891840.0728 | 0 | 0 | 458153.4527 | 0 | 0 | 704844.3181 | 0 | 0 | 9705533.4806 | 0 | 0 | 18804975.6991 | 0 | 0 | 16481657.3726 | 0 | 0 | 10258638.3656 | 0 | 0 | 4043115.1986 | 0 | 0 | 3843948.5319 | 0 | 0 | 2192676.4185 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
[73 empty] | 0 |  |  | 0 | [17 empty] | 0
|  |  |  | CONTINGENCY PROVISIONS: | [68 empty] | 0 |  |  | 0 | [17 empty] | 0
NIDS355 | PROJ-CONTIN1 | IDBFunded | 25 | Provisions for Contingency |  | 1 | 2669454.9383 | [65 empty] | 0 |  |  | 0 | [11 empty] | 1334727.4692 |  |  | 1334727.4692 |  |  | 2669454.9383
|  |  |  | CONTINGENCY PROVISIONS: |  |  | 2669454.9383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1334727.4692 | 0 | 0 | 1334727.4692 | 0 | 0 | 2669454.9383 | 0 | 0 | 0 | 0
|  |  |  | Grand Total |  |  | 68000000 | [65 empty] | 0 |  |  | 0 | [17 empty] | 0
2669454.9383
Note on H20: Warren Vernon: 75 Months for PEU Core Staff - Start in May 2017
Note on H34: Warren Vernon: Deployment Officer will begin working in April 2018, therefore a total of 63 months
Note on H36: Warren Vernon: Production staff will begin working in May 2018, therefore a total of 62 months
Note on G143: Warren Vernon: Hosting for 63 months
Note on G144: Warren Vernon: DR Hosting for 62 months
Note on G145: Warren Vernon: Certificates for 6 years
Note on G147: Warren Vernon: ISP connectivity for 62 months
Note on G149: Warren Vernon: ISP connectivity for 55 months. Sites are turned on in phases
Note on G150: Warren Vernon:62 months hosting for DR sites
Note on G151: Warren Vernon: ISP links Installations for 43 sites
Note on G159: Warren Vernon: Two Application Administrator
Note on G160: Warren Vernon: Project manager will be engaged for 3 years during the solution implementation at eGov.
Note on G161: Warren Vernon: Two Developers will be engaged to assist with the development of Identity Verification Services - Web services
Note on G222: Warren Vernon: 10 UPS for Card and NIN production Staff
Note on G225: Warren Vernon: 18 Phase 1 Sites LANs
Note on G226: Warren Vernon: 25 Phase 2 sites LANs
Note on G227: Warren Vernon: UPS for 43 LANs telecommunication cabinet. 1 UPS per site.
Note on G228: Warren Vernon: One 24 Port Switch per enrollment site - to provide connectivity for enrollment workstations
Note on G229: Warren Vernon: Firewalls for Data Center and DR sites
Note on G230: Warren Vernon: 43 Firewalls - 1 per enrollment site. Required to secure links between enrollment sites and eGov data center
Note on G235: Warren Vernon: 24 Months Task Force to drive the initial setup of all enrollment sites
Note on G236: Warren Vernon: Project Officer - will be tasks with managing all activities relating to project implementation at Jamaica Post for 3 years
Note on G238: Warren Vernon: 11 Regional Managers - Enrollment sites are assigned to regional managers.
Note on BY238: Warren Vernon: Phase 1 Enrollment Officers begin working August 2018
Note on G239: Warren Vernon: 18 Supervisors for Phase 1 enrollment sites. Note 1 Supervisor per site
Note on G240: Warren Vernon: 4 Officers per site - 18 sites x 4 officers = 72
Note on G242: Warren Vernon: 10 Additional sites for Phase 2 - 1 Supervisor per site
Note on G243: Warren Vernon: 40 additional officers for Phase 2
Note on G245: Warren Vernon: 10 additional supervisors for Phase 3
Note on G246: Warren Vernon: 40 additional officers for phase 3
Note on G248: Warren Vernon: Phase 4 - 5 additional supervisors. 20 additional enrollment staff
Note on G250: Warren Vernon: Taxi and Supper for 60 months
Note on H252: Warren Vernon: Modification of spaces for Production site
Note on H253: Warren Vernon: Modification of spaces for 18 Phase 1 sites
Note on H254: Warren Vernon: Modification of spaces for 25 additional enrollment sites (Phases 2-4)
Note on H256: Warren Vernon: Rent and Utilities during the life of project
Note on K353: Warren Vernon: Total Budget in USD
Note on CT357: Warren Vernon: Total Annual Recurrent Cost for NIRA
Note on K358: Warren Vernon: Total Budget in USD

## 18-Month Procurement Plan
Procurement Plan FOR April 2017 TO September 2018
WORKS | [13 empty] | 2017-07-31
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
REGISTRAR GENERAL DEPARTMENT
OPM - RGD | Site Power & Cooling (qty 6) Modification of spaces for the Digitization of records and operation of NIDS (1) Electrical Works (1) Relocation of Generator room (1) |  | International Competitive Bidding | 1 | RGDMODSPC1 | 304276.93 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-08-01 | Request to use NCB with Justification
JAMAICA POST
OPM - JAPOST | Production Center - Modification of Spaces (1) Enrolment Sites - Modification of Spaces - Urban (18) Enrolment Sites - Modification of Spaces - Rural (25) |  | International Competitive Bidding | 1 | JAMPOST2 | 1230329.8 | 100 |  | Component 2 | Ex-Ante | 2017-04-01 | 2017-07-01 | Request to use NCB with Justification
GOODS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
PROJECT COORDINATION
OPM - PEU | Project Staff equipment (1 Laptop, 1 Monitor) |  | Shopping |  | PROJ-CORD1 | 18000 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-07-01
OPM - PEU | Furniture & Supplies (Project Team) |  | Shopping |  | PROJ-CORD2 | 10000 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-07-01
OPM - PEU | Furniture & Supplies (Production & Vetting staff) |  | Shopping |  | PROJ-CORD3 | 13000 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-07-01
OPM - PEU | ACCPAC Software license ACCPAC Software |  | Shopping |  | PROJ-CORD4 & PROJ-CORD5 | 19000 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-07-01
OPM - PEU | Servers to host accounting software |  | Shopping |  | PROJ-CORD6 | 6000 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-07-01
OPM - PEU | SPSS -One license |  | Shopping |  | PROJ-CORD7 | 6000 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-07-01
OPM - PEU | Office productivity software (MS Project) |  | Direct Contracting |  | PROJ-CORD8 | 11000 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-07-01 | Government to Government - Microsoft Enterprise Agreement
OPM - PEU | Printer |  | Shopping |  | PROJ-CORD9 | 4000 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-07-01
EGOV JAMAICA LIMITED
OPM-EGOVJA | Addition of redundant 24KVA feed from substation to support higher uptime objective for NIDS hosting site |  | National Competitive Bidding |  | eGovMDA5 | 54260 | 100 |  | Component 2 | Ex-Ante | 2017-07-01 | 2017-11-01
OPM-EGOVJA | Specialized electrical tools for the eGovJa Power Team to support new infrastructure |  | Shopping |  | eGovMDA8 | 9000 | 100 |  | Component 2 | Ex-Ante | 2017-04-01 | 2017-05-01
OPM-EGOVJA | Installation of overhead cable tray for networking and storage |  | Shopping |  | eGovMDA19 | 11000 | 100 |  | Component 2 | Ex-Ante | 2017-03-01 | 2017-04-01
ENROLMENT AND PRODUCTION INFRASTRUCTURE
OPM-PEU | LAN Installation - Prod/Card Distribution Site - 1 1000VA UPS (Workstations) - 10 24 port POE switch (1) LAN Installation for 18 Parish Capitals Enrolment Sites (18) 1000VA UPS(Enrolment Sites Racks) - 43 24 Port POE switch - 43 |  | International Competitive Bidding |  | ENROL-LAN1 | 216900 | 100 |  | Component 2 | Ex-Ante | 2017-04-01 | 2017-07-01 | Request to use NCB with justification
OPM-EGOVJA | Equipment - MDA Connectivity |  | International Competitive Bidding |  | eGovMDA2 | 1900000 | 100 |  | Component 2 | Ex-Ante | 2017-04-01 | 2017-08-01
OPM-EGOVJA | Additional LTO tape drives to facilitate backup regime of the NIDS solution |  | Shopping |  | eGovMDA11 | 14000 | 100 |  | Component 2 | Ex-Ante |  | 2017-06-01
OPM-EGOVJA | Network Equipment to create High Availability Environment for NIDS servers and to connect GoJ MDAs |  | International Competitive Bidding |  | eGovMDA17 | 239000 | 100 |  | Component 2 | Ex-Ante | 2017-04-01 | 2017-09-01
OPM-EGOVJA | Web Filtering Security Application ( 2 devices) |  | Shopping |  | eGovSOF8 | 20000 | 100 |  | Component 2 | Ex-Ante | 2017-04-01 | 2017-08-01
OPM-PEU | 1. Mobile Enrolment Tablets for RGD New Born (160) 2. Mobile Enrolment Tablets Shoulder Bag for RGD (160) 3. Servers, Racks, PDUs Blade Enclosures, SANs, Load Balancers, Other Appliances, Physical Backup Devices to host the NIDS Solution - Supply and Install (1) 4. Core System Software and modifications (customization of off-the-shelf software; supply and install software) Plus Operation System and Database Software (1) 5. Verification System -Web portal and API/Web Services) (1) 6. ABIS Biometrics System (fingerprint and facial recognition software) (1) 7. ABIS Biometrics System (fingerprint and facial recognition software) (1) 8. Backup / Failover / Disaster Recovery (Supply and install software & hardware for the DR Site) (1) 9. Backup / Failover / Disaster Recovery (Supply and install software & hardware for the DR Site) (1) 10. Technical and End Users Training / Documentation, Vendor PM Services (1) 11. Hardware and Software Maintenance & Warranty (1) 12. 4 Racks (3) 13. Enrolment Workstation(Fixed Computer) (172) 14. Cameras (129) 15. Fingerprint Scanners (129) 16. Document Scanners (172) 17. Signature Capture Devices (129) 18. Receipt Printers at Enrolment sites (129) 19. Receipt Printers - Thermal Printing Roll (189) 20. Mobile Enrolment Devices - For General Mobile Enrolment + Bags (30) 21. Mobile Fingerprint Scanners (30) 22. Workstation(Fixed Computer) (43) 23. Fingerprint Scanners(Single Finger) (43) 24. Contactless Card Readers (43) 25. Production Workstation(Fixed Computer) (8) 26. Machine Operators - Printers (2) 27. Quality Control Officers - Fixed Workstations (8) 28. Contactless Card Readers (8) 29. Card Printers (2) 30. Cards (3000000) 31. ID Cards personalization and production software (1) 32. Maintenance - Printers and Software (1) |  | International Competitive Bidding | 1 | IDMS_SOL1 | 29386393 | 100 |  | Component 1 & 2 | Ex-Ante | 2017-04-01 | 2017-12-01
Network Connectivity
| Mobile Hot Spot - VPN Back to Central Site (20) |  | National System |  | IDMS_SOL2 | 4000 | 100 |  | Component 2 | Ex-Ante | 2017-04-01 | 2017-12-01
Registrar General Department
OPM - RGD | 67 Desks; 67 Chairs |  | National System |  | RGDDSKCHR1 | 19326.93 | 100 |  | Component 1 | Ex-Ante | 2017-08-01 | 2017-12-01 | Limited Tendering
OPM - RGD | 4 MS Office; 1 MS 2016 Data Center Server Edition & 1 MS 2016 CALS License; 1 Paper Scan Version 1.7 50 License; 1 SQL License Server & 1 Anti Virus |  | Direct Contracting |  | RGDSTR1 & RGDSOF1 | 41615.39 | 100 |  | Component 1 | Ex-Ante | 2017-08-01 | 2017-12-01 | Government to Government - Microsoft Enterprise Agreement
OPM - RGD | 68 Computer (Micro Desktop) 2 Laptops |  | National Competitive Bidding | 2 | RGDHRD1 | 60000 | 100 |  | Component 1 | Ex-Ante | 2017-06-01 | 2017-11-01 | Limited Tendering
OPM - RGD | 2 Virtual Host Server 1 Verification Server |  | National System |  | RGDSERV1 | 23076.93 | 100 |  | Component 1 | Ex-Ante | 2017-08-01 | 2017-12-01 | Limited Tendering
OPM - RGD | 2 NAS Drives (72 TB) |  | National System |  | RGDSTOR1 | 18461.5385 | 100 |  | Component 1 | Ex-Ante | 2017-08-01 | 2017-12-01 | Limited Tendering
OPM - RGD | 16 Scanner Flat Bed; 16 Scanners Roller Feed; 64 Rollers for Scanners |  | International Competitive Bidding |  | RGDHRD1 | 180923.08 | 100 |  | Component 1 | Ex-Ante | 2017-07-01 | 2017-12-01
OPM - RGD | 1 Tape Library |  | National System |  | RGDHRD2 | 16000 | 100 |  | Component 1 | Ex-Ante | 2017-08-01 | 2017-12-01 | Limited Tendering
EGOV JAMAICA LIMITED
OPM - EGOVJA | 100 Ports (labour); 1 Rack; 3 Patch Panel (48 Ports); 12 Network Cable CAT6 (box) & 3 Switch (1 GB Layer 2) |  | National System |  | RGDNET1 | 18700 | 100 |  | Component 1 | Ex-Ante | 2017-08-01 | 2017-12-01 | Limited Tendering
OPM - EGOVJA | 18KVA UPS (1) |  | National System |  | RGDHRD1 | 13076.9231 | 100 |  | Component 1 | Ex-Ante | 2017-08-01 | 2017-12-01 | Limited Tendering
OPM - EGOVJA | Redundant emergency power for NIDS hosting site (Replacement of both generators & ATS) |  | International Competitive Bidding |  | eGovMDA4 | 600000 | 100 |  | Component 2 | Ex-Ante | 2017-07-01 | 2018-01-01
OPM - EGOVJA | Replacement of redundant UPS system to improve power uptime for NIDS and supporting ICT systems hosted at eGovJa |  | National Competitive Bidding |  | eGovMDA6 | 117500 | 100 |  | Component 2 | Ex-Ante | 2017-12-01 | 2018-05-01
OPM - EGOVJA | In-Suite power distribution & management system to improve redundancy & cooling efficiency at NIDS hosting site |  | National Competitive Bidding |  | eGovMDA7 | 80000 | 100 |  | Component 2 | Ex-Ante | 2017-06-01 | 2017-11-01
OPM - EGOVJA | Replacement of second CRAC unit to support onsite redundancy |  | National Competitive Bidding |  | eGovMDA12 | 77800 | 100 |  | Component 2 | Ex-Ante | 2017-12-01 | 2018-05-01
OPM - EGOVJA | Replacement of ACs for UPS Room (1) |  | National System |  | eGovMDA18 | 22000 | 100 |  | Component 2 | Ex-Ante | 2017-10-01 | 2018-02-01 | Limited Tendering
ENROLMENT AND PRODUCTION INFRASTRUCTURE
OPM - EGOVJA | Infrastructure - MDA Connectivity |  | Direct Contracting |  | eGovMDA1 | 410000 | 100 |  | Component 2 | Ex-Ante | 2018-01-01 | 2018-07-01 | Justification Required for DC
OPM - EGOVJA | Tools to Support the NIDS |  | National Competitive Bidding |  | eGovMDA3 | 110000 | 100 |  | Component 2 | Ex-Ante | 2018-02-01 | 2018-07-01
OPM - EGOVJA | Digital Certificate (6) |  | Direct Contracting |  | eGovHOST3 | 4470 | 100 |  | Component 2 | Ex-Ante | 2018-02-01 | 2018-05-01 | Justification Required for DC
OPM - EGOVJA | Link to Facilitate Accredited Organizations and Connectivity from Public Networks - 100MB |  | Direct Contracting |  | eGovHOST4 | 75600 | 100 |  | Component 2 | Ex-Ante | 2017-12-01 | 2018-04-01 | Justification Required for DC
OPM - EGOVJA | 10 mb DIA from Central to Urban Enrolment Sites (18 Parish Capital Sites) Installation one time cost per site |  | Direct Contracting |  | eGovHOST5 | 779520 | 100 |  | Component 2 | Ex-Ante | 2018-02-01 | 2018-06-01 | Justification Required for DC
OPM - EGOVJA | Central to DR Site 50mb link (private) Installation one time cost per site |  | Direct Contracting |  | eGovHOST7 | 62930 | 100 |  | Component 2 | Ex-Ante | 2017-12-01 | 2018-04-01 | Justification Required for DC
OPM - EGOVJA | Populated core services rack to provide onsite redundancy for NIDS and supporting systems |  | International Competitive Bidding |  | eGovMDA9 | 150000 | 100 |  | Component 2 | Ex-Ante | 2017-05-01 | 2017-11-01
OPM - EGOVJA | Mid-level SAN to host storage for core services to support onsite redundancy |  | National Competitive Bidding |  | eGovMDA10 | 75000 | 100 |  | Component 2 | Ex-Ante | 2018-07-01 | 2017-11-01 | Limited Tendering
OPM - EGOVJA | LTM Load Balancer Cluster Solution |  | International Competitive Bidding |  | eGovMDA14 | 328700 | 100 |  | Component 2 | Ex-Ante | 2017-06-01 | 2017-12-01
OPM - EGOVJA | Network Management Software Solution to support the NIDS |  | National Competitive Bidding |  | eGovMDA16 | 115000 | 100 |  | Component 2 | Ex-Ante | 2017-09-01 | 2018-02-01
OPM - EGOVJA | 2 - Firewall servers for upgrade of cluster capacity (merge w/10 GB transceivers) - Increased interface throughput (10GB interfaces) |  | National Competitive Bidding |  | eGovMDA20 | 31000 | 100 |  | Component 2 | Ex-Ante | 2017-10-01 | 2018-02-01 | Limited Tendering
OPM - EGOVJA | High availability local storage for SIEM (log analysis & incident correlation engine) to facilitate inclusion of NIDS logs |  | National System |  | eGovMDA21 | 15000 | 100 |  | Component 2 | Ex-Ante | 2018-01-01 | 2018-05-01 | Limited Tendering
OPM - EGOVJA | Capacity upgrade / replacement of blade infrastructure hosting validation web services and supporting applications: - Replacement of Gen 1 HP Blades with current servers - Replacement of Virtual Connect modules on older blade enclosures - Additional blade enclosures for eGovJa DC - 2 enclosures |  | International Competitive Bidding |  | eGovMDA22 | 876000 | 100 |  | Component 2 | Ex-Ante | 2017-07-01 | 2018-01-01
OPM - EGOVJA | Expansion / replacement of backup solution to facilitate the inclusion of NIDS in the backup schedule |  | National Competitive Bidding |  | eGovSOF1 | 55000 | 100 |  | Component 2 | Ex-Ante | 2017-08-01 | 2017-12-01 | Limited Tendering
OPM - EGOVJA | Expansion of VMware virtualization platform to include provision of cloud services to validation web services and supporting applications |  | International Competitive Bidding |  | eGovSOF2 | 610000 | 100 |  | Component 2 | Ex-Ante | 2017-07-01 | 2018-01-01
OPM - EGOVJA | Data Centre monitoring tool - support renewal & expansion |  | Direct Contracting |  | eGovSOF3 | 53000 | 100 |  | Component 2 | Ex-Ante | 2017-11-01 | 2018-04-01 | Existing product in place. Purchasing directly from developer with proprietary rights.
OPM - EGOVJA | LDAP replacement (clustered w/migration effort) |  | National Competitive Bidding |  | eGovSOF4 | 85000 | 100 |  | Component 2 | Ex-Ante | 2017-06-01 | 2017-11-01
OPM - EGOVJA | Firewall - Additional VPN (user) licenses (unlimited) - merged with CPU cores |  | National Competitive Bidding |  | eGovSOF5 | 93000 | 100 |  | Component 2 | Ex-Ante | 2018-02-01 | 2018-07-01
OPM - EGOVJA | Provision of centralized Windows Management platform to streamline integration of supporting applications with NIDS [Windows System Centre (Hyper-V), Windows Server - Data Centre Edition] |  | National Competitive Bidding |  | eGovSOF6 | 36000 | 100 |  | Component 2 | Ex-Ante | 2017-07-01 | 2017-11-01 | Limited Tendering
OPM - EGOVJA | Provision of support for enterprise-class open source email solution to facilitate application email notification management for NIDS and related applications [Zimbra CS Email - Perpetual User License] |  | National System |  | eGovSOF7 | 14250 | 100 |  | Component 2 | Ex-Ante | 2017-07-01 | 2017-11-01 | Limited Tendering
OPM - EGOVJA | Vulnerability Management Tool |  | National System |  | eGovSOF9 | 20000 | 100 |  | Component 2 | Ex-Ante | 2017-07-01 | 2017-11-01 | Limited Tendering
OPM - EGOVJA | Automated service recovery / availability tool for virtualized environments |  | International Competitive Bidding |  | eGovSOF10 | 164350 | 100 |  | Component 2 | Ex-Ante | 2017-07-01 | 2018-01-01
OPM - EGOVJA | Central Firewall (DR, Central and Standby) and Branch Offices Firewall plus configurations for linking enrolment sites with eGov Data Center/NIDS 43 Sites + 1 Cards Production Site |  | International Competitive Bidding |  | WAN-ENROL1 | 275000 | 100 |  | Component 2 | Ex-Ante | 2017-05-01 | 2017-11-01
NON CONSULTING SERVICES
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Bidding Documents | Contract Signature
REGISTRAR GENERAL'S DEPARTMENT
OPM - RGD | Printing |  | Shopping |  | RGDPR1 | 3384.6154 | 100 |  | Component 1 | Ex-Ante | 2017-05-01 | 2017-08-01
COMMUNICATIONS, MARKETING & BEHAVIOUR CHANGE
OPM - PEU | PR Support for NIDS Activities (e.g. Presentations, speeches, press releases,) |  | Shopping |  | COMPR1 | 7384.6154 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | PR Consultant Support - Writers, Execution Agency, Co-coordinator, Facilitator etc. |  | Shopping |  | COMPR1 | 14769.2308 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | External Engagement Island wide - Assocs. Advocate Group, Media etc. |  | Shopping |  | COMPR1 | 6461.5385 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | Employee Engagement/Internal Communications across Agencies |  | Shopping |  | COMPR1 | 2769.2308 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
PRODUCTION COSTS
OPM - PEU | Television |  | Shopping |  | COMADV1 | 23076.9231 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | Radio Ads & Programmes |  | Shopping |  | COMADV1 | 3692.3077 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | Outdoor (billboards, video boards, supermarket screens, bus sheds, bus sides etc. |  | Shopping |  | COMADV1 | 18461.5385 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | Print Ads & Advertorials |  | Shopping |  | COMADV1 | 5538.4615 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | Newsletters, Brochures, Leaflets, Posters, Flyers, Fact Sheets other collateral material |  | Shopping |  | COMADV1 | 3692.3077 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | Promotional Material e.g. t-shirts, cups, pens etc. |  | Shopping |  | COMADV1 | 2769.2308 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | Digital Media (including Google Ads) |  | Shopping |  | COMADV1 | 1846.1538 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
PLACEMENT/ RENTAL/ POSTERING COSTS
OPM - PEU | Television |  | National Competitive Bidding |  | COMPLAC1 | 55384.6154 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01 | Justification needed to use Shopping instead of NCB.
OPM - PEU | Radio |  | Shopping |  | COMPLAC1 | 4615.3846 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | Outdoor Rentals/Postering & Transport (billboards, video boards, supermarket screens, bus sheds, bus sides etc. |  | National Competitive Bidding |  | COMPLAC1 | 25846.1538 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01 | Justification needed to use Shopping instead of NCB.
OPM - PEU | Print |  | National Competitive Bidding |  | COMPLAC1 | 32307.6923 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01 | Justification needed to use Shopping instead of NCB.
OPM - PEU | Digital Media |  | Shopping |  | COMPLAC1 | 3692.3077 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | Outside Broadcasts (Radio & Television) |  | Shopping |  | COMPLAC1 | 5538.4615 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | Promotional Material e.g. t-shirts, cups, pens etc. |  | National Competitive Bidding |  | COMPLAC1 | 27692.3077 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01 | Justification needed to use Shopping instead of NCB.
COMMUNITY
OPM - PEU | Town Hall Meetings |  | Shopping |  | COMEVENTS2 | 4615.3846 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | Focus Groups |  | Shopping |  | COMEVENTS3 | 2769.2308 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | Community Engagement/ Roll Out in New Areas e.g. Town Criers & Promotional Incentive events |  | Shopping |  | COMEVENTS4 | 2769.2308 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | School Engagement activities |  | Shopping |  | COMEVENTS5 | 2769.2308 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | Media Sponsorships/Partnerships |  | Shopping |  | COMEVENTS6 | 5538.4615 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | Ambassadors & Celebrity Endorsements/ Activities |  | Shopping |  | COMEVENTS7 | 2769.2308 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
COMPETITIONS
OPM - PEU | Local Competitions, Promotions & Prizes |  | Shopping |  | COMCOMP1 | 3692.3077 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
JAMAICA POST
OPM - JAPOST | Jamaica Post Implementation Task Force (24 Individuals) |  | Direct Contracting |  | JAMPOST1 | 19200 | 100 |  | Component 2 | Ex-Ante | 2017-04-01 | 2017-07-01
REGISTRAR GENERAL'S DEPARTMENT
OPM - RGD | 6 Classes and 2 Documentation Manual |  | National System |  | RGDTR1 | 5384.61 | 100 |  | Component 1 | Ex-Ante | 2017-10-01 | 2018-01-01 | Collaboration between RGD and HEART
OPM - RGD | Transport of staff for digitization |  | Shopping |  | RGDTRAN1 | 51930 | 100 |  | Component 1 | Ex-Ante | 2017-08-01 | 2018-01-01 | Justification for transportation cost not being NCB
EGOV JAMAICA LIMITED
OPM-EGOVJA | Hosting for NIDS Racks |  | Direct Contracting |  | eGovHOST1 | 56347 | 100 |  | Component 2 | Ex-Ante | 2018-01-01 | 2018-05-01 | Justification Required for DC
OPM-EGOVJA | DR Site Hosting |  | Direct Contracting |  | eGovHOST2 | 87000 | 100 |  | Component 2 | Ex-Ante | 2018-02-01 | 2018-06-01 | Justification Required for DC
OPM-EGOVJA | Provision of DR Co-location facility |  | Direct Contracting |  | eGovDRSITE1 | 228000 | 100 |  | Component 2 | Ex-Ante | 2017-10-01 | 2018-02-01 | Justification Required for DC
OPM-EGOVJA | Global load balancer service from ISP |  | Direct Contracting |  | eGovMDA15 | 180000 | 100 |  | Component 2 | Ex-Ante | 2017-08-01 | 2017-12-01 | Justification Required for DC
CONSULTING FIRMS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
FINANCIAL SECTOR AND GOJ SPECIAL PROJECTS: Regulatory Review and Training
OPM - PEU | Financial Sector Comprehensive Review Consultancy |  | Quality and Cost Based Selection | FINSEC1 | 300000 | 100 |  | Component 3 | Ex-Ante | 2017-04-01 | 2017-09-01
OPM - PEU | Establish a Business Model for the NIRA: Establish Structure for NIRA Governance, Resources and Staff Develop Job Descriptions Design Revenue Model for NIRA Develop Decisions Making Processes Mechanism for Accountability | Consultancy to assist with the establishment of NIRA | Quality and Cost Based Selection | NIRA1 | 405000 | 100 |  | Component 1 | Ex-Ante | 2017-11-01 | 2018-04-01 |  | Local Competitive Bidding
AUDIT, MONITORING & EVALUATION
OPM - PEU | Financial Audits |  | Quality and Cost Based Selection | M&E1 | 120000 | 100 |  | Component 3 | Ex-Ante | 2017-10-01 | 2018-03-01 |  | Local Competitive Bidding
EGOV JAMAICA LIMITED
OPM - EGOVJA | Tier III Gap Analysis & Design |  | Single Source Selection | eGovCONSULT1 | 40000 | 100 |  | Component 2 | Ex-Ante | 2017-04-01 | 2017-06-01 |  | Uptime Institute in Seattle , Washington State to provide training
OPM-EGOVJA | Consultant to configure Switches, Routers, VLANs , Access Lists etc. |  | Quality and Cost Based Selection | eGovTECHN7 | 230769.2308 | 100 |  | Component 2 | Ex-Ante | 2017-12-01 | 2018-04-01
OPM-EGOVJA | Consultancy to facilitate the replacement of second CRAC unit to support onsite redundancy |  | Quality and Cost Based Selection | eGovMDA13 | 14200 | 100 |  | Component 2 | Ex-Ante | 2018-11-01 | 2018-03-01
OPM - EGOVJA | Consultant to Design LANs, Manage Installation of 43 LANS |  | Quality and Cost Based Selection | eGovTECHN6 | 230769.2308 | 100 |  | Component 2 | Ex-Ante | 2017-04-01 | 2017-08-01
INDIVIDUAL CONSULTANTS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Estimated Number of Consultants: | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  |  | No Objection to TOR's | Contract Signature
OPM - PEU | Project Director | 3yr Contract | 3CV | NIDSPEU1 | 317538.45 | 100 |  | 1 | Component 1 | Ex-Ante |  | 2017-04-01
OPM - PEU | Project Coordinator - NIDS CORE TEAM | 3yr Contract | Comparison of Qualifications - National Individual Consultant | NIDSPEU2 | 180000 | 100 |  | 1 | Component 1 | Ex-Ante |  | 2017-04-01
OPM - PEU | Procurement Manager | 3yr Contract | 3CV | NIDSPEU3 | 272769.21 | 100 |  | 1 | Component 1 | Ex-Ante |  | 2017-04-01
OPM - PEU | Financial Manager | 3yr Contract | 3CV | NIDSPEU4 | 180000 | 100 |  | 1 | Component 1 | Ex-Ante |  | 2017-04-01
OPM - PEU | Project Accountant | 3yr Contract | 3CV | NIDSPEU5 | 120000 | 100 |  | 1 | Component 1 | Ex-Ante |  | 2017-04-01
OPM - PEU | Legal Specialist | 3yr Contract | 3CV | NIDSPEU6 | 135000 | 100 |  | 1 | Component 1 | Ex-Ante |  | 2017-04-01
OPM - PEU | Systems Support Manager | 3yr Contract | Comparison of Qualifications - National Individual Consultant | NIDSPEU7 | 180000 | 100 |  | 1 | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
OPM - PEU | ICT Coordinator | 3yr Contract | 3CV | NIDSPEU8 | 138000 | 100 |  | 1 | Component 1 | Ex-Ante |  | 2017-04-01
OPM - PEU | Research & Development Officer | 3yr Contract | 3CV | NIDSPEU9 | 133416 | 100 |  | 1 | Component 1 | Ex-Ante |  | 2017-04-01
OPM - PEU | Business Process and Documentation | 3yr Contract | 3CV | NIDSPEU10 | 133416 | 100 |  | 1 | Component 1 | Ex-Ante |  | 2017-04-01
OPM - PEU | Marketing, PR & Communication | 3yr Contract | Comparison of Qualifications - National Individual Consultant | NIDSPEU11 | 180000 | 100 |  | 1 | Component 1 | Ex-Ante |  | 2017-04-01
OPM - PEU | Procurement Assistant | 3yr Contract | 3CV | NIDSPEU12 | 174000 | 100 |  | 2 | Component 1 | Ex-Ante |  | 2017-04-01
OPM - PEU | Administrative Assistant | 3yr Contract | 3CV | NIDSPEU13 | 84000 | 100 |  | 1 | Component 1 | Ex-Ante |  | 2017-04-01
| Monitoring and Evaluation Officer | 3yr Contract | 3CV | NIDSPEU14 | 180000 | 100 |  | 1 | Component 1 | Ex-Ante |  | 2017-04-01
RGD
| Programmers | 3yr Contract | 3CV | RGDPEU4 | 80000 | 100 |  | 2 | Component 1 | Ex-Ante | 2017-04-01 | 2017-07-01
| Project Coordinator - RGD ACTIVITIES | 3yr Contract | 3CV | NIRA2 | 192000 | 100 |  | 2 | Component 1 | Ex-Ante | 2017-04-01 | 2017-06-01
| Architecture, Engineer and Quantity Surveyor services | 3yr Contract | 3CV | RGDMODSPC1 | 22153.8462 | 100 |  | 1 | Component 1 | Ex-Ante |  | 2017-04-01
OPM - Enrolment | Consultant to manage workstations installation at all sites (Advanced Procurement) |  | Comparison of Qualifications - National Individual Consultant | ENROL-CONSUL1 | 5000 | 100 |  | 1 | Component 2 | Ex-Ante | 2017-04-01 | 2017-07-01
OPM - PEU | Consultant to manage workstations installation at all sites |  | Comparison of Qualifications - National Individual Consultant | ENROL-CONSUL1 | 57500 | 100 |  | 1 | Component 2 | Ex-Ante | 2018-02-01 | 2018-04-01
JAMAICA POST
OPM - JAPOST | Project Coordinator - JAMAICA POST ACTIVITIES |  | Comparison of Qualifications - National Individual Consultant | JAMPOST1 | 92400 | 100 |  | 3 | Component 2 | Ex-Ante | 2017-04-01 | 2017-07-01
OPM-JAPOST | Jamaica Post Service (11 Regional Manager, 18 Enrolment Supervisor, 72 Enrolment Officers) | Phase 1 | Single Source Selection | JAMPOST1 | 1290950 | 100 |  | 101 | Component 2 | Ex-Ante | 2018-04-01 | 2018-08-01
EDUCATION SECTOR: Identity Verification Services Implementation
OPM - JAPOST | Comprehensive Review of Existing Identification Services in Primary, Secondary and Tertiary Institutions; Clean Data in Primary and Secondary Institutions Education Management Information Systems |  | Comparison of Qualifications - National Individual Consultant | EDUSEC1 | 150000 | 100 |  | 1 | Component 3 | Ex-Ante | 2017-04-01 | 2017-08-01
FINANCIAL SECTOR AND GOJ SPECIAL PROJECTS: Regulatory Review and Training
OPM - PEU | Consultant-Financial Sector Activities Coordinator |  | 3CV | FINSEC1 | 65000 | 100 |  | 1 | Component 3 | Ex-Ante | 2017-04-01 | 2017-08-01
OPM - PEU | ICT - Deployment and Support Personnel |  | Comparison of Qualifications - National Individual Consultant | NIDSPEU15 | 396000 | 100 |  | 4 | Component 1 | Ex-Ante | 2017-12-01 | 2018-04-01
OPM - PEU | Senior Manager, Card & NIN Services |  | 3CV | NIDSPEU17 | 180000 | 100 |  | 1 | Component 1 | Ex-Ante | 2018-02-01 | 2018-05-01
OPM - PEU | Production and Distribution Manager |  | 3CV | NIDSPEU18 | 133416 | 100 |  | 1 | Component 1 | Ex-Ante | 2018-02-01 | 2018-05-01
OPM - PEU | Vetting Manager |  | 3CV | NIDSPEU19 | 133416 | 100 |  | 1 | Component 1 | Ex-Ante | 2018-02-01 | 2018-05-01
OPM - PEU | Machine Operators - Printers |  | 3CV | NIDSPEU20 | 132000 | 100 |  | 2 | Component 1 | Ex-Ante | 2018-02-01 | 2018-05-01
OPM - PEU | Vetting Officers - QC Vetting Section |  | Comparison of Qualifications - National Individual Consultant | NIDSPEU21 | 552000 | 100 |  | 8 | Component 1 | Ex-Ante | 2018-01-01 | 2018-05-01
OPM - PEU | Quality Control Officers - Printing Room |  | Comparison of Qualifications - National Individual Consultant | NIDSPEU22 | 552000 | 100 |  | 8 | Component 1 | Ex-Ante | 2018-01-01 | 2018-05-01
OPM - PEU | Store Room and Distribution Officers |  | 3CV | NIDSPEU23 | 69000 | 100 |  | 1 | Component 1 | Ex-Ante | 2017-12-01 | 2018-04-01
OPM - PEU | Consultancy - National Identification Systems |  | Single Source Selection | IDMS_SOL3 | 300000 | 100 |  | 1 | Component 2 | Ex-Ante | 2017-09-01 | 2017-12-01
REGISTRAR GENERAL'S DEPARTMENT
OPM-RGD | Scanning Officers |  | 3CV | RGDPEU1 | 415384.8 | 100 |  | 30 | Component 1 | Ex-Ante | 2017-10-01 | 2018-01-01 | HEART NTA will do training
OPM-RGD | Data Entry Officers |  | 3CV | RGDPEU2 | 1246154.4 | 100 |  | 90 | Component 1 | Ex-Ante | 2017-10-01 | 2018-01-01 | HEART NTA will do training
OPM-RGD | Supervisors |  | 3CV | RGDPEU3 | 92307.7 | 100 |  | 5 | Component 1 | Ex-Ante | 2017-10-01 | 2018-01-01
OPM-RGD | IT Technicians |  | 3CV | RGDPEU5 | 46153.84 | 100 |  | 2 | Component 1 | Ex-Ante | 2017-08-01 | 2017-11-01
OPM-RGD | Trainer |  | 3CV | RGDTR1 | 4615.4 | 100 |  | 2 | Component 1 | Ex-Ante | 2017-09-01 | 2018-01-01
EGOV JAMAICA LIMITED
OPM-EGOVJA | Customer Service officer |  | 3CV | eGovSUPPORT1 | 34615.38 | 100 |  | 1 | Component 2 | Ex-Ante | 2018-05-01 | 2018-08-01
OPM-EGOVJA | System Administrator |  | 3CV | eGovSUPPORT2 | 72813 | 100 |  | 1 | Component 2 | Ex-Ante | 2018-05-01 | 2018-08-01
OPM-EGOVJA | Subsistence (Support Staff) |  | 3CV | eGovSUPPORT3 | 3461.5385 | 100 |  | 1 | Component 2 | Ex-Ante | 2018-01-01 | 2018-04-01
OPM-EGOVJA | Snr Database Administrator |  | 3CV | eGovTECHN1 | 163161.84 | 100 |  | 1 | Component 2 | Ex-Ante | 2018-01-01 | 2018-04-01
OPM-EGOVJA | Application Administrator/Manager |  | 3CV | eGovTECHN2 | 194256.48 | 100 |  | 2 | Component 2 | Ex-Ante | 2018-01-01 | 2018-04-01
OPM -EGOVJA | Developers - EGOV WEB SERVICES |  | 3CV | eGovTECHN4 | 145626.6 | 100 |  | 2 | Component 2 |  | 2017-05-01 | 2017-08-01
OPM - EGOVJA | Project Manager - EGOV ACTIVITTIES |  | 3CV | eGovTECHN3 | 120404.5731 | 100 |  | 1 | Component 2 | Ex-Ante | 2017-04-01 | 2017-05-01
Education Sector: Identity Verification Services Implementation
OPM-PEU | Modification of Existing Systems to use the NIDS Identification Services and Clean Database |  | Comparison of Qualifications - National Individual Consultant | EDUSEC1 | 250000 | 100 |  | 1 | Component 3 | Ex-Ante | 2017-10-01 | 2018-02-01
Review of the MLSS Systems: Data Cleaning and Software Upgrade to Verify Beneficiaries and Workers using NIDS
OPM-PEU | Comprehensive Review of Existing Information Systems in the MLSS and Data Cleaning |  | Comparison of Qualifications - National Individual Consultant | SOCSEC1 | 200000 | 100 |  | 1 | Component 3 | Ex-Ante | 2017-06-01 | 2017-10-01
OPM-PEU | Local Project Execution Team - Implement Modified System in the MLSS |  | Comparison of Qualifications - National Individual Consultant | SOCSEC1 | 100000 | 100 |  | 1 | Component 3 | Ex-Ante | 2017-06-01 | 2017-10-01
Review of the Ministry of National Security(MNS) Information Systems: Data Cleaning and Software Upgrade to Verify persons identity using NIDS
OPM-PEU | Comprehensive Review of Existing Information Systems in the MNS and Data Cleaning |  | Comparison of Qualifications - National Individual Consultant | SECURSEC1 | 200000 | 100 |  | 1 | Component 3 | Ex-Ante | 2017-07-01 | 2017-11-01
OPM-PEU | Modification of Existing Systems in the MNS to use the NIDS Identity Verification Services |  | Comparison of Qualifications - National Individual Consultant | SECURSEC1 | 200000 | 100 |  | 1 | Component 3 | Ex-Ante | 2018-02-01 | 2018-06-01
OPM-PEU | Local Project Execution Team - Implement Modified System in the MNS |  | Comparison of Qualifications - National Individual Consultant | SECURSEC1 | 100000 | 100 |  | 1 | Component 3 | Ex-Ante | 2017-06-01 | 2017-10-01
Review of the National Training Agency and Housing Agency Information Systems: Data Cleaning and Software Upgrade to Verify persons identity using NIDS
OPM-PEU | Comprehensive Review of Existing Information Systems in the HEART Trust/NTA and National Housing Trust; Data Cleaning |  | Comparison of Qualifications - National Individual Consultant | HOUSINGSEC1 | 200000 | 100 |  | 1 | Component 3 | Ex-Ante | 2017-09-01 | 2018-01-01
OPM-PEU | Local Project Execution Teams - Implement Modified System in the MLSS |  | Comparison of Qualifications - National Individual Consultant | HOUSINGSEC1 | 100000 | 100 |  | 1 | Component 3 | Ex-Ante | 2017-08-01 | 2017-12-01
Review of the Tax Administration Systems: Data Cleaning and Software Upgrade to Verify Tax Payers (RAiS, Drivers License, TRN)
OPM-PEU | Comprehensive Review of Existing Information Systems in the Tax Services and Data Cleaning |  | Comparison of Qualifications - National Individual Consultant | TAXSEC1 | 200000 | 100 |  | 1 | Component 3 | Ex-Ante | 2017-06-01 | 2017-10-01
OPM-PEU | Local Project Execution Team - Implement Modified System in the Tax Services |  | Comparison of Qualifications - National Individual Consultant | TAXSEC1 | 100000 | 100 |  | 1 | Component 3 | Ex-Ante | 2017-06-01 | 2017-10-01
AUDIT, MONITORING& EVALUATION
OPM-PEU | Monitoring and Evaluation |  | Comparison of Qualifications - National Individual Consultant | M&E1 | 300000 | 100 |  | 1 | Component 3 | Ex-Ante | 2017-12-01 | 2018-04-01
TRAINING
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Annual Training Plan (ATP) | End of Activity
EGOV JAMAICA LIMITED
OPM-EGOVJA | Data Centre Management training |  | Quality and Cost Based Selection | eGovCONSULT2 | 20000 | 100 |  | Component 2 | Ex-Ante | 2018-02-01 |  |  | Local Trainers to be recruited to facilitate training.
OPM-EGOVJA | UPS manufacturer training |  | Single Source Selection | eGovCONSULT3 | 18000 | 100 |  | Component 2 | Ex-Ante | 2018-05-01 |  |  | Manufacturer/Provider of UPS to facilitate training
OPM-EGOVJA | Generator maintenance training |  | Single Source Selection | eGovCONSULT4 | 12000 | 100 |  | Component 2 | Ex-Ante | 2018-06-01 |  |  | Manufacturer/Provider of Generator to facilitate training
OPM-EGOVJA | HP One View |  | Single Source Selection | eGovCONSULT5 | 10000 | 100 |  | Component 2 | Ex-Ante | 2017-11-01 |  |  | HP Provider or partner to provide training
OPM-EGOVJA | HP Virtual Connect |  | Single Source Selection | eGovCONSULT6 | 10000 | 100 |  | Component 2 | Ex-Ante | 2017-11-01 |  |  | HP Provider or partner to provide training
OPM-EGOVJA | Data Power Administration training |  | Single Source Selection | eGovCONSULT8 | 16800 | 100 |  | Component 2 | Ex-Ante | 2018-01-01 |  |  | IBM Representatives to provide training
OPM-EGOVJA | Zimbra email training |  | Single Source Selection | eGovCONSULT9 | 6000 | 100 |  | Component 2 | Ex-Ante | 2017-11-01 |  |  | Zimbra will provide training. Licenses will be procured from Zimbra.
OPM-EGOVJA | Hyper-V System Centre training |  | Quality and Cost Based Selection | eGovCONSULT10 | 22400 | 100 |  | Component 2 | Ex-Ante | 2018-01-01 |  |  | Local trainers to be recruited to provide training (Microsoft Suite)
OPM-EGOVJA | Windows Server training |  | Quality and Cost Based Selection | eGovCONSULT11 | 30000 | 100 |  | Component 2 | Ex-Ante | 2017-11-01 |  |  | Local trainers to be recruited to conduct training
OPM-EGOVJA | Red Hat Enterprise Linux (RHCE) Training |  | Single Source Selection | eGovCONSULT12 | 22400 | 100 |  | Component 2 | Ex-Ante | 2018-02-01 |  |  | Fujitsu or manufacturer partner in Jamaica to facilitate training.
FINANCIAL SECTOR AND GOJ SPECIAL PROJECTS: Regulatory Review and Training
OPM-PEU | Training - Supervisory Agencies (BOJ, FSC, FID) Training for - Train the Trainer |  | Quality and Cost Based Selection | FINSEC1 | 95000 | 100 |  | Component 3 | Ex-Ante | 2018-04-01 |  |  | To be initiated after Financial Sector Comprehensive Review is completed
TRANSFERS
Executing Agency: | Transfer Purpose: | Additional Information: | Process Number: | Estimated Amount |  |  | Associated Component: | Estimated Number of Transfers: | Dates |  |  |  | Comments - for UCS include selection method
|  |  |  | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Contract Signature | Transfer Date

## ListDefinitions
National System
Ex-Post
Ex-Ante
Cancelled
Contract Concluded
Contract in Execution
Contract Terminated
Null and Void
Ongoing
Planned
Rejection of all Bids
Re-Tendering
International Competitive Bidding
National Competitive Bidding
Shopping
Direct Contracting
National System
Limited Competitive Bidding
Prequalification
Two-envelope International Competitive Bidding
International Competitive Bidding by Lots
Comparison of Qualifications - National Individual Consultant
Comparison of Qualifications - International Individual Consultant
Quality and Cost Based Selection
Quality Based Selection
Selection Based on the Consultants' Qualifications
Single Source Selection
National System
Least Cost Selection
Selection under a Fixed Budget
Comparison of Qualifications - National Individual Consultant
Comparison of Qualifications - International Individual Consultant
Turnkey | Goods
Unit Prices | Goods
Lump-Sum | Goods
Turnkey | Works
Unit Prices | Works
Lump-Sum | Works
Non-Consulting Services
Non-Consulting Services
Lump-Sum | Non-Consulting Services
Lump-Sum | Consulting Firms
Lump-Sum + Reimbursable Expenses | Consulting Firms
Time-Based | Consulting Firms
Individual Consultants
Individual Consultants
Procurement of Textbooks and Reading Materials | Goods
Procurement of Goods | Goods
Procurement of Health Sector Goods | Goods
Price Comparison for Goods | Goods
Technical Specifications | Goods
Procurement of plant Design , Supply and Installation | Goods
Procurement of IT Products and/or Services | Goods
Price Comparison for Works | Works
Procurement for Works | Works
Procurement for Smaller Works | Works
Prequalification for Procurement of Works | Works
Price Comparison | Non-Consulting Services
Terms of Reference | Non-Consulting Services
Procurement of Non-Consulting Services | Non-Consulting Services
Technical Specifications | Non-Consulting Services
Request for Proposals and Terms of Reference | Consulting Firms
Terms of Reference | Consulting Firms
Lump-Sum
Time-Based
Single Source Selection
Comparison of Qualifications - National Individual Consultant
Comparison of Qualifications - International Individual Consultant
3CV