INTER-AMERICAN DEVELOPMENT BANK

Belize

Agricultural Services Program

(BL-L1009)

Environmental and Social Management Report

(ESMR)

September 2009

Project Team: John Horton (INE/RND) and Juan de Dios Mattos (RND/CGU) co-team leaders, Juliana Almeida (INT/INT), Juan Carlos Perez-Segnini (LEG/SGO), Vanessa Lynch (CID/CBL), Lisa Restrepo (INE/RND) and Ernani Pilla (VPS/ESG)

TABEL OF CONTENTS

1. IntroductiON

2. PROJECT DESCRIPTION

3 Environmental and Social Setting

4 instiTutional and Regulatory Context

5 Impacts and RISKs

6 Environmental, Social, Health and Safety Management PLAN

7 INFORMATION DISCLOSURE AND Public CONSULTATION

8 REcommendations

| Abbreviations |  |
| --- | --- |
| ACDI (CIDA) | Canadian International Development Agency |
| BAHA | Belize Agricultural Health Authority |
| BOPA | Belize Organic Producers Association |
| CARDI | Caribbean Agricultural Research and Development Institute |
| BSE | Bovine Spongiform Encephalitis (BSE) |
| CARDI | Caribbean Agricultural Research and Development Institute |
| CITES | Convention on International Trade in Endangered Species of Wild Fauna and Flora |
| CSF | Classic Swine Fever |
| DOE | Department of the Environment |
| ESMR | Environmental and Social Management Report |
| EPA | Environmental Protection Act |
| ESS | Environmental and Social Strategy |
| FAO | Food and Agriculture Organization |
| FMD | Foot and Mouth Disease |
| GDP | Gross Domestic Product |
| GHG | Green House Gases |
| GIS | Geographical Information Systems |
| GMO | Genetically Modified Organisms |
| IDB | Inter-American Development Bank |
| IPPC | International Plant Protection Convention |
| IPM | Integrated Pest Management |
| MAF | Ministry of Agriculture and Fisheries |
| M&E | Monitoring and Evaluation |
| NCCARD | National Coordinating Committee for Agricultural Research & Development |
| NEAC | National Environmental Appraisal Committee |
| OIE | World Organization for Animal Health |
| OIRSA | Organismo Internacional Regional de Sanidad Agropecuaria |
| PIU | Project Implementation Unit |
| PCB | Pesticide Control Board |
| SPS | Sanitary and Phytosanitary Standards |
| TCGA | Toledo Cacao Growers Association |
| TORs | Terms of Reference |
| WHO | World Health Organization |
| WTO | World Trade Organization |

# Introduction

The Ministry of Agriculture and Fisheries (MAF) of Belize has created the Agricultural Services Program to increase the competitiveness and exportation of the sector which should lead to increased rural income and, in turn, to the reduction of rural poverty. The specific objective of the investment program to be financed by the Inter-American Development Bank and MAF is to strengthen the core public agricultural services that provide access to applied production technology corresponding to market opportunities, while reducing the risks derived from threats to plant and animal health and food safety. This in turn will contribute to the broader goal to enhance the competitive productive base upon which Belizeans can increase their income. The Program will be national in scope, expanding the basic public services to support enhanced competitiveness in agricultural production and quality control across a range of rural supply chains with demonstrated market potential. The Program will consist of two components: (i) Applied Production Innovation; and (ii) Plant, Animal and Food Safety Risk Management.

# Project description

## Component I: Agricultural Innovation

In order to exploit the agricultural growth potential, the efficiency of the agricultural sector needs to be enhanced substantially to (continue to) compete in international markets. This component will include (i) institutional strengthening of the agricultural innovation, (ii) Capacity building and capital investments and (iii) a Competitive funding scheme for agricultural innovation projects. focusing on food security ―rice, beans, poultry, pigs…―, commodities of corns for food and feed―, rice, beans, direct export ―papayas, hot peppers, fruit…―, import replacement , among others.

## Component 2: Plant, Animal and Food Safety Risk Management

The purpose of this component is to improve and consolidate the effective operation of the plant health, animal health and food safety systems to protect the domestic production and its consumers from pests and diseases and to ensure that Belize exports meet international standards. Component 2 consist of 5 subcomponents: (i) Plant Health to improve, consolidate and make sustainable the Plant Health System to safeguard the Phytosanitary situation and facilitate the trade in plant and plant products, (ii) Animal Health To improve, consolidate and make sustainable the animal health system with the view to increase the national production, safeguard public health and facilitate the trade in animal and products of animal origin, (iii) Food Safety To improve, consolidate and make sustainable the food Safety System to safeguard the quality of agricultural and fishery products and to diminish the risk of food borne diseases (iv) To improve, consolidate and make sustainable the Quarantine and Inspection Services and (v) Institutional To improve, consolidate and make sustainable the management of the Agricultural Health and Food Safety Services.

# Environmental and Social Setting

The Program overall interventions in Belize are aimed at the broad institutional strengthening of the agricultural innovation system, including capacity building, competitive funding scheme for innovation projects, and plant, animal and food safety risk management. As such, the Program does not generate potential impacts in protected areas, areas with high conservation value, or areas subject to natural disasters.

Similarly, the Program does not negatively affect vulnerable populations, indigenous peoples or ethnic minorities.

# Institutional and regulatory context

The institutional and regulatory framework describes the context of the Environmental and Social Impact Assessment and analysis. The institutions involved in the Program are led by the Ministry of Agriculture and Fisheries (MAF). Institutional responsibilities are as follows:

Ministry of Agriculture and Fisheries of Belize (MAF): responsible for all developments and affairs concerning the agricultural and fisheries sector. It will serve as Program Executor, through the Project Implementation Unit (PIU), which will be responsible for project management and financial control and procurement.

National Coordinating Committee for Agricultural Research and Development (NCCARD): the Executive Secretariat of NCCARD, which will be created to strengthen NCCARD, will function as the Project Implementation Unit (PIU) for the agricultural innovation component of the project (Component 1).

Belize Agricultural Health Authority (BAHA): is the official regulatory body attached to the MAF in order to assure agricultural health and food safety for primary production and processing of foods. Its responsibility is harmonizing the sanitary and food safety norms and regulations following the recommendations of the international bodies of reference. BAHA consists of four Technical Departments: Plant Health, Animal Health, Food Safety and Quarantine.

Department of Environment (DOE): part of the Ministry of Natural Resources and Environment, the DOE is not directly involved in program execution. However, as the national environmental authority responsible for requiring EIAs the DOE should be informed of projects to be developed and asked for required environmental authorisation (Environmental Protection Act-EPA requirements). The National Environmental Appraisal Committee (NEAC) is responsible for the evaluation and approval of Environmental Impact Assessments.

The agricultural sector and the environment can count on an extensive base of regulations, of which only the most important ones are discussed in light of implementation of environmental, social and health & safety requirements for Program activities overall and the subset of projects to be financed under component 1.3.

The Environmental Protection Act (Chapter 328, 2000)

The Act grants the Department of the Environment broad regulatory and enforcement authority for the prevention and control of environmental pollution, conservation and management of natural resources, and environmental impact assessment. The Department of the Environment is responsible for the enforcement of several Regulations made under the Environmental Protection Act. Most pertinent of which are: i) The Environmental Protection (Effluent Limitations) Regulations (S.I. 94 of 1995), intended to control and monitor discharges of effluent into any inland waters or the marine environment of Belize; and ii ) The Pollution Regulations (S.I. 56 of 1996), which are the mechanisms currently in force to monitor and control air, noise, water, and land pollution. MAF/BAHA laboratories are required to comply with the national regulations on effluent limitations and pollution control.

Forest Act (Chapter 213)

The Forest Act ensures that a permanent national forest base is maintained, taking into consideration the need for agricultural development and the protection of the environment.

Law on Biosecurity

A law on Biosecurity is being prepared with support from the Food and Agriculture Orginisation of the UN to regulate the introduction of Genetically Modified Organisms (GMO´s) in Belize.

Organic Agricultural Production Standard

A draft of the “National Organic Agricultural Production Standard” is scheduled for completion by the end of 2009.

International Agreements

In addition, BAHA is required to adhere to the WTO Agreement on the Application of Sanitary and Phytosanitary Measures (SPS-agreement) on the basic rules for food safety and animal and plant health standards; Health standards by the World Organization for Animal Health (OIE), International Plant Protection Convention (IPPC) recommendations to prevent the spread and introduction of pests of plants and plant products, and to promote appropriate measures for their control; and FAO’s Codex Alimentarius.

IDB Safeguard Requirements

- The Environmental and Social Strategy (ESS) for the Program was presented to the IDB Environmental and Social Review in April 2009 (session 2009-15).  The ESS presented the Program as a Category B in accordance with the IDB Environment and Safeguards Compliance Policy.

- In terms of direct and indirect impacts the Program has triggered and is consistent with the OP-703 Pollution Prevention and Abatement (B.11), Hazardous Materials (B.10), Consultation (B.6) and Public Disclosure (OP-102) Policies.

- Because of the mix of Belizean population the Program also triggers OP-765 (Indigenous Peoples).  As such, in establishing agricultural research and development priorities under component 1 the Program has foreseen specific training activities to mobilize the participation of farmer from around the country in agricultural innovation projects (farmer outreach groups), budgeting workshop resources for this purpose.  This includes pro-active efforts to disseminate information and mobilize participation in the poorest areas of the country, notably in Toledo District, where the highest concentrations of indigenous populations live. The Program strives to be a model in this regard doing tracking in the M&E system the participation of historically underprivileged ethnic group members, with data disaggregated by ethnic group

DOE requirements

According to the Belizean Environmental Impact Assessment (EIA) regulations the Program does not require an EIA. For those projects not requiring EIA, the DOE should be properly informed on the program activities and asked for a non-objection letter, as mentioned in regulation 11.

# Impacts and Risks

Main direct environmental impacts of the Program are air pollution (from agricultural machinery acquired) and, more significantly, risks related to improper chemical management and the production and disposal of toxic waste in BAHA laboratories.

Effects of the agricultural innovation projects that will be undertaken should be identified in the period between the proposals submission and final approval. After impact identification, impact management measures (correction, mitigation or compensation) and follow-up programs will have to be included in the project proposals. In order to minimise the impact of these projects and to facilitate the project selection process, selection criteria are listed in chapter 6.1 and Annex I.

- Activities included in the Program have a strategic interest in the agricultural and fishery sectors. More intensive agricultural and fishery practices could be one of the main mid- and long term effects of the program. Potential environmental indirect impacts could be, for instance, an increase in use of pesticides and fertilizers, or undesirable changes in land uses, among others. However, the Program also creates excellent opportunities to mainstream good agricultural practices such as organic farming and IPM. To make use of this opportunity, the Program should reinforce the coordination among its two components and encourage the implementation and extension of good practices, e.g. strengthening IPM and organic farming programs and favouring those projects under component 1 focusing on these issues.

BAHA Laboratories

The rehabilitation or construction works foreseen at BAHA facilities under the Program will not generate any significant negative impacts. Localized, limited negative impacts will be mitigated with readily available measures through effective application of environmental management and risk reduction specifications recommended by EA (environmental analysis as defined in OP-703) for any works. EAs may also be required for a few, particular cases that may arise with innovation projects selected and approved for financing. These specifications will be included in tender documents and contracts for construction.

Regular operations in BAHA’s laboratories have the potential to generate environmental and social impacts.  These risks are mainly linked to the use, storage and disposal of products (chemical, biological):

- Microbiological waste not adequately sterilized before disposal.

- Products discharged directly into the sewer system without adequate pre-treatment.

- Inadequate storage and conservation measures not properly observed. (fire and the emission of toxic gases).

- Health risk for personnel if health and safety standards and measures are not systematically applied. Proper use of personal protection and security is required.

- Accidents and the outbreak of diseases because of possibly contaminated and dangerous waste if it is not managed properly.

BAHA is also concerned about the increased risk of accidents (such as spills) as the laboratory of the Food Health department is currently located within Belize City. Construction of a new Food Health laboratory in Belmopan  is foreseen by BAHA, but it is not expected to be completed during the program life time and therefore is not a part of the loan.  As the new laboratory would be located far away from natural disaster risks and more populated areas, a decrease of risk of accidents and subsequent impacts may be expected.

Other general risks of the project

Indirect negative effects of the Program are related to the risk of increasing the use of pesticides and sanitary treatments as a result of a growth of the agricultural activity:

  - Affecting/reducing soil and water quality due to contamination

  - Affecting/reducing food quality/properties, if not applied properly, because of raised levels of medicines (antibiotics) and toxic substances in animal (increasing medical treatment of cattle and toxic substances in their food) and plant (increasing the use of pesticides) products.

Apart from the direct and indirect environmental and social impacts specifically related to both components, the broader effect of the Program on the agricultural sector may suffer from general risks. The Program intends to increase the sectors competitiveness and to expand its export markets, which may imply greater intensification and specialisation, which may provoke environmentally negative consequences. Conversely, the program will support diversification of the currently limited agricultural offer.

Main and more common risks of agriculture intensification and expansion are: (i) Risk of reduction of soil and water quality due to contamination by pesticides and fertilizers, (ii) Risk of food properties affection (safety risk) because of raised levels of toxic substances originating from the improper use of pesticides and fertilizers, in animal (increasing medical treatment of cattle and toxic substances in their food) and plant (increasing the use of pesticides) products, (iii) Risk of land use changes, including deforestation and/or degradation of natural habitats and/or socially sensitive areas, (iv) Risk of air quality reduction (air pollution, dust generation and GHG emissions) due to the increased use of machinery for agricultural practices (v) Risk of affecting animal welfare

Specialisation of the sector also may have effects on the environment: (i) Decreased resistance against diseases and pests due to losses in genetic resources and variability, (ii) Crop/livestock substitution, (iii) Loss of landscape diversity (crop type distribution and total linear landscape features)

Diversification: Agriculture growth and access to new export markets may imply new opportunities for crops that may be new to Belize or produced so far only in relatively small quantities. The installation of new crops has the risk of bringing along new pests and diseases which could: (i) Negatively affect human and ecosystem’s health and (ii) Contaminate soil, water and food quality because of the increased use of pesticides needed to combat these new diseases.

# Environmental, Social, Health and Safety Management

An ESMP was prepared as part of the operation that includes project activities, generic information on potential impacts, mitigation measures and institutional responsibilities for implementation for the mitigation measures, monitoring arrangements, cost elements (budget) and an institutional and capacity building program as applicable to each project component. The ESMP also contains reference to IDB’s Exclusion List that details the products, substances or activities that are not eligible for financing. In addition, companies involved with the products, substances, or activities listed below are not eligible for trade financing

The ESMP framework will be integrated into the Operations Manual. Close coordination between components 1 and 2 will contribute to reducing the environmental risks of the program, particularly those of agricultural intensification.

Management of environmental, social, health and safety include the following for each component:

## Component I

Innovation research projects to be financed must comply with environmental national regulations, international agreements signed by Belize as well as with IDB’s environmental safeguards policy. In order to ensure compliance, a suggested list of criteria to be used for the selection process is included in Annex I: Project Selection Criteria . Special attention will be paid to the eligibility of the projects for their relevance in terms of environmental and social issues. Dissemination of project results and replication of expected benefits will also be a meaningful objective for all financed projects.

Additional selection criteria that foster links between the two program components of the program will also be considered, such as:

- Improving agricultural training and awareness on environmental issues;

- Improving agricultural practices, including Integrated Pest Management (IPM);

- Quantifiable reductions in GHG emissions, including use of bioenergy;

- Promotion of organic farming, integrated farming and other bets management practices;

- Reduction of the use of inputs like pesticides and fertilizers and promote its integrated management (IPM);

- Reducing and/or improving the management of the environmental problems of specialization (e.g. promotes the use of endogenous genetic resources);

- Introduction of rationale land use (for instance, GIS could be applied in order to monitor the impact on forests when expanding agricultural areas);

- Involvement of cooperatives, agriculture groups (thus ensuring greater acceptance and dissemination of results at the farm level);

- Taking into consideration special needs of vulnerable social groups and, in particular, for the indigenous people.

In relation with machinery-related air pollution and GHG emission all acquired machinery will be new and will be properly maintained and specifications on GHG emissions will be considered as a selection criteria.

## Component II

### Laboratory usage

Good management is the key in handling the risks related to increased laboratory activities. By applying the existing/proper guidelines and measures for usage, disposal and storage of laboratory products, many risks and impacts can be avoided or reduced. Apart from the already existing standards, the following mitigation measures will be adopted to improve labs operation:

- Health & Safety of laboratory personnel: adopting an appropriate management plan for chemicals and for bio-security for workers to increase the security of laboratory personnel.

- Waste disposal (solid, effluents and emissions): a plan for surveillance, treatment and disposal of wastes generated by chemicals used in analysis would reduce environmental and bio-security risks.

- Storage of chemicals: to avoid or minimise risks during storage, special measures have to be taken, particularly for the selection of the storage area (it must be situated far from areas with high risk of fire or densely populated; rooms should be kept at appropriate temperatures and present air should be frequently replaced)

- External audit on labs facilities and operation: An external audit will be carried out to verify and assess current labs facilities and operations. Audit conclusions will be used as an input for the above mentioned mitigation measures and for new facilities design.

## M&E system

Suggestions are made for Components 1 and 2 to facilitate the M&E system in collecting and tracking key environmental and social impact information in order to provide effective supervision and evaluation at the program level.

The Environmental officer of the PIU will prepare quarterly reports for the Bank on the status of compliance with the benchmarks of the ESMP laid out above.

Mid term and final evaluations will be performed by independent consultants who will verify the accomplishments of the Program and performance in undertaking the various aspects of the Environmental and Social Management Plan.

Component 1

Main environmental and social aspects of Component 1 are related to the projects that will be accomplished within the competitive financing scheme of component 1. The monitoring process will be based on two levels, using monitoring indicators for: i) the selection criteria of the projects, ii) the projects themselves. Environmental and social monitoring of the other activities of component 1 will suffice by verifying that the acquired machinery is new (in general, modern machinery is less contaminating).

. Monitory will be mostly the responsibility of the PIU’s environmental officer. For projects financed under Competitive Funding Scheme monitoring will also be performed by the projects’ selection committee and NCCARD.

Component 2

Specific monitoring arrangements of the environmental and social impacts of the program’s Component 2 are included in the ESMP. Monitoring will be mostly the responsibility of the PIU’s environmental officer. Monitoring will also be performed by the NCCARD for some activities.

# Information disclosure and public consultation

An environmental analysis has been conducted for this project by an external consultant. His report formed the basis for this ESMR, and it will be made available at the executing agency’s (MAF) website shortly as per directives of the OP-703 (B.6) Policy.  Also, MAF will conduct formal consultations as part of the elaboration of the detailed ESMP framework, and of the selection and evaluation criteria to be developed prior to the call for proposals under the financial fund scheme of component II.

This ESMR will be made available to the public prior to Board Approval, as per OP-102 Policy.

# Recommendations

Loan Agreement

8.2              IDB will require as part of the Loan Agreement that the Government shall, during the life of the Loan Agreement, comply with each of the following:

a.         All applicable environmental, health and safety and labor Belizean regulatory requirements associated with any environmental, health and safety related permits, authorizations or licenses that apply to the project.

b.       Applicable IDBs environmental and social policy and requirements including the Environmental and Safeguards Compliance Policy (OP-703: Hazardous Materials B.10, Consultation B.6, and Pollution Prevention and Abatement B.11), the Disclosure of Information (OP-102) and Indigenous Peoples (OP-765) policies.

c.         As part of the Bank’s supervision activities, IDB will monitor the environmental, social, health and safety aspects. The Bank may request an environmental, social and health and safety audit or evaluation.

Operational Manual

8.3              IDB will require that following items will be included in the Operation Manual, which will be approved by the Bank prior to the first disbursement:

a.      Reference to the ESMP and the application of the ESMP.

d.      TORs for activities which will be developed during project implementation will include a section on the preparation of EAs or other environmental and social procedures as required (for instance, for component II).

e.       The Operational Manual will include a list with activities (or selection criteria for projects) for which the preparation of an EA or any other environmental and social tool is needed

h.       As part of the routine project reporting, MAF will include a section on environmental and social issues to report on the progress of the implementation of the ESMP, work programs, problems encountered, etc. An outline for such a report will be included in the OM.

i.         The current ESMP includes a generic Monitoring and Evaluation program. MAF will refine the ESMP to include a more detailed description of monitoring and evaluation arrangements. Key indicators will be included in the overall project monitoring and evaluation framework. The ESMP will also include the outcome of the consultation process (e.g. a summary of comments received).

j.        At all stages of the program, the executing agency, and other public institutions involved as well as building contractors must incorporate gender criteria that promote the equitable participation of women and men in the design and evaluation projects, public participation, training and decision making as per Bank Policy on Women in Development (OP-761). The project will also promote the inclusion of an indigenous peoples perspective in all phases and actions of the Program, pursuant to the Bank’s OP-765 Policy.

# Annex I: Project Selection Criteria for Component 1.3.

Project proposals should provide appropriate information so they can be properly evaluated according defined eligibility criteria. Proposal should include, at least, information on:

- Partnership and technical and financial soundness

- Project objectives and tasks

- Environmental and social impacts

- Project risks and contingency plan

- Transferability of results

- Dissemination activities

- Detailed work plan

The Operational guidelines shall define environmental criteria for projects selection. To support the sustainable development of the sector, application of eligibility criteria should be oriented not only to minimise the environmental and social impacts of projects (ensuring that impacts have been identified and the corresponding correction and mitigation measures adopted), but also to stimulate the submission of proposals for projects on any of the priorities listed in title Component I6.1 above. To facilitate the access to and extended application of project results, a demonstration component should be included in the project as well.

What follows is a list of eligibility criteria which are relevant from and environmental and social perspective.

- Soundness of participants

  - Does the developer (or its partners) have the experience and/or expertise necessary to carry out the project?

  - Is the available information on the participants’ financial situation satisfactory?

- Technical feasibility

  - Are the assumptions and aims realistic?

  - Are the difficulties and potential risks analysed and taken into account?

  - Are the authorisations and administrative measures required described and included in the project? (In particular those of environmental significance, including, but not only, EIA procedure.)

  - Are there plans to redesign the project if any problems occur?

- Financial feasibility

  - Is the budgetary estimate realistic and do the costs seem consistent with the action proposed?

- Integration of environmental and social priorities

  - Has the project identified environmental risks and impacts and defined appropriate measures to minimise their effects?

  - Does the project relate to one of the environmental/social priority fields specified in the Operational guidelines? (see priority list under title 6.1)

    - Is the problem addressed by the project important in the agricultural sector?

    - Is the pollution problem to be prevented or tackled a major one?

    - Does the project imply introduction of exotic species?

    - Does the project favour (in any way) the use of pesticides?

    - Does the project favour (in any way) the reduction of GHG emissions?

    - Does the project develop or favour IPM mechanisms?

    - Does the project include training in preventive practices?

    - Does the project contribute to or support the development of Belize bio-energetic potential?

  - Will the project help to integrate the environment into socio economic activities?

  - Will the project help to integrate vulnerable social sectors (e.g. indigenous populations) into socio economic activities?

  - Is the project likely to have a substantial impact on development of these activities?

  - Does the project provide added value compared with current application of the environment policy and legislation?

  - Will the project encourage suitable cooperation between the different stakeholders concerned by the environment problem?

  - Will the expected results of the project directly bring about a significant and lasting change in the state of the environment (pollution levels, available resources, etc.)?

- Transferability and dissemination of results

  - Can the results from the project be easily reproduced and adapted for efficient use in different circumstances?

  - Are there plans in the project to facilitate and/or organise the transfer of results?

  - Are there enough potential users for the proposed practices, techniques or products?

  - Are the dissemination activities sufficient or appropriate to allow the project to meet its objectives in terms of demonstration and transferability?

  - Does the project require specific dissemination actions to be a success? Are these actions properly planned?

  - Are the planned actions appropriate for reaching the objectives and targets?

- IDB’s Exclusion List. Selected projects will comply with IDB’s Exclusion List of products, substances or activities listed below are not eligible for financing (IDBDOCS-#2005806-Exclusion_List_SCF-FMK).

Environmental Protection Act - Nº 22 of 1992. Environmental Impact Assessment Regulations. Statutory Instrument Nº 107 of 1995.

An increase of current laboratory activities implies a greater risk for environmental impacts and workers accidents. Appropriate measures are suggested in the Environmental and Social Management Plan section below.

Belmopan is Belize’s capital. Being placed in the interior of the country, far from the coastal zone, Belmopan is less vulnerable than Belize city to natural disasters, such us flows or hurricanes. Belmopan is as well a much less populated area than Belize city.

IDBDOCS-#2005806-Exclusion_List_SCF-FMK

Security for workers is regulated by the Ministry of Labour; BAHA is in the process of adopting specific measures on this regard.

Eligibility criteria ensure that selected projects comply with pre-established (environmental and other) criteria. Eligibility criteria are also useful when several projects compete for limited financial resources, helping to promote those that better suite the program technical and environmental requirements. However, elegibility criteria do not ensure the submission of proposals focused in any of the priorities listed in title Component I6.1. To facilitate the submission of such proposals it would require additional criteria and mechanism, e.g. defining a system of quotas (this is, reserving part of total funds for projects on these priority areas) or designating someone at the management board with the specific responsibility of identifying project opportunities and facilitating partnerships around these priorities.

When environmental and social objectives are not critical to the project success, there is a clear risk they are not fully and successfully developed, particularly in case of unexpected deviations occur that can affect the financial viability of the project. Therefore, it is important the project identifies potential risks and plans the corresponding corrective actions.