## Sheet1
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Regional |  |  |  |  | Executing agency: IDB (IFD/IFD) |  |  |  |  | Public or private sector: Public
Project number: RG-T2665 |  |  |  |  | Title of Project: China-LAC Knowledge and Policy Exchange Initiative (KPEI)
Period covered by the plan: 2016-2018
Threshold for ex post review of procurements: |  |  |  | Goods and services (in US$): |  | 475000 |  | Consulting services(in US$): | 25000
Item No. | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (ex-ante or ex-post) (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/ICSF % | Local/other %
1 |  | Component 1: China–LAC Joint Research Activities | 75000
Non-Consulting Sevices
1.1 |  | Workshops | 12500 | PC | ex-post | 100% |  | 2016-05-01
1.2 |  | Travel and logistics costs | 32500 | PC | ex-post | 100% |  | 2016-05-01
1.3 |  | Publication of materials | 30000 | PC | ex-post | 100% |  | 2016-06-01
2 |  | Component 2: Dialogues, Policy Summits, Business Meetings and other events | 250000
Non-Consulting Sevices
2.1 |  | Dialogues, Summits, Meetings and other events | 50000 | PC | ex-post | 100% |  | 2016-09-01
2.2 |  | Travel and logistics costs | 200000 | PC | ex-post | 100% |  | 2016-09-01
3 |  | Component 3: Capacity Building and Institutional Exchanges through South-South Cooperation | 150000
Non-Consulting Sevices
3.1 |  | Training sessions and workshops | 50000 | PC | ex-post | 100% |  | 2016-05-01
3.2 |  | Travel and logistics costs | 100000 | PC | ex-post | 100% |  | 2016-05-01
4 |  | Monitoring, assessment, dissemination and overall management | 25000
Consulting Sevices
4.1 |  | Consultants to support management, dissemination and other program activities | 25000 | IICQ | ex-post | 100% |  | 2016-03-01
Total |  |  | 500000 | Roberto Manrique (IFD/IFD) |  |  | Date: October 7, 2015
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(3) Ex ante/ex post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex post review is the standard modality. Ex ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.