Results Matrix

| Project Objective | The objective of this program is to improve the learning outcomes of Jamaica’s students by: supporting the modernization of the Ministry of Education, increasing the effectiveness of the delivery of the education services, improving the standards and quality of education, raising the level of professionalism of the teaching profession, enhancing the accountability of the system and improving stakeholder and community involvement in education. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Result Indicator |  | Unit of measure | Baseline | After 1st operation (2008) | After 2nd operation (2010) | After 3rd operation (2015) | Means of verification |  |
| Result 1. Improved students’ learning |  |  |  |  |  |  |  |  |
| % of students with proficiency in grade 4 math |  | Percentage | 38% (2004) | 39% | 42% | 58% | Report on Test results |  |
| % of students with proficiency in grade 4 language |  | Percentage | 57% (2004) | 68,9% | 67% | 78% | Report on Test results |  |
| Average percentage score at GSAT for math and language |  | Percentage | - Math: 44% (2004) Language: 48% (2004) |  |  | - Math: 63% Language: 63% | Report on Test results |  |
| % of cohort attaining Grades 1-3 in 5 CSEC subjects including Math and English |  | Percentage | 12.5% (2006) |  |  | 18% | Report on Test results |  |
| Result 2. Modernized central Ministry of Education focusing on policy formulation, monitoring and evaluation, standard setting and agencies coordination |  |  |  |  |  |  |  |  |
| Organizational structure of a policy MOE developed |  | Number | 0 | 1 |  |  | Loan disbursement document (JA-L1002) |  |
| MOE operating with new roles: policy formulation, monitoring and evaluation, standard setting and agencies coordination |  | Number | 0 |  |  | 1 | Functional profile document and operational manuals |  |
| National Education Trust (NET) for construction and maintenance operational |  | Number | 0 |  | 1 |  | Loan disbursement document (JA-L1024) |  |
| Result 3. Effective delivery of education through decentralization of functions to the regions |  |  |  |  |  |  |  |  |
| Number of REAS created aligned with parish boundaries and autonomous providing quality support to schools and better inter-sectoral coordination |  | Number | 0 | 5 | 2 |  | Loan disbursement document (JA-L1002 and JA-L1024) |  |
| DSS operational |  | Number | 0 |  |  | 1 | Letter from PS noting Cabinet decision |  |
| Result 4. Improved standards and quality of the education system at all levels |  |  |  |  |  |  |  |  |
| National Education Inspectorate (NEI) operational |  | Number | 0 |  |  | 1 | Letter from PS |  |
| Result 5. Raised level of professionalism and quality of teaching |  |  |  |  |  |  |  |  |
| Jamaica Teaching Council (JTC) operational |  | Number |  |  |  | 1 | Letter from PS |  |
| % of teacher with BA |  | Percentage | 30% (2006) | 34.2% | 43% | 62% | Loan disbursement document (JA-L1002 and JA-L1024) and Letter from the PS |  |
| % of teachers registered in an Unified System of Registration |  | Percentage | 0% |  | 60% | 95% | Letter from PS |  |
| Result 6. Enhanced accountability of the system |  |  |  |  |  |  |  |  |
| National College of Educational Leadership (NCEL) operational |  | Number | 0 |  |  | 1 | Letter from PS noting Cabinet decision |  |
| NEI’s appraisal reports used by NCEL to target principals training in under performing schools |  | Number | 0 |  |  | 1 | Letter from the PS |  |
| NEI’s appraisal reports used by JTC to focus in-service training |  | Number | 0 |  |  | 1 | Letter from the PS |  |
| Result 7: Improved stakeholder and community involvement in education |  |  |  |  |  |  |  |  |
| National Parent Teacher Association (NPTA) created |  | Number | 0 | 1 |  |  | Loan disbursement document (JA-L1002) |  |
| National Parenting Policy legislation approved |  | Number |  |  |  | 1 | PS letter with Cabinet approval |  |
| National Parenting Support Commission operational |  | Number | 0 |  |  | 1 | PS letter with Cabinet approval |  |

| Product Indicator | Unit of measure | Baseline | After 1st operation (2008) | After 2nd operation (2010) | After 3rd operation (2015) | Means of verification |
| --- | --- | --- | --- | --- | --- | --- |
| Products for Result 2. Modernized central Ministry of Education focusing on policy formulation, monitoring and evaluation, standard setting and agencies coordination |  |  |  |  |  |  |
| Students benefitted by education project | Number | 0 |  |  | 630,000 316,000 (Male) 314,000 (Female) 132,000 (preprimary) 257,000 (primary) 240,000 (secondary) | Education Statistics Report. Note that all students enrolled in the education system benefit from the reforms of this PBL. |
| Functions of the DSS and central MOE defined | Number | 0 |  |  | 1 | Functional profile document and operational manuals |
| Action Plan to transform MOE including HR transition and ToRs, staffing, training and operational arrangements developed | Number | 0 | 1 |  |  | Loan disbursement document (JA-L1002) |
| Key HR positions filled | Number | 0 |  |  | 3 | Letter from the PS indicating key positions |
| Business Plan for 2013-2015 and operational plan for 2014-2015 completed | Number | 0 |  |  | 2 | Document of business and operational plan |
| Job descriptions for NET completed | Number | 0 |  |  | 1 | NET’s framework document, functional profile and business plan |
| PPP manager for school construction recruited at NET | Number | 0 |  |  | 1 | NET’s framework document, functional profile and business plan |
| EMIS designed and connecting MOE with regional offices | Number | 0 |  |  | 1 | EMIS framework document |
| Space audit of school updated for de-shifting of secondary schools | Number | 0 |  | 1 |  | Loan disbursement documents (JA-L1024) |
| Number of schools de-shifted | Number | 0 |  |  | 25 | Summary document with rationalization plan including number of schools de-shifted |
| Proposal for legislative changes, including the Education Act and the creation of agencies (NEI, JTC and NET) drafted | Number | 0 | 1 |  |  | Loan disbursement documents (JA-L1002) |
| Consultations on establishment of JTC legislation completed | Number | 0 |  |  | 1 | Consultation report on JTC |
| Legislation on establishment of JTC drafted by CPC for submission to Parliament | Number | 0 |  |  | 1 | Consultation report on JTC |
| Drafting instructions for amendment of Education Act sent to CPC | Number | 0 |  |  | 1 | Drafting instruction for amendment of the Education Act |
| Products for Result 3. Effective delivery of education through decentralization of functions to the regions |  |  |  |  |  |  |
| Ministerial decision to create REAS aligned with parish boundaries to provide quality support to schools | Number | 0 | 1 |  |  | Loan disbursement documents (JA-L1002) |
| Blueprint for REA operations drafted | Number | 0 |  | 1 |  | Loan disbursement documents (JA-L1024) |
| Number of schools administered and supervised by REAs | Number | 0 |  | 22 | 204 | Loan disbursement documents (JA-L1024) and PS report |
| Percentage of schools completing school improvement plan | Percentage | 0% |  |  | 80% | School improvement plan summary report |
| Number of school working with DSS for including NEI recommendations in school improvement plan. | Number | 0 |  |  | 204 | DSS operation turnaround report |
| Number of quality education circles established to support all schools in improving performance | Number | 0 |  |  | 63 | Letter from PS with report on activities and copy of map showing location of QECs |
| Products for Result 4. Improved standards and quality of the education system at all levels |  |  |  |  |  |  |
| NEI’s framework document containing role, function & management structure of the agency | Number | 0 | 1 |  |  | Loan disbursement documents (JA-L1002) |
| NEI core staff hired | Number | 0 |  |  | 6 | PS letter and description of the 6 positions hired |
| Chief inspector hired and Performance Agreement signed by him/her and PS | Number | 0 | 1 |  |  | Loan disbursement documents (JA-L1002) |
| Number of school participating in the pilot test for school evaluation | Number | 0 |  | 10 |  | Loan disbursement documents (JA-L1024) |
| Guidelines for school self-evaluation created | Number |  |  |  | 1 | Guidelines for Self Evaluation and PS Letter |
| Number of schools with self-evaluation completed | Number | 0 |  |  | 954 | NEI Report |
| NEI Inspection handbook printed | Number | 0 |  |  | 1 | Inspection Handbook |
| NEI inspectors for the evaluation of the education system trained | Number | 0 |  |  | 300 | Letter from the PS stating the number of inspector trained |
| Schools with first cycle of inspections completed | Number | 0 |  |  | 2,661 | NEI report and PS letter |
| National Literacy Strategy (NLS) approved by MOE | Number | 0 | 1 |  |  | Loan disbursement documents (JA-L1002) |
| National Mathematics Strategy (NMS) approved by MOE | Number | 0 | 1 |  |  | Loan disbursement documents (JA-L1002) |
| Number of underperforming school in mathematics supported | Number | 0 | 244 |  |  | Loan disbursement documents (JA-L1002) |
| Database to monitor literacy performance containing benchmarks and targets completed | Number | 0 |  | 1 |  | Loan disbursement documents (JA-L1024) |
| All schools informed about their performance | Number | 0 |  | 793 |  | Loan disbursement documents (JA-L1024) |
| Number of schools with Grade 4 Literacy and Numeracy Tests implemented | Number | 0 |  | 793 |  | Loan disbursement documents (JA-L1024) |
| Review of transition methodology/assessment GSAT completed | Number | 0 |  | 1 |  | Loan disbursement documents (JA-L1024) |
| Proficiency Pathways for primary education students operational | Number | 0 |  |  | 1 | Handbook and charts of Proficiency Pathway program |
| Method to identify children with special needs operational | Number | 0 |  |  | 1 | Child find report |
| Alternative Program for Exceptional Students (APEX) developed | Number | 0 |  |  | 1 | Program’s Concept Document |
| Products for Result 5. Raised level of professionalism and quality of teaching |  |  |  |  |  |  |
| JTC’s framework document containing role, function, budget and management structure prepared. | Number | 0 | 1 |  |  | Loan disbursement documents (JA-L1002) |
| Head of JTC hired and Performance Agreement signed by him/her and PS | Number | 0 | 1 |  |  | Loan disbursement documents (JA-L1002) |
| Standards for teaching profession developed | Number | 0 |  |  | 1 | Booklet of standards |
| Framework document for teachers’ licensing completed | Number | 0 |  | 1 |  | Loan disbursement documents (JA-L1024) |
| Teacher licensing regime developed | Number | 0 |  |  | 1 | Manual for teacher licensing regime |
| Number of mentors trained for the Teacher Mentorship Program | Number | 0 |  |  | 900 | Mentoring program handbook |
| In-service teacher training program under way | Number | 0 |  |  | 1 | Report of in service teacher training program |
| Revolving Loan Fund to support teachers in attaining graduate status created | Number | 0 | 1 |  |  | Loan disbursement documents (JA-L1002) |
| Products for Result 6. Enhanced accountability of the system |  |  |  |  |  |  |
| Instrument to appraise performance of principals, guidance counselors and teachers created | Number | 0 | 1 |  |  | Loan disbursement documents (JA-L1002) |
| Number of schools using performance appraisal instruments to evaluate principals, guidance counselors | Number | 0 |  | 75 |  | Loan disbursement documents (JA-L1024) |
| Performance appraisal instruments in use for Principals and Guidance Counselors | Number | 0 |  |  | 1 | NCEL report and performance appraisal documents |
| Products for Result 7: Improved stakeholder and community involvement in education |  |  |  |  |  |  |
| Plan of a Community Consultation Program drafted | Number | 0 | 1 |  |  | Loan disbursement documents (JA-L1002) |
| Parents mentors trained by NPSC to reach out to parents in the community | Number | 0 |  |  | 70 | Report on parents mentor program |
| Number of regional meetings with stakeholder in Literacy | Number | 0 |  | 6 |  | Loan disbursement document (JA-L1024) |
| Number of regional stakeholder consultation in school safety | Number | 0 |  | 4 |  | Loan disbursement document (JA-L1024) |
| Manual for school security and safety completed and distributed | Number | 0 |  | 1 |  | Loan disbursement documents (JA-L1024) |
| Marketing campaign ongoing including the distribution of Newsletters to all staff and schools and regular TV and radio broadcasts | Number | 0 |  |  | 1 | Letter from the PS |
| School Wide Program for Behavior in Schools (SWPBIS) implemented | Number | 0 |  |  | 1 | Letter from the PS |

See Monitoring and Evaluation Plan for further information on the indicators

Indicators listed for the first and second PBLs have already been achieved

This indicator is the Corporate Sectoral Indicator (CSI) for the Corporate Results Framework (CRF).