LEGIII/RG-442166-04

THE ANNEX

THE PROJECT

Promoting SME Competitiveness in the Caribbean through Technical Standards

I.	Objective

  - The general objective of the Project is to strengthen the competitiveness of recipient Small and medium-sized enterprises (“SMEs”) by getting them involved in industry, country and region-wide standardisation efforts to facilitate trade in goods and services and promote regional, hemispheric and global integration.

  - The specific objective is to build on the existing infrastructure of regional standardisation and develop a model for technical standard setting, demonstrating to the government and the private sector its strategic importance for trade facilitation and the need to ensure its sustainability through a steady demand for standards development with an increasingly large share of co-financing furnished by stakeholders.

II.	Description

- 2.01	The Project will achieve the objectives described in Section I through the following components: (I) Awareness-raising activities; (II) Development of standards and conformity assessment guidelines; (III) Training; and (IV) National and regional information system.

- Awareness-raising activities

  - The objective of this component is to sensitize government and the private sector in Barbados, Guyana, Jamaica, Trinidad and Tobago and in the rest of the Caribbean Community (“CARICOM”), to the importance and benefits of standards. Project activities under this component include the organization of national conferences in four (4) pilot countries, the implementation of a regional communications plan, publication of standards and guidelines, and attendance at trade shows and congresses.

  - The targeted outcome is a government and private sector that are aware of the benefits of technical standardisation and familiar with the accomplishments of standardisation programmes. The Project will benefit a minimum of five hundred (500) Small and medium-sized enterprises (“SME”) owners, as well as professionals in the government and private sectors. Other targeted outcomes include the publication of sixteen (16) standards compendiums; the participation of the National Standards Bureaus (“NSBs”) in a minimum of four (4) trade shows, congresses and conferences; and the distribution of a minimum of five thousand (5,000) sector-specific brochures.

- Development of standards and conformity assessment guidelines

  - The objective of this component is to support efforts to develop national and regional technical standards and conformity assessment guidelines in targeted sectors and, where applicable, promote involvement in hemispheric and international standardisation processes. Activities to be conducted under this component include: (i) an assessment of national and regional technical requirements for major export markets, in order to identify specific national or regional sectors/products for standardisation, and establish procedures for updating such requirements; (ii) the establishment of progress and performance indicators and a corresponding monitoring system based on the use of surveys; (iii) the development of standards and conformity assessment guidelines; (iv) the participation of the International Organization for Standardisation (“ISO”), Pan-American Standards Commission (“COPANT”) and CARICOM Regional Organization for Standards and Quality (“CROSQ”) committees; and (v) the implementation of conformity assessment procedures. The national standardisation coordinators will work with the coordinator at the CROSQ Secretariat to harmonise resulting documents based on national and regional technical requirements identified for major export markets.

  - The targeted outcome is: (i) the development of a minimum of sixty-eight (68) published standards and twelve (12) conformity assessment guidelines based on international standards; (ii) the diagnostics and technical assistance that will be provided to meet the technical requirements of conformity for at least twenty (20) companies; and (iii) participation in at least two (2) international committees.

- Training

  - This component provides training in priority areas as required for purposes of Component II. To achieve this objective, this component provides courses to support the implementation of the standards developed, technical requirements and assessment procedures (requirements and standards in priority areas under Component II). The targeted outcome is the training of a minimum of seven hundred and twenty (720) participant SMEs.

IV.	National and regional information system

  - The information system will help coordinate activities conducted as part of national and regional standardisation processes and train country experts involved in standardisation work. Scheduled activities under this component include: (i) the design and implementation of national and regional information systems; (ii) a course/workshop for experts (public/private sector representatives on committees for the development of standards and technical regulations) on good practices for standardisation management (at enforcement and monitoring agencies including trade associations, oversight bodies, advocacy organizations, and auditors); (iii) a publication of the compendiums of national standards developed under Component II; and (iv) conferences for dissemination of compendiums of national standards.

  - The targeted outcomes are: an operational national and regional information system, and the provision of training in good practices for standardisation management. Activities under this component will produce an operational networked information system accessed and used by at least ten percent (10%) of the SMEs and agencies and organizations in each country targeted by awareness-raising activities under Component I; and six (6) courses per country providing training to a minimum of seven hundred and twenty (720) participants, including representatives of agencies in charge of the drafting of technical regulations.

III.	Total Cost of the Project

3.01	The estimated cost of the Project is the equivalent of one million seven hundred ninety six thousand nine hundred and thirty five dollars (US$1,796,935), in accordance with the following investment categories and sources of financing:

Budget

(in US$)

| Activities | Bank | Local Contribution | Total |
| --- | --- | --- | --- |
| Component I | 176,800 | 134,600 | 311,400 |
| Component II | 461,260 | 239,600 | 700,860 |
| Component III | 33,120 | 19,200 | 53,320 |
| Component IV | 64,600 | 15,300 | 79,900 |
| Project coordination unit | 298,800 | 21,600 | 320,400 |
| Equipment and logistics | 59,300 | 90,000 | 149,300 |
| Evaluation consultant, midterm reviews (1) and final evaluation | 60,000 |  | 60,000 |
| Audits (4) | 40,000 |  | 40,000 |
| Sub-total | 1,193,880 | 520,300 | 1,714,180 |
| Contingencies | 47,755 |  | 47,755 |
| TOTAL PROJECT BUDGET | 1,241,635 | 520,300 | 1,761,935 |
| Cluster activities | 35,000 |  | 35,000 |
| GRAND TOTAL | 1,276,635 | 520,300 | 1,796,935 |
| Percentages | (70%) | (30%) |  |

IV.	Execution

4.01	The CROSQ will be the executing agency for the Project CROSQ will have technical and financial responsibility for the Project, and will manage it based on an Annual Work Plan. CROSQ will host a Project Executing Unit (“PEU”) which will be in charge of all dealings with the Bank, particularly referrals of requests for non objections for procurements of goods and services under the Project and administrative matters. The PEU will be staffed with: (i) a Project Manager, who will also serve as the Regional Administrative Coordinator; (ii) an Administrative Assistant/Secretary Support; and (iii) an Accountant.

  - CROSQ will execute the Project through the PEU and, at the country level, by the Bureau of Standards Jamaica (“JBS”), the Trinidad and Tobago Bureau of Standards (“TTBS”), the Barbados National Standards Institute (“BNSI”), and the Guyana National Bureau of Standards (“GBS”), as sub-executing agencies. CROSQ will enter into sub-execution agreements with these subexecuting agencies, to set out their respective responsibilities and contributions to the Project. This will enable the CROSQ Secretariat to promote regional activities to be conducted as part of the Project and coordinate regional harmonisation efforts with respect to the standards developed there under. Each sub-executing agency will have a coordinator, who will report directly to the project manager at the PEU.

  - Consultative committees will guide the selection of the standardisation programmes, which are to be presented for Project funding. They will ensure that these programmes meet the requirements of the Operating Regulations with respect to their national/regional scope, sector, and the type of project, activities and beneficiaries involved. The committees will include all stakeholders interests, in accordance with the Standardisation Code of Good Practice.

# V.	Monitoring and Evaluation

  - The Bank’s Country Office in Barbados will be responsible for Project supervision and oversight, monitoring compliance with contractual provisions, processing disbursement requests and obtaining audited financial statements. The Bank, in coordination with CROSQ, will hire an evaluation consultant prior to commencement of Project activities to develop the benchmarks and a monitoring system for evaluating Project outcomes. The consultant will subsequently conduct both the midterm and final evaluations of the Project to determine the extent to which its expected results have been achieved, and will participate in a Closing Workshop.

  - The Project financial statements will be audited annually by a firm of independent public accountants selected and hired pursuant to relevant Bank policies and procedures. Contracting and procurement will be in accordance with Bank policies and practices. CROSQ will submit semiannual status reports, in accordance with the Bank’s standard reporting requirements.

  - Project monitoring and evaluation activities will be coordinated with the Bank, so as to meet the regional integration objectives for the Project.

This amount will be deducted from the total MIF contribution going to the beneficiary at the time of signing of the TC Agreement, and will be used by the Bank for Cluster Activities.

The programming of activities will be done through this Annual Work Plan, ruled by the Operating Regulations: The first annual plan will be presented during the first three months after the agreement is signed; subsequent annual plans should be presented before March 1st.