LEGIII/RG-543489-05

# ANNEX A

THE PROGRAM

Grenada Reconstruction, Recovery, and Development Program

I.	Objective

1.01	The objective of the Program is to provide an effective mechanism to support the economic recovery and reconstruction of Grenada in the aftermath of Hurricane Ivan that hit the island in September 2004. The funds of the Program will be available to CDB to finance investment projects in the private sector in the area of business revitalization and in the public sector in the areas of housing infrastructure for properties with clear land titles, and environmental and public infrastructure reconstruction. The activities to be financed with loan funds will be specific development projects that are technically, socially, economically, financially, and environmentally viable and sound. Within Operating Regulations agreed by the Bank and CDB, the latter will determine the composition and design of the specific projects to be financed.

1.02	As established in the Operating Regulations agreed with CDB, funding to financial intermediaries will be possible with Program resources. Resources would be on-lent to private sector enterprises affected by Hurricane Ivan in all economic sectors. CDB would ensure that these funds are provided, at market rates and conditions, to sub-borrowers affected by the hurricane for the purpose of restoring their businesses (hotels, manufacturing plants, stores, or other economic activity). Funds will not be used for providing housing mortgage credit. Economic reactivation activities will be funded with resources from this Program only if the corresponding sector policies, legal and institutional framework, and enforcement mechanisms are adequate as determined by CDB’s guidelines.

II.	Description

2.01	The Government of Grenada (“GOGR”) has determined that the following areas have priority: (i) human shelter; (ii) agriculture and reforestation, including watershed management; (iii) business sector reactivation; (iv) school rehabilitation; (v) social recovery, including counselling; (vi) skills training; and (vii) sporting facility rehabilitation, including the national stadium.

2.02	Consistent with the original request and current thinking at CDB about the evolving circumstances in Grenada, and as noted above, the Program will broadly support a series of sub-projects in Grenada in the following three component areas: (i) housing infrastructure (sites and services), (ii) business revitalization, and (iii) environmental and public infrastructure reconstruction. An allocation between these and related sub-projects will be made according to the relative priority of each and its compliance with Program requirements, including environmental safeguards. Once determined eligible, the selection of projects will be done by CDB on a first-come-first-served basis. Following is a description of each component along with its associated parameters.

2.03	Sites and services component. With respect to sub-projects in the sites and services preparation component, specific eligibility criteria will be included to ensure that: (i) when the beneficiary takes possession, he or she will also have clear title to the property or a valid long-term leasehold contract on the land; (ii) the site is in a safe area; (iii) the site complies with all relevant urban regulations (e.g. land use, zoning requirements, etc.); (iv) the site has access to primary transportation, water, and power networks; (v) the housing complies with appropriate building codes; and (vi) an effective beneficiary selection mechanism is in place that targets vulnerable and low-income households.

2.04	Business revitalization component. A line of credit for business revitalization can be funded through this Program, in which CDB will act as the second-tier financial institution and will only lend to eligible first-tier intermediaries willing to on-lend resources to businesses in Grenada. When it is activated it will be a multisectoral credit line open to all sectors of the economy for reconstruction and recovery activities. Only medium and long-term investments will be financed with this credit line. Funds cannot be used for working capital financing. The size of individual operations with, and total CDB exposure to, each intermediary will be limited by CDB policy. In addition single loans to final beneficiaries cannot exceed US$1 million. The wholesale lending rate of CDB to first-tier financial institutions will be market-based, as determined by rates paid on time deposits and term CDs. A more detailed specification will be contained in the overall credit regulations to be agreed between IDB and CDB prior to activation of the credit line. The retail lending rate to final sub-borrowers will be freely set by the first-tier institutions. The interest rate spread earned by CDB for this component, net of administration and risk costs, and reflows from this loan net of debt service to IDB shall be utilized in accordance with any stipulations or policies of the Borrower regarding the use of its Other Special Funds.

2.05	First-tier institutions will on-lend the resources according to terms agreed with CDB prior to implementation of the credit component. These terms will be consistent with the aforementioned credit regulations.

2.06	CDB will be responsible for reviewing the condition of the first-tier financial institutions to determine their eligibility to participate in the Program. Such review will be done in accordance with the Credit Regulations previously agreed with the Bank.

2.07	CDB has extensive experience in lending to financial institutions, both public and privately owned. As of end-2003, CDB had 23 credits outstanding provided to financial institutions, of which nine were to private entities. CDB is aware that portfolio management of financial sector subprojects require constant supervision including the monitoring of the financial and operating performance of the institutions. Supervision reporting on the performance of each financial institution covers all aspects of the institution’s operations and is usually done annually. Since this supervision is dependent on timely and efficient reporting by the financial institutions to CDB, the Credit Regulations will include the reporting requirements of the borrowing financial institutions, including the description of the monitoring indicators and financial ratios to be provided.

2.08	Environmental and public infrastructure reconstruction component. This component will be financed with sub-loans directly to GOGR and will be subject to CDB’s procurement and environmental provisions. Sub-projects include control of land-slips and related natural disaster management activities, primary bridge and road improvement, bridge replacement, and secondary road improvement. The funding will rectify damage suffered during the hurricane and/or will rehabilitate infrastructure critical to the post hurricane economic recovery. CDB will take into consideration government priorities in selecting eligible sub-projects under this component.

III.	Total Cost of the Program and Financing Plan

3.01	The estimated cost of the Program is eleven million one hundred thousand dollars (US$11,100,000), as follows:

(in US$ millions)

|  | - Bank | - Counterpart | - Total |
| --- | --- | --- | --- |
| - FSO Loan | - 10 | - 1.1 | - 11.1 |
| - Inspection and Supervision Fees | - Not Applicable | - Not Applicable | - Not Applicable |
| - TOTAL | - 10 | - 1.1 | - 11.1 |

### Execution

  - The operation will be executed and administered by CDB and in turn CDB will implement its sub-projects through sub-executing agencies, including the respective Ministries and financial institutions (in the case of the credit line component). Operations financed by the Program will be selected and appraised following the policies and procedures of CDB, which are consistent with the policies and objectives of the IDB. The Operating Regulations agreed with CDB specify the eligibility criteria and requirements for access to the funds of this Program. In particular, these regulations limit the use of the funds to sub-projects in Grenada that support its economic recovery and rehabilitation and are socially and economically viable. In addition, the regulations also specify the types of operations and uses of funds that are prohibited by Bank policies. CDB will provide semi-annual progress reports, a mid-term evaluation and a final evaluation for each sub-project, in addition to a copy of its annual report on project implementation that provides general information on the sub-projects as requested. These reports will assist in IDB’s ex-post monitoring of sub-project compliance with Program objectives. The Agency for Reconstruction and Development (“ARD”) will also be expected to present harmonized or standardized performance reports to donors on projects funded with external resources that will be used by CDB to complement its own inspection visits and analysis.

  - Moreover, to ensure effective evaluation of the operations supported, the Operating Regulations of the Program include specific reporting requirements to facilitate an evaluation of the effectiveness of the sub-projects and thereby the development effectiveness of the Program itself.

V.	Monitoring and evaluation

5.01	A Logical Framework has been developed that will be the basis for monitoring progress under the Program. This framework has been prepared taking into consideration CDB’s suggestions and includes a set of indicators for the evaluation system. The Bank has also agreed with CDB on the mechanisms for a mid-term evaluation of the Program that would allow the implementation of corrective actions if deemed necessary. This evaluation will consist of joint IDB/CDB reviews of the various sub-projects and an assessment of the effectiveness of the Program as a whole.

5.02	The IDB’s Country Office in Barbados will supervise the execution of the Program. CDB’s Project Performance Evaluation System (“PPES”) is a relatively advanced monitoring and evaluation system. CDB will make data from this system available to the Country Office, as well as semi-annual supervisory reports of the sub-projects financed with Loan resources. These reports include an assessment of the sub-project’s performance and the specification of remedial measures, when necessary. In addition, CDB will provide IDB with a copy of its annual report on the implementation of projects, which provides data on all CDB projects in execution. This report will allow the IDB to compare the performance of projects financed with the loan resources with other CDB loans by sector and by country. This information will be sufficient to indicate whether the project is meeting the execution goals in the logical framework. The Bank’s Project Completion Report (PCR) will be based on CDB’s own project completion exercise.

5.03	All projects financed by CDB with a total cost of more than $100,000 have a logical framework that includes measurable result indicators to show whether the supported projects meet their development objectives. These indicators and development objectives will be reviewed periodically by CDB and IDB staff as part of the evaluation process. The PPES scores for each sub-project supported by the Program and an appropriately weighted average will be provided. CDB Appraisal Documents shall include baseline data and define execution and project termination benchmarks for these performance indicators that are agreed with the sub-borrower as part of the sub-loan agreements. These indicators, along with the information included in CDB’s performance evaluation system, will allow for an evaluation of the effectiveness of the operations supported by this Financing and thereby the effectiveness of the Program itself.

VI.	Procurement of goods and services

6.01	When works or goods to be procured or services to be contracted for the sub-projects, including those related to any form of transportation or insurance, are to be financed in whole or in part with resources of the Financing, the procedures and specific requirements for the bidding or other forms of contracting, shall permit the unrestricted participation of suppliers of goods and services from member countries of the Bank. Consequently, no conditions that would prevent or restrict the offer of goods or the participation of contractors from such countries shall be established in such procedures or specific requirements. In order to both facilitate the administration of the Program and to provide sub-executing agencies with uniform procedures in order to facilitate access to the Program’s resources, CDB’s procurement procedures shall be used with the following provisions:

- Eligibility for procurement using the resources of the Financing shall be open only to IDB members and CDB members;

- With the non-objection of the IDB, CDB may permit the use of Loan resources to finance the execution by force account, including community self-help programs, up to US$2 million;

- The IDB reserves the right to carry out, at any stage of the procurement process, ex-ante or ex-post review of the procedures being followed; and

- Sub-executing agencies may reject all bids, after consultation with CDB, if the lowest evaluated bid exceeds the estimate by an amount deemed by CDB to provide a reasonable justification. In such cases, with the approval of CDB, the sub-executing agency may call for new bids from at least all who were invited to bid in the first instance.

VII.	Consulting Services

7.01	In the selection and contracting of consulting services financed in whole or in part with the Financing, no conditions or stipulations may be established that restrict or prevent the participation of consultants from IDB member countries. In all other respects, CDB’s Procedures for the Selection and Engagement of Consultants by Recipients of CDB Financing shall govern the selection and contracting of consulting services.

VIII.	Private Sector Development Policies and Operational Guidelines (PSDPOG)

8.01	Implementation of CDB’s private sector development policy is effected through CDB’s PSDPOG which includes a series of limits and ratios presented for guidance only and are subject to the requirements contained in CDB’s OCR Financial Policies and Operating Guidelines, as presently determined, and as may be adjusted from time to time. Financial intermediary operations are limited to US$5 million per intervention and cumulative loans outstanding to any financial institution cannot exceed US$10 million.

8.02	In its intermediary lending, the PSDPOG indicate that CDB is guided by requirements of sound management, acceptable asset quality, prudent financial and operational policies and adequate capital structure. Financial institutions will also be required to adhere to prudential principles, generally accepted accounting principles and regulations accepted by the appropriate supervisory authority, where applicable. Resources from this Program will not be used to restructure debts.

Including rehabilitation and restoration of tourist infrastructure especially at heritage sites frequented by cruise ships and a line of credit for refurbishment or rehabilitation of all type of business activities in the country, including the commercial and tourist sectors.

i.e. construction will be limited to areas not prone to natural hazards.

CDB definition of medium term (4 – 7 years) and long term (8+ years) will be used.