LEGIII/RG-563434-05

# ANNEX C

# PROCEDURES FOR THE SELECTION AND ENGAGEMENT OF

CONSULTANTS BY RECIPIENTS OF CDB FINANCING

# Grenada Reconstruction, Recovery, and Development Program

FOREWORD

1. INTRODUCTION

- Purpose

- General Considerations

2. DEFINITIONS 
3. APPLICABILITY OF PROCEDURES 
4. TERMS OF REFERENCE 
5. ASSIGNMENT BUDGET 
6. SHORTLIST OF CONSULTANTS

- Advertising

- Eligibility

- Shortlist Selection

- Registration of Consultants

7. INVITATION PROCEDURES 
8. PROPOSAL EVALUATION 
9. NEGOTIATIONS 
10. SUPERVISION 
11. PERFORMANCE EVALUATION
12. SELECTION OF INDIVIDUAL CONSULTANTS 

FOREWORD

The "Procedures for the Selection and Engagement of Consultants by Recipients of CDB Financing" replaces the booklet entitled "Guidelines for Choice of Consultants".

The Procedures for the Selection and Engagement of Consultants by Recipients of CDB Financing seek to:

- facilitate CDB Staff, the Recipients of CDB financing, their executing agencies, Consultants and other interested persons in better understanding the process of selection and engagement of Consultants in order to foster the achievement of the objectives of the consultancy; and

- separate the required procedures from the reference material (which has been significantly increased and placed in a Handbook) to facilitate ease of use.

1. INTRODUCTION

1.1 Purpose

1.1.1      The purpose of these Procedures for the Selection and Engagement of Consultants (the Procedures) is to set out procedures which are required by the Caribbean Development Bank (CDB) to be followed for the selection and engagement of Consultants by Recipients of CDB financing.

1.1.2      The Loan or Grant Agreement to which a Recipient of CDB financing is a party, governs the legal relationship between the parties and as provided in the Agreement, the Procedures are required to be followed in the selection and engagement of Consultants. The rights and obligations which arise from the relationship between the Recipient of CDB financing and Consultants are governed by the relevant Letter of Invitation (LOI), issued by the Recipient of CDB financing, and accepted by the Consultants and not by the Procedures or Loan or Grant Agreement. No party other than the Recipient of CDB financing shall have any claim to the proceeds of the loan or grant. 

1.2 General Considerations

1.2.1      The Recipient of CDB financing is responsible for the selection of the Consultants, the award of the consultancy contract and the subsequent administration of the consultancy contract. The need for engagement of Consultants will be carefully considered by CDB at the time of making the appraisal of the loan or grant application and CDB may, where necessary, require that Consultants be engaged by the Recipient of CDB financing.

1.2.2      CDB's role in the process is to ensure that:

- selection is transparent and equitable;

- the Consultants are fully competent to provide the services;

- the services to be provided are appropriate for the assignment and compatible with other services required for the assignment or the project/programme;

- the responsibilities of the Consultants are clearly set out in the consultancy contract with the Recipient of CDB financing;

- the consultancy contract does not contravene any of the terms and conditions of the Financing Agreement between CDB and the Recipient of CDB financing; and

- the services are delivered in an economic, efficient and timely manner.

1.2.3      To facilitate the use of the Procedures a companion Handbook (defined at paragraph 2.1) has been produced.

1.2.4      The Procedures and Handbook together constitute CDB's Procedures for the Selection and Engagement of Consultants (the Procedures).

1.2.5      Under paragraph 1 of Article 38 of the Agreement establishing CDB, the official language of CDB is English. All invitations and responses thereto, specifications and consultancy contracts must therefore be prepared in English.

2. DEFINITIONS

2.1      Hereinafter in the Procedures the following terms shall have the following meanings:

- "Consultant" means an individual Consultant, a consulting firm, a consulting company or other body corporate, including those owned by or affiliated to universities, capable of providing consulting services, and a joint venture of such an individual, firm, company or other body corporate, or any combination thereof but excluding Government owned or controlled entities unless approved by CDB as provided for in paragraph 6.2.3 below;

- "Financing Agreement" means the Loan or Grant Agreement between the Bank and the Recipient of CDB financing which provides for the financing in whole or in part by CDB of the consultancy;

- "Handbook" means the Handbook for the Selection and Engagement of Consultants which contains guidance, standard forms of documentation required by the Procedures and illustrations of current best practice;

- "LIN" means the Letter of Invitation to Negotiate which is sent to the Consultant whose Proposal gains the highest score on evaluation;

- "LOI" means the Letter of Invitation which is sent to a shortlisted Consultant inviting the Consultant to submit a Proposal;

- "No-objection" means a written instrument from CDB to the Recipient informing the Recipient that CDB has no objection to the section of the draft or proposed procedure to which it relates;

- "Proposal" means the response by a Consultant to the LOI (with accompanying Terms of Reference (TOR), supplementary information for Consultants and the appropriate form of consultancy contract) including a detailed description of the Consultant's organisation and staff, plan of approach, experience and capabilities of personnel to be assigned, quality of supervisory leadership, the facilities and experience and any proposed variations to the TOR;

- "Recipient" means a borrower, executing agency or grantee utilising in whole or in part CDB financing for the engagement of Consultants;

- "Statement of Capability" means a response by a Consultant to an invitation to bid for a consultancy assignment, showing the qualifications and relevant experience of personnel to be assigned, with pertinent comments on the assignment; and

- "TOR" means the terms of reference specifying the assignment for which the Consultant is to be engaged.

2.2      In the Procedures references to paragraphs and appendices are references to paragraphs in the Procedures and to the appendices which are included in the Handbook. Words in the singular shall include the plural and words in the plural shall include the singular unless the context otherwise requires. References to the masculine gender are not meant to be gender specific and shall include the feminine gender.

3. APPLICABILITY OF PROCEDURES

3.1  a.   The Procedures set out requirements applicable to the engagement of Consultants by Recipients.

b.  The Procedures apply to all contracts for consulting services financed in whole or in part from CDB resources or funds administered by CDB. In procuring consultancy services not financed by CDB, the Recipient may adopt other procedures. In such cases, CDB shall satisfy itself that the procedures to be used are efficient and economic, that the Consultant selected has the necessary qualifications, and that the services to be provided are of satisfactory quality and will be carried out in accordance with the agreed project implementation schedule.

3.2      Recipients are required to use the Procedures in the selection and engagement of Consultants. The Recipient shall inform CDB of any proposed departures therefrom which shall be subject to CDB's approval. Failure to provide CDB with such information, and any action inconsistent with the Guidelines or CDB's decision on the proposed departure will make any expenditure on account of the consultancy ineligible for CDB funding and shall be a sufficient ground for suspension of CDB funding. Any such suspension could lead to the cancellation of CDB funding, together with any other funds the proper and efficient use of which CDB may feel to be jeopardised by such failure.

3.3      The various matters which are provided for in the Procedures are specified below, and are treated in detail in the order in which they arise during the cycle of selection and engagement of Consultants, namely:

- Terms of Reference

- Assignment Budget

- Shortlist of Consultants

- Contracts

- Selection Procedure

- Invitation Procedure

- Proposal Evaluation

- Negotiations

- Supervision

- Evaluation

4. TERMS OF REFERENCE

4.1      The TOR must be prepared before any steps are taken for the selection and engagement of Consultants, except as provided for in paragraph 6.1.5. They should preferably be already in draft form before application is made to CDB for financing of the consultancy.

4.2      The TOR must be approved by CDB before issue to Consultants. The CDB review will cover clarity and appropriateness. CDB may suggest the use of external assistance for their finalisation.

4.3      Any subsequent modifications to TOR as approved under paragraph 4.2 above, as may occur after negotiation with the selected Consultants, must also be approved by CDB.

4.4      At the time the Recipient or potential Recipient presents the TOR to CDB the Recipient must inform CDB of the type of contract considered suitable for the work. CDB's No-objection to the draft contract must be obtained. 

5. ASSIGNMENT BUDGET 

5.1      After preparing the TOR, the Recipient or potential Recipient will calculate an estimated budget for the consultancy, based on anticipated inputs. This budget, which must show levels of staff capability, length of time required, as well as target start and completion dates, must be submitted to the CDB together with the TOR, to give an indication of the depth of effort required. The Recipient or potential Recipient must at the same time indicate the expected source of the expertise, which must reflect level of staff salaries and travel costs. 

6. SHORTLIST OF CONSULTANTS 

6.1 Advertising 

6.1.1      Except as otherwise provided in this paragraph, Recipients are required to advertise their invitation for interested Consultants to submit Statements of Capability. This is a preliminary requirement for Consultants to be considered for inclusion in the shortlist of Consultants who will be invited to submit Proposals.

6.1.2      If the nature of the assignment is such that only a few specialist Consultants are qualified to undertake it, and these are known to the Recipient, the Recipient may, without advertising, send to CDB a list of those qualified Consultants, together with its recommendation for a shortlist from among them, and a note explaining the specialised technical requirements and how those requirements are met by the shortlisted Consultants. Subject to the No-objection by CDB, written invitations to submit Proposals may then be sent to such shortlisted Consultants. Recipients should note that the eligibility of such specialist Consultants is governed by the eligibility criteria as indicated in paragraph 6.2 below, and that any exceptions will require a waiver from CDB.

6.1.3      Subject to prior approval of CDB, advertising may be dispensed with where the Consultants' fees and expenses are not expected to be greater than US$100,000, and where there is no expectation of a follow-on or second phase contract. In such cases, Recipients may invite technical Proposals or Statements of Capability from a list of not less than three (3) or more than six (6) eligible Consultants submitted to and approved by CDB.

6.1.4      Where advertising for Consultants is required, the invitation to interested Consultants to submit Statements of Capability containing appropriate information for the purpose of shortlisting should be advertised in a newspaper of wide circulation in the country of the Recipient, in at least one other newspaper having a wide circulation outside such country and in "Development Business", the Business Edition of the Development Forum, a publication of the United Nations. CDB must approve the text of the invitation referred to in this sub-paragraph.

6.1.5      In order to save time, and with the prior approval of the CDB, where the TOR have not been finalised, but the work requirements are sufficiently well defined, the Recipient may nonetheless advertise for Statements of Capability. In no case however, will the selection of the shortlist of Consultants commence until the TOR and the estimated budget for the consultancy are complete.

6.1.6      In all cases, a copy of the advertisement must be sent by CDB before first publication to the persons designated as the Channels of Communication for Procurement.

6.1.7      A minimum of thirty (30) calendar days should be allowed from the first date of publication of the advertisement to the closing date for replies.

6.1.8      On the basis of detailed assessment of the experience and capabilities presented, a shortlist of not less than three (3) or more than six (6) eligible Consultants most suitable to receive LOIs to submit Proposals must be prepared and submitted to CDB, together with a prequalification report showing the scores and the ranking of all the candidates. Except as otherwise agreed with CDB, the shortlist mentioned in this paragraph must include Consultants from a minimum of two (2) eligible countries. No invitations should be issued until the Recipient has secured CDB's No-objection to the shortlist. In assessing the shortlist, CDB will address the technical capability and experience of the Consultants as set out in the prequalification report, its own experience of them and their eligibility.

6.2 Eligibility 

6.2.1      In relation to consultancy services, a Consultant, each member of a joint venture or consortium and any sub-contracted Consultant, shall be eligible for procurement if:

- in the case of a body corporate, it is legally incorporated or otherwise organised in an eligible country, has its principal place of business in an eligible country and is more than 50% beneficially owned by a citizen or citizens and/or a bona fide resident or residents of an eligible country or countries or by a body corporate or by a body or bodies corporate meeting these requirements;

- in the case of individuals and unincorporated firms, the person or persons is or are a citizen or citizens or bona fide resident or residents of an eligible country; and

- in all cases, the Consultant has no arrangement and undertakes not to make any arrangements whereby any substantial part of the net profits or other tangible benefits of the contract will accrue or be paid to a person not a citizen or bona fide resident of an eligible country.

6.2.2      Except as provided for in the Financing Agreement, only Consultants who satisfy the eligibility requirements as stated at paragraph 6.2.1 above are eligible for selection as Consultants.

6.2.3      Government owned or controlled entities, or subsidised organisations, are generally not eligible for selection as Consultants. Under certain circumstances, however, they may be proposed, under terms and conditions negotiated by the Recipient and stated in the LOI, as a common resource centre for all Consultants to whom a LOI is sent. In all such cases the approval of the CDB is necessary and should be sought at the same time as the submission of the shortlist, with reasons for the request. Individuals including those who are part of a body corporate or firm who are employees of national or regional institutions (government, civil service, university etc.) will need to have formal letters of approval for leave of absence from their institutions in order to be eligible to undertake consultancies on projects financed by CDB.

6.2.4      Consultants, who are part of or associated with other commercial activities or concerns including construction contractors, manufacturers, or suppliers are acceptable to CDB if they are qualified to perform the tasks required. However, in order to ensure professional impartiality they must agree to limit their role to that of consulting services and to disqualify themselves and their associates/affiliates for work in any other capacity when working on the same project. Only in special circumstances and with clear justification, after taking into account the nature of the services performed as consultant, may CDB and the Recipient jointly agree, in the course of prequalification procedures, to permit the type of Consultants mentioned above in this paragraph and/or their associates/affiliates to tender for participation in a project either as a contractor, a manufacturer, supplier or operator of any other commercial activity or concern.

6.3 Shortlist Selection 

6.3.1      In preparing the prequalification report mentioned at 6.1.8 above, the Recipient shall apply the following factors:

- technical competence of the Consultants;

- qualification and experience of Consultants Staff;

- local and regional experience of the Consultants on similar projects;

- financial capability; and

- commitments.

The factors set out above are expanded and explained in the Handbook.

6.3.2      Recipients must be careful to avoid creating situations of conflict of interest which could result from selecting Consultants for a shortlist who have had a previous connection with the consultancy assignment/project and who could benefit from the result thereof. All cases of doubt should be brought to the attention of CDB at the same time that the shortlist is submitted

6.3.3      Where no advertisement is required CDB may, if requested by the Recipient, supply to the Recipient a list of Consultants registered with the CDB. In appropriate cases where the Recipient is unfamiliar with the relevant sector, CDB may recom-mend that a Consultant be engaged, to assist with preparation of the TOR, selection of the shortlist and with Proposal evaluation, in which case the provisions of paragraph 6.4 are applicable. Such a Consultant will, however, be excluded from any participation in the project itself. In all cases, despite any assistance from CDB or need for approval by the CDB, the responsibility for selection, engagement and supervision of the Consultants, as well as all matters pertaining to the contract for the consultancy, are entirely the responsibility of the Recipient.

6.3.4      Consultants, either individually or as a member of a joint venture or con-sortium shall be represented only once on the shortlist. 

6.4 Registration of Consultants 

6.4.1      CDB maintains a Consultant registration system with basic information covering the expertise and qualification of a wide range of Consultants. This system allows CDB to provide a list of possible Consultants for Recipients when required to do so. The amount and type of information, however, varies and CDB cannot certify its accuracy. As a result CDB recommends that Recipients request a submission of qualification information from such Consultants and prepare a shortlist, in order to form their own independent judgement on the Consultants' qualification for a specific assignment.

6.4.2      The fact that CDB has included Consultants on such a list does not endorse the Consultants' qualifications or competence and is not to be construed as an approval of the Consultants appointment for a specific assignment. CDB does not have a list of approved Consultants nor does it require registration as a condition of engagement.

6.4.3      All registered Consultants receive copies of CDB's press releases which identify projects approved for financing by CDB. Consultants are expected to identify suitable opportunities through the required advertisements or the press releases. 

7. INVITATION PROCEDURES 

7.1      CDB's No-objection must be obtained before the short listed Consultants can be invited to submit Proposals. Once CDB's No-objection to the shortlist of Consultants has been received, the Recipient must send a LOI to each Consultant on the shortlist. Model LOIs, covering different evaluation systems, are included in the Handbook. The Recipient should base the LOI on these models, indicating to the CDB why a particular model LOI has been selected (with the justification for the selection of a particular evaluation procedure) and also any changes made in the text of the model LOI. Any changes not so identified may be treated as an unsubmitted change (see paragraph 7.3). Recipients must inform all unsuccessful applicants that they have not been shortlisted.

7.2      All blank spaces in the LOI requiring completion by the Recipient must be completed and special requirements (evaluation methodology, response time, budget) shall be inserted where necessary.

7.3      No LOI must be issued without the previous No-objection of the CDB. Any differences between the model LOIs mentioned at paragraph 7.1 and the version submitted to CDB for its No-objection must be clearly identified. Any differences or changes thereafter must similarly be submitted to CDB for its No-objection. The provisions of paragraph 3.2 above with respect to ineligibility, suspension and cancellation shall apply to any differences or changes not so identified by the Recipient.

7.4      Attachments to the LOI shall include, as indicated therein, Supplementary Information for Consultants, the TOR, and the draft Contract. The attachments and the LOI mentioned in this paragraph may be referred to cumulatively as the Request for Proposal (RFP). Guidance in preparation of the TOR and formats for the other documents in the RFP are included in the Handbook.

7.5      The LOI shall allow sufficient time for the submission of Proposals. Except as otherwise agreed with CDB the period specified for submission of Proposals in the LOI shall be a minimum of thirty (30) calendar days from the date of its posting or other form of transmission.

7.6      Only one (1) Proposal is allowed from each shortlisted Consultant. Consultants who wish to combine their Proposals may do so, but must inform the Recipient within fourteen (14) days of receipt of the LOI. Any such combination will have to be in the form of a joint venture whereby each joint venture partner will have joint and several responsibility. For each such combination, the Recipient may add another name to the shortlist after receiving a No-objection from CDB regarding the aforementioned combination. In such a case the response time of all Consultants invited will be recalculated on the basis of the transmission date of the last invitation and all shortlisted Consultants must be informed of the new response time accordingly.

7.7      The services of a Consultant with specialised expertise may be incorporated into the Proposals of all shortlisted Consultants. The procedure is applicable, for example in industrial projects when a methodology or process has been retained, often as a result of a previous consultancy. Whenever a Recipient proposes to nominate the use of any such Consultant with specialised expertise as a resource to a consultancy funded by CDB the Recipient must seek the No-objection of CDB.

8. PROPOSAL EVALUATION 

8.1      Proposal evaluation may include price as a factor in the evaluation exercise. Whether and how this is done is of critical importance in the selection process. The Recipient's preference, together with the reasons for that preference, must be submitted to CDB for its No-objection. As this will affect the form of the LOI, this submission must precede the issue of the LOI. The decision is best taken at the time of submitting the TOR, the form of which could be affected by the decision to include or exclude price as a factor in the evaluation exercise. The factors to be taken into account by the Recipient, and which will be considered by CDB, are set out in the Handbook.

8.2      The weightings of the criteria to be taken into account in the technical evaluation must be submitted to CDB by the Recipient, no later than the time of submission of the draft LOI.

8.3      The Recipient will also inform CDB of the composition of the Evaluation Committee, including official designation and qualifications of its members. This committee should preferably include personnel who were responsible for the drafting of the TOR, who will be responsible for supervision, and who will be prime beneficiaries of the assignment.

8.4      The Recipient must transmit its evaluation report to CDB, together with its recommended selection for negotiations. This recommendation must also indicate the second choice, in the event that negotiations with the first choice should be unsuccessful. The LIN must not be issued before the Recipient has received CDB's No-objection. No indication of the ranking of unsuccessful proposers other than the second shall be issued at any time.

8.5      The evaluation report must also mention any variations in the TOR or model contract which may have been proposed by the Consultant and which the Recipient wishes to discuss during the negotiations. Variations, especially if a condition of acceptance, may necessitate a change in the order of preference. Receipt of CDB's No-objection and/or its comments, on any suggested variations must also precede the issue of any LIN. 

9. NEGOTIATIONS

9.1      Once CDB's No-objection to the choice of Consultant has been received, the Recipient must send the first ranked Consultant a LIN, using the model from the Handbook. At the same time, all other contestants except the second ranked should be informed that their Proposals were not successful, while the second ranked is informed that he has been so ranked and is requested to hold himself or his team, as the case may be, in readiness in case negotiations with the first ranked should be unsuccessful. Model letters to be sent by the Recipient to all the parties mentioned in this paragraph are included in the Handbook

9.2      The negotiations should follow the programme outlined in the Handbook. After completion, whether successful or unsuccessful a copy of the negotiation notes, signed by both parties, shall be submitted to CDB. In the event that negotiations are unsuccessful, a copy of the negotiation notes shall be submitted to CDB prior to the issuing of any further LIN. In the event that negotiations are successful, then preferably at the same time of submittal of the negotiation notes, but in no case later than two weeks after the completion of negotiations, a clean final draft of the contract shall be submitted to CDB. CDB will thus be able to make any comments or reservations before the signing of the contract. No amendments to such final draft, nor to the contract, may be made without the prior No-objection of CDB.

9.3      As soon as the contract is signed, the Recipient should notify the second ranked Consultant that the contract has been awarded to the first ranked Consultant. A form of letter suitable for such notification is included in the Handbook.

9.4      At this stage the Recipient may make a public announcement of the award of the contract. If the Recipient does not wish to make such an announcement, or after such an announcement has been made, CDB may make its own announcement. 

10. SUPERVISION 

10.1      Contract supervision is the responsibility of the Recipient. Nonetheless, copies of all reports by the Consultant to the Recipient shall be sent to CDB by the Recipient for information. Furthermore, the Recipient shall allow CDB to send representatives to meetings with the Consultants if CDB so desires, and shall call meetings with the Consultants for CDB's intervention if CDB deems this necessary. CDB shall not however meet with the Consultants without giving the Recipient the opportunity to participate. 

11. PERFORMANCE EVALUATION 

11.1      The Recipient will undertake an evaluation of the performance of the consultant at the time of acceptance of the final Consultants' report or, if acceptance is delayed because of disagreements regarding such report, within two (2) months of its submission with a further report to be made at the time of acceptance.

11.2      The performance evaluation report will follow the format given in the Handbook. The Recipient will supply CDB with any clarifications regarding the performance evaluation which CDB may require. 

12. SELECTION OF INDIVIDUAL CONSULTANTS 

12.1   a.   Individual Consultants should generally be selected on the basis of a Statement of Capability only. An interview may also be useful where for example the personality of the Consultant is important to the outcome of the assignment.
b.  Appointment can be by means of a Letter of Appointment instead of a full form contract.
c.  Reporting requirements can be reduced, especially when the Consultant is being engaged as a technical resource to be attached to an existing department.

12.2      Individual Consultants are normally to be employed on assignments for which:

- teams of personnel are not required;

- no additional outside (home office) professional support is required; and

- the experience and qualifications of the individual are the paramount requirements.

12.3      When three or more individual Consultants are to be employed on one project, coordination, administration, and collective responsibility can become difficult. In such cases, it may be advisable to employ a firm of Consultants.

12.4      Individual Consultants are selected on the basis of their qualifications for the assignment. They shall meet all relevant qualifications and shall be fully capable of carrying out the assignment. Capability is judged on the basis of academic back-ground, experience and, as appropriate, knowledge of the local conditions such as the legal system, form of government, culture, language, and natural geographic conditions.

12.5      From time to time, permanent staff of a firm of Consultants may be available as individual Consultants. In such cases, where the firm of Consultants has a previous connection with the consultancy/project the conflict of interest provision at paragraph 6.3.2 shall apply to the firm of Consultants and not to the permanent staff member in his role as an individual Consultant.