LEGIII/RG-714987-06

# ANNEX

THE PROGRAM

Promoting Diaspora and Local Support for Productive Initiatives

I.	Objective

  - The general objective of the Program is to improve the economic condition of low-income communities in the region affected by migration.  The purpose of the Program is to develop transnational linkages to foster local productive development among communities throughout the participating countries.

II.	Description

2.01	In order to achieve the above aforementioned objectives, the Program will include the following three components: (i) Promotion and Local Capacity-Building for Productive Development; (ii) Support to Productive Community Initiatives; and (iii) Monitoring, Evaluation and Dissemination of the results.

- Component I: Promotion and Local Capacity-Building for Productive Development

  - The objective of this Component is twofold: to promote the opportunities presented by this Program and to organize local partners and institutional platforms in each country.  The promotional and outreach activities are intended to ensure that potential grantees, transnational and inter-regional organizations, home communities, and potential co-funders are aware of opportunities to support local productive development in the Program.  Activities in this Component will include: (i) a symposium to announce the Program; (ii) exchanges between current grantees and potential grantees; (iii) diaspora meetings and other similar sessions; (iv) informative sessions to generate increased interest and opportunities for the Program; and (v) development of local sites and institutional partners for Program activities in additional countries.

  - For the Program launch, HIP will invite representatives from key organizations throughout the participating countries as well as those outside those countries.  Informational materials, articles, interviews, fact sheets and project profiles for HIP and other appropriate publications will be produced to inform constituents and promote the Program.  HIP and Program staff will also participate in other events to increase awareness and support in the region for this Program. Specific efforts will be included to promote participation of minority groups or underserved populations such as people of African descent, youth, women and indigenous groups to ensure they are made aware of the opportunities presented by this Program.

  - Program activities in each of the six countries will be rolled out in phases.  The first phase will focus on work with the local partners and fundraising (both locally and abroad with the diaspora and other interested entities).  Local partners will be selected based on the following characteristics (i) interest and ability to provide local funds; (ii) proven ability to provide technical assistance to grantees; (iii) experience working with local community groups or Non Governmental Organizations (NGOs); (iv) experience in the area of economic development, job training and income-generating activities and technical knowledge related to project activities; (v) proven ability to collaborate with public and/or private sector partners; and (vi) commitment to expanding local philanthropy. The second phase will be to undertake promotional activities in the country to generate interest among potential grantees under Component II.  The final phase will be to initiate the competitive grant process under Component II through a call for proposals in the country, and in the cases of Argentina and Mexico, in the participating areas.

- Component II:  Support to Productive Community Initiatives

  - The objective of this component is to support local economic development projects that incorporate transnational elements and assist low-income communities in the region.  All projects financed through this component will focus on income-generating activities.  Projects eligible for financing from the Program may include such activities as: direct support for micro and smaller enterprises; institutional or other support for cooperatives; support for community-based businesses or other organizations that might assist with developing the entrepreneurial capacities of their constituents.

  - Initiatives supported by this Program must relate directly and strategically to the transnational or inter-regional context. Such elements may include: (i) community groups in the participating countries that partner with diaspora organizations such as hometown associations, sports clubs, cultural clubs, local communities or other emigrant associations; (ii) small-scale producers and cottage industries that export to new markets, including diaspora markets; (iii) human capital investment, such as volunteerism, by diaspora organizations; (iv) remittance of financial resources, new skills, ideas or practices; and (v) initiatives in communities with significant out-migration. Within the Program goals of reaching low-income communities, priority will be given to projects submitted by NGOs or other eligible institutions serving minority or underserved populations such as people of African descent, youth, women and indigenous groups.

  - Grants will be made to nonprofit organizations that are legally based in the target countries including: local, regional or national organizations with a general experience in local economic development; foundations; business and local community associations; and technical/training institutions.  A general call for proposals will be issued in each country periodically and proposals will be reviewed on a competitive basis.  Proposals will be evaluated by the executing agency and a committee composed of local country funding partners, based on technical merit and coverage of the Program objectives, and on the expected ability of the proponent organizations to sustain extend, and duplicate the project upon completion of the grant.

  - A total of at least thirty three (33) grants are expected by the Program.  Grants will be awarded beginning in the first semester of the Program and thereafter on a periodic basis until the end of month forty eight (48) (“Commitment Period”) and all grant projects should conclude by month sixty (60) of the Program. Grants will have a minimum duration of twelve (12) months and a maximum duration of thirty six (36) months.  The Fund will require local matching resources from the beneficiary entity of a minimum of twenty per cent (20%) of the total cost (as cash or in kind contributions). Projects would range in size from fifty thousand dollars (US$50,000) to a maximum of two hundred and fifty thousand dollars (US$250,000) with an average project amount of one hundred and fifty thousand dollars (US$150,000).  The Bank shall contribute on average forty per cent (40%) of the total amount per project and HIP would contribute forty per cent (40%) on average. The Bank’s contribution will not exceed one hundred thousand dollars (US$100,000) for any given project.  This funding range was arrived at based on an overview of HIP’s grant programs in the region and the overall absorptive capacity of NGOs with local economic development experience.

- Component III:  Monitoring, Evaluation and Dissemination of the results

  - The objective of this component is two-fold: to monitor and evaluate the impact of the Program, and to disseminate the results.  Publications and materials for dissemination will be produced and distributed, including articles, fact sheets and a video.  These materials will be used in various forums, including conferences to be organized by the executing agency.  Two international conferences are anticipated to disseminate results and lessons learned for grantees, diaspora organizations, policy-makers and other actors.

  - In addition, this component will include the development of a screening instrument and monitoring system that will encompass specific environmental and social indicators for each of the projects supported in Component II.  For this, a consultant will be contracted to adapt the monitoring system already developed by HIP to include specific environmental and social parameters as well as other indicators specific to the context in the region.  Program and partner institution staff will then be trained in the use of environmental and social screening techniques and related indicators.

  - As part of the Program monitoring, grantee organizations are expected to attend two (2) grantee workshops per year.  During these workshops, grantees will receive technical assistance for institutional strengthening.  These topics include strategic and business planning and financial literacy, among many others. The workshops will also serve as an opportunity to assess the progress with grantee projects and discuss project sustainability.  Grantees will be required to submit written progress and financial reports on a biannual basis along with a final report due at the end of the funding period.

III.	Total Cost of the Program

3.01	The estimated cost of the Program is the equivalent of seven million three hundred and forty-five thousand dollars (US$7,345,000), in accordance with the following Budget:

Budget

(in US$)

| Activities | Bank (mif) | Local Counterpart (HIP) | Other Local Contributions (NGOs) | Total | % |
| --- | --- | --- | --- | --- | --- |
| I. Promotion and Local Capacity-Building for Productive Development | 43,275 | 34,875 | -- | 78,150 | 1.1 |
| II. Grant Fund to Support to Productive Community Initiatives | 1,920,000 | 1,920,000 | 960,000 | 4,800,000 | 65.8 |
| III. Monitoring, Evaluation and Dissemination of the results | 564,090 | 242,110 | -- | 806,200 | 11.0 |
| Administration | 397,769 | 877,572 | -- | 1,275,341 | 17.5 |
| Evaluations | 100,000 | -- | -- | 100,000 | 1.4 |
| Financial Audits | 62,500 | -- | -- | 62,500 | 0.9 |
| Contingencies | 152,366 | 25,443 | -- | 177,809 | 2.4 |
| Subtotal | 3,240,000 | 3,100,000 | 960,000 | 7,300,000 | 100 |
| Cluster Activities | 45,000 | -- | -- | 45,000 |  |
| TOTAL | 3,285,000 | 3,100,000 | 960,000 | 7,345,000 |  |
| Percentage | 45% | 42% | 13% |  |  |

IV.	Execution

4.01	Hispanics in Philanthropy (HIP) will be the Executing Agency and will be responsible for counterpart resources and for administering the grants.

- 4.02	For the administration of the activities, four (4) positions are anticipated.  A part-time Transnational Director, two (2) Program Managers (one manager will work full time on the project and the other part-time) and a full-time Program Assistant.  The Transnational Director will be responsible for: identifying and securing local funders; hiring, training and managing consultants and staff; supervising development and execution of the overall program; and will function as primary interlocutor with the Bank and other partners.  Each of the two (2) Program managers will be responsible for: overseeing the activities in three of the six (6) participating countries; manage grant-making rounds in their respective countries; develop additional outreach strategies that publicize the Program; provide support to the evaluation and documentation process; and manage overall communication and coordination at the sites with all the local partners and grantees. The two (2) Program Managers and Program Assistant will report directly to the Transnational Director.

- 4.03	For each country, HIP will identify and collaborate with local institutional partners interested in providing financing and support to the activities of the Program.  This approach has been utilized by HIP already in Argentina and the Dominican Republic.  In Argentina, Fundación Minetti, Fundación BankBoston and the Universidad de Católica de Córdoba will be the principal local institutional partners.  In the Dominican Republic, Fundación Falconbridge will be the lead organization of an expected consortium of institutional partners in that country.   In Mexico, the Hewlett and Ford Foundations have already contributed counterpart funds.  All of these partners have important on the ground experience in the countries and relevant economic development related experiences that will help assure effective project targeting.  For the remaining three countries, institutional partners will be identified and confirmed in the early part of the Program.

- 4.04	The gradual country roll out approach will allow the Executing Agency time to develop relationships with the most appropriate partners in each remaining country as well as allow the Program to incorporate lessons learned from the initial three (3) countries into the latter three (3).

V.	Monitoring and Evaluation

- 5.01	Monitoring:  The Executing Agency will prepare and submit to the Bank project progress reports within thirty (30) days after the completion of each semester and a final report within thirty (30) days from the final disbursement.  These reports will follow a format previously agreed with the Bank and will address project activities and finances, as well as results measured in terms of the indicators and benchmarks identified in the project’s logical framework. The Bank will utilize these reports to monitor Program implementation progress and to prepare a Project Completion Report.  For projects supported in Component II, the Bank may undertake periodic visits as part of its monitoring efforts.

- 5.02	Drawing on the budget item for cluster activities, the Bank will administer resources to cover the expenditures of cluster related activities such as workshops and the technical adviser costs.  The technical advisor will offer assistance to Executing Agencies of the different projects in the cluster, and will also provide assistance in the area of monitoring and data collection for the Bank.

- 5.03	Evaluations:  An intermediate and a final evaluation of the Program will be undertaken by external consultants contracted directly by the Bank with Program funds.  The mid-term evaluation will be prepared twenty four (24) months after the commencement of Program implementation or when sixteen (16) grants in Component II have been approved. A final evaluation will be conducted three months after the end of Program execution or when ninety five per cent (95%) of the Bank’s contribution has been disbursed.  For the mid-term evaluation, the consultant will consider, among other items: (i) total number of proposals with transnational elements received by HIP; and (ii) the overall quality of the proposals and whether adjustments in the guidelines need to be made.  For the final evaluation, the consultant will take into account: (i) the economic opportunities generated as a result of the grants provided in Component II; and (ii) the exact role and function of diaspora communities within the grant projects supported by the Program.  With its own financial resources distinct from the counterpart requirement, the executing agency has agreed to undertake an ex post evaluation of this Program one year after completion to measure the impact and assess the lessons learned. These results will be shared with the Bank.

- 5.04	During the Program’s execution, the Executing Agency will compile supervision and project evaluation indicators. These indicators are set forth in the Logical Framework of the Program and will be used by the Bank and HIP to gauge the overall impact and to assess the results.  HIP will provide access to all the information and documentation needed to conduct these evaluations.