- LEGIII/RG-797-04

- APPENDIX I

- THE PROGRAM

Diagnosis of Caribbean Private Sector Organizations and their Trade-related Services

I.	Objective

1.01	The general objective of the Program is to strengthen the capacity of Private Sector Organizations (“PSOs”) in the region to assist their clients in understanding and preparing for a more liberalized trading environment.

1.02	The specific objectives of the Program are to: (a) assess existing PSOs in the Caribbean Common Market (“CARICOM”) in terms of their institutional and technical capacity to provide clients with trade-related services; (b) identify gaps in respect of the demand for, and supply of, such services; (c) raise awareness among donors, governments and the private sector about these gaps and how they could be addressed in a positive socio-environmental manner; (d) recommend specific actions that could be taken at national and regional levels to support the development of Caribbean PSOs; and (e) identify PSOs that could act as Executors of Bank, MIF and other donor-financed programs.

II.	Description

The Program will consist of the following two (2) components:

2.01	A comprehensive diagnosis of existing PSOs in the region (both publicly and privately financed, and regional and national), including recommendations on how to strengthen national and regional activities aimed at promoting the private sector’s trade-related interests. The outputs of this component will be: (a) an analytical report and proposed action plan, and; (b) as an annex to that report, a matrix of existing national and regional PSOs in each CARICOM country and at a regional level. The matrix should catalog organizations at the national and regional level, describing in detail their mandate, institutional structure and the scope and quality of services offered.

2.02	A regional workshop to present the results of the diagnosis to relevant stakeholders in the region. The workshop would be organized prior to completion of the above-mentioned report so as to incorporate any recommendations emerging from that meeting.  The one-day workshop will be held in Trinidad and Tobago and will involve presentation of the consultant's draft report and discussion of the proposed action plan with stakeholders. Private sector representatives from all CARICOM countries, as well as heads of all private sector organizations analyzed in the report, and officials from key regional organizations (RNM, CARICOM Secretariat, etc.) will be invited.  These invitees will pay their own travel.

2.03	The consulting services required for the Program’s implementation include a Senior Consultant, who will be a French national, for six (6) months and local consultants in each of the fifteen (15) CARICOM member countries (estimated at one month per non-OECS country, and one month for the OECS countries combined). In accordance with TC Fund guidelines, the Bank will select and hire these consulting services.

2.04	The Program will be implemented over a six-month period. In month 1, the Senior Consultant will develop a questionnaire and matrix for the analysis of private sector institutions in the region. In month 2, local consultants will conduct in-country analysis using these tools. A network of contacts and points of communication between the consulting team and PSOs should be established during this period, and desk research should be completed. In months 3-5, the Senior Consultant will travel to the region to conduct additional fieldwork with assistance from the local consultants, including interviews with PSOs, relevant government entities and other stakeholders. A draft report and matrix will be delivered by the Senior Consultant at the end of month 5. Organization of the regional workshop and finalization of the diagnostic report will be carried out in the final month of the Program.

- III.	Cost and financing

- 3.01	The estimated cost of the Program is one hundred thirty thousand dollars (US$130,000), in accordance with the following categories of investment.

Cost and Financing

| Type of Expense (US$) | IDB | Local | Total |
| --- | --- | --- | --- |
| Senior Consultant (French national) |  |  |  |
| Honorarium 6 months @$10,000 | 60,000 |  | 60,000 |
| Travel: 4 trips @ $2,500 to and within the region | 10,000 |  | 10,000 |
| Travel: 65 days per diem @ $200 | 13,000 |  | 13,000 |
| Local Consultants (Local nationals) |  |  |  |
| Honorarium 10 consultants @ 1 month @$2,000 | 20,000 |  | 20,000 |
| Travel: Intra-regional travel 6 trips @ 500 | 3,000 |  | 3,000 |
| Travel: 6 * 3 days @ $200 plus 1*2 days | 4,000 |  | 4,000 |
| Workshop organization (logistics) |  | 10,000 | 10,000 |
| General local support |  | 10,000 | 10,000 |
| TOTAL | 110,000 | 20,000 | 130,000 |
| Senior Consultant as % of total IDB Contribution | 75.5% |  |  |
| Local Consultants as % of total IDB Contribution | 24.5% |  |  |