LEGIII/RG-584847-05

ANNEX

## THE PROJECT

Experiences in Promoting a Culture of Citizen Participation

I.	Objective

- 1.01	The Project aims to increase the awareness of civil society organizations and government’s institutions in the Region of the importance of building trust between the citizenry and their governments, and fostering a culture of engaged citizenry to strengthen democratic governance.

- 1.02	The Project’s specific objectives consist in: (a) the preparation of an historical overview of NGO’s evolution and contribution for the advancement of democratic societies, (b) the preparation of ten analytical essays that review experiences and draw lessons about fostering and maintaining effective citizen participation in economic and social development projects; (c) concrete guidelines for next-generation programs to expand effective and informed democratic participation, and (d) delineate significant new roles that civil society organizations, particularly community based groups and Non Governmental Organizations (NGOs), can and should play in building democratic societies.

### Description

In order to achieve the above-mentioned objectives, the Project will finance the following activities:

  - Essays

- 2.01	There are two inter-dependent parts to the Project. First, a review of the evolution of democratic participation over the past 60 years.  Then, reports will be prepared by the leaders of active civil society organizations in promoting the cause of civil society in Latin America, drawing explicit links to the growth of NGOs, community organizations’ concerns with democracy and civil society.  These analytical papers will offer perspectives on the past, but will focus particularly on new and emerging roles that community based groups and NGOs, can and should play in building democratic societies.

- 2.02	The initial essay will highlight changes in “democracy” in the world and the Region over the last 60 years. Note will be taken of such global changes, and of evolving views on how best to build civil society and democratic participation. This historical review will also embrace some of the key NGOs in the Region that have played important roles in constructing democratic societies in LAC.

- 2.03	The authors of the complementary analytical papers will be expected to recognize both the past and future of civil society and active citizen participation. Attention will be given to the current status of popular engagement, the rise of NGOs and community organizations specific examples of both successful and frustrated citizen participation. Tomorrow’s concerns of an informed citizenry are expected to be substantially different from yesterdays.  Future citizen engagement will be directly affected by a variety of now pervasive influences including email and the Internet, economic globalization and global dispersal of high tech industry, mass rural-urban population shifts, international worker migration with attendant cash remittances flows to home countries.  Issues emerging from these and more accustomed concerns – providing decent housing, reducing crime, preventing political corruption, gaining legal and economic equality for women—will surely continue to dominate public debate and expanded citizen involvement. The analytical papers must give attention to promising options for strengthening the role of civil society in this increasingly complex and interactive global society.

- 2.04	The themes and treatments in the analytical papers will operate within guidelines to be developed jointly by the project manager, the essayists and participants at the Project Planning meeting to be scheduled in the initial months of the project. In general terms, all ten analytical papers shall embrace the following aspects: (a) analysis of the experience on a particular feature of citizen participation, (b) How was trust building conducted and achieved? (c) How can a “culture of participation” be attained and/or how important is it for the success of programs, policies and ultimately democratic governance. These considerations may lead to conclusions as to how the local experiences can provide answers for types of citizen participation at the national or regional level, thus further strengthening democratic institutions and principles.

- 2.05	Upon completion of the draft analytical papers, a technical meeting will be convened for review and critiques of the document by peers in the field. The final report would include relevant commentaries received during this meeting.

  - Dissemination

- 2.06	Findings of the Project will be disseminated in several ways:

- Through the mass media, with discussions of findings, interviews and articles by the authors of the essays;

- Meetings convened by Esquel and other NGOs and civil society groups with industry and government representatives;

- Workshops with civil society organizations to share the findings and establishing the role civil society can play with governments to improve their policies and practices;

- On web-pages including links among NGOs and the Bank.  Webcasts will include videos of interviews and case study communities.

- 2.07	The studies shall provide concrete guidelines for government, civil society and multilateral institutions to fostering and maintaining effective citizen participation in economic and social development projects.  The project will also chart a future path for expanding effective democratic participation in the region.

III.	Total Cost of the Project

3.01	The estimated cost of the Project is the equivalent of one hundred and ninety-six thousand five hundred dollars (US$196,500), in accordance with the following Budget:

Budget

(in US$)

| Categories | FSO | Esquel |
| --- | --- | --- |
| I. Project management |  |  |
| 1.1 Project Director ($1,000/month @ 15 months 1/4 time) |  | 15,000 |
| 1.2 Project Associate (600/month @ 15 months 1/4 time) |  | 9,000 |
| II. Technical review workshops (2) |  |  |
| 2.1 Travel and accommodation for 15 Participants ($1,200 x 15 participants X 2 workshops) | 36,000 |  |
| 2.2 Meeting Accommodation ($1,000 x 2 workshops) | 2,000 |  |
| 2.3 Recording/Transcription ($1,000 x 2 workshops) | 2,000 |  |
| III. Essays and analytical pieces |  |  |
| 3.1 Principal Investigator/Editor for Essays ($2,000/month @ 8 months ½ time) 3.2 Travel & per diem: 2 trips @ 3,500 per trip | 16,000 7,000 |  |
| 3.3 Research Assistant (40 days @ 200 per day) | 8,000 |  |
| 3.4 Transcription and Translation (20 days @ $200 per day) | 4,000 |  |
| 3.5 Essays (10 essays @ $5,000 each) | 50,000 |  |
| 3.6 Equipment (video/tape recorders) |  | 10,000 |
| IV. Publication |  |  |
| 4.1 Book Publishing | 15,000 |  |
| 4.2 Web publishing |  | 2,500 |
| V. Dissemination |  | 10,000 |
| VI. Final financial audited report | 5,000 |  |
| VII. Contingencies | 5,000 |  |
| Total | 150,000 | 46,500 |

3.02	The resources of the Bank will finance the activities of, the Principal Investigator, Research Assistant, Translator and Consultant services for the ten (10) analytical papers; travel and accommodation for the technical workshop participants; meeting logistics; the editing and publication of documents and the final financial audited report. The executing agency will cover all expenses related to project administration and also contribute funds required for the preparation of multimedia material, web-page publishing and dissemination activities, estimated at forty six thousand five hundred dollars (US$46,500).

IV.	Execution

  - The FGEB President and the Principal Investigator, with the support of the Project Associate, will implement this Project. The President will be responsible for coordinating overall Project activities and ensuring its timely completion. The Principal Investigator will be responsible for liaising with the researchers, and will act as the focal point for coordinating and facilitating the planning, peer review meetings and other logistical concerns. The Project Associate will administer funds, arrange logistics and prepare financial and programmatic reports in coordination with the Project Director and Principal Investigator.

  - The Executing Agency will be responsible for: (a) the selection and contracting of consultants for the essays to be prepared, in accordance with applicable Bank policies and procedures; (b) prepare the final Terms of Reference for all consultant services and seek their Bank approval; (c) facilitate travel arrangements for the consultant services as well as their access to relevant sources of information for their research activities; (d) prepare agenda and organize all logistical aspects related to the technical review meetings; (e) ensure the full collaboration of all Esquel Group offices in the Region; (f) select and contract firms and / or individual consultants for the publishing of the essays in accordance with applicable Bank procedures, norms and policies; and (g) ensure dissemination of products such as through web-pages and additional events organized by Esquel Group offices in the Region once Project activities are completed.