LEGIII/RG-644767-05

THE ANNEX

THE PROGRAM

# A Comprehensive Assessment of Transboundary Conversation Opportunities in

Latin America

I.	Objective

1.01	The objective of the Program is to provide the technical data and policy analysis necessary to prioritize potential Transboundary Conservation Areas (“TBCAs”) in the Americas, and to facilitate the institutional, social, technical, and financial analyses necessary to design and develop regional TBCA projects.

II.	Description

2.01	Resources of the Program will be used to prepare a comprehensive analysis of transboundary conservation opportunities in the Americas. The transboundary conservation model integrates biodiversity conservation, the sustainable use and management of natural resources, and enhanced integration across national, state, or other political boundaries through harmonized regional agreements.

2.02	The Program will produce a policy and implementation manual and regional atlas that will help stimulate dialogue, consultation and technical support among representatives of the donor community, government and non-governmental organizations (“NGOs”), and community-based organizations (“CBOs”) from beneficiary countries in order to identify, evaluate, analyze and establish potential transboundary conservation areas in the Americas.  The manual will be produced in English and Spanish in hard copy and digital formats, with an expanded Executive Summary in Portuguese, and will include a thorough overview and mapped delineation of prioritized transboundary conservation opportunities in the Caribbean, Central and South America. Ten bound copies of the final document will be produced and delivered to the Bank in hard copy and five copies will be delivered in digital format.  Distribution of the hard copies will be determined by the Bank during the course of Program execution.

2.03	The analysis of potential sites will use qualitative and quantitative measures of national and regional sources, governmental and non-governmental institutional assets and constraints, and environmental benefits for each prioritized site as well as incorporating an initial screening of possibilities based on input from Bank Regional Operations Department staff and stakeholders in beneficiary countries. The Program will also include an assessment of lessons learned from selected TBCA projects and programs in Africa and Asia, and will demonstrate how the benefits from these models can be successfully adapted to the Americas.

The Program will finance the implementation of the following activities:

2.04	A qualitative analysis of lessons learned from Peace Park and TBCA programs in the Americas, Africa and Asia, and an interpretation of how these lessons can be applied in the Americas to improve the success of TBCA projects.  Consultation with donors, practitioners and beneficiaries engaged in TBCA projects on the ground in the regions of Africa and Asia, as well as in others -- including at least one project in America -- and a comprehensive analysis of existing literature documenting their experience and results to date, will be used to build a framework to support the selection, prioritization and evaluation of potential TBCA sites in the Americas.

2.05	A database that includes an annotated bibliography of reports, documents, publications and other visual and recorded materials addressing natural resource management and conservation in transboundary contexts.  The database will provide a source of reference materials on the scientific, policy and institutional aspects of TBCA planning, management, and evaluation.  The database will be accessible to beneficiaries in CD-ROM format and through the FTP site.

2.06	A prioritization and assessment of at least 10 potential TBCA sites in the Americas, including a mapped delineation of sites; a GIS interpretation of critical social, economic, institutional and environmental characteristics that can support transboundary conservation initiatives in each site; and an elaboration of criteria that can be used to select and prioritize additional potential TBCAs.  The results from this activity will be compiled into a visual and written text that can serve as a manual and atlas for TBCA planning and assessment in the Americas.  The sites selected will be generated from an initial broad list of potential regional TBCAs.  This list will first be narrowed down through detailed analysis of existing literature, and consultation with stakeholders, policymakers in Bank borrowing member countries (environmental and financial), relevant Bank Regional Operations Department staff, donors, and practitioners working with conservation and development projects throughout the Americas.  The project will then apply to this list of screened possibilities a qualitative and quantitative methodology to select and analyze 10 potential TBCA sites by using a mix of environmental, social, cultural, economic, infrastructure, institutional and policy criteria.  Each site analysis will be prepared as a case study. An interpretation of criteria and methodology used for the site selection will be included, in order to assist planners and practitioners with future potential TBCA site inventories and assessments. This methodology will include a detailed analysis of the institutional, social, economic and policy opportunities and risks that could affect the implementation of Regional projects, which considers transboundary conservation sites. The site assessment and prioritization will be supported by a comprehensive analysis of opportunities and risks for Bank and donor engagement in one or more the identified sites. The analysis of opportunities and risks will also be built from the lessons learned component of the project, and will demonstrate the institutional and policy measures that should be put in place in order to support the identification, design, implementation and evaluation of TBCA projects in the Americas. The results from this analysis will be posted on a File Transfer Protocol (“FTP”) site accessible through the Internet.

2.07	Development of a methodology for applying planning, training, and capacity-building tools to guide the application of the TBCA concept at specific potential sites in the Americas. The proposed methodology is designed to assist local and national governments, NGOs, CBOs, corporations, and donors as well as the Bank to develop the skills and capacity necessary to plan, administer, manage, and evaluate TBCA programs. The analysis of the methodology will provide beneficiaries with a strategy for the design of training and technical assistance support that can be used to guide the development of terms of reference for TBCA projects.

2.08	Production of a manual and atlas to guide regional and local policymakers, planners and managers in the selection, implementation and evaluation of transboundary conservation projects.  The manual and atlas will be produced in hard copy and digital formats in English and Spanish, also including an Executive Summary in Portuguese.  The manual and atlas will summarize the results achieved in the activities referred to in paragraphs 2.04 to 2.07 of this Annex, and be structured to serve as a user-friendly resource to guide the development of regional planning and site-specific transboundary conservation projects.

2.09	An initial information sharing workshop will be conducted with selected Bank staff, representatives from international and regional NGOs, national and subnational government authorities, business community representatives and donors to assess and validate the results from the Program, and identify opportunities to develop follow-on site based initiatives.  The workshop will be conducted in a forum conducive to participation from a wide audience, or may elect to use electronic mediums such as teleconferencing.  Invitees will be determined during the course of execution of the Program.  This initial workshop will be followed by a number of other dissemination and training activities, in particular side events and other programs that take advantage of various regional and international, such as meetings of parties to the UN Conventional on Biodiversity.  However, with the resources available for this Program, only an initial step in dissemination to build interest in follow-on work is included.

III.	Total Cost of the Program

3.01	The estimated cost of the Program is the equivalent of two hundred-thirty six thousand dollars (US$236,000), in accordance with the following Budget:

Budget

(in US$)

| Description | Bank | Beneficiary | Total |
| --- | --- | --- | --- |
| A. Case Study Analysis | 21,830 | 18,500 | 40,330 |
| Consultants - Honoraria - Travel (tickets + per-diem) Communications Reproductions/Materials | 18,000 2,930 200 700 | 16,000 1,800 500 200 | 34,000 4,730 700 900 |
| B. Database Development | 13,600 |  | 13,600 |
| Consultants - Honoraria - Travel (tickets + per-diem) Communications | 11,200 2,100 300 |  | 11,200 2,100 300 |
| C. TBCA Site Selection and Assessment | 57,700 | 54,500 | 112,200 |
| Consultants - Honoraria - Travel (tickets + per-diem) Communications Reproductions/Materials | 50,000 6,150 300 1,250 | 48,000 4,700 750 1,050 | 98,000 10,850 1,050 2,300 |
| D. Methodology Development | 13,055 | 13,500 | 26,555 |
| Consultants - Honoraria - Travel (tickets + per-diem) Communications Reproductions/Materials | 12,000 950 105 | 12,000 1,250 100 150 | 24,000 2,200 205 150 |
| E. Manual and Atlas publication | 17,160 |  | 17,160 |
| Consultants - Honoraria - Travel: Communications Reproduction/Materials | 14,000 2,200 300 660 |  | 14,000 2,200 300 660 |
| F. Training | 14,680 |  | 14,680 |
| Consultants - Honoraria - Travel: Communications Materials and Facility | 10,000 3,780 150 750 |  | 10,000 3,780 150 750 |
| 2. Audit | 4,000 |  | 4,000 |
| 3. Contingencies (5%) | 7,475 |  | 7,475 |
| TOTAL | 149,500 | 86,500 | 236,000 |

3.02	Resources of the Contribution will be used to finance: (a) the honoraria and travel of consultants; (b) materials and communications costs; (c) workshop logistical costs; and (d) editing, translation, publication and distribution costs for Program outputs.

3.03	Counterpart Resources to be provided by the Executing Agency through in kind services and infrastructure, will finance: (a) the remuneration and travel of the Executing Agency staff personnel assigned to the Program; and (b) infrastructure and services provided to the Program.

IV.	Execution

4.01	The Executing Agency will be responsible for conducting the competitive selection process and contracting of the consultants hired to develop and produce the manual, atlas and related products.  It will also supervise the development and implementation of the program FTP site and organize and conduct a training workshop for regional planners and decision makers in the methodology developed.  A Program Manager will supervise and administer the work of the overall Program.

4.02	Progress reports will be presented to the Bank by the Executing Agency on a quarterly basis, and will detail the activities of the previous 3 months of Program execution, the problems encountered and how they were solved, and details of expenditures and procurement to that date.  It will also include a plan of activities for the next 3 months of Program execution, together with projections of monthly expenditures and procurement activities. A final report should be presented 30 days before the completion of Program execution.  This report should detail the activities undertaken, the results obtained, problems encountered with their solution, and lessons learned from the Program.