LEGIII/RG-683759-06

ANNEX

THE PROJECT

Support for Consensus Building within the Rio Group

I.	Objective

1.01	The general objective of the Project is to help the Rio Group member states build consensus and common positions on pressing regional and international issues, and, as such, to develop trust among the member states, advance their political and economic integration agenda, and help them gain greater diplomatic weight in international fora.

II.	Description

- 2.01	In pursuit of the aforementioned objective, the Project will consist of the following two (2) components: (i) Preparation and Translation of Working Papers and Issue Statements; and (ii) Facilitation of Negotiations and Dissemination of Information on Policy Positions.

- Component 1. Preparation and Translation of Working Papers and Issue Statements

  - The Project will provide financing for the preparation of working papers on the pressing issues facing the Rio Group for discussion at Working Group meetings.

  - Under this component, one or more consultants will: (a) work with the Government of Guyana to select major challenges of key relevance to the Group in the year 2006; and (ii) prepare comprehensive analyses of the relevance of the challenges and a set of practical recommendations for overcoming them, particularly through concerted action among the Rio Group members. The Government of Guyana will consult with the Rio Group member states on the issues covered in the analyses.

  - The consultant will be available on an as-needed basis to work with the Ministry of Foreign Affairs on drafting up to twenty (20) issue statements on hemispheric and global political and economic issues of relevance to the Group, as selected by the Ministry. The Government of Guyana will circulate the draft issue statements for discussion and building consensus on them among the Rio Group members. After consensus has been reached, the Government of Guyana will issue the statements at the United Nations and other appropriate international fora.

  - The Project will also finance services to translate the working paper, the position papers and other Rio Group documentation from English into Spanish for the duration of the chairmanship.

- Component 2. Facilitation of Negotiations and Dissemination of Information on Policy Positions

  - This Component will provide technological support for the Pro Tempore Secretariat of the Rio Group (hosted by the Ministry of Foreign Affairs) to ensure effective communication among the Rio Group member states, including consultations on the documents prepared in Component 1 of this proposal.

  - The required inputs under this component are two-fold. First, the Project will finance hardware and software to upgrade electronic communication between the Pro Tempore Secretariat and the Rio Group members. Second, the technical cooperation will support the Ministry of Foreign Affairs in developing a comprehensive and inter-active Website on the Rio Group and its activities during Guyana’s Chairmanship. The new Website will allow member governments to access up-to-date information on Rio Group consultations, register on-line for meetings, and facilitate the dissemination of Rio Group activities to non-governmental audiences. Specifically, the Project will finance the acquisition of specialized software, while the Ministry of Foreign Affairs will assume responsibility for designing the Website.

  - The Project components will result in the following outputs: (a) one comprehensive working paper and up to twenty (20) draft issue statements on issues of importance to Rio Group members; (b) the  modernization of the communications and information systems between the Pro Tempore Secretariat and the member states of the Rio Group to facilitate the negotiations on the aforementioned agenda; and (c) the enhanced capacity of the Rio Group to reach consensus on priority issues for its members.

III.	Total Cost of the Project

3.01	The estimated cost of the Project is the equivalent of US$95,000, in accordance with the following Budget:

Budget

(in US$)

| Activities | Bank | Local Contribution | Total |
| --- | --- | --- | --- |
| Component 1: Preparation of Working Paper and Issue Statements | 49,300 | 11,000 | 60,300 |
| Component 2: Facilitation of Negotiations and Dissemination of Information on Policy Positions | 19,260 | 2,500 | 21,760 |
| Project Audit and Administration | 5,000 | 5,000 | 10,000 |
| Contingencies | 1,440 | 1,500 | 2,940 |
| TOTAL | 75,000 | 20,000 | 95,000 |

IV.	Execution

  - The Executing Agency will be the Ministry of Foreign Affairs of the Republic of Guyana. The Government of Guyana has appointed the Ministry of Foreign Affairs’ Director General as Project Manager with responsibilities for the Project’s day-to-day implementation. As the administrative head of the Ministry, the Director General will also be the official with oversight of the Rio Group chairmanship and the Pro Tempore Secretariat. The Project Manager will be the Secretariat’s focal point for all Project participants and the day-to-day contact for the Bank.

  - The Executing Agency will maintain an accounting system, which includes records and accounts, and will be able to generate financial statements to reflect the operations, resources and expenditures related to the Project. The accounting unit will prepare and submit statements of expenditures for reimbursement in accordance with Bank's procedures. The accounting unit will also be responsible for establishing internal control mechanisms and filing system containing the support documentation related to Project expenditures. The Ministry of Foreign Affairs will also open bank accounts specifically to receive Bank and counterpart funds.

- V.	Monitoring and Evaluation

  - Bank supervision. The Bank, though its Country Office in Guyana will be responsible for Project administration and general supervision, and will prepare a Project Completion Report (“PCR”).

  - Reports to be submitted by the Executing Agency. The Ministry of Foreign Affairs will submit the following reports to the Bank:

    - A Project execution timeline (condition for first disbursement).

    - A progress report six (6) months into execution, containing (i) information on the activities completed to date, which includes both achievements and problems encountered and proposed solutions; (ii) the execution of the budget by category and source of financing; (iii) an assessment of progress achieved with regard to expected Project outputs and outcomes; and (iv) a work and disbursement plan for the remainder of the execution time.

    - A final report, within thirty (30) days after the execution period ends, summarizing and evaluating all activities carried out under the project and detailing the application of funds contributed by the Bank and Counterpart resources. The report should describe how the various Project activities have contributed to achieving the Project’s objectives. The Project’s expected outputs and outcomes outlined in paragraph 2.08 above,  should be used as guidance for preparing this report.

    - A financial audit to be prepared in accordance with Bank policies and procedures.

- 5.03	Evaluation. Instead of an independent evaluation upon completion of the Project, the Project team will convene a meeting to discuss and assess whether and to what extent the Project has achieved its development objectives. The meeting will be held within forty five (45) days after the termination of the execution period. Besides the team members, participants in this meeting will include all relevant Bank units and representatives of the Executing Agency (via video conference). A draft of PCR will serve as an input to this final Project assessment, with a final version to be prepared after the meeting.