LEGIII/RG-660243-06

THE ANNEX

THE PROGRAM

# Regional Study on Disclosure of Political Finance

I.	Objective

1.01	The general objective of the Program is to improve political finance practices in Latin America to increase transparency and accountability and thereby raise public confidence in democratic institutions.

II.	Description

  - In order to achieve the above-mentioned objective, the Program will finance the following Components:

Component 1. Methodology and Matrix.

2.02	Beginning prior to this program, Transparency International (TI) will design the methods and indicators for measuring disclosure; the presentation of a draft methodology will be submitted to the Bank at the date of signature of the technical cooperation agreement. The Bank’s contribution will be used for an initial application of the methods in four Latin American countries.

2.03	The methodology will consist of a standardized reporting framework that includes an information matrix and a contextualizing guided narrative report. A single information matrix on disclosure will be applied across all the cases to facilitate comparisons - detailed terms of reference will be drafted to ensure cross-case comparability of the data. Country specialists familiar with disclosure will be commissioned to gather information to fill in the matrix in each of the four cases. The legal framework will be taken as a starting point only; experts will also look at how disclosure works in practice, working in consultation with specialists, practitioners and stakeholders.

Component 2. Survey.

- 2.04	Simultaneously a second methodology to gather data will be applied, conducting a small survey within each country to better understand how information that is disclosed is used. The country specialists will identify the government institutions practicing control of political finance, political party campaign leaders, journalists, NGOs and other stakeholders and survey their leaders about current usage of disclosed data and also the crucial data that is not disclosed and inhibits their ability to exercise control in practice.

- 2.05	Next, TI (with its staff experts, experts from its Advisory Council, a voluntary group with expertise on disclosure, and TCC) will review the data, to request, additional information where necessary to assure comparability. Each country specialist will also provide a narrative report to contextualize the findings and expand upon them.

Component 3: Guidebook

- 2.06	At the conclusion of the case studies, TI (in collaboration with The Carter Center, TCC) will prepare a short guidebook explaining the application of the methods and results in the four countries. The report will emphasize the comparative nature of the work, and may guide civil society organizations in other countries wishing to assess disclosure. Governments will find it useful in understanding the types of indicators that the international community is looking for when assessing disclosure and identifying good practice models.

- Component 4: Dissemination

- 2.07	Prior to the presentation of the findings (data) to the public, the preliminary project results will be presented to the electoral authorities of the four beneficiary countries for feedback and discussion on priorities and future strategy for political finance reform.

- 2.08	Findings of the project will be disseminated in three ways: 1) targeted meetings and expert consultations with government representatives; 2) workshops with civil society organizations aimed at sharing the findings and establishing the role civil society can play in pressuring governments to improve disclosure policies and practices; and 3) through mass media. Work with international, national and local media can help explain to the wider public why opaque financing of political parties and campaigns is such a problem and what can be done about it, and demonstrate which countries have been reluctant to improve their record on this issue, as well as presenting positive models for change.

III.	Total Cost of the Program

3.01	The estimated cost of the Program is the equivalent of ninety five thousand one hundred  and fifty dollars (US$95,150). The local counterpart will be thirty thousand and one hundred fifty dollars in kind (US$30,150). The Bank will provide sixty five thousand dollars (US$65,000) in accordance with the following Budget:

Budget

(in US$)

| Categories | # IADB |
| --- | --- |
| - I. Methodology - International Consultant ($3,500/month x 5 months, or 10 months at ½ time) - Travel international consultant to 4 countries ($1,500 x 4) | 23.500 17,500 6,000 |
| - II. Survey - 4 country surveys ($5,000 x 4) - Application surveys in 4 countries ($2,500 x 4) | 30,000 20,000 10,000 |
| - III. Dissemination - 3.1 4 In-country workshops (US$1,500 x 4 countries - 3.2. General expenses | 9,500 6,000 3,500 |
| - IV. Audited Report | 2,000 |
| ## Total | 65,000 |

IV.	Execution.

4.01	TI will manage the project in close collaboration with TCC. A detailed memorandum of understanding of roles and responsibilities for the different components of the project will be signed between both parties and presented to the Bank as a condition prior to first disbursement. TI will consult International IDEA on important aspects of the project.

4.02	The Project Co-coordinator based in Brazil will coordinate project execution. The co-coordinator will be responsible for liaising with the local experts in gathering and processing country data. The co-coordinator will also act as a focal point for coordinating and facilitating follow up work in the different countries.

4.03	The Bank may grant TI, The Carter Center or IDEA, upon its request, licenses free of charge, not exclusive, for the reproduction, distribution, dissemination and or publication of the works and documents produced with Bank resources.

The international consultant will coordinate and oversee the project, commissioning experts, coordinating with the advisory panel and project partners, producing reports, ensuring that deadlines are met, controlling quality and comparability, etc.

This sum covers the fee for the expert in each country and some of the costs he or she may incur in completing the task, such as internal travel (the reports may assess how disclosure works at encompass regional and local level elections and may look in detail at one or population centers in addition to the capital).