LEGIII/RG-375571-05

Mr. Jeremy Collymore

Coordinator

Caribbean Disaster Emergency

Response Agency - CDERA

Building #1 Manor Lodge
Lodge Hill, St Michael
Barbados

Ref:	Regional Nonreimbursable Technical Cooperation No. ATN/NP-8906-RG. Adaptation for Climate Change and Disaster Mitigation: Township Planning Strategies For Storm Surge in the Caribbean.

Dear Mr. Collymore:

This letter of agreement, the “Agreement”, between the Caribbean Disaster Emergency Response Agency, the “Beneficiary” or “CDERA”, and the Inter-American Development Bank, the “Bank”, which we are submitting for your consideration, is to formalize the terms of a grant of a nonreimbursable technical cooperation, the “Contribution” to the Beneficiary, up to the amount of one hundred and ninety thousand dollars of the United States of America (US$190,000), which shall be chargeable to the resources of the Netherlands Environmental Partnership Trust Fund. The Contribution will be used to finance the contracting of consulting services and procurement of goods necessary for the execution of a technical cooperation program to assist Caribbean countries in the development of adaptation strategies needed to deal with the impact of natural disasters and severe weather events anticipated to occur in association with climate change, and to strengthen their capacity for adaptation to this phenomenon, hereinafter the “Program”, which is set forth in the Annex of this Agreement. Unless otherwise stated in this Agreement, the term “dollars” shall hereinafter refer to the currency of legal tender in the United States of America.

This Agreement is entered into pursuant the Amendment dated as of September 17, 2004 to the Arrangement between the Netherlands Minister for Development Cooperation and the Inter-American and Development Bank dated December 5, 2000, with reference to the Project “The Netherlands and Inter-American Development Bank Partnership Program in Environment”.

The Bank and the Beneficiary agree upon the following:

First.  Components of the Agreement.  This Agreement consists of this part one, referred to as the “Special Conditions”; part two, referred to as the “General Conditions”, and the Annex, which are attached hereto.  The prevalence between the above-mentioned Sections and the Annex is established in Article 1 of the General Conditions.

Second.  Executing Agency.  The Executing Agency of this Program shall be the Bank, with the assistance of the Beneficiary.

Third.  Conditions Prior to First Disbursement.  The first disbursement of the Contribution shall be subject to the fulfillment, to the satisfaction of the Bank, of the conditions set forth in Article 2 of the General Conditions, as well as the presentation, by the Executive Agency, of a detailed initial work plan for Program activities.

Fourth.  Reimbursement of Expenditures Chargeable to the Contribution.  With the consent of the Bank, resources of the Contribution may be used to reimburse expenditures incurred or to finance those that may be incurred in the Program on or after October 24, 2004, and up to the date of this Agreement, provided that requirements substantially similar to those set forth in this Agreement have been fulfilled.

Fifth.  Disbursement Procedure.  Notwithstanding the provisions of Article 3 of the General Conditions,the Bank shall disburse the total amount of the Contribution as follows:

- Thirty five percent (35%) upon the fulfillment of the conditions prior to first disbursement referred to in Clause Third of this Special Conditions, signing of this Agreement and delivery of acceptable inception report;

- Twenty five percent (25%) following the acceptance, by the Bank, of the Intermediate Risk Assessment Report on Pilot Cities, and the Intermediate Action Report on Pilot Cities;

- Twenty five percent (25%) upon acceptance, by the Bank, of the Draft Toolkit; and

- Fifteen percent (15%) after the succesful participation and collaboration in National and Regional Workshops, and the acceptance, by the Bank, of the Final Report.

Sixth.  Deadlines.  (a) The period for execution of the Program shall be fifthteen (15) months, from the effective date of this Agreement.

(b)	The period for the last disbursement of the resources of the Contribution shall be eighteen (18) months from the effective date of this Agreement, which shall include the period required for the payment of independent auditors referred to in Article 11 of the General Conditions. Any part of the Contribution which has not been utilized within this period shall be canceled.

(c)	The aforementioned deadlines and any others that may be stipulated in this Agreement may be extended, when duly justified, with the written consent of the Bank.

Seventh.  Total Cost of the Program and Additional Resources.  (a) The Beneficiary undertakes to make timely provision of the resources required, hereinafter “the Counterpart Resources”, in addition to the Contribution, for the complete and uninterrupted execution of the Program. The total Counterpart Resources required is estimated to be the equivalent of twenty-five thousand dollars (US$25,000), of which four thousand dollars (US$4,000) will be provided in currency to make up a sum equivalent to two hundred fifteen thousand dollars (US$ 215,000), which is estimated to be the total cost of the Program.  These estimates do not reduce the obligation of the Beneficiary to provide any additional resources required to complete the Program.

(b)	The Counterpart Resources provided by the Beneficiary shall be used to finance the cost categories, which are chargeable to it, as established in the Program’s budget set forth in the attached Annex.

Eight.  Recognition of Expenses Chargeable to the Counterpart Resources.  The Bank may recognize as part of the Counterpart Resources expenditures incurred or which may be incurred in the Program on or after October 24, 2004, and up to the date of this Agreement, provided that requirements substantially similar to those set forth in this Agreement have been fulfilled.

Ninth.  Currencies for Disbursements. The Bank shall disburse the Contribution in dollars. The Bank may convert these convertible currencies into other currencies, including the local currency by applying the exchange rate indicated in Article 7 of the General Conditions.

Tenth. Use of Contribution, Contracting of Consulting Services and Procurement of Goods. The resources of the Contribution shall only be used for the payment of consulting services and goods originating from the member countries of the Bank. The hiring of consulting services shall be carried out in accordance with the Bank’s Policies and Procedures for the Procurement of Consulting Services, set forth in Document GN-2350-4 of January 2005. The Beneficiary confirms its familiarity with the provisions of said document. In the procurement of goods, the provisions set forth in Article 10 of the General Conditions shall be followed.

Eleventh.  Procedure for the Procurement of Consulting Services. (a) Contracting by the Bank.

(i)	In accordance with the Netherlands and Inter-American Development Bank Partnership Program in Environment, the Bank will hire a consulting firm or specialized entity via International Competitive Bidding (ICB) process to undertake the Pilot Projects (Component I) and the development of the Toolkit (Component II). The final selection of the firm or entity among those presenting proposals will be carried out  in consultation with the Beneficiary.

- The Bank undertakes to obtain the Beneficiary’s approval of the short list of Consultants prior to the signature of the consulting firm or specialized entity contract, and to inform the Beneficiary of the name of the Consulting Firm or specialized entity that has been contracted.

Twelfth. Information Disclosure. The Beneficiary undertakes to notify the Bank, in writing, within a maximum period of ten (10) working days from the date of signature of this Agreement, whether it considers any part of the Agreement to be confidential or sensitive, or whether it contains information that may adversely affect relations between the member countries and the Bank or between private sector clients and the Bank, in which case the Beneficiary undertakes to identify those provisions considered as such. In accordance with the Bank’s Disclosure of Information Policy, the Bank will make the text of this Agreement available to the public once it has been signed and has entered into effect, with the sole exception of that information which the Beneficiary has specifically identified as confidential, sensitive or adverse to relations with the Bank in the manner indicated in this paragraph.

Thirteenth.  Notice.  Any notice, request, or communication from one party to another by virtue of this Agreement shall be made in writing and shall be considered to have been made when the relevant documents is delivered to the addressee, unless the parties otherwise agree in writing.  If to the Beneficiary, such notice shall be addressed to the same address indicated above and to Facsimile: (246) 425-8854.

If to the Bank, such notice shall be addressed to:

Inter-American Development Bank

1300 New York Avenue, N.W.

Washington, D.C. 20577

U.S.A.

Facsimile: (202) 623-3096

Please confirm your acceptance of the terms and conditions of this Agreement, in representation of the Beneficiary, by signing and returning one of the originals to the Bank’s Country in Barbados.

This Agreement shall be signed in two (2) originals of equal tenor by duly authorized representatives, and will enter into force on the date of its signature by the Beneficiary.

Yours Faithfully, Inter-American Development Bank /s/ Nohra Rey de Marulanda _______________________ Nohra Rey de Marulanda Manager, Integration and Regional Programs Department

AGREED:

Caribbean Disaster Emergency

Response Agency

/s/ Jeremy Collymore

_____________________________

Jeremy Collymore

CDERA Coordinator

Date:	13-6-05

Place:  Washington, D.C.