LEGIII/RG-545673-05

# ANNEX D

OPERATING REGULATIONS

Grenada Reconstruction, Recovery, and Development Program

# I. 	PURPOSE

  - These Operating Regulations establish the terms and conditions for the execution of the Loan Program for Grenada ("the Program"). These Regulations should be interpreted together with the agreement set out in Loan Contract 1637/SF- RG entered into by the Inter-American Development Bank (IDB) and the Caribbean Development Bank (CDB) on July 18, 2005.

# II. 	DEFINITIONS

  - CDB: Caribbean Development Bank (“the Borrower”).

  - GOGR: Government of Grenada.

  - IDB: Inter-American Development Bank

  - Loan Contract: Agreement between IDB and CDB as specified in paragraph 1.1.

  - Loan Funds: Funds received by CDB under the Loan Contract and on-lent by CDB to the Government of Grenada or to entities authorized to do business in Grenada, for the purpose of financing eligible sub-projects.

  - Regulations: These Operating Regulations.

  - Sub-projects: Individual activities financed with Loan Funds lent by CDB to the sub-borrowers.

  - Sub-borrowers: Recipients of Loan Funds lent by CDB for individual sub-projects contemplated by the terms of the Program.

  - Sub-loans: The Loan Funds lent to Sub-borrowers.

# III. 	PURPOSE AND DESCRIPTION OF THE PROGRAM

  - The purpose of the Program is to provide IDB resources to CDB to provide an effective mechanism to support the economic recovery and reconstruction of Grenada in the aftermath of Hurricane Ivan that hit the island in September 2004.

  - The funds of the Program will be available to CDB to finance investment projects in the public and private sectors in Grenada. The following areas (lines of activity) will be eligible: (i) housing infrastructure on properties with clear land titles or a valid long-term leasehold contract on the land, (ii) environmental and public infrastructure reconstruction, and (iii) business revitalization. Each line of activity will constitute a separate component of the program.

  - The resources of the Program consist of up to US$10 million in funds from the IDB's Fund for Special Operations, and up to US$1.1 million in counterpart funding to be provided by the Sub-borrowers and/or beneficiaries.

# IV. 	ELIGIBILITY OF THE PROJECTS

#### The projects to be financed with Loan Funds will be specific development projects that are technically, socially, economically, financially, and environmentally viable and sound. To ensure environmental sustainability of the sub-projects, CDB will apply its Environmental Review Guidelines and Guidelines for the Social Analysis of Development Projects in order to classify proposed sub-projects based on their environmental and social impacts, and to determine the corresponding breadth and depth of the socio-environmental analyses and impact management measures required. Projects meeting the eligibility criteria specified below will be selected on a first-come-first-served basis.

#### Housing infrastructure component. The following specific eligibility criteria will be considered by CDB when funding housing infrastructure activities to ensure that: (i) when the beneficiary takes possession, he or she will also have clear title to the property or a valid long-term leasehold on the land; (ii) the site is in a safe area; (iii) the site complies with all relevant urban regulations (e.g. land use, zoning requirements, etc.); (iv) the site has access to primary transportation, water, and power networks; (v) the housing complies with appropriate building codes; and (vi) an effective beneficiary selection mechanism is in place that targets vulnerable and low-income households. (see also paragraph 4.9 below).

#### In addition, Environmental Management Plans (EMPs) and environmental specifications will be incorporated into bidding documents and construction contracts. Contractors or other executing entities must obtain construction permits as well as authorizations or permits for the use of natural resources. Any donated, prefabricated houses must meet the National Building Code standards.

#### Environmental and public infrastructure reconstruction component. The following procedures and criteria will be applied to ensure that reconstruction is not done in vulnerable areas, and that there is adequate community participation. Furthermore CDB will take into consideration government priorities in selecting eligible sub-projects.

#### Construction contractors or other executing entities will be required to meet technical environmental specifications agreed upon by CDB and the IDB, which will be incorporated into construction contracts. In addition, contractors must obtain the applicable permits, concessions or authorizations for the use of natural resources. In the case of Infrastructure Rehabilitation, Environmental Management Plans (EMP) will be required in addition to the preceding requirements. The EMP will be part of bidding documents and construction contracts. (see also paragraph 4.9 below)

#### Business revitalization component. Funds of the Program can be used to establish a credit line to finance private sector business revitalization sub-projects to enterprises affected by Hurricane Ivan. The credit facility will have the following characteristics: (i) CDB will act as the second-tier financial institution for this line of credit and will lend only to eligible first-tier financial institutions that provide financing to businesses in Grenada; (ii) it will be a multisectoral credit line providing medium/long-term resources to businesses in all sectors of the economy for reconstruction and recovery activities.3 (Funds cannot be used for working capital financing); (iii) first-tier institutions will be advised to mitigate their credit risk by requiring clients to obtain adequate insurance coverage for the investments financed; (iv) the maximum amount for the size of the sub-loans to the final beneficiaries will be US$1 million; and (v) the wholesale lending rate of CDB to first-tier financial institutions will be market-based. A more detailed specification will be contained in the Credit Regulations. (See paragraph. 4.8) The retail lending rate to final sub-borrowers will be freely set by the first-tier institutions. CDB will channel the funds to the first-tier financial institutions directly.

#### All reconstruction and repair of structures related to business revitalization will be required to meet the specifications of the National Building Code. In addition, building contractors or other executing entities must obtain required construction permits.

#### Credit regulations for this credit line (private enterprise financing) will be prepared prior to its implementation with resources from this Program. The credit regulations will (a) assure that only financially sound intermediaries participate in the program, (b) include methodology for determining the market rate of interest on, and tenor of, loans from CDB to the intermediary, (c) specify eligibility criteria for the final beneficiaries, (d) make reference to construction and environmental standards for the projects financed (as noted in paragraphs. 4.1 and 4.7 and (e) include such other provisions as considered appropriate by CDB and IDB. These regulations shall be reviewed and agreed by CDB and IDB. The loan agreements between CDB and participating first-tier intermediaries will be consistent with these credit regulations.

#### General. Regarding the housing sites and services component and the business reconstruction component, an exclusion list will be applied which prohibits construction on sites located in the following: (i) environmentally sensitive areas (wetlands, primary forest, etc.); (ii) protected natural ecosystems (national parks, wildlife refuges, etc.); (iii) areas prone to natural hazards (floods, geotechnically unstable, etc.); and (iv) sites requiring extensive earth movement (cut and fill) or significant intervention of vegetation or water bodies.

#### Any economic reactivation activity should only be funded with resources from this Program if the corresponding sector policies and legal and institutional framework are adequate as determined in accordance with the pertinent CDB guidelines and policies.

# V. 	TERMS AND CONDITIONS OF THE SUB-LOANS

5.1	CDB will apply the following terms and conditions for sub-loans made under the Program:

a. 	Tenor: Up to forty years, including ten years' grace. No grace period will be granted for interest payments. Tenor on loans to first-tier intermediaries participating in the business revitalization component will be of shorter duration, to be specified in the credit regulations.

b. 	Rate of Interest: The rate of interest to be charged to a sub-borrower by CDB for the housing infrastructure and environmental mitigation and public reconstruction components will be the same rate as that charged to the relevant sub-borrower on loans from its Special Development Fund (Unified) resources. The rate of interest charged to first-tier financial intermediaries for the credit component will be market-based as specified in paragraph 4.6 above.

5.2 	Additionally, CDB will:

a. 	require the sub-borrowers to ensure that the proceeds of the sub-loans be used exclusively to purchase the goods and services required to execute the respective sub-project;

b. 	secure the right of CDB and IDB to inspect the machinery and equipment, sites, works and other aspects of the sub-project during its execution;

c. 	require the sub-borrower to supply the information that CDB may reasonably request in relation to the sub-project;

d. 	require the sub-borrower to ensure that the acquisition of goods and services will be made according to the principles of efficiency and economy;

- obtain the right to suspend disbursements of the sub-loan if the sub-borrower defaults in the fulfillment of any of its obligations;

- require that all sub-projects have measurable performance criteria that demonstrate the effectiveness of the sub-project in meeting its development objectives, and that benchmark values, and target values for project implementation and completion are established and agreed with the borrower as part of the sub-loan agreements; and,

- include provisions in the sub-loan agreements to ensure appropriate maintenance of equipment or works purchased with Loan Funds, as well as requiring periodic reports regarding the sub-borrower’s maintenance programs.

5.3 	The Loan Funds can only be used to finance up to 90% of the total cost of projects in Grenada. The Loan Funds may be blended with the other loan resources of CDB, in proportions to be determined by CDB.

5.4 	Consistent with IDB and CDB policies currently in force, the Loan Funds may not be used to finance:

a. 	the payment of debts or the refinancing of loans;

b. 	the purchase of shares, bonds, participations in private-sector enterprises, or other securities;

c. 	sub-projects which do not comply with CDB's environmental regulations and with those of Grenada;

d. 	taxes or duties;

e. 	military equipment; and

f. 	the acquisition of goods and services from countries, which are not members of CDB or IDB.

# VI.	PROCUREMENT and RETROACTIVE FINANCING

6.1 	CDB procurement procedures will be used with the following provisions:

      - Eligibility for procurement using the resources of the loan should be open only to IDB member countries and CDB member countries;

      - With the non-objection of IDB, loan resources may be to used to finance execution of works by force account, including community self-help programs, in an amount not to exceed US$2 million;

      - IDB reserves the right to carry out, at any stage of the procurement process, ex-ante or ex-post review of the procedures being followed;

      - All bids may be rejected, after consultation with CDB, if the lowest evaluated bid exceeds the estimate by an amount deemed by CDB to provide a reasonable justification. In such cases, with the approval of CDB, the executing agency may call for new bids from at least all who were invited to bid in the first instance.

6.2 	Retroactive financing, consistent with the provisions of section 3.03 of the special conditions of the Loan Contract, in an amount not to exceed US$500,000 may be used for the housing infrastructure component.

# VII.	AUDITS, INSPECTIONS AND SUPERVISION

7.1 	CDB and the IDB reserve the right to audit and inspect the sub-projects, on an ex-post basis, to verify the correct application of the Loan Funds and compliance with these Operating Regulations. CDB will inspect each sub-project, at least once a year during execution, to determine the compliance with environmental regulations, implementation benchmarks, and performance indicators, and agree on measures to ensure compliance.

7.2 	If CDB determines that a sub-project is not following the relevant environmental guidelines, CDB will:

a.	inform the sub-project executing entity of the lack of compliance;

- inform the Government of Grenada;

- require enforcement of applicable sanctions; and

- in case remedial measures are not taken, cease disbursements on the sub-project until it is in compliance with the relevant environmental regulations.

7.3	To facilitate effective supervision and evaluation of the loan by the IDB, CDB will provide to the IDB copies of the sub-project appraisal reports, sub-project supervision reports, sub-project completion reports as well as semi-annual supervisory reports of the sub-projects financed with Loan Funds and any other evaluation of the financed sub-projects once they are completed. These reports will include an assessment of the sub-project’s performance and the specification of remedial measures, when necessary. CDB will also make available to the IDB data from its Project Performance Evaluation System (PPES). In addition, CDB will provide a copy of its annual report on the implementation of projects, which provides data on all CDB projects in execution.

# VIII. MODIFICATION OF THESE OPERATING REGULATIONS

8.1 	CDB can request modifications to these Operating Regulations, in order to adapt the Program to new conditions that may present themselves during the execution of the Program. Any modification to these Regulations will become effective as and when the IDB expresses its agreement in writing.

8.2	These Regulations will become effective on the date that the IDB makes Loan Funds available for re-lending pursuant to IDB Loan 1637/SF-RG.

i.e. Construction will be limited to areas not prone to natural hazards.

Such as government agencies that carry out construction directly by force account.

3 CDB’s definition of medium term (4 – 7 years) and long term (8+ years) will be used.