## Detailed Procurement Plan
PROCUREMENT PLAN INITIAL LOAD INFORMATION (ONGOING AND/OR LAST PRESENTED)
WORKS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount, in JA$: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method | Comments
[7 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
MNS | Renovation & Expansion of Gayle Multi-Purpose Centre |  | National Competitive Bidding |  | 1122a | 58300000 | 451937.9845 | 100 |  | Component 1 | Ex-Ante | 2017-08-01 | 2017-10-01 | In Process
MNS | Repairs - Glendevon Centre |  | Shopping |  | 18-1122a | 2500000 | 19379.845 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Infrastructural Works - Parade Gardens Community Centre |  | Shopping |  | 18-1122b | 8000000 | 62015.5039 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Repairs - Dela Vega Community Centre |  | Shopping |  | 18-1122c | 3500000 | 27131.7829 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Repairs - York Town Community Centre |  | Shopping |  | 18-1122d | 1500000 | 11627.907 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Retrofittiing of VSD Office - St. Catherine & Kingston |  | Shopping |  | 18-1311(i) | 8195700 | 63532.5581 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Retrofitting of Parish Courts for Mediation |  | Shopping |  | 1313(i) | 4000000 | 31007.7519 | 100 |  | Component 3 | Ex-Post | 2017-04-01 | 2017-04-01
MNS | Retrofitting of RJ Centres |  | Shopping |  | 18-1315(i) | 10000000 | 77519.3798 | 100 |  | Component 3 | Ex-Post | 2018-06-01 | 2018-06-01 |  | Activity to be carried out on an ongoing basis
MNS | Minor Repairs - CSJP Offices |  | Shopping |  | 18-1611a | 500000 | 3875.969 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Peremiter Fencing - Effortville Primary School |  | Shopping |  | 1611ah | 5974300 | 46312.4031 | 100 |  | Component 1 | Ex-Post | 2017-08-01 | 2017-08-01 | In Process
GOODS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount, in JA$: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method | Comments
[7 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
MNS | Parenting Programme - Stationery and Course Materials |  | Shopping |  | 18-1111a(ii) | 1800000 | 13953.4884 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis across alll 3 regions
MNS | Parenting Programme - Certificates |  | Shopping |  | 118-1111a(iii) | 550000 | 4263.5659 | 100 |  | Component 2 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Parenting Program -Polo Shirts ,Tote Bags, etc. |  | Shopping |  | 1111a(iv) | 350000 | 2713.1783 | 100 |  | Component 1 | Ex-Post | 2017-05-01 | 2017-05-01 | In Process
MNS | MWAM - Brochures |  | Shopping |  | 18-1111b(ii) | 200000 | 1550.3876 | 100 |  | Component 1 | Ex-Post | 2018-03-01 | 2018-03-01
MNS | MWAM - Men's Day - Trophies |  | Shopping |  | 1111b(xviii) | 50000 | 387.5969 | 100 |  | Component 1 | Ex-Post | 2017-11-01 | 2017-11-01
MNS | MWAM- Men's Day - Games |  | Shopping |  | 1111b(xix) | 30000 | 232.5581 | 100 |  | Component 1 | Ex-Post | 2017-11-01 | 2017-11-01
MNS | Psycho-Ed Workshops - Stationery |  | Shopping |  | 18-1112a(ii) | 720000 | 5581.3953 | 100 |  | Component 1 | Ex-Post | 2018-01-17 | 2018-01-17 |  | Activity to be carried out on an ongoing basis across alll 3 regions
MNS | Capacity Building Schools -Stationery |  | Shopping |  | 18-1112b(ii) | 450000 | 3488.3721 | 100 |  | Component 1 | Ex-Post | 2018-01-17 | 2018-01-17 |  | Activity to be carried out on an ongoing basis across alll 3 regions
MNS | Group Counselling -Therapeutic Materials |  | Shopping |  | 18-1112c(ii) | 152000 | 1178.2946 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Group Counselling - Stationery |  | Shopping |  | 18-1112c(iii) | 96000 | 744.186 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis across alll 3 regions
MNS | Psychometric Instruments |  | Direct Contracting |  | 18-1112d | 1467500 | 11375.969 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Direct contracting is most appropriate given that the required instruments are proprietary and are only available from one source, PAR Inc. The Bank's no-objection received vide CCB/CJA/1023/2014 and CCB/CJA/246/2016.
MNS | Life Skills - Stationery & Supplies |  | Shopping |  | 18-1112e(ii) | 800000 | 6201.5504 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis across alll 3 regions
MNS | Good News Campaign - Brochures |  | Shopping |  | 18-1115b(i) | 300000 | 2325.5814 | 100 |  | Component 1 | Ex-Post | 2018-02-01 | 2018-02-01
MNS | Good News Campaign - Paraphernalia |  | Shopping |  | 18-1115b(ii) | 600000 | 4651.1628 | 100 |  | Component 1 | Ex-Post | 2018-02-01 | 2018-02-01
MNS | Good News Campaign - PIOJ - Booklets |  | Shopping |  | 18-1115b(iii) | 100000 | 775.1938 | 100 |  | Component 1 | Ex-Post | 2018-09-18 | 2018-09-18
MNS | CSJP Youth Ambassador - Launch - Press Kits |  | Shopping |  | 1115b(vii) | 80000 | 620.155 | 100 |  | Component 1 | Ex-Post | 2017-11-01 | 2017-11-01
MNS | Mixer Adapter |  | Shopping |  | 18-1115c | 10000 | 77.5194 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Computers, Related Equipment, Software & Supplies |  | Shopping |  | 18-1115d | 320000 | 2480.6202 | 100 |  | Component 1 | Ex-Post | 2018-04-01 | 2018-04-01
MNS | Furniture & Equipment - Community Centres |  | Shopping |  | 18-1122e | 3608000 | 27968.9922 | 100 |  | Component 1 | Ex-Post | 2018-01-17 | 2018-01-17 |  | Activity to be carried out on an ongoing basis
MNS | Stakeholder Workshops - SDC/VPA Findings |  | Shopping |  | 18-1123a | 750000 | 5813.9535 | 100 |  | Component 1 | Ex-Post | 2018-02-18 | 2018-02-18 |  | Activity to be carried out on an ongoing basis across alll 3 regions
MNS | Support to CACs - Trophies & Medals |  | Shopping |  | 18-1124a | 2000000 | 15503.876 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Support to CACs - T-Shirts/Gears |  | Shopping |  | 18-1124b | 1500000 | 11627.907 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Goals for Life -Football Gears and Equipment |  | Shopping |  | 18-1124d | 3000000 | 23255.814 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Goals for Life -Stationery |  | Shopping |  | 18-1124e | 500000 | 3875.969 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | VST - Stationery |  | Shopping |  | 18-1212a(i) | 80000 | 620.155 | 100 |  | Component 2 | Ex-Post | 2018-01-17 | 2018-01-17 |  | Activity to be carried out on an ongoing basis across alll 3 regions
MNS | VST -Refreshments and Venue |  | Shopping |  | 1212b | 4290000 | 33255.814 | 100 |  | Component 2 | Ex-Post | 2017-01-17 | 2017-01-17 |  | Activity to be carried out on an ongoing basis across alll 3 regions
MNS | Pre-VST - Stationery |  | Shopping |  | 1214a | 350000 | 2713.1783 | 100 |  | Component 2 | Ex-Post | 2017-01-17 | 2017-01-17 |  | Activity to be carried out on an ongoing basis across alll 3 regions
MNS | Pre-VST -Refreshments and Venue |  | Shopping |  | 1214b | 4020000 | 31162.7907 | 100 |  | Component 2 | Ex-Post | 2017-01-17 | 2017-01-17 |  | Activity to be carried out on an ongoing basis across alll 3 regions
MNS | Job Readiness - Refreshments and venue |  | Shopping |  | 1221a | 13000 | 100.7752 | 100 |  | Component 2 | Ex-Post | 2017-01-17 | 2017-01-17 |  | Activity to be carried out on an ongoing basis across alll 3 regions
MNS | On-the-Job - Safety Gears |  | Shopping |  | 1222a(i) | 9725000 | 75387.5969 | 100 |  | Component 2 | Ex-Post | 2017-04-01 | 2017-04-01 |  | Activity to be carried out across alll 3 regions
MNS | On-the-Job - IDs |  | Shopping |  | 1222a(ii) | 100000 | 775.1938 | 100 |  | Component 2 | Ex-Post | 2017-04-01 | 2017-04-01
MNS | On-the-Job -Certificates and related items |  | Shopping |  | 1222a(iii) | 100000 | 775.1938 | 100 |  | Component 2 | Ex-Post | 2017-04-01 | 2017-04-01
MNS | On-the-Job -Chairs |  | Shopping |  | 1222a(iv) | 100000 | 775.1938 | 100 |  | Component 2 | Ex-Post | 2017-04-01 | 2017-04-01
MNS | On-the-Job -Refreshments |  | Shopping |  | 1222a(v) | 300000 | 2325.5814 | 100 |  | Component 2 | Ex-Post | 2017-04-01 | 2017-04-01
MNS | VST - Stationery |  | Direct Contracting |  | 18-1212a(ii) | 20000 | 155.0388 | 100 |  | Component 2 | Ex-Post | 2017-01-17 | 2017-01-17 |  | This includes the purchase of CSJP branded envelopes which are only obtainable from one source, the Jamaica Printing Services Limited. Bank's no-objections received vide CCB/CJA/1023/2016, 298/2016, 295/2016, 245/2016
MNS | Job Readiness - Stationery |  | Shopping |  | 18-1221b | 40000 | 310.0775 | 100 |  | Component 2 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | On-the-Job Training - Safety Gears |  | Shopping |  | 18-1222a | 2500000 | 19379.845 | 100 |  | Component 2 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out across alll 3 regions
MNS | Summer Employment - Stationery |  | Shopping |  | 18-1222b(ii) | 50000 | 387.5969 | 100 |  | Component 2 | Ex-Post | 2018-07-17 | 2018-07-17
MNS | Office Furniture and equipment including IT |  | Shopping |  | 18-1311(i) | 5000000 | 38759.6899 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis; No single engagement is to exceed US $25,000
MNS | Stakeholder workshops - Stationery |  | Shopping |  | 18-1311(iii) | 160000 | 1240.3101 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Cultural Resocialisation - Therapeutic Tools |  | Shopping |  | 18-1311c(ii) | 1840000 | 14263.5659 | 100 |  | Component 3 | Ex-Post | 2018-07-01 | 2018-07-01 |  | Activity to be carried out on an ongoing basis
MNS | Cultural Resocialisation - Stationery |  | Shopping |  | 18-1311c(iii) | 860000 | 6666.6667 | 100 |  | Component 3 | Ex-Post | 2018-07-01 | 2018-07-01 |  | Activity to be carried out on an ongoing basis
MNS | Cultural Resocialisation - T/Polo Shirts |  | Shopping |  | 18-1311c(iv) | 1100000 | 8527.1318 | 100 |  | Component 3 | Ex-Post | 2018-07-01 | 2018-07-01 |  | Activity to be carried out on an ongoing basis
MNS | SIP - Therapeutic Tools |  | Shopping |  | 18-1311c(vi) | 990000 | 7674.4186 | 100 |  | Component 3 | Ex-Post | 2018-06-01 | 2018-06-01 |  | Activity to be carried out on an ongoing basis
MNS | SIP - Resource Materials and stationery |  | Shopping |  | 18-1311c(vii) | 660000 | 5116.2791 | 100 |  | Component 3 | Ex-Post | 2018-06-01 | 2018-06-01 |  | Activity to be carried out on an ongoing basis
MNS | SIP - Certificates |  | Shopping |  | 18-1311c(viii) | 30000 | 232.5581 | 100 |  | Component 3 | Ex-Post | 2018-06-01 | 2018-06-01 |  | Activity to be carried out on an ongoing basis
MNS | Overcomers In Action - Resource Material and Stationery |  | Shopping |  | 18-1311c(x) | 180000 | 1395.3488 | 100 |  | Component 3 | Ex-Post | 2018-05-01 | 2018-05-01
MNS | Overcomers In Action - Graduation -Certificates and tokens |  | Shopping |  | 18-1311c(xii) | 247500 | 1918.6047 | 100 |  | Component 3 | Ex-Post | 2018-05-01 | 2018-05-01
MNS | Overcomers In Action - Therapeutic Tools |  | Shopping |  | 18-1311c(xiii) | 495000 | 3837.2093 | 100 |  | Component 3 | Ex-Post | 2018-05-01 | 2018-05-01
MNS | Public Awareness - Brochures and Paraphernalia |  | Shopping |  | 18-1311e(i) | 1000000 | 7751.938 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Training - Stationery |  | Shopping |  | 18-1311h(ii) | 120000 | 930.2326 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | West Kingston - Training of VSD Volunteers - Stationery |  | Shopping |  | 18-1311h(iv) | 60000 | 465.1163 | 100 |  | Component 3 | Ex-Post | 2018-06-01 | 2018-06-01
MNS | Training - Stationery and resource materials |  | Shopping |  | 18-1312c(ii) | 320000 | 2480.6202 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Legal Aid Fairs - Resource Materials |  | Shopping |  | 18-1312d(ii) | 200000 | 1550.3876 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Mobile Unit -Branded Table Cloth |  | Shopping |  | 18-1312f(i) | 15000 | 116.2791 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Mobile Unit -Brochure Holders |  | Shopping |  | 18-1312f(ii) | 10000 | 77.5194 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Qualifying Training -Stationery and Course Material |  | Shopping |  | 18-1313b(ii) | 1200000 | 9302.3256 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 | In Process | Activity to be carried out on an ongoing basis
MNS | Advanced Training - Stationery & Course Material |  | Shopping |  | 18-1313c(ii) | 852000 | 6604.6512 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Furniture, Equipment and Appliances for RJ Centres |  | Shopping |  | 18-1315(i) | 2000000 | 15503.876 | 100 |  | Component 3 | Ex-Post | 2018-06-01 | 2018-06-01 |  | Activity to be carried out on an ongoing basis
MNS | Stationery & Office Supplies |  | Shopping |  | 18-1315(ii) | 700000 | 5426.3566 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 | In Process | Activity to be carried out on an ongoing basis
MNS | RJ Week - Retractable Banners |  | Shopping |  | 18-1315(iii) | 135000 | 1046.5116 | 100 |  | Component 2 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | RJ Week - Oxford Shirts |  | Shopping |  | 18-1315(iv) | 135000 | 1046.5116 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | RJ Week - Conference Materials |  | Shopping |  | 18-1315(v) | 250000 | 1937.9845 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | RJ Multi-Media campaign - Paraphernalia |  | Shopping |  | 18-1315(vi) | 1000000 | 7751.938 | 100 |  | Component 3 | Ex-Post | 2018-11-01 | 2018-11-01
MNS | RJ Week - Conference Parapernalia |  | Shopping |  | 18-1315(xxiii) | 250000 | 1937.9845 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Judiciary Training - Stationery |  | Shopping |  | 18-1315b(iii) | 700000 | 5426.3566 | 101 |  | Component 3 | Ex-Post | 2018-04-01 | 2018-04-01
MNS | RJ Volunteers - Graduation - Certificates and awards |  | Shopping |  | 18-1315b(vii) | 100000 | 775.1938 | 100 |  | Component 3 | Ex-Post | 2018-05-01 | 2018-05-01
MNS | Staff Development - Stationery and resource materials |  | Shopping |  | 18-1315b(ix) | 40000 | 310.0775 | 100 |  | Component 3 | Ex-Post | 2018-06-01 | 2018-06-01
MNS | Training Workshops - Stationery |  | Shopping |  | 18-1316(i) | 100000 | 775.1938 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Stationery & Office Supplies |  | Shopping |  | 18-1316(iv) | 200000 | 1550.3876 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis.
MNS | Case Management -Stationery |  | Shopping |  | 18-1511b | 1030000 | 7984.4961 | 100 |  | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | JCO - Maintenance of Licence |  | Direct Contracting |  | 18-1512 | 1500000 | 11627.907 | 100 |  | Component 5 | Ex-Post | 2018-06-01 | 2018-07-01 |  | Access to the software is only obtainable through one source, Ministry of Water, Land, Environment and Climate Change.
MNS | M & E -Hardware & Software |  | Shopping |  | 18-1513a | 565000 | 4379.845 | 100 |  | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | M & E -Furniture & Office Supplies |  | Shopping |  | 18-1513b | 140000 | 1085.2713 | 100 |  | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | M & E - Stationery |  | Shopping |  | 18-1513d(i) | 250000 | 1937.9845 | 100 |  | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | M & E - Stationery |  | Direct Contracting |  | 18-1513d(ii) | 50000 | 387.5969 | 100 |  | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01 |  | This includes the purchase of CSJP branded envelopes which are only obtainable from one source, the Jamaica Printing Services Limited. Bank's no-objections received vide CCB/CJA/1023/2016, 298/2016, 295/2016, 245/2016
MNS | IE Treatment Control Group - Incentives - Gadgets/Appliances |  | Shopping |  | 18-1523a | 3217000 | 24937.9845 | 100 |  | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | IE Treatment Control Group - Incentives - Phone Cards |  | Shopping |  | 18-1523b | 750000 | 5813.9535 | 100 |  | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01 |  | There are two service providers in Jamaica. The engagement of either LIME/Digicel will be determined by service provider to which the participants' telephone number is assigned.
MNS | Other Surveys/Assessments - Stationery |  | Shopping |  | 18-1524b | 260000 | 2015.5039 | 100 |  | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Stationery & Office Supplies |  | Shopping |  | 18-1611b(i) | 2715000 | 21046.5116 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 | In Process | Activity to be carried out on an ongoing basis
MNS | Stationery & Office Supplies |  | Direct Contracting |  | 18-1611b(ii) | 300000 | 2325.5814 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 |  | This includes the purchase of CSJP branded envelopes which are only obtainable from one source, the Jamaica Printing Services Limited. Bank's no-objections received vide CCB/CJA/1023/2016, 298/2016, 295/2016, 245/2016
MNS | Furniture & Office Equipment |  | Shopping |  | 18-1611c | 450000 | 3488.3721 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | IT Equipment |  | Shopping |  | 18-1611d(i) | 200000 | 1550.3876 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | IT Equipment |  | Direct Contracting |  | 18-1611d(ii) | 100000 | 775.1938 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 |  | This includes purchase of equipment that needs to be compatible with existing equipment or where equipment is proprietary and only obtainable from one source. These include: Avaya PBX instruments - LIME has proprietary rights to Avaya PBX system and the telephone instruments to be purchased have to be compatible with the Avaya PBX system; Replacement parts for Xerox photocopiers - Productive Business Solutions has proprietary rights to all Xerox machines.
MNS | Software and Licenses |  | Shopping |  | 18-1611e | 952800 | 7386.0465 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Cheque Leaves |  | Direct Contracting |  | 18-1611f | 800000 | 6201.5504 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 |  | Xsomo International Limited has the designs/layout for all the requisite cheque leaves. Activity to be carried out on an ongoing basis
MNS | Tyres - Programme Vehicle |  | Shopping |  | 18-1611h | 60000 | 465.1163 | 100 |  | Programme Management | Ex-Post | 2018-10-01 | 2018-10-01 |  | Activity to be carried out on an ongoing basis
MNS
NON CONSULTING SERVICES
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount, in JA$: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method | Comments
[7 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Bidding Documents | Contract Signature
MNS | Parenting Program - Reproduction of Training Manual and Workbook |  | Shopping |  | 1111a(v) | 4200000 | 32558.1395 | 100 |  | Component 1 | Ex-Post | 2017-09-17 | 2017-09-17
MNS | Parenting Program - Accommodation |  | Shopping |  | 1111a(vi) | 640000 | 4961.2403 | 100 |  | Component 1 | Ex-Post | 2017-07-17 | 2017-07-17 |  | Activity to be carried out on an ongoing basis across Central and Western regions
MNS | Parenting Programme - Refreshments and Venue |  | Shopping |  | 18-1111a(i) | 4940000 | 38294.5736 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis across alll 3 regions.
MNS | Parenting Programme - Transportation |  | Shopping |  | 18-1111a(iv) | 1440000 | 11162.7907 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis across the 3 regions
MNS | Parenting Programme - Reproduction of Manuals |  | Shopping |  | 18-1111a(v) | 800000 | 6201.5504 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Parenting Programme - Décor |  | Shopping |  | 18-1111a(vi) | 80000 | 620.155 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Parenting Programme - Rental of PA System, etc |  | Shopping |  | 18-1111a(vii) | 170000 | 1317.8295 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | MWAM - Personal Developmet Workshops - Refreshments |  | Shopping |  | 18-1111b(i) | 40000 | 310.0775 | 100 |  | Component 1 | Ex-Post | 2018-05-01 | 2018-05-01 |  | Activity to be carried out on an ongoing basis
MNS | MWAM - Men's Day - Refreshments & Venue |  | Shopping |  | 1111b(xvii) | 300000 | 2325.5814 | 100 |  | Component 1 | Ex-Post | 2017-11-01 | 2017-11-01
MNS | FEP IDEVAW - Refreshment & venue |  | Shopping |  | 1111b(xx) | 324000 | 2511.6279 | 100 |  | Component 1 | Ex-Post | 2017-10-24 | 2017-10-24
MNS | MWAM -Mens Day Rental of Chairs |  | Shopping |  | 1111b(xxi) | 100000 | 775.1938 | 100 |  | Component 1 | Ex-pOST | 2017-11-24 | 2017-11-24
MNS | MWAM -Mens Day Live Outside Broadcast |  | Shopping |  | 1111b(xxii) | 480000 | 3720.9302 | 100 |  | Component 1 | Ex-pOST | 2017-11-24 | 2017-11-24
MNS | MWAM-Mens Day Transportation |  | Shopping |  | 1111b(xxiii) | 210000 | 1627.907 | 100 |  | Component 1 | Ex-Post | 2017-11-24 | 2017-11-24
MNS | FEP - Int'l Women's Day - Live Outside Broadcast |  | Shopping |  | 18-1111b(iii) | 240000 | 1860.4651 | 100 |  | Component 1 | Ex-Post | 2018-03-01 | 2018-03-01
MNS | Psycho-Ed Workshops - Refreshments and venue |  | Shopping |  | 18-1112a(i) | 1200000 | 9302.3256 | 100 |  | Component 1 | Ex-Post | 2018-01-17 | 2018-01-17 |  | Activity to be carried out on an ongoing basis across alll 3 regions
MNS | Psycho Ed Workshops - Transportation |  | Shopping |  | 18-1112a(iii) | 480000 | 3720.9302 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis across all 3 regions
MNS | Capacity Building - Transportation |  | Shopping |  | 18-1112b(iii) | 360000 | 2790.6977 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis across all 3 regions
MNS | Life Skills - Transportation |  | Shopping |  | 18-1112e(iii) | 1130000 | 8759.6899 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis across all 3 regions
MNS | Capacity Building Schools - Refreshments and venue |  | Shopping |  | 18-1112b(i) | 810000 | 6279.0698 | 100 |  | Component 1 | Ex-Post | 2018-01-17 | 2018-01-17 |  | Activity to be carried out on an ongoing basis across alll 3 regions
MNS | Group Counselling - Refreshments |  | Shopping |  | 18-1112c(i) | 576000 | 4465.1163 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis across alll 3 regions
MNS | Life Skills -Venue & Refreshments |  | Shopping |  | 18-1112e(i) | 8649000 | 67046.5116 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis across alll 3 regions
MNS | PeaceMobile - Refreshments |  | Shopping |  | 18-1115a(i) | 80000 | 620.155 | 101 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | PeaceMobile - Tents, Tables, Chairs, Portable Toilets, etc |  | Shopping |  | 18-1115a(ii) | 100000 | 775.1938 |  |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | PeaceMobile - Live Outside Broadcast |  | Shopping |  | 18-1115a(iii) | 220000 | 1705.4264 |  |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | PeaceMobile -Entertainment |  | Shopping |  | 18-1115a(iv) | 200000 | 1550.3876 |  |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Good News Campaign - Facility Branding |  | Shopping |  | 18-1115b(iv) | 2000000 | 15503.876 | 100 |  | Component 1 | Ex-Post | 2018-05-01 | 2018-05-01
MNS | Good News Campaign -Road Signage |  | Shopping |  | 18-1115b(v) | 1300000 | 10077.5194 | 100 |  | Component 1 | Ex-Post | 2018-05-01 | 2018-05-01
MNS | Good News Campaign -Décor/Booth Fabrication |  | Shopping |  | 18-1115b(vi) | 400000 | 3100.7752 | 100 |  | Component 1 | Ex-Post | 2018-08-01 | 2018-08-01 |  | Activity to be carried out on an ongoing basis
MNS | Good News Campaign - PIOJ - Streaming |  | Shopping |  | 18-1115b(vii) | 180000 | 1395.3488 | 100 |  | Component 1 | Ex-Post | 2018-09-01 | 2018-09-01
MNS | Good News Campaign - PIOJ - Live OB |  | Shopping |  | 18-1115b(viii) | 240000 | 1860.4651 | 100 |  | Component 1 | Ex-Post | 2018-09-01 | 2018-09-01
MNS | CSJP Youth Ambassador - Launch - Refreshments & venue |  | Shopping |  | 1115b(vi) | 80000 | 620.155 | 100 |  | Component 1 | Ex-Post | 2017-11-01 | 2017-11-01
MNS | CSJP Youth Ambassador - Launch - Décor |  | Shopping |  | 1115b(viii) | 20000 | 155.0388 | 100 |  | Component 1 | Ex-Post | 2017-11-01 | 2017-11-01 |  | Activity to be carried out in KMA and Western regions
MNS | CSJP Youth Ambassador - Launch - Entertainment |  | Shopping |  | 1115b(ix) | 230000 | 1782.9457 | 100 |  | Component 1 | Ex-Post | 2017-11-01 | 2017-11-01 |  | Activity to be carried out in KMA and Western regions
MNS | Social Marketing Adverts- Engagement of Consulting Firms |  | Direct Contracting |  | 18-1115e | 240000 | 1860.4651 | 100 |  | Component 1 | Ex-Post | 2018-02-01 | 2018-02-01 |  | Jamaica Information Services is agency established by the Government of Jamaica to provide communication services to all Ministries, Departments and Agencies. All agencies of the Government are mandated by the Ministry of Finance & Planning to advertise all procurements through JIS. Activity to be carried out on an ongoing basis.
MNS | Goals for Life - Refreshments and Venue |  | Shopping |  | 18-1124c | 4500000 | 34883.7209 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Support to CACs - Live OB |  | Shopping |  | 18-1124f | 960000 | 7441.8605 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Support to CACs - Rental- Public Address System |  | Shopping |  | 18-1124g | 150000 | 1162.7907 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Goals for Life -Transportation |  | Shopping |  | 18-1124h | 1000000 | 7751.938 | 100 |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Job Readiness - Refreshments and venue |  | Shopping |  | 18-1221a | 1460000 | 11317.8295 | 100 |  | Component 2 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out across alll 3 regions
MNS | Summer Employment - Refreshments |  | Shopping |  | 18-1222b(i) | 450000 | 3488.3721 | 100 |  | Component 2 | Ex-Post | 2018-07-17 | 2018-07-17 |  | Activity to be carried out across alll 3 regions
MNS | Stakeholder workshops - Refreshments and Venue |  | Shopping |  | 18-1311(ii) | 960000 | 7441.8605 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 | In Process | Activity to be carried out on an ongoing basis
MNS | Advertisements |  | Direct Contracting |  | 18-1311(iv) | 240000 | 1860.4651 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Jamaica Information Services is agency established by the Government of Jamaica to provide communication services to all Ministries, Departments and Agencies. All agencies of the Government are mandated by the Ministry of Finance & Planning to advertise all procurements through JIS. Activity to be carried out on an ongoing basis.
MNS | Cultural Resocialisation - Refreshments and Venue |  | Shopping |  | 18-1311c(i) | 1760000 | 13643.4109 | 100 |  | Component 3 | Ex-Post | 2018-07-01 | 2018-07-01 |  | Activity to be carried out on an ongoing basis
MNS | SIP - Refreshments |  | Shopping |  | 18-1311c(v) | 1845000 | 14302.3256 | 100 |  | Component 3 | Ex-Post | 2018-06-01 | 2018-06-01 |  | Activity to be carried out on an ongoing basis
MNS | Overcomers In Action - Refreshments and venue |  | Shopping |  | 18-1311c(ix) | 885000 | 6860.4651 | 100 |  | Component 3 | Ex-Post | 2018-05-01 | 2018-05-01 |  | Activity to be carried out on an ongoing basis
MNS | Overcomers In Action - Graduation -Refreshments & Venue |  | Shopping |  | 18-1311c(xi) | 660000 | 5116.2791 | 100 |  | Component 3 | Ex-Post | 2018-05-01 | 2018-05-01
MNS | Cultural Resocialization - Transportation |  | Shopping |  | 18-311c(xiv) | 840000 | 6511.6279 | 100 |  | Component 3 | Ex-Post | 2018-07-01 | 2018-07-01 |  | Activity to be carried out on an ongoing basis
MNS | Cultural Resocialization - Medical Services |  | Shopping |  | 18-1311c(xv) | 160000 | 1240.3101 | 100 |  | Component 3 | Ex-Post | 2018-07-01 | 2018-07-01 |  | Activity to be carried out on an ongoing basis
MNS | Training - Refreshments and venue |  | Shopping |  | 18-1311h(i) | 1560000 | 12093.0233 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | West Kingston - Training of VSD Volunteers - Refreshments and venue |  | Shopping |  | 18-1311h(iii) | 1170000 | 9069.7674 | 100 |  | Component 3 | Ex-Post | 2018-06-01 | 2018-06-01 |  | Activity to be carried out on an ongoing basis
MNS | Training - Refreshments and venue |  | Shopping |  | 18-1312c(i) | 814000 | 6310.0775 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Legal Aid Fairs - Refreshments and venue |  | Shopping |  | 18-1312d(i) | 840000 | 6511.6279 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Legal Aid Fairs - Rental of chairs, tents, portable toilets, generator, PA system |  | Shopping |  | 18-1312d(iii) | 718000 | 5565.8915 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis.
MNS | Legal Aid Fairs - Live Outside Broadcast |  | Shopping |  | 18-1312d(iv) | 800000 | 6201.5504 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis.
MNS | Legal Aid Fairs - Town Crier |  | Shopping |  | 18-1312d(v) | 140000 | 1085.2713 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Mobile Unit- Rental of Venue |  | Shopping |  | 18-1312f(iii) | 1775000 | 13759.6899 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis.
MNS | JP Consultations - refreshments |  | Shopping |  | 18-1313(i) | 3600000 | 27906.9767 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Trainers Manual - Refrements and venue |  | Shopping |  | 18-1313(ii) | 400000 | 3100.7752 | 100 |  | Component 3 | Ex-Post | 2018-12-01 | 2018-12-01
MNS | Printing of JP Manuals |  | Shopping |  | 18-1313(iii) | 2400000 | 18604.6512 | 100 |  | Component 3 | Ex-Post | 2018-11-01 | 2018-11-01
MNS | Advertisements |  | Direct Contracting |  | 18-1313(iv) | 80000 | 620.155 | 100 |  | Component 3 | Ex-Post | 2018-04-01 | 2018-04-01 |  | Jamaica Information Services is agency established by the Government of Jamaica to provide communication services to all Ministries, Departments and Agencies. All agencies of the Government are mandated by the Ministry of Finance & Planning to advertise all procurements through JIS. Activity to be carried out on an ongoing basis.
MNS | Qualifying Training - Refreshments and venue |  | Shopping |  | 18-1313b(i) | 7260000 | 56279.0698 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 | In Process | Activity to be carried out on an ongoing basis
MNS | Qualifying Training - Hotel Accommodation |  | Shopping |  | 18-1313b(iii) | 1886400 | 14623.2558 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 | In Process | Activity to be carried out on an ongoing basis.
MNS | Advanced Training - Refreshments and venue |  | Shopping |  | 18-1313c(i) | 13596000 | 105395.3488 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis.
MNS | Advanced Training - Transportation |  | Shopping |  | 18-1313c(iii) | 480810 | 3727.2093 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis.
MNS | Advanced Training - Hotel Accommodation |  | Shopping |  | 18-1313c(iv) | 7002920 | 54286.2016 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis.
MNS | Maintenance of office equipment, appliance and furniture |  | Shopping |  | 18-1315(vii) | 150000 | 1162.7907 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis.
MNS | Maintenance of office equipment, appliance and furniture |  | Direct Contracting |  | 18-1315(viii) | 50000 | 387.5969 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis.
MNS | Advertisements |  | Direct Contracting |  | 18-1315(ix) | 80000 | 620.155 | 100 |  | Component 3 | Ex-Post | 2017-05-01 | 2017-05-01 |  | Jamaica Information Services is agency established by the Government of Jamaica to provide communication services to all Ministries, Departments and Agencies. All agencies of the Government are mandated by the Ministry of Finance & Planning to advertise all procurements through JIS. Activity to be carried out on an ongoing basis.
MNS | RJ Week - Minister's Message & Testimonial |  | Direct Contracting |  | 18-1315(x) | 240000 | 1860.4651 | 101 |  | Component 4 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Jamaica Information Services is agency established by the Government of Jamaica to provide communication services to all Ministries, Departments and Agencies. All agencies of the Government are mandated by the Ministry of Finance & Planning to advertise all procurements through JIS. Activity to be carried out on an ongoing basis.
MNS | RJ Week -Décor |  | Shopping |  | 18-1315(xi) | 100000 | 775.1938 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | RJ Week -Live Outside Broadcast |  | Shopping |  | 18-1315(xii) | 390000 | 3023.2558 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | RJ Week -Transportation |  | Shopping |  | 18-1315(xiii) | 200000 | 1550.3876 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | RJ Week -Tent, chairs, portable toilet, tables, PA System, etc |  | Shopping |  | 18-1315(xiv) | 250000 | 1937.9845 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | RJ Week -Performing Artiste |  | Direct Contracting |  | 18-1315(xv) | 20000 | 155.0388 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | The RJ Conference seeks to engage secondary school students who are influrnced by gang violence. Knox College, the winner of the All Together Sing competion is deemed most qualified for this activity.
MNS | RJ Week - Refreshments & Venues |  | Shopping |  | 18-1315(xxii) | 1520000 | 11782.9457 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | RJ Week - Airfare for Presenter |  | Direct Contracting |  | 18-1315(xxiii) | 206400 | 1600 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Selection will be based on the most direct route from United Kingdom to Kingston.
MNS | RJ Volunteers - Graduation - Transportation |  | Shopping |  | 18-1315b(x) | 100000 | 775.1938 | 100 |  | Component 3 | Ex-Post | 2018-05-01 | 2018-05-01
MNS | School Administration Training - Refreshments and venue |  | Shopping |  | 18-1315b(i) | 5998000 | 46496.124 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Judiciary Training - Refreshments and venue |  | Shopping |  | 18-1315b(ii) | 10300000 | 79844.9612 | 100 |  | Component 3 | Ex-Post | 2018-04-01 | 2018-04-01 |  | This is proposed to be a residential training commencing on a Thursday through to Sunday and hence the estimated cost.
MNS | Police and JP Training - Refreshments and venue |  | Shopping |  | 18-1315b(iv) | 8000000 | 62015.5039 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis.
MNS | Training RJ Volunteers - Refreshments and venue |  | Shopping |  | 18-1315b(v) | 267500 | 2073.6434 | 100 |  | Component 3 | Ex-Post | 2018-05-01 | 2018-05-01 |  | Activity to be carried out on an ongoing basis
MNS | RJ Volunteers - Graduation - Refreshments |  | Shopping |  | 18-1315b(vi) | 337500 | 2616.2791 | 100 |  | Component 3 | Ex-Post | 2018-05-01 | 2018-05-01
MNS | Staff Development - Refreshments and venue |  | Shopping |  | 18-1315b(viii) | 120000 | 930.2326 | 100 |  | Component 3 | Ex-Post | 2018-06-01 | 2018-06-01
MNS | RJ Sensitization - Refreshments and venue |  | Shopping |  | 18-1315c(i) | 2000000 | 15503.876 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | RJ Sensitization - Rental of equipment, etc. |  | Shopping |  | 18-1315c(ii) | 80000 | 620.155 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis.
MNS | RJ Case Conference - Refreshments |  | Shopping |  | 18-1315d(i) | 480000 | 3720.9302 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Quarterly Meetings - Refreshments |  | Shopping |  | 18-1316(ii) | 30000 | 232.5581 | 100 |  | Component 3 | Ex-Post | 2018-11-01 | 2018-11-01 |  | Activity to be carried out on an ongoing basis.
MNS | Training Workshops - Refreshments & Venue |  | Shopping |  | 18-1316(iii) | 330000 | 2558.1395 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Judicial Training (Residential) - Venue & Refreshments |  | Shopping |  | 18-1316(v) | 11000000 | 85271.3178 | 100 |  | Component 3 | Ex-Post | 2018-07-01 | 2018-07-01 |  | Activity to be carried out on an ongoing basis.
MNS | Training of Police Officers & JPs - Refreshments & Venue |  | Shopping |  | 18-1316(vi) | 8000000 | 62015.5039 | 100 |  | Component 3 | Ex-Post | 2018-07-01 | 2018-07-01 |  | Activity to be carried out on an ongoing basis.
MNS | CD Sensitizations - Refreshments & Venue |  | Shopping |  | 18-1316(vii) | 1200000 | 9302.3256 | 100 |  | Component 3 | Ex-Post | 2018-08-01 | 2018-08-01 |  | Activity to be carried out on an ongoing basis.
MNS | Maintenance - Office Equipment |  | Shopping |  | 18-1316(viii) | 50000 | 387.5969 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis.
MNS | Training Workshop - Hotel Accommodation |  | Shopping |  | 18-1316(ix) | 2145000 | 16627.907 | 100 |  | Component 3 | Ex-Post | 2018-10-01 | 2018-10-01 |  | Activity to be carried out on an ongoing basis.
MNS | Advertisements |  | Direct Contracting |  | 18-1316(x) | 80000 | 620.155 | 100 |  | Component 3 | Ex-Post | 2018-04-01 | 2018-04-01 |  | Jamaica Information Services is agency established by the Government of Jamaica to provide communication services to all Ministries, Departments and Agencies. All agencies of the Government are mandated by the Ministry of Finance & Planning to advertise all procurements through JIS. Activity to be carried out on an ongoing basis.
MNS | Producing & Placing Multi-Media Ads |  | Shopping |  | 1316(xi) | 2000000 | 15503.876 | 100 |  | Component 3 | Ex-Post | 2017-06-01 | 2017-06-01
MNS | MDA Sensitization Sessions - Refreshments & Venue |  | Shopping |  | 18-1411a | 600000 | 4651.1628 | 100 |  | Component 4 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Case Management - Refreshments and venue |  | Shopping |  | 18-1511a | 2210000 | 17131.7829 | 100 |  | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01 | In Process | Activity to be carried out on an ongoing basis
MNS | Case Management - Transportation |  | Shopping |  | 1511c | 40000 | 310.0775 |  |  | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | M & E - Refreshments and venue |  | Shopping |  | 18-1513c | 1060000 | 8217.0543 | 100 |  | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Advertisements |  | Direct Contracting |  | 18-1513e | 100000 | 775.1938 | 100 |  | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Jamaica Information Services is agency established by the Government of Jamaica to provide communication services to all Ministries, Departments and Agencies. All agencies of the Government are mandated by the Ministry of Finance & Planning to advertise all procurements through JIS. Activity to be carried out on an ongoing basis.
MNS | M & E - Hotel Accommodation |  | Shopping |  | 18-1513f | 1945000 | 15077.5194 | 100 |  | Component 5 | Ex-Post | 2017-10-01 | 2017-11-01 |  | Activity to be carried out on an ongoing basis
MNS | Community Survey - Refreshments & Venue |  | Shopping |  | 18-1517a | 130000 | 1007.7519 | 100 |  | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Community Survey - Presentation-Airfare |  | Direct Contracting |  | 18-1517b | 361200 | 2800 | 100 | 2 | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Selection will be based on the most direct route from destinations(Trinidad/Canada) to Kingston.
MNS | Impact Evaluation - Gate Keepers |  | Direct Contracting |  | 18-1523c | 250000 | 1937.9845 | 100 |  | Component 5 | Ex-Post | 2018-04-01 | 2018-04-01 |  | A pool of gatekeepers was approved by the Bank vide CCB/CJA/1027/2016. The intention is to engage available persons from the respective communities to provide safe passage to data collectors.
MNS | Other Surveys/Assessments - Refreshments and venue |  | Shopping |  | 18-1524a | 640000 | 4961.2403 | 100 |  | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Other Surveys/Assessments - Transportation |  | Shopping |  | 18-1524c | 100000 | 775.1938 | 100 |  | Component 5 | Ex-Post | 2018-08-01 | 2018-08-01
MNS | Refreshments |  | Shopping |  | 18-1611g | 500000 | 3875.969 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 | In Process | Activity to be carried out on an ongoing basis
MNS | Equipment Maintenance |  | Shopping |  | 18-1611i | 651500 | 5050.3876 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Equipment Maintenance |  | Direct Contracting |  | 18-1611j | 300000 | 2325.5814 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 |  | Includes ongoing servicing of equipment that are proprietary to companies, for example, Productive Business Solution has proprietary rights to all Xerox photocopiers .
MNS | Repairs to Furniture |  | Shopping |  | 18-1611k | 50000 | 387.5969 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Servicing of fire extinguishers |  | Shopping |  | 18-1611l | 210650 | 1632.9457 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Boarding of Assets |  | Shopping |  | 18-1611m | 400000 | 3100.7752 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Boarding of Assets - E-Waste |  | Direct Contracting |  | 18-1611n | 100000 | 775.1938 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 |  | The National Solid Waste ManagementAuthority (NSWMA) is the only authorised agency to dispose of electronic waste. This is done on a periodic basis.
MNS | Hotel Accommodation |  | Shopping |  | 18-1611o | 2000000 | 15503.876 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Advertisements |  | Direct Contracting |  | 18-1611p | 200000 | 1550.3876 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Accounting Software Maintenance & Licenses |  | Direct Contracting |  | 18-1611q | 1000000 | 7751.938 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 |  | CER Consultants has proprietary rights to Accpac accounting software.
MNS | Other Admin Services |  | Shopping |  | 18-1611r | 1000000 | 7751.938 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | [7 empty] | 100
CONSULTING FIRMS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): |  | Process Number: | Estimated Amount |  |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method | Comments
[6 empty] | Estimated Amount, in JA $: | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
MNS | Capacity Building of NPSC in support of Transition |  | Single Source Selection |  | 18-1111a(viii) | 15500000 | 120155.0388 | 100 |  | Component 1 | Ex-Ante | 2018-02-01 | 2018-03-01 |  | The National Parenting Support Commission is only entity qualified for the scope of work as it is the agency through which the Parenting Programme will be transitioned.
MNS | MWAM - Capacity Building |  | Single Source Selection |  | 18-1111b(v) | 400000 | 3100.7752 | 100 |  | Componenet 1 | Ex-Ante | 2018-06-01 | 2018-06-01 |  | UWI has experience has exceptional worth. This activity involves the utilizing the university to enhance the theoretical knowledge of MWAM cohort in social work.
MNS | Substance Misuse Treatment |  | Single Source Selection |  | 18-1112f | 17892500 | 138701.5504 | 100 |  | Component 1 | Ex-Ante | 2017-08-17 | 2017-09-17 |  | National Council on Drug Abuse (NCDA) has experience of exceptional worth. It is an agency of the Government of Jamaica, established to educate the general public about the dangers of drug use, to prevent the indiscriminate use of drugs and to treat persons affected by the misuse of drugs. Bank's no-objection received vide CCB/CJA/634/2016.
MNS | Substance Misuse Treatment - Residential |  | Single Source Selection |  | 18-1112g | 1500000 | 11627.907 | 100 |  | Component | Ex-Ante | 2018-01-18 | 2018-01-18 |  | Teen Challenge Jamaica is the only entity qualified for the scope of work as it is the only institution that offers residential treatment up to 12 months while at the same time provide vocational skills training.
MNS | Violence Interruption Services - PMI East |  | Single Source Selection |  | 18-1113a | 31000000 | 240310.0775 | 100 |  | Component 1 | Ex-Ante | 2018-04-01 | 2018-05-01 |  | PMIs have experience of exceptional worth for this assignment and are the only non-governmental organization established specifically for gang demobilization in inner city communities. They are also the only entities trained by the Cure Violence Organization (CV) which was commissioned by the World Bank to provide assistance to the Ministry of National Security (MNS) for implementation of a comprehensive and national programme of violence interruption.
MNS | Violence Interruption Services - PMI West |  | Single Source Selection |  | 18-1113b | 30500000 | 236434.1085 | 100 |  | Component 1 | Ex-Ante | 2018-03-01 | 2018-04-01 |  | PMIs have experience of exceptional worth for this assignment and are the only non-governmental organization established specifically for gang demobilization in inner city communities. They are also the only entities trained by the Cure Violence Organization (CV) which was commissioned by the World Bank to provide assistance to the Ministry of National Security (MNS) for implementation of a comprehensive and national programme of violence interruption.
MNS | SSP - Conflict Resolution Intervention |  | Single Source Selection |  | 18-1114a | 19122185 | 148233.9922 | 100 |  | Component 1 | Ex-Ante | 2018-04-01 | 2018-04-01 |  | The Dispute Resolution Foundation is the only entity authourized to conduct mediation training and certify mediators. The entity also has experience of exceptional worth with its flagship School Suspension Programme.
MNS | Good News Campaign - Public Awareness |  | Single Source Selection |  | 18-1115b(ix) | 8000000 | 62015.5039 | 100 |  | Component 1 | Ex-Ante | 2018-01-01 | 2018-04-01 |  | JIS is an Executive Agency established by the Government of Jamaica to manage the dissemination of information and to enhance the public awareness of policies and programmes of Ministries, Departments and Agencies. CSJP, being a government initiative, is mandated to use JIS for its communication services where possible. The company also has experience of exceptional worth .
MNS | Good News Campaign - Cross Country Invasion |  | Single Source Selection |  | 18-1115b(x) | 1250000 | 9689.9225 | 100 |  | Component 1 | Ex-Ante | 2018-01-01 | 2018-01-01 |  | RJR Communication Group has experience of exceptional worth .
MNS | Anti-Gang Campaign - Badness A Madness |  | Selection Based on the Consultants' Qualifications |  | 18-1115f | 10000000 | 77519.3798 | 100 |  | Component 1 | Ex-Ante | 2018-03-01 | 2018-04-01
MNS | We Have Justice Campaign |  | Selection Based on the Consultants' Qualifications |  | 18-1115g | 9920000 | 76899.2248 | 100 |  | Component 1 | Ex-Ante | 2018-03-01 | 2018-04-01
MNS | Women Stand Against Violence Campaign |  | Selection Based on the Consultants' Qualifications |  | 18-1115h | 2000000 | 15503.876 | 100 |  | Component 1 | Ex-Ante | 2018-06-01 | 2018-07-01
MNS | Community events- Partnership with CSSB |  | Shopping |  | 18-1116 | 4000000 | 31007.7519 | 100 |  | Component 1 | Ex-Post | 2018-03-01 | 2018-03-01 |  | To improve citizen/police relationship, a partnership is to be formalized between the CSJP and the Community Safety & Security Branch (CSSB) of the Jamaica Constabulary Force by way of a MOU. This is to be submitted to the Bank as soon as the details are finalized. The CSSB was formed out of the desire to have the police and other agencies more involved in the overall development of the community, therefore being able to offer maximum safety and security. The major role of the CSSB is to provide the point of contact between the police and other external bodies which fosters community safety, security and development. It is therefore the only body through which the target of improving police/citizen relationship can be achieved. Additionally, the CSJP2 financed the purchase and branding of a convertible stage truck as well as sound equipment for the CSSB which were integral to community engagement activities undertaken by both the CSJP and CSSB. The CSSB was responsible for the maintenance and operation, and provision of the requisite technical expertise needed for the community engagements. This arrangement will continue under CSJP 3.
MNS | Crisis Intervention |  | Single Source Selection |  | 18-1117 | 11348250 | 87970.9302 | 100 |  | Component 1 | Ex-Ante | 2018-01-01 | 2018-01-01 |  | VPA is the only organization that prepares technology-based Asset Maps. The company also has experience of exceptional worth as it relates data collection work and coordination of activities associated with violence related injuries.
MNS | Capacity Building Training CDCs |  | Single Source Selection |  | 18-1121a | 7000000 | 54263.5659 | 100 |  | Component 1 | Ex-Ante | 2018-01-01 | 2018-01-01 |  | Contract with Department of Cooperatives and Friendly Societies. Single-Source Selection is being recommended on the basis that DCFS is the only agency with responsibility for regulating Community Development Committee Benevolent Societies. DCFS provided same service under CSJP II. Bank's no-objection received for existing arrangement vide CCB/CJA/1638/2014 and CCB/CJA/677/2016
MNS | Engagement of CDCs to Implement Community Based Interventions |  | Single Source Selection |  | 18-1121b | 35000000 | 271317.8295 | 100 |  | Component 1 | Ex-Ante | 2018-01-01 | 2018-01-01 |  | Several CDCs that maintain registration with DCFS are to be directly engaged. This request is based on ongoing discussions between representatives of the Programme and the Bank. The agreed approach was to develop a mechanism by way of MOU to engage each benevolent and to disburse funds on deliverables in lieu of making direct transfers to the community based organizations.
MNS | Supervision Services - Construction of Gayle Multi-Purpose Centre |  | Quality and Cost Based Selection |  | 1122d | 3500000 | 27131.7829 | 100 |  | Component 1 | Ex-Ante | 2017-05-01 | 2017-05-01 | In Process
MNS | Development of Community Profiles |  | Single Source Selection |  | 18-1123b | 17000000 | 131782.9457 | 100 |  | Component 1 | Ex-Ante | 2018-01-17 | 2017-03-17 |  | The SDC is the only government agency with the legal directive and policy mandate to facilitate community development planning process across Jamaica. It was originally intended for the SDC to be the sole provider to deliver the proposed service, (preparation of the Community Safety Plans) but it was later decided that in order to meet the objectives of the CSJP and to enhance the data, Assets Maps are critical to the planning process and therefore VPA is being engaged to provide this service. Bank's no-objection received vide CCB/CJA/57/2013 and CCB/CJA/403/2015.
MNS | Safety Plans & Audits |  | Single Source Selection |  | 18-1123c | 14000000 | 108527.1318 | 100 |  | Component 1 | Ex-Ante | 2017-01-17 | 2017-03-17 |  | Accordingly, the VPA is the only organization that prepares technology-based Asset Maps. This process involves the collection of data at the community level and the subsequent preparation of Maps using geo-spatial programming and analysis. The organization works in collaboration with Mona Infomatix Limited, an arm of the University of the West Indies, which is the only entity with the technical capacity in this highly specialized area of geo-spatial programming. Bank's no-objection received vide CCB/CJA/57/2013 and CCB/CJA/403/2015.
MNS | Business Development - Ornamental Fish Farming |  | Single Source Selection |  | 18-1223 | 2000000 | 15503.876 | 100 |  | Component 2 | Ex-Ante | 2018-01-01 | 2018-01-01 |  | The Competitiveness Company is the only company in Jamaica operating at the community level in the area of ornamnental fish farming.
MNS | RJ Multimeadia Campaign |  | Selection Based on the Consultants' Qualifications |  | 18-1315(xvi) | 2000000 | 15503.876 | 100 |  | Component 3 | Ex-Ante | 2018-03-01 | 2018-05-01
MNS | CD Public Awareness campaign |  | Selection Based on the Consultants' Qualifications |  | 18-1316(xi) | 2000000 | 15503.876 | 100 |  | Component 3 | Ex-Post | 2018-06-01 | 2018-06-01
MNS | Case Management System - Customization |  | Single Source Selection |  | 18-1511g | 6000000 | 46511.6279 | 100 |  | Component 5 | Ex-Ante | 2018-01-01 | 2018-01-01 |  | Through efforts of the MNS, the CSJP was granted access to Fight For Peace Case Management System. There is need to customized the system which was developed by Upshot. Upshot therefore has proprietary rights to the system and will be engaged accordingly to customize system.
MNS | Case Management Capacity Building |  | Single Source Selection |  | 18-1511h | 2274000 | 17627.907 | 100 |  | Component 5 | Ex-Ante | 2018-01-01 | 2018-01-01 |  | UWI has experience has exceptional worth. This activity involves the utilizing the university to enhance the theoretical knowledge of CCMOs in Case Management.
MNS | Procurement Training |  | Single Source Selection |  | 18-1611s | 557000 | 4317.8295 | 100 |  | Component 5 | Ex-Ante | 2018-01-01 | 2018-01-01 |  | Inpri is the only entity mandated by the Government of Jamaica to carry out the Public Procurement Certification Series of Training
INDIVIDUAL CONSULTANTS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  |  | Estimated Number of Consultants: | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method | Comments
[5 empty] | Estimated Amount, in JA$: | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  |  | No Objection to TOR's | Contract Signature
MNS | MWAM - Male Empowerment - Facilitators |  | 3CV | 1111b(xi) | 700000 | 5426.3566 | 100 |  | 7 | Component 1 | Ex-Post | 2017-05-17 | 2017-05-17
MNS | Parenting Programme - Facilitators |  | Single Source Selection | 18-1111a(viii) | 864000 | 6697.6744 | 100 |  | 6 | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | MWAM - Personal Development Workshop - Facilitator |  | 3CV | 18-1111b(iv) | 100000 | 775.1938 | 100 |  | 2 | Component 1 | Ex-Post | 2018-05-01 | 2018-05-01
MNS | Psycho-Ed Workshop - Facilitators |  | 3CV | 18-1112a(iv) | 552000 | 4279.0698 | 100 |  | 6 | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Consultants to be engaged on an ongoing basis across KMA, Central and Western regions.
MNS | Individual Counselling - Referrals |  | Single Source Selection | 18-1112i | 1440000 | 11162.7907 | 100 |  | 30 | Component 1 | Ex-Post | 2017-01-17 | 2017-01-17 |  | The Bank approved a list of psychological service providers vide CCB/CJA/1308/2014. Each service provider will be selected based on location of client, availability of service provider and severity of client's needs. Updated list of service providers was approved by the Bank vide CCB/CJA/225/2016 and CCB/CJA/601/2017. Activity will be conducted on an ongoing basis across KMA, Central and Western regions.
MNS | SSP - Administrators |  | 3CV | 18-1114b | 6400000 | 49612.4031 | 100 |  | 8 | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Consultants to be engaged across KMA, Central and Western regions.
MNS | SSP - Facilitators |  | 3CV | 18-1114c | 8000000 | 62015.5039 | 100 |  | 10 | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Consultants to be engaged across KMA, Central and Western regions.
MNS | SSP - Secretarial Assistant |  | 3CV | 18-1114d | 600000 | 4651.1628 | 100 |  | 1 | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | SSP - Social Worker |  | 3CV | 18-1114e | 1800000 | 13953.4884 | 100 |  | 1 | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | CSJP Youth Ambassador - Facilitators |  | 3CV | 1115b(v) | 86000 | 666.6667 | 100 |  | 1 | Component 1 | Ex-Post | 2017-07-01 | 2017-07-01
MNS | Goals for Life -Life Skiils/Football Training Facilitators |  | 3CV | 18-1124i | 3000000 | 23255.814 | 100 |  |  | Component 1 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Activity to be carried out on an ongoing basis
MNS | Production of animation films of healing for Tivoli Incursion victims |  | 3CV | 18-1311(v) | 1440000 | 11162.7907 | 100 |  | 1 | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Stakeholder workshops - facilitators |  | 3CV | 18-1311(vi) | 280000 | 2170.5426 | 100 |  | 4 | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Consultants to be engaged on an ongoing basis across KMA, Central and Western regions.
MNS | Screening of 150 students |  | 3CV | 18-1311(vii) | 3000000 | 23255.814 | 100 |  | 1 | Component 3 | Ex-Post | 2018-09-01 | 2018-10-01
MNS | Consultant to Authenticate and Norm VSD's Missing Children Risk Assessment Tool |  | 3CV | 18-1311b | 6000000 | 46511.6279 | 100 |  | 1 | Component 3 | Ex-Post | 2018-01-01 | 2018-02-01
MNS | Cultural Resocialisation - Facilitators |  | 3CV | 18-1311c(xvi) | 320000 | 2480.6202 | 100 |  | 8 | Component 3 | Ex-Post | 2018-07-01 | 2018-07-01 |  | Consultants to be engaged on an ongoing basis across KMA, Central and Western regions.
MNS | SIP - Facilitators |  | 3CV | 18-1311c(xvii) | 600000 | 4651.1628 | 100 |  | 6 | Component 3 | Ex-Post | 2018-06-01 | 2018-06-01 |  | Consultants to be engaged on an ongoing basis across KMA, Central and Western regions.
MNS | SIP - Re-inforcement Facilitators |  | 3CV | 18-1311c(xviii) | 360000 | 2790.6977 | 100 |  | 6 | Component 4 | Ex-Post | 2018-06-01 | 2018-06-01 |  | Consultants to be engaged on an ongoing basis across KMA, Central and Western regions.
MNS | Overcomers In Action - Facilitators |  | 3CV | 18-1311c(xix) | 90000 | 697.6744 | 100 |  | 3 | Component 3 | Ex-Post | 2018-05-01 | 2018-05-01 |  | Consultants to be engaged on an ongoing basis across KMA, Central and Western regions.
MNS | Consultant - Develop and Produce Manual for Play Therapy Training |  | Comparison of Qualifications - National Individual Consultant | 18-1311g | 1500000 | 11627.907 | 100 |  | 1 | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Training - Facilitators |  | 3CV | 18-1311h(iv) | 240000 | 1860.4651 | 100 |  | 2 | Component 3 | Ex-Post | 2018-06-01 | 2018-06-01
MNS | West Kingston - Training of VSD Volunteers - Facilitators |  | 3CV | 18-1311h(v) | 240000 | 1860.4651 | 100 |  | 6 | Component 3 | Ex-Post | 2018-06-01 | 2018-06-01
MNS | Training - Facilitators |  | Single Source Selection | 18-1312c(iii) | 400000 | 3100.7752 | 100 |  | 4 | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | The Bank approved a list of service providers vide CCB/CJA/1353/2016. Each service provider will be selected based on location of client and availability of service provider. Activity will be conducted on an ongoing basis.
MNS | Legal Aid Driver |  | 3CV | 18-1312f(iii) | 840000 | 6511.6279 | 100 |  | 1 | Component 3 | Ex-Ante | 2018-01-01 | 2018-01-01
MNS | Consultant - Revision to training manual and training of trainers |  | 3CV | 18-1313(viii) | 1000000 | 7751.938 | 100 |  | 1 | Component 3 | Ex-Post | 2018-07-01 | 2018-07-01
MNS | Mediation Consultant |  | Comparison of Qualifications - National Individual Consultant | 18-1313(v) | 3540000 | 27441.8605 | 100 |  | 1 | Component 3 | Ex-Post | 2018-02-01 | 2018-02-01
MNS | Mediation Pilot Project - Mediators |  | Single Source Selection | 18-1313(vi) | 4800000 | 37209.3023 | 100 |  | 50 | Component 3 | Ex-Post | 2018-07-01 | 2018-07-01 |  | Individuals certified by the Dispute Resolution Foundation to conduct mediations sessions. These individuals are the only qualified persons in Jamaica to carry out scope of services. Each service provider will be selected based on location of client and availability of service provider. Activity will be conducted on an ongoing basis. The estimated cost is approximately US $50 per mediator per session.
MNS | Mediation Consultant |  | Comparison of Qualifications - National Individual Consultant | 18-1313(vii) | 3540000 | 27441.8605 | 100 |  | 1 | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Qualifying Training - Facilitators |  | Single Source Selection | 18-1313b(iv) | 1500000 | 11627.907 | 100 |  | 3 | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | The Bank approved a list of service providers vide CCB/CJA/682/2016 and CCB/CJA/1291/2016. Each service provider will be selected based on location of client and availability of service provider. Activity will be conducted on an ongoing basis.
MNS | Advanced Training - Facilitators |  | Single Source Selection | 18-1313c(v) | 1150000 | 8914.7287 | 100 |  | 10 | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | The Bank approved a list of service providers vide CCB/CJA/682/2016 and CCB/CJA/1291/2016. Each service provider will be selected based on location of client and availability of service provider. Activity will be conducted on an ongoing basis.
MNS | RJ Week - Note-takers |  | 3CV | 18-1315(xvii) | 40000 | 310.0775 | 100 |  | 2 | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | RJ Week - Rapporteurs |  | 3CV | 18-1315(xviii) | 30000 | 232.5581 | 100 |  | 2 | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | RJ Week - International Presenter |  | Single Source Selection | 18-1315(xix) | 1000000 | 7751.938 | 100 |  | 1 | Component 3 | Ex-Ante | 2018-01-01 | 2018-01-01 |  | Details to be presented in submission to the Bank.
MNS | Centre Managers and Office Attendants |  | Comparison of Qualifications - National Individual Consultant | 18-1315(xx) | 11020673 | 85431.5736 | 100 |  | 3 | Component 3 | Ex-Ante | 2018-04-01 | 2018-04-01
MNS | Community Liaison Officers |  | 3CV | 18-1315(xxi) | 20376900 | 157960.4651 | 100 |  | 10 | Component 3 | Ex-Ante | 2018-04-01 | 2018-04-01
MNS | RJ Sensitization - Facilitators |  | Single Source Selection | 1315c(iii) | 1680000 | 13023.2558 | 100 |  | 30 | Component 3 | Ex-Post | 2018-04-01 | 2018-04-01 |  | The Bank approved a list of service providers vide CCB/CJA/871/2016 and CCB/CJA/531/2016. Each service provider will be selected based on location of client and availability of service provider. Activity will be conducted on an ongoing basis.
MNS | RJ Case Conference - Facilitators |  | Single Source Selection | 1315d(ii) | 1920000 | 14883.7209 | 100 |  | 20 | Component 3 | Ex-Post | 2018-04-01 | 2018-04-01 |  | The Bank approved a list of service providers vide CCB/CJA/871/2016 and CCB/CJA/531/2016. Each service provider will be selected based on location of client and availability of service provider. Activity will be conducted on an ongoing basis.
MNS | Training Consultant |  | Comparison of Qualifications - National Individual Consultant | 18-1316(xii) | 1300000 | 10077.5194 | 100 |  | 1 | Component 3 | Ex-Ante | 2018-10-01 | 2018-10-01 |  | Consultant was engaged competitively and is to be re-engaged on the basis of continuation of services.
MNS | National Oversight Committee - Honorarium to Committee Members |  | Single Source Selection | 18-1316(xiii) | 200000 | 1550.3876 | 100 |  | 12 | Component 3 | Ex-Ante | 2018-10-01 | 2018-10-01 |  | The formation of the National Committee will be as per approved Bill. The membership includes representatives of various stakeholder groups re Child Diversion. Activity will be conducted on an ongoing basis.
MNS | National Oversight Committee - Facilitators |  | Single Source Selection | 1316(xiv) | 60000 | 465.1163 | 100 |  | 12 | Component 3 | Ex-Ante | 2017-07-01 | 2017-07-01 |  | Experts in various fields will be called upon periodically to provide guidance to the committee through presentations. Details to be provided upon submission
MNS | Justice Services Coordinator |  | Comparison of Qualifications - National Individual Consultant | 1318 | 5274000 | 40883.7209 | 100 |  | 1 | Component 3 | Ex-Ante | 2017-10-01 | 2017-10-01 | In Process
MNS | Transition Specialist/Adviser or Change Management Specialist |  | Comparison of Qualifications - National Individual Consultant | 18-1411b | 6000000 | 46511.6279 | 100 |  | 1 | Component 4 | Ex-Ante | 2017-05-01 | 2017-05-01 | In Process
MNS | Re-engagement of members of the Technical Advisory team |  | Single Source Selection | 18-1411c | 36098400 | 279832.5581 | 100 |  | 3 | TAT | Ex-Ante | 2018-08-01 | 2018-08-01 |  | TAT members were engaged competitively. Same individuals are to be re-engaged on the basis of continuation of services.
MNS | Data Analyst |  | 3CV | 1513g | 2000000 | 15503.876 | 100 |  |  | Component 5 | Ex-Ante | 2017-08-01 | 2017-09-01
MNS | Training Consultant |  | 3CV | 1513h | 130000 | 1007.7519 | 100 |  |  | Component 5 | Ex-Post | 2017-10-01 | 2017-11-01
MNS | M & E - Training Consultant |  | 3CV | 18-1513h | 1445000 | 11201.5504 | 100 |  | 3 | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01 |  | Consultants to be engaged on an ongoing basis.
MNS | Data Entry Clerks |  | 3CV | 18-1513i | 7980000 | 61860.4651 | 100 |  | 7 | Componenet 5 | Ex-Ante | 2018-01-01 | 2018-01-01
MNS | Other Surveys/Assessments - Lead Researcher |  | 3CV | 1524e | 8400000 | 65116.2791 | 100 |  | 1 | Componenet 5 | Ex-Ante | 2017-09-01 | 2017-10-01 | In Process
MNS | Other Surveys/Assessments - Assistant Researchers |  | 3CV | 18-1524f | 3600000 | 27906.9767 | 100 |  | 8 | Component 5 | Ex-Ante | 2018-01-01 | 2018-01-01
MNS | Other Surveys/Assessments - MWAM Evaluation |  | 3CV | 18-1524g | 2000000 | 15503.876 | 100 |  | 8 | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01
MNS | Field Coordinator |  | 3CV | 18-1524i | 3000000 | 23255.814 | 100 |  | 8 | Component 6 | Ex-Ante | 2018-01-01 | 2018-01-01
MNS | Social Workers |  | 3CV | 1611z | 18367788 | 142385.9535 | 100 |  | 5 | Programme Management | Ex-Ante | 2017-02-01 | 2017-03-01 |  | All Regions
MNS | Accounting Officer |  | 3CV | 1611t | 2355139 | 18256.8915 | 100 |  | 1 | Programme Management | Ex-Ante | 2017-01-01 | 2017-02-01
MNS | Office Attendants- Temporary services |  | 3CV | 18-1611t | 300000 | 2325.5814 | 100 |  | 4 | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 |  | These individuals are to be temporarily engaged to relieve those who opt to take vacation days
MNS | Community Case Management Officers |  | 3CV | 18-1611u | 7347116 | 56954.3876 | 100 |  | 2 | Programme Management | Ex-Ante | 2018-01-01 | 2018-01-01 |  | All Regions
MNS | MIS Officer |  | 3CV | 1611ae | 3930511 | 30469.0775 | 100 |  | 1 | Programme Management | Ex-Ante | 2017-08-01 | 2017-09-01
MNS | Accounts Payable Clerk |  | 3CV | 1611ai | 915000 | 7093.0233 | 100 |  | 1 | Programme Management | Ex-Ante | 2017-08-01 | 2017-09-01
MNS | Compliance Coordinator |  | 3CV | 1611aj | 3762655.87 | 29167.875 | 100 |  | 1 | Programme Management | Ex-Ante | 2017-08-01 | 2017-09-01
MNS | Accountant |  | 3CV | 1611ak | 3762655.87 | 29167.875 | 100 |  | 1 | Programme Management | Ex-Ante | 2017-08-01 | 2017-09-01
MNS | Procurement Clerk |  | 3CV | 1611am | 1000000 | 7751.938 | 100 |  | 1 | Programme Management | Ex-Ante | 2017-11-01 | 2017-11-01
MNS | Administrative Assistant - KMA |  | 3CV | 18-1611an | 2813504.6 | 21810.1132 | 100 |  | 1 | Programme Management | Ex-Ante | 2017-12-01 | 2018-01-01
TRAINING
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method |  | Comments
[5 empty] | Estimated Amount, in JA$: | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Annual Training Plan (ATP) | End of Activity
TRANSFERS
Executing Agency: | Transfer Purpose: | Additional Information: |  | Process Number: | Estimated Amount |  |  |  | Associated Component: | Estimated Number of Transfers: | Dates |  | Comments - for UCS include selection method |  | Comments
[5 empty] | Estimated Amount, in JA$: | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Contract Signature | Transfer Date
Exchange Rate | 129
Awarded / In-Process
Civil Works
MNS | Grilling Works - Parade Gardens CMC |  | Shopping | 1122f | 470000 | 3643.4109 | 100 |  | Component 1 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | Ernest McDowell 21.3.17
MNS | Grilling - Central Village CMC |  | Shopping | 1122h | 415776 | 3223.0698 | 100 |  | Component 1 | Ex-Post | 2017-02-01 | 2017-03-01 | Completed
MNS | Minor Repairs - Drewsland Computer Lab |  | Shopping | 1122j | 92100 | 713.9535 | 100 |  | Component 1 | Ex-Post | 2017-02-01 | 2017-03-01 | Completed |  | Damion Franklyn 14.3.17
MNS | Retrofitting of RJ Centres |  | Shopping | 1315(i) | 5607413 | 43468.3178 | 100 |  | Component 3 | Ex-Post | 2017-04-01 | 2017-04-01 | Completed |  | The Modern Ricam Construction 13.4.17
[13 empty] | Completed |  | The Modern Ricam Construction 21.4.17
[13 empty] | Completed |  | Impact Signs Solutions 11.7.17
MNS | Retrofitting of CD Centres |  | Shopping | 1316(xxii) | 3000000 | 23255.814 | 100 |  | Component 3 | Ex-Post | 2017-04-01 | 2017-04-01 | Completed |  | Damion Franklyn 18.4.17
[13 empty] | Completed |  | Cibocon Systems 27.4.17
MNS | Retrofitting of Steer Town Office |  | Shopping | 1611a | 3000000 | 23255.814 | 100 |  | Programme Management | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | Howard Construction 10.3.17
MNS | Minor Works - Montego Bay Office |  | Shopping | 1611ab | 350000 | 2713.1783 | 100 |  | Programme Management | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | WG Northover & Associates 6.7.17
MNS | Minor Works - Kingston Office |  | Shopping | 1611ac | 223000 | 1728.6822 | 100 |  | Programme Management | Ex-Post | 2017-03-01 | 2017-03-01 | Completed
MNS | Minor Works - Gayle Office |  | Shopping | 1611ad | 265400 | 2057.3643 | 100 |  | Programme Management | Ex-Post | 2017-06-01 | 2017-06-01 | Completed |  | Shawn Stoddart 10.4.17
MNS | Water Storage Project -Spanish Town Office |  | Shopping | 1611ag | 1004350 | 7785.6589 | 100 |  | Programme Management | Ex-Post | 2017-07-01 | 2017-07-01 | Completed |  | Modern Ricam 10.8.17
Goods
MNS | Parenting Program - Refreshments and Venue |  | Shopping | 1111a(i) | 13576000 | 105240.3101 | 100 |  | Component 1 | Ex-Post | 2017-07-17 | 2017-07-17 | Completed |  | Hotel Gloriana 8.2.17
[13 empty] | Completed |  | Arians Restaurant 8.2.17
[13 empty] | Completed |  | Shirleys Retreat 9.2.17
[13 empty] | Completed |  | Villa Sonate 9.2.17
[13 empty] | Completed |  | Hotel Gloriana 16.2.17
[13 empty] | Completed |  | Yvonne Williams 03.11.17
[13 empty] | Completed |  | Kingston YM 03.11.17
[13 empty] | Completed |  | Altamont Court Hotel 27.10.17
[13 empty] | Completed |  | Altamont Court Hotel 07.11.17
[13 empty] | Completed |  | Drummonds Catering 12.12.17
MNS | Parenting Program - Stationery |  | Shopping | 1111a(ii) | 466072 | 3612.9612 | 100 |  | Component 1 | Ex-Post | 2017-05-01 | 2017-05-01 | Completed |  | The Stationery Centre
MNS | Parenting Program - ID Cards |  | Shopping | 1111a(iii) | 102500 | 794.5736 | 100 |  | Component 1 | Ex-Post | 2017-05-01 | 2017-05-01 | Awarded |  | Pugh's Photo Lab 05.01.18
MNS | Parenting Program -Polo Shirts ,Tote Bags, etc. |  | Shopping | 1111a(iv) | 350000 | 2713.1783 | 100 |  | Component 1 | Ex-Post | 2017-05-01 | 2017-05-01 | In Process |  | Logo Stitch Manufacturing Limited 15.01.18
MNS | FEP - Personal Development Workshop - Refreshments and venue |  | Shopping | 1111b(v) | 250679 | 1943.2481 | 100 |  | Component 1 | Ex-Post | 2017-03-01 | 2017-03-01 | Completed |  | Arians Restaurant 24.2.17
| FEP - Banners |  | Shopping | 1111b(xv) | 14599.11 | 113.1714 | 100 |  | Component 1 | Ex-Post | 2017-03-01 | 2017-03-01 | Completed |  | National Outdoor Advertising 24.2.17
MNS | Psycho-Ed Workshops - Refreshments and venue |  | Shopping | 1112a(i) | 1680000 | 13023.2558 | 100 |  | Component 1 | Ex-Post | 2017-01-17 | 2017-01-17 | Completed |  | Hotel Gloriana 16.6.17
[13 empty] | Completed |  | Medallion Hall Hotel 19.6.17
[13 empty] | Completed |  | Arians Restaurant 23.6.17
[13 empty] | Completed |  | Arians Restaurant 3.8.17
[13 empty] | Completed |  | Shirley Retreat 3.8.17
[13 empty] | Completed |  | Hotel Gloriana 3.8.17
MNS | Psycho-Ed Workshops - Stationery |  | Shopping | 1112a(ii) | 600000 | 4651.1628 | 100 |  | Component 1 | Ex-Post | 2017-01-17 | 2017-01-17 | Completed |  | Office Supplies Brokers 8.2.17
[13 empty] | Completed |  | The Stationery Centre 28.7.17
MNS | Capacity Building Schools - Refreshments and venue |  | Shopping | 1112b(i) | 900000 | 6976.7442 | 100 |  | Component 1 | Ex-Post | 2017-07-17 | 2017-07-17 | Completed |  | Shiela's Homemade Pastries 24.2.17
[13 empty] | Completed |  | Hotel Gloriana & Spa 28.2.17
[13 empty] | Completed |  | Arians Restaurant 24.2.17
[13 empty] | Completed |  | Hotel Commingle 15.12.17
MNS | Capacity Building Schools - Stationery |  | Shopping | 1112b(ii) | 300000 | 2325.5814 | 100 |  | Component 1 | Ex-Post | 2017-07-17 | 2017-07-17 | Completed |  | Office Supplies 17.2.17
MNS | Group Counselling - Refreshments |  | Shopping | 1112c(i) | 288000 | 2232.5581 | 100 |  | Component 1 | Ex-Post | 2017-04-17 | 2017-04-17 | Completed |  | Denise Ricketts 20.3.17
[13 empty] | Completed |  | Arians Investment 20.3.17
[13 empty] | Completed |  | Yvonne Williams 20.3.17
[13 empty] | Completed |  | Arians Investment 22.3.17
[13 empty] | Completed |  | Yvonne Williams 23.3.17
[13 empty] | Completed |  | Hungry Sams 22.3.17
[13 empty] | Completed |  | Yvonne Williams 10.8.17
MNS | Group Counselling - Stationery |  | Shopping | 1112c(ii) | 96000 | 744.186 | 100 |  | Component 1 | Ex-Post | 2017-04-17 | 2017-04-17 | Completed |  | The Stationery Centre 17.3.17
The Stationery Centre 10.8.17
MNS | Psychometric Instruments |  | Direct Contracting | 1112e(i) | 531000 | 4116.2791 | 100 |  | Component 1 | Ex-Post | 2017-03-17 | 2017-04-17 | Awarded |  | PAR Inc.
MNS | Individual Counseling - Office Furniture & Supplies |  | Shopping | 1112g(i) | 180000 | 1395.3488 |  |  | Component 1 | Ex-Post | 2017-03-01 | 2017-03-01 | Completed |  | Rapid Procurement 3.3.17
[6 empty] | 0 | [6 empty] | Completed |  | Rapid procurement 8.3.17
MNS | Life Skills - Stationery & Supplies |  | Shopping | 1112h(i) | 810000 | 6279.0698 | 100 |  | Component 1 | Ex-Post | 2017-08-01 | 2017-08-01 | Completed |  | Century Business Machines 25.8.17
MNS | Life Skills - Incentive and awards |  | Shopping | 1112h(ii) | 222500 | 1724.8062 | 100 |  | Component 1 | Ex-Post | 2017-08-01 | 2017-08-01
MNS | Life Skills -Venue & Refreshments |  | Shopping | 1112h(iii) | 36765000 | 285000 | 100 |  | Component 1 | Ex-Post | 2017-08-01 | 2017-08-01 | Completed |  | Rosemarie Lyons 15.9.17
[13 empty] | Completed |  | Dappaz restaurant 12.9.17
[13 empty] | Completed |  | Yvonne Williams 25.8.17
[13 empty] | Completed |  | Yvonne Williams 4.9.17
[13 empty] | Completed |  | Mobay E-Learning 12.9.17
[13 empty] | Completed |  | Yvonne Williams 23.8.17
[13 empty] | Completed |  | Institute of Higher Learning 18.10.17
[13 empty] | Completed |  | Golden Academy Resource and Training Centre 18.12.17
[13 empty] | Completed |  | Everybody's Restaurant 27.12.17
MNS | Good News Campaign - Banners |  | Shopping | 1115a(ii) | 300000 | 2325.5814 | 100 |  | Component 1 | Ex-Post | 2017-01-17 | 2017-01-17 | completed |  | Graphic Concepts 27.1.17
[13 empty] | completed |  | National Outdoor Advertising 14.2.17
[13 empty] | completed |  | Mapco Printers 14.7.17
[13 empty] | completed |  | Mapco Printers 15.9.17
| Youth Empowerment Fair |  |  | 1115(xi) | 190000 | 1472.8682 | 100 |  | Component 1 |  | 2017-02-01 | 2017-02-01 | Completed |  | Hitz 92 FM 25.4.17
MNS | Police Citizen Relations - Refreshments |  | Shopping | 1116a | 150000 | 1162.7907 | 100 |  | Component 1 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | Yvonne Williams 3.3.17
MNS | Capacity Building CDCs - Refreshments and venue |  | Shopping | 1121b | 2403000 | 18627.907 | 100 |  | Component 1 | Ex-Post | 2017-01-17 | 2017-01-17 | completed |  | Hotel Gloriana & Spa 25.4.17
MNS | Furniture & Equipment - Multi-Purpose Centres |  | Shopping | 1122b | 2000000 | 15503.876 | 100 |  | Component 1 | Ex-Post | 2017-05-01 | 2017-05-01 | completed |  | The Electronic & Computer Place 30.1.17
MNS | Goods - Grilling Works Central Village |  | Shopping | 1122k | 722000 | 5596.8992 | 100 |  | Component 1 | Ex-Post | 2017-03-01 | 2017-03-01 | completed |  | Deens Hardware 28.3.17
[13 empty] | completed |  | TankWeld 28.3.17
MNS | Peace Buildiing - Trophies, Medals & Certificates |  | Shopping | 1124a | 3150000 | 24418.6047 | 100 |  | Component 1 | Ex-Post | 2017-03-01 | 2017-03-01 | completed |  | Chalcass Trophies 15.3.17
[13 empty] | completed |  | WB Trophies 21.3.17
MNS | VST - Stationery |  | Shopping | 1212a(i) | 100000 | 775.1938 | 100 |  | Component 2 | Ex-Post | 2017-01-17 | 2017-01-17 | completed |  | Stationery & Office Supplies 22.2.17
[13 empty] | completed |  | Office Supplies Brokers 14.3.17
[13 empty] | completed |  | Century Business 27.3.17
MNS | VST - Stationery |  | Direct Contracting | 1212a(ii) | 50000 | 387.5969 | 100 |  | Component 2 | Ex-Post | 2017-01-17 | 2017-01-17 | completed |  | Jamaica Printing Services 22.2.17
| VST - Training Material |  | Shopping | 1212f | 90000 | 697.6744 | 100 |  | Component 2 | Ex-Post | 2017-01-17 | 2017-01-17 | completed |  | Rapid Procurement 05.01.18
MNS | Job Readiness - Refreshments and venue |  | Shopping | 1221a | 1460000 | 11317.8295 | 100 |  | Component 2 | Ex-Post | 2017-01-17 | 2017-01-17 | completed |  | Hungry Sam'a Restaurant 23.2.17
MNS | On-the-Job - Safety Gears |  | Shopping | 1222a(i) | 9725000 | 75387.5969 | 100 |  | Component 2 | Ex-Post | 2017-04-01 | 2017-04-01 | completed |  | Jamaica Public Service 27.4.17
MNS | Summer Employment - Refreshments |  | Shopping | 1222b(i) | 400000 | 3100.7752 | 100 |  | Component 2 | Ex-Post | 2017-07-17 | 2017-07-17 | completed |  | Yvonne Williams 23.6.17
[13 empty] | completed |  | Yvette Mason 23.6.17
[13 empty] | completed |  | Oral Farquhan 23.6.17
[13 empty] | completed |  | Marjorie Johnson Wolfe 23.6.17
[13 empty] | completed |  | Daphne Matthews 23.6.17
[13 empty] | completed |  | Yvonne Williams 25.7.17
[13 empty] | completed |  | Citas Cakes n Catering 27.7.17
MNS | Summer Diversion - Stationery |  | Shopping | 1222b(iv) | 40000 | 310.0775 | 100 |  | Component 2 | Ex-Post | 2017-07-17 | 2017-07-17 | completed |  | The Stationery Centre 19.6.17
MNS | Stakeholder workshops - Refreshments and Venue |  | Shopping | 18-1311(ii) | 960000 | 7441.8605 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 | In Process
MNS | Office Furniture and equipment including IT |  | Shopping | 1311(iv) | 1000000 | 7751.938 | 100 |  | Component 3 | Ex-Post | 2017-05-01 | 2017-05-01 | completed |  | The Stationery Centre 18.12.17
[13 empty] | completed |  | Century Business Machines 18.12.17
[13 empty] | completed |  | Modern Refrigeration & Air Conditioning 18.10.17
MNS | Stakeholder workshops - refreshments |  | Shopping | 1311(v) | 180000 | 1395.3488 | 100 |  | Component 3 | Ex-Post | 2017-05-01 | 2017-05-01 | completed |  | Maurva Catering Service 15.9.17
MNS | Cultural Resocialisation - Therapeutic Tools |  | Shopping | 1311c(ii) | 840000 | 6511.6279 | 100 |  | Component 3 | Ex-Post | 2017-06-01 | 2017-06-01 | completed |  | Logo Stitch Manufacturing 18.9.17
[13 empty] | completed |  | General Trading 15.9.17
[13 empty] | completed |  | Media Impact 15.9.17
[13 empty] | completed |  | Logo Stitch 15.9.17
[13 empty] | completed |  | New Horizon 15.9.17
[13 empty] | completed |  | Campbells Office Supplies 14.9.17
MNS | SIP - Refreshments |  | Shopping | 1311c(v) | 615000 | 4767.4419 | 100 |  | Component 3 | Ex-Post | 2017-07-01 | 2017-07-01 | completed |  | Mother's Enterprise 31.10.17
MNS | Cultural Resocialisation - T/Polo Shirts |  | Shopping | 1311c(iv) | 275000 | 2131.7829 | 100 |  | Component 3 | Ex-Post | 2017-10-01 | 2017-10-01 | completed |  | Logo Stitch 15.9.17
MNS | SIP - Resource Materials and stationery |  | Shopping | 1311c(vii) | 210000 | 1627.907 | 100 |  | Component 3 | Ex-Post | 2017-05-01 | 2017-05-01 | completed |  | Office Supplies Brokers 11.10.17
New Horizon 11.10.17
MNS | Overcomers In Action - Resource Material and Stationery |  | Shopping | 1311c(ix) | 107005 | 829.4961 | 100 |  | Component 3 | Ex-Post | 2017-08-01 | 2017-08-01 | completed |  | Century Business 11.10.17
[13 empty] | completed |  | New Horizon Pharmacy 11.10.17
[13 empty] | completed |  | Hyltons Limited 24.10.17
[13 empty] | completed |  | New Horizons 10.12.17
[13 empty] | completed |  | Century Business 10.10.17
MNS | West Kingston - SIP - Therapeutic Tools |  | Shopping | 1311c(xvii) | 300000 | 2325.5814 | 100 |  | Component 3 | Ex-Post | 2017-08-01 | 2017-08-01 | completed |  | New Horizons 18.10.17
| Children In Court - Play Therapy Tools |  | Shopping | 1311d(iv) | 500000 | 3875.969 | 100 |  | Component 3 | Ex-Post | 2017-05-01 | 2017-05-01 | completed |  | Azan Super Centre 23.3.17
[13 empty] | completed |  | Baby Bop 23.3.17
MNS | Public Awareness - Brochures and Paraphernalia |  | Shopping | 1311e(i) | 300000 | 2325.5814 | 100 |  | Component 3 | Ex-Post | 2017-05-01 | 2017-05-01 | completed |  | Jemar Printery 4.9.17
[13 empty] | completed |  | Jemar Printing 8.9.17
[13 empty] | completed |  | Mapco Printing 8.9.17
[13 empty] | completed |  | Hott Off The Press 18.10.17
[13 empty] | completed |  | Emkay Sports 18.10.17
[13 empty] | completed |  | Media Impact 18.10.17
| Office Furniture & Equipment |  | Shopping | 1312 | 600000 | 4651.1628 | 100 |  | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | completed |  | The Electronic & Computer Place 10.2.17
[13 empty] | completed |  | Century Business Machines 24.1.17
MNS | Training - Stationery and resource materials |  | Shopping | 1312c(ii) | 90000 | 697.6744 | 100 |  | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | completed |  | Neveast 27.3.17
[13 empty] | completed |  | Office Supplies 27.3.17
[13 empty] | completed |  | Century Business 27.3.17
[13 empty] | completed |  | office Supplies Brokers 27.3.17
MNS | Legal Aid Fairs - Refreshments and venue |  | Shopping | 1312d(i) | 1351961 | 10480.3178 | 100 |  | Component 3 | Ex-Post | 2017-03-01 | 2017-03-01 | completed |  | Sheilas Homemade Pastries 27.3.17
[13 empty] | completed |  | Icon Importers & Distributors 25.5.17
[13 empty] | completed |  | Melody Allen 25.5.17
[13 empty] | completed |  | Dappaz Restau 27.9.17
[13 empty] | completed |  | Verna's Restaurant 13.7.17
[13 empty] | completed |  | Greendale Citizens Association 14.7.17
MNS | Legal Aid Fairs - Resource Materials |  | Shopping | 1312d(ii) | 90000 | 697.6744 | 100 |  | Component 3 | Ex-Post | 2017-03-01 | 2017-03-01 | completed |  | Century Business Machines 29.3.17
MNS | Service Points - Resource materials and fliers |  | Shopping | 1312f | 225000 | 1744.186 | 100 |  | Component 3 | Ex-Post | 2017-04-01 | 2017-04-01 | completed |  | Hot Off The Press 23.3.17
[13 empty] | completed |  | Mapco Printers 23.3.17
[13 empty] | completed |  | Mapco 13.7.17
MNS | Printers |  | Shopping | 1313(ii) | 1557000 | 12069.7674 | 100 |  | Component 3 | Ex-Post | 2017-04-01 | 2017-04-01 | Completed |  | The Electronics & Computer Place 7.3.17
MNS | Qualifying Training - Refreshments and venue |  | Shopping | 1313b(i) | 2028348 | 15723.6279 | 100 |  | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | Melody Allen 1.5.17
[13 empty] | Completed |  | Hotel Tim Bamboo 2.5.17
[13 empty] | Completed |  | Icon Importers & Distributors 3.5.17
[13 empty] | Completed |  | Casa Maria Hotel 29.5.17
[13 empty] | Completed |  | Farmers Training Centre 28.8.17
[13 empty] | Completed |  | Jamaica Red Cross 28.8.17
[13 empty] | Completed |  | Golf View Hotel 15.9.17
[13 empty] | Completed |  | White Diamond Hotel 11.9.17
[13 empty] | Completed |  | STETHS 24.10.17
[13 empty] | Completed |  | Amekia's Catering 24.10.17
[13 empty] | Completed |  | Maurva Cunningham 25.10.17
[13 empty] | Completed |  | Claudette Lewis 03.11.17
[13 empty] | Completed |  | Galina Breeze 08.11.17
[13 empty] | Completed |  | Idlers Rest Beach Hotel 14.11.17
[13 empty] | Completed |  | Claudette Lewis 11.10.17
[13 empty] | Completed |  | Lorine Metcalfe 2.09.17
[13 empty] | Completed |  | Webley Centre of Excellence 11.09.17
[13 empty] | Completed |  | Farmers Training Centre 29.8.17
[13 empty] | Completed |  | Almond Tree Restaurant 15.09.17
MNS | Qualifying Training - Refreshments and venue |  | Shopping | 18-1313b(i) | 7260000 | 56279.0698 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 | In Process |  | Hope Wright 13.01.17
MNS | Qualifying Training -Stationery and Course Material |  | Shopping | 18-1313b(ii) | 1200000 | 9302.3256 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 | In Process |  | Office Supplies Brokers 16.01.18
MNS | Qualifying Training -Stationery and Course Material |  | Shopping | 1313b(ii) | 120000 | 930.2326 | 100 |  | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | Office Supplies Brokers 2.5.17
[13 empty] | Completed |  | Impact Signs Solutions 31.1.17
[13 empty] | Completed |  | Hot Off the Press 1.2.17
[13 empty] | Completed |  | Jemar Printery 1.2.17
[13 empty] | Completed |  | Mapco 30.1.17
[13 empty] | Completed |  | Office Outlet 04.09.17
[13 empty] | Completed |  | Copy Shop 2.10.17
[13 empty] | Completed |  | Copy Shop 22.9.17
[13 empty] | Completed |  | Office Supplies 30.05.17
[13 empty] | Completed |  | Century Business Machines 30.05.17
[13 empty] | Completed |  | Office Outlet Limited 28.08.17
MNS | Advanced Training - Refreshments and venue |  | Shopping | 1313c(i)-i | 10084933 | 78177.7752 | 100 |  | Component 3 | Ex-Post | 2017-04-01 | 2017-04-01 | Completed |  | Maurva Catering Service 8.2.17
[13 empty] | Completed |  | Maurva Catering Service 9.2.17
[13 empty] | Completed |  | West Jamaica Conference 16.2.17
[13 empty] | Completed |  | NCU 3.4.17
[13 empty] | Completed |  | Phillipop Baptist 24.5.17
[13 empty] | Completed |  | The Wexford Hotel 31.5.17
[13 empty] | Completed |  | Golf View 18.7.17
[13 empty] | Completed |  | Angela McPherson 25.7.17
[13 empty] | Completed |  | Casa Maria Hotel 15.9.17
[13 empty] | Completed |  | Lorna Nembhard 18.8.17
[13 empty] | Completed |  | St Elizabeth Technical 17.8.17
[13 empty] | Completed |  | Sandals Ocho Rios 2.3.17
[13 empty] | Completed |  | Sandals Ocho Rios 2.3.17
[13 empty] | Completed |  | Youth Services Division/HEART TRUST NTA 20.7.17
[13 empty] | Completed |  | Almond Tree Restaurant 15.9.17
[13 empty] | Completed |  | Whispering Bamboo 12.10.17
[13 empty] | Completed |  | Whispering Bamboo 4.12.17
[13 empty] | Completed |  | Grandioas Hotel 06.10.17
[13 empty] | Completed |  | Hotel Tim Bamboo 13.10.17
[13 empty] | Completed |  | Arians Investment 25.05.17
[13 empty] | Completed |  | Angela McPherson 12.09.17
[13 empty] | Completed |  | International University of the Caribbean 14.06.17
MNS | Advanced Training - Refreshments and venue |  | Direct Contracting | 1313c(i)-ii | 2200000 | 17054.2636 | 100 |  | Component 3 | Ex-Ante | 2017-01-01 | 2017-02-01 | Completed |  | UDC 31.1.17
MNS | Advanced Training - Stationery & Course Material |  | Shopping | 1313c(ii) | 1037000 | 8038.7597 | 100 |  | Component 3 | Ex-Post | 2017-04-01 | 2017-04-01 | Completed |  | Pear Tree Xpress 16.2.17
[13 empty] | Completed |  | Century Business 16.2.17
[13 empty] | Completed |  | Office Outlet 26.5.17
[13 empty] | Completed |  | Office Supplies Brokers 26.5.17
[13 empty] | Completed |  | Century Business Machines 16.11.17
[13 empty] | Completed |  | Century Business Machines 04.12.17
[13 empty] | Completed |  | Office Supplies 26.05.17
MNS | Stationery & Office Supplies |  | Shopping | 18-1315(ii) | 700000 | 5426.3566 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 | In Process |  | Worldwide Technology 03.01.18
MNS | School Administration Training - Refreshments and venue |  | Shopping | 18-1315b(i) | 5998000 | 46496.124 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 | In Process |  | Sagicor Pooled Investment Fund/Jewel Run Away Bay 15.01.18
MNS | Furniture, Equipment and Appliances for RJ Centres |  | Shopping | 1315(ii) | 2661030 | 20628.1395 | 100 |  | Component 3 | Ex-Post | 2017-05-01 | 2017-05-01 | Completed |  | Rapid Procurement 21.4.17
[13 empty] | Completed |  | Century Business Machines 25.4.17
[13 empty] | Completed |  | Rapid Procurement 23.3.17
[13 empty] | Completed |  | Century Business Machines 23.3.17
[13 empty] | Completed |  | Century Business Machines 20.2.17
[13 empty] | Completed |  | Office Supplies Brokers 22.5.17
[13 empty] | Completed |  | Century Business Machines 22.5.17
[13 empty] | Completed |  | One Stop Computers 25.5.17
[13 empty] | Completed |  | Worldwide 25.5.17
[13 empty] | Completed |  | Azan Super Centre 29.5.17
[13 empty] | Completed |  | Century Business 21.9.17
[13 empty] | Awarded |  | NevEast Office Depot 05.01.18
[13 empty] | Completed |  | The Electronics & Computer Place 29.5.17
[13 empty] | Completed |  | Office Supplies Brokers 6.10.17
[13 empty] | Completed |  | Singer Jamaica Limited 07.11.17
[13 empty] | Completed |  | Comfort Systems Limited 16.11.17
MNS | Stationery & Office Supplies |  | Shopping | 1315(iii) | 1356124 | 10512.5891 | 100 |  | Component 3 | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | The Stationery Centre 22.3.17
[13 empty] | Completed |  | Century Business Machines 2.2.17
[13 empty] | Completed |  | The Stationery Centre 3.3.17
[13 empty] | Completed |  | PBS 28.2.17
[13 empty] | Completed |  | Tara Courier Services
[13 empty] | Completed |  | Productive Business Solutions 23.3.17
[13 empty] | Completed |  | Office Supplies Brokers 10.2.17
[13 empty] | Completed |  | The Stationery Centre 20.3.17
[13 empty] | Completed |  | Campbell Office Supplies 11.5.17
[13 empty] | Completed |  | Sampars Cash & Carry 15.5.17
[13 empty] | Completed |  | Office Supplies Brokers 14.7.17
[13 empty] | Completed |  | Campbells Supplies 14.7.17
[13 empty] | Completed |  | Sampars Cash & Carry 8.9.17
[13 empty] | Completed |  | General Trading 8.9.17
[13 empty] | Completed |  | General Trading 15.9.17
[13 empty] | Completed |  | Viomark Trading Co 6.10.17
[13 empty] | Completed |  | The Stationery Centre 12.01.17
[13 empty] | Completed |  | The Stationery Centre 07.07.17
[13 empty] | Completed |  | Sampars Cash & Carry 04.07.17
[13 empty] | Completed |  | The Stationery Centre 16.11.17
[13 empty] | Completed |  | Sampars Cash & Carry 07.04.17
[13 empty] | Completed |  | Century Business Machines 25.10.17
[13 empty] | Completed |  | The Electronics & Computer Place 14.07.17
MNS | RJ Week -Refreshments and venue |  | Shopping | 1315(iv)-i | 1100000 | 8527.1318 | 100 |  | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | Smith & Stewart 23.1.17
[13 empty] | Completed |  | Ja. Pegasus 4.1.17 & 20.1.17
[13 empty] | Completed |  | Karleen Smith & Company 19.1.17
[13 empty] | Completed |  | Karleen Smith & Company 19.1.17
[13 empty] | Completed |  | Flamin Wok Catering 2.2.17
MNS | RJ Week -Refreshments and venue |  | Direct Contracting | 1315(iv)-ii | 275078 | 2132.3876 | 100 |  | Component 3 | Ex-Ante | 2017-01-01 | 2017-02-01 | Completed |  | NHT 30.1.17
[13 empty] | Completed |  | Guardsman 30.1.17
[13 empty] | Completed |  | Hope Gardens 30.1.17
[13 empty] | Completed |  | St James Parish Council 30.1.17
[13 empty] | Completed |  | Girls Guides Association 30.1.17
[13 empty] | Completed |  | Port Authority Mgmt Services 30.1.17
MNS | RJ Week - Conference Materials |  | Shopping | 1315(vi) | 240000 | 1860.4651 | 100 |  | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | Touchline 19.1.17
[13 empty] | Completed |  | The Stationery Centre 1.2.17
[13 empty] | Completed |  | Century Business Machines 12.01.17
MNS | RJ Multi-Media Campaign - Paraphernalia |  | Shopping | 1315(vii) | 1000000 | 7751.938 | 100 |  | Component 3 | Ex-Post | 2017-11-01 | 2017-11-01 | Completed |  | Logo Stitch 24.1.17
[13 empty] | Completed |  | West indies Promotion 25.1.17
[13 empty] | Completed |  | Logo Stitch 2.2.17
[13 empty] | Completed |  | Logo Stitch 30.1.17
[13 empty] | Completed |  | Mapco printers 1.2.17
[13 empty] | Completed |  | Logo Stitch 11.5.17
[13 empty] | Completed |  | Mapco Printers 16.3.17
[13 empty] | Completed |  | National Outdoor Advertising 9.3.17
[13 empty] | Completed |  | Logo Stitch 4.7.17
[13 empty] | Completed |  | Mapco Printers 13.7.17
[13 empty] | Completed |  | Media Impact 24.10.17
MNS | Refresher workshops - refreshments |  | Shopping | 1315b(i) | 660000 | 5116.2791 | 100 |  | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | Yvonne Williams 20.6.17
MNS | School Administration Training - Refreshments and venue |  | Shopping | 1315b(iii) | 2520000 | 19534.8837 | 100 |  | Component 3 | Ex-Post | 2017-10-01 | 2017-10-01 | Completed |  | Jamaica Employers Federation 6.3.17
[13 empty] | Completed |  | Jewel Runaway Bay 13.10.17
MNS | Training RJ Volunteers - Stationery and course materials |  | Shopping | 1315b(vii) | 200000 | 1550.3876 | 100 |  | Component 3 | Ex-Post | 2017-05-01 | 2017-05-01 | Completed |  | Office Supplies Brokers 6.7.17
[13 empty] | Completed |  | Media Impact 14.7.17
MNS | Staff Development - Refreshments and venue |  | Shopping | 1315b(x) | 120000 | 930.2326 | 100 |  | Component 3 | Ex-Post | 2017-06-01 | 2017-06-01 | Completed |  | Surrey Hotel management 21.6.17
MNS | Staff Development - Stationery and resource materials |  | Shopping | 1315b(xi) | 40000 | 310.0775 | 100 |  | Component 3 | Ex-Post | 2017-06-01 | 2017-06-01 | Completed |  | UWI Bookshop 19.6.17
[13 empty] | Completed |  | Logo Stitch Manufacturing 20.6.17
MNS | IIRP Materials |  | Direct Contracting | 1315b(xxiv) | 750000 | 5813.9535 | 100 |  | Component 3 | Ex-Ante | 2017-10-01 | 2017-11-01 | Awarded |  | IIRP has proprietary rights to the materials being purchased.
MNS | RJ Sensitization - Refreshments and venue |  | Shopping | 1315c(i) | 2617581 | 20291.3256 | 100 |  | Component 3 | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | Karleen Smith & Company 23.1.17
[13 empty] | Completed |  | Karleen Smith & Company 23.1.17
[13 empty] | Completed |  | Yvonne Williams 16.3.17
[13 empty] | Completed |  | Maurva Cunningham 18.12.17
[13 empty] | Completed |  | Yvonne Williams 23.3.17
[13 empty] | Completed |  | Yvonne Williams 27.3.17
[13 empty] | Completed |  | Mona Visitors Lodge 2.5.17
[13 empty] | Completed |  | Yvonne Williams 24.5.17
[13 empty] | Completed |  | Nadine Simpson 10.7.17
[13 empty] | Completed |  | Mona Visitors Lodge 04.01.17
[13 empty] | Completed |  | Drummonds Catering 16.11.17
[13 empty] | Completed |  | Western Fast Food 29.08.17
MNS | Stationery & Office Supplies |  | Shopping | 1316(iii) | 316402 | 2452.7287 | 100 |  | Component 3 | Ex-Post | 2017-05-01 | 2017-05-01 | Completed |  | The Stationery Centre 1.2.17
[13 empty] | Completed |  | Office Supplies Brokers 14.3.17
[13 empty] | Completed |  | Productive Solutions 1.2.17
[13 empty] | Completed |  | General Trading 24.5.17
[13 empty] | Completed |  | Sampars Cash & Carry 24.5.17
MNS | Training Workshops - Refreshments and venue |  | Shopping | 1316(vi) | 1905888 | 14774.3256 | 100 |  | Component 3 | Ex-Post | 2017-06-01 | 2017-06-01 | Completed |  | Maurva Cunningham 23.3.17
[13 empty] | Completed |  | Maurva Cunningham 10.5.17
MNS | Training - Equipment |  | Shopping | 1316(viii) | 50000 | 387.5969 | 100 |  | Component 3 | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | Worldwide Technology 10.4.17
MNS | Case Management System - Tablets |  | Shopping | 1511a | 5000000 | 38759.6899 | 100 |  | Component 5 | Ex-Ante | 2017-05-01 | 2017-05-01 | Completed |  | Unicorp Solutions 25.7.17
MNS | Case Management - Refreshments and venue |  | Shopping | 1511c | 886919 | 6875.3411 | 100 |  | Component 5 | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | Activity to be carried out on an ongoing basis
MNS | Case Management -Stationery |  | Shopping | 1511d | 400000 | 3100.7752 | 100 |  | Component 5 | Ex-Post | 2017-06-01 | 2017-06-01 | Completed |  | The Electronics & Computer Place 21.12.16
MNS | M & E - Refreshments and venue |  | Shopping | 18-1513c | 1060000 | 8217.0543 | 100 |  | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01 | Awarded |  | Northern Caribbean University 05.01.18
| M & E - Hardware & Software |  | Shopping | 1513a(i) | 550000 | 4263.5659 | 100 |  | Component 5 | Ex-Post | 2017-03-01 | 2017-03-01 | Completed |  | Unicorp Solutions 6.3.17
[13 empty] | Completed |  | Innovative Solutions
| M & E - Office Furniture |  | Shopping | 1513a(ii) | 50000 | 387.5969 | 100 |  | Component 5 | Ex-Post | 2017-03-01 | 2017-03-01 | Completed |  | Neveast 2.5.17
[13 empty] | Completed |  | Office Supplies Brokers 20.3.17
MNS | M & E - Stationery |  | Shopping | 1513d(i) | 312351 | 2421.3256 | 100 |  | Component 5 | Ex-Post | 2017-03-01 | 2017-03-01 | Completed |  | Century Business 19.1.17
[13 empty] | Completed |  | Office Supplies 20.3.17
[13 empty] | Completed |  | One Stop Computers 22.6.17
MNS | M & E - Stationery |  | Direct Contracting | 1513d(ii) | 100000 | 775.1938 | 100 |  | Component 5 | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | This includes the purchase of CSJP branded envelopes which are only obtainable from one source, the Jamaica Printing Services Limited. Bank's no-objections received vide CCB/CJA/1023/2016, 298/2016, 295/2016, 245/2016
MNS | Community Survey - Refreshments and Venue |  | Shopping | 1517a | 400000 | 3100.7752 | 100 |  | Component 5 | Ex-Post | 2017-07-17 | 2017-07-17 | Completed |  | The Wexford Hotel 4.7.17
[13 empty] | Completed |  | Dappaz 29.6.17
[13 empty] | Completed |  | Alhambra Inn 29.6.17
[13 empty] | Completed |  | NCU 10.7.17
[13 empty] | Completed |  | Yvonne Williams 10.7.17
MNS | Community Survey - Stationery |  | Shopping | 1517b | 59500 | 461.2403 | 100 |  | Component 5 | Ex-Post | 2017-07-17 | 2017-07-17 | Completed |  | The Stationery Centre 29.6.17
[13 empty] | Completed |  | Office Supplies Brokers 10.7.17
MNS | Other Surveys/Assessments - Refreshments and venue |  | Shopping | 1524a | 150000 | 1162.7907 | 100 |  | Component 5 | Ex-Post | 2017-04-01 | 2017-04-01 | Completed |  | Hungry Sams 20.3.17
[13 empty] | Completed |  | Yvonne Williams 2.5.17
MNS | Stationery & Office Supplies |  | Shopping | 18-1611b(i) | 2715000 | 21046.5116 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 |  | In Process | Consumer Meat Plus 17.01.18
MNS | Stationery & Office Supplies |  | Shopping | 1611b(i) | 2810587 | 21787.4961 | 100 |  | Programme Management | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | The Electronics & Computer Place 21.12.16
[13 empty] | Completed |  | Office Supplies Brokers Limited 12.1.17
[13 empty] | Completed |  | Century Business machines 31.1.17
[13 empty] | Completed |  | Modern Rubber Stamp 9.3.17
[13 empty] | Completed |  | Campbells Office Supplies 14.3.17
[13 empty] | Completed |  | Office Supplies Brokers 17.3.17
[13 empty] | Completed |  | Camcorp Industrial 27.3.17
[13 empty] | Completed |  | Office Supplies Brokers 27.3.17
[13 empty] | Completed |  | The Stationery Centre 4.4.17
[13 empty] | Completed |  | Consumer Meat plus 4.4.17
[13 empty] | Completed |  | Camcorp Industrial 25.4.17
[13 empty] | Completed |  | Campbells 13.6.17
[13 empty] | Completed |  | Century Business 13.6.17
[13 empty] | Completed |  | One Stop 14.6.17
[13 empty] | Completed |  | Sampars Cash & carry 20.6.17
[13 empty] | Completed |  | Rapid Procurement 5.7.17
[13 empty] | Completed |  | Sanmerna Paper Products 11.7.17
[13 empty] | Completed |  | Viomark Trading Company 3.8.17
[13 empty] | Completed |  | Campbells Office Supplies 2.8.17
[13 empty] | Completed |  | Office Supplies Brokers 15.8.17
[13 empty] | Completed |  | Office Supplies Brokers 8.9.17
[13 empty] | Completed |  | Consumer Meat Plus 19.9.17
[13 empty] | Completed |  | Sampars 9.10.17
[13 empty] | Completed |  | Sanmerna Paper Products 11.01.18
MNS | Stationery & Office Supplies |  | Shopping | 1611b(ii) | 500000 | 3875.969 | 100 |  | Programme Management | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | Ja. Printing Services 27.1.17
[13 empty] | Completed |  | Jamaica Printing Services 17.8.17
MNS | Furniture & Office Equipment |  | Shopping | 18-1611c | 450000 | 3488.3721 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 | In Process |  | Comfort Systems 05.01.18
MNS | Furniture & Office Equipment |  | Shopping | 1611c | 4528921 | 35107.9147 | 100 |  | Programme Management | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | Century Business 23.1.17
[13 empty] | Completed |  | Singer Ja Ltd 25.1.17
[13 empty] | Completed |  | Century Business Machines 2.2.17
[13 empty] | Completed |  | One Stop 9.2.17
[13 empty] | Completed |  | Century Business Machines 15.2.17
[13 empty] | Completed |  | Appliance Traders Limited 17.2.17
[13 empty] | Completed |  | Office Supplies Brokers 21.2.17
[13 empty] | Completed |  | Appliance Traders Limited 24.2.17
[13 empty] | Completed |  | Century Business Machines 24.2.17
[13 empty] | Completed |  | Century Business Machines 3.3.17
[13 empty] | Completed |  | Campbells Office Supplies 16.3.17
[13 empty] | Completed |  | Century Business Machines 23.3.17
[13 empty] | Completed |  | Rapid Procurement 12.6.17
[13 empty] | Completed |  | Century Business machines 15.6.17
[13 empty] | Completed |  | Campbells 2.5.17
[13 empty] | Completed |  | Nev East 2.5.17
[13 empty] | Completed |  | Century Business 2.5.17
[13 empty] | Completed |  | Singer 9.5.17
[13 empty] | Completed |  | Rapid Procurement 7.6.17
[13 empty] | Completed |  | Rapid Procurement 23.6.17
[13 empty] | Completed |  | Copiers & Consumables 24.7.17
[13 empty] | Completed |  | Camcorp Industrial 8.9.17
[13 empty] | Completed |  | Comfort Systems 01.12.17
MNS | IT Equipment |  | Shopping | 1611d | 2497200 | 19358.1395 | 100 |  | Programme Management | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | Unicorp 7.2.17
[13 empty] | Completed |  | Century Business Machines 15.2.17
[13 empty] | Completed |  | Camcorp Industrial 12.4.17
[13 empty] | Completed |  | Rapid Procurement 12.4.17
[13 empty] | Completed |  | The Electronics & Computer Place 12.4.17
[13 empty] | Completed |  | Unicorp 19.4.17
[13 empty] | Completed |  | The Electronics & Computer Place 15.5.17
[13 empty] | Completed |  | Office Supplies Brokers Ltd 10.7.17
[13 empty] | Completed |  | Worldwide Technology 11.7.17
MNS | IT Equipment |  | Direct Contracting | 1611e | 300000 | 2325.5814 | 100 |  | Programme Management | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | Accupoer Jamaica Ltd 27.4.17
[13 empty] | Completed |  | Lime Ja Ltd 4.7.17
[13 empty] | Completed |  | Accupower Jamaica Ltd 2.8.17
MNS | Cheque Leaves |  | Direct Contracting | 1611h | 800000 | 6201.5504 | 100 |  | Programme Management | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | Xsomo International 20.7.17
MNS | Refreshments |  | Shopping | 18-1611g | 500000 | 3875.969 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 | Awarded | In Process | Donna Jervis 03.01.18
MNS | Refreshments |  | Shopping | 1611y | 400000 | 3100.7752 | 100 |  | Programme Management | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | Yvonne Williams 15.2.17
[13 empty] | Completed |  | Hungry Sams 17.3.17
MNS | Tyres - Programme Vehicle |  | Shopping | 1611al | 60000 | 465.1163 | 100 |  | Programme Management | Ex-Post | 2017-10-01 | 2017-10-01 | Completed
Non Consulting Services
MNS | FEP Live Outside Broadcast |  | Shopping | 1111b(xvi) | 125000 | 968.9922 | 100 |  | Component 1 | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | Power 106 24.2.17
MNS | Psycho Ed Workshops - Transportation |  | Shopping | 1112a(iv) | 480000 | 3720.9302 | 100 |  | Component 1 | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | Kiuki Tours & Transport 13.2.17
[13 empty] | Completed |  | Kerron Green 16.2.17
[13 empty] | Completed |  | Leroy Lester 16.2.17
[13 empty] | Completed |  | Real Tours Jamaica 28.2.17
[13 empty] | Completed |  | Sun Island Tours 21.6.17
[13 empty] | Completed |  | Real Tours Jamaica 27.6.17
[13 empty] | Completed |  | Persan Tours 28.6.17
[13 empty] | Completed |  | Persan Tours 9.8.17
[13 empty] | Completed |  | Kiuki Tours 10.8.17
[13 empty] | Completed |  | Donovan Hamilton 14.8.17
[13 empty] | Completed |  | Persan Tours 15.8.17
MNS | Social Marketing Adverts- Engagement of Consulting Firms |  | Direct Contracting | 1115a(vi) | 160000 | 1240.3101 | 100 |  | Component 1 | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | JIS 10.2.17
MNS | Good News Campaign - Facility Branding |  | Shopping | 1115a(vii) | 1000000 | 7751.938 | 100 |  | Component 1 | Ex-Post | 2017-07-01 | 2017-07-01 | Completed |  | Impact Signs Solutions 24.7.17
[13 empty] | Completed |  | Impact Signs Solutions 10.7.17
MNS | Good News Campaign - PIOJ - Streaming |  | Shopping | 1115a(xiv) | 180000 | 1395.3488 | 100 |  | Component 1 | Ex-Post | 2017-11-01 | 2017-11-01 | Completed
MNS | Good News Campaign - PIOJ - Live OB |  | Shopping | 1115a(xv) | 240000 | 1860.4651 | 100 |  | Component 1 | Ex-Post | 2017-11-01 | 2017-11-01 | Completed
| Youth Empowerment Fair |  | Shopping | 1115a(xIi) | 190000 | 1472.8682 | 100 |  | Component 1 | Ex-Post |  |  | Completed |  | Hitz 92 FM 25.4.17
| Capacity Building CDC Transportation |  | Shopping | 1121d | 130000 | 1007.7519 | 100 |  | Component 1 | Ex-Post |  |  | Completed |  | Ceon Howe 30.3.17
MNS | Cultural Resocialization - Transportation |  | Shopping | 1311c(xix) | 195000 | 1511.6279 | 100 |  | Component 3 | Ex-Post | 2017-11-01 | 2017-11-01 | Completed |  | Persan Tours 17.10.17
MNS | Cultural Resocialization - Medical Services |  | Shopping | 1311c(xx) | 40000 | 310.0775 | 100 |  | Component 3 | Ex-Post | 2017-11-01 | 2017-11-01 | Completed |  | Sure Time Emergency Medical Services 15.11.16
MNS | Legal Aid Fairs - Live Outside Broadcast |  | Shopping | 1312d | 600000 | 4651.1628 | 100 |  | Component 3 | Ex-Post | 2017-07-01 | 2017-07-01 | Completed |  | IRIE FM 28.3.17
[13 empty] | Completed |  | IRIE FM 17.7.17
[13 empty] | Completed |  | IRIE FM 19.9.17
MNS | Legal Aid Fairs - Town Crier |  | Shopping | 1312f (ii) | 200000 | 1550.3876 | 100 |  | Component 3 | Ex-Post | 2017-09-01 | 2017-09-01 | Completed |  | T Flex promotions 8.3.17
[13 empty] | Completed |  | Dream Lab Recordings 14.3.17
[13 empty] | Completed |  | Dream Lab Recordings 28.3.17
[13 empty] | Completed |  | Dream Lab Recordings 29.3.17
[13 empty] | Completed |  | Noel Roberts 27.3.17
MNS | Legal Aid Fairs - Rental of chairs, tents, portable toilets, generator |  | Shopping | 1312d(iii) | 1392577 | 10795.1705 | 100 |  | Component 3 | Ex-Post | 2017-03-01 | 2017-03-01 | Completed |  | Vantage One 27.3.17
[13 empty] | Completed |  | Vantage One 27.3.17
[13 empty] | Completed |  | Central Cesspool 27.3.17
[13 empty] | Completed |  | Vantage One 13.7.17
[13 empty] | Completed |  | Ward Cesspool Services 19.9.17
MNS | Qualifying Training - Hotel Accommodation |  | Shopping | 18-1313b(iii) | 1886400 | 14623.2558 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 |  | In Process | Idlers Rest Beach Hotel 19.01.18
MNS | Qualifying Training - Hotel Accommodation |  | Shopping | 1313b(v) | 312000 | 2418.6047 | 100 |  | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | Hotel Commingle 2.1.17
[13 empty] | Completed |  | Casa Maria Hotel 30.5.17
[13 empty] | Completed |  | Golf View Hotel 15.03.17
MNS | Advanced Training -- Hotel Accommodation |  | Shopping | 1313c(vi) | 1352000 | 10480.6202 | 100 |  | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | Idlers Rest Beach Hotel 18.8.17
[13 empty] | Completed |  | The Wexford Hotel 25.5.17
[13 empty] | Completed |  | The Wexford Hotel 31.5.17
[13 empty] | Completed |  | Casa Maria Hotel 27.11.17
[13 empty] | Completed |  | Idlers Rest Beach Hotel 18.10.17
[13 empty] | Completed |  | Casa Maria Hotel 18.10.17
[13 empty] | Completed |  | The Wexford Hotel 14.9.17
MNS | Maintenance of office equipment, appliance and furniture |  | Shopping | 1315(viii) | 90000 | 697.6744 | 100 |  | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | Omar Edwards 15.9.17
[13 empty] | Completed |  | Cold Air Refrigeration 17.5.17
[13 empty] | Completed |  | Digisoft Computer Systems 18.5.17
[13 empty] | Completed |  | Cold Air Refrigeration 16.11.17
MNS | RJ Sensitization - Refreshments and venue |  | Shopping | 18-1315c(i) | 2000000 | 15503.876 | 100 |  | Component 3 | Ex-Post | 2018-01-01 | 2018-01-01 | Awarded |  | Jewel Runaway Bay Beach & Golf Resort 19.01.18
MNS | Maintenance of office equipment, appliance and furniture |  | Direct Contracting | 1315(ix) | 77750 | 602.7132 | 100 |  | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | PBS 30.1.17
[13 empty] | Completed |  | PBS 28.03.17
MNS | Advertisements |  | Direct Contracting | 1315(x) | 80000 | 620.155 | 100 |  | Component 3 | Ex-Post | 2017-05-01 | 2017-05-01 | Completed |  | Jamaica Information Service 23.6.17
Jamaica Information Service 10.02.17
MNS | RJ Week - Décor |  | Shopping | 1315(xii) | 80000 | 620.155 | 100 |  | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | Patricia Spence 2.2.17
[13 empty] | Completed |  | Paradise Catering and Décor 13.01.17
MNS | RJ Week -Live OB |  | Shopping | 1315(xiii) | 150000 | 1162.7907 | 100 |  | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | Power 106 17.01.17
MNS | RJ Week -Rental of equipment |  | Shopping | 1315(xiv) | 237000 | 1837.2093 | 100 |  | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | Strictly Events Jamaica 23.1.17
[13 empty] | Completed |  | Vantage One 23.1.17
MNS | RJ Week -Rental of tents, table, chairs, portable toilets |  | Shopping | 1315(xv) | 119500 | 926.3566 | 100 |  | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | Strictly Events Jamaica 1.2.17
[13 empty] | Completed |  | Strictly Events Jamaica 23.01.17
[13 empty] | Completed |  | Strictly Events Jamaica 17.01.17
[13 empty] | Completed |  | Strictly Events Jamaica 18.01.17
MNS | RJ Week -Transportation |  | Shopping | 1315(xvi) | 180000 | 1395.3488 | 100 |  | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | Everton Esmie 13.2.17
Everton Esmie 13.2.17
Everton Esmie 12.01.17
Everton Esmie 17.01.17
Persan Tours 12.01.17
Persan Tours 08.02.17
MNS | Graduation - Transportation |  | Shopping | 1315b(xvii) | 100000 | 775.1938 | 100 |  | Component 3 | Ex-Post | 2017-05-01 | 2017-05-01 | Completed |  | Persan Tours 24.5.17
[13 empty] | Completed |  | Glenroy Maragh 24.5.17
MNS | Advertisements |  | Direct Contracting | 1411c | 120000 | 930.2326 | 100 |  | Component 4 |  | 2017-07-01 | 2017-07-01 | Completed |  | JIS 6.7.17
[13 empty] | Completed |  | JIS 12.9.17
MNS | Case Management - Refreshments and venue |  | Shopping | 18-1511a | 2210000 | 17131.7829 | 100 |  | Component 5 | Ex-Post | 2018-01-01 | 2018-01-01 | Completed |  | Donna Jervis 05.01.18
[13 empty] | Awarded |  | Donna Jervis 09.01.18
[13 empty] | Completed |  | Grandioas Hotel 10.01.18
MNS | Case Management - Internet Services Tablets |  | Shopping | 1511e | 1409100 | 10923.2558 | 100 |  | Component 5 | Ex-Post | 2017-06-01 | 2017-06-01 | Completed |  | Digicel 4.9.17
MNS | Advertisements |  | Direct Contracting | 1513g | 100000 | 775.1938 | 100 |  | Component 3 | Ex-Post | 2017-02-01 | 2017-03-01 | Completed |  | JIS 24.7.17
[13 empty] | Completed |  | JIS 10.4.17
MNS | Community Survey - Gate Keepers |  | Direct Contracting | 1517e | 300000 | 2325.5814 | 100 |  | Component 5 | Ex-Post | 2017-07-01 | 2017-07-01 | Completed |  | Patricia Ferguson 6.7.17
[13 empty] | Completed |  | odene Younger 6.7.17
[13 empty] | Completed |  | Carol Peterkin 6.7.17
[13 empty] | Completed |  | Antoinette Burke 6.7.17
[13 empty] | Completed |  | Patricia Pearce 6.7.17
[13 empty] | Completed |  | Taskia Manderson 6.7.17
Completed
MNS | Equipment Maintenance |  | Shopping | 1611i | 651500 | 5050.3876 | 100 |  | Programme Management | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | Imaging Systems & Solutions Limited 13.01.17
[13 empty] | Completed |  | Geddes Refrigeration 15.8.17
[13 empty] | Completed |  | Desmond Thomas 05.01.18
[13 empty] | Completed |  | Comfort Systems Ltd. 05.01.18
[13 empty] | Completed |  | Cold Air Refrigeration 19.1.17
[13 empty] | Completed |  | Geddes Refrigeration 11.7.17
[13 empty] | Completed |  | Geddes Refrigeration 19.9.17
[13 empty] | Completed |  | Geddes Refrigeration 13.9.17
MNS | Equipment Maintenance |  | Direct Contracting | 18-1611j | 300000 | 2325.5814 | 100 |  | Programme Management | Ex-Post | 2018-01-01 | 2018-01-01 | Awarded |  | Accupower Jamaica Ltd. 05.01.18
MNS | Equipment Maintenance |  | Direct Contracting | 1611j | 300000 | 2325.5814 | 100 |  | Programme Management | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | Productive Business Solutions 20.2.17
[13 empty] | Completed |  | Productive Business Solutions 6.6.17
[13 empty] | Completed |  | Cable & Wireless 20.6.17
MNS | Boarding of Assets - E-Waste |  | Direct Contracting | 1611n | 100000 | 775.1938 | 100 |  | Programme Management | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | Inet Jamaica Ltd 19.4.17
MNS | Advertisements |  | Direct Contracting | 1611p | 200000 | 1550.3876 | 100 |  | Programme Management | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | Activity to be carried out on an ongoing basis
MNS | Accounting Software Maintenance & Licenses |  | Direct Contracting | 1611q | 1000000 | 7751.938 | 100 |  | Programme Management | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | CER Consultants 10.4.17
[13 empty] | Completed |  | CER Consultants 10.4.17
MNS | Other Admin Services |  | Shopping | 1611r | 1000000 | 7751.938 | 100 |  | Programme Management | Ex-Post | 2017-01-01 | 2017-01-01 | Completed |  | Shawn Stoddart 28.2.17
[13 empty] | Completed |  | Rentokil 20.2.17
[13 empty] | Completed |  | Gordon Laing 12.6.17
[13 empty] | Completed |  | Regency 12.6.17
[13 empty] | Completed |  | Mack Jones Ltd 23.6.17
[13 empty] | Completed |  | Comprehensive Fire Services 17.7.17
[13 empty] | Completed |  | Mack Jones Ltd 27.7.17
[13 empty] | Completed |  | Comprehensive Fire Service 4.10.17
[13 empty] | Completed |  | Target Pest Control 4.10.17
[13 empty] | Completed |  | Mack Jones (Locksmith) Limited 05.01.18
[13 empty] | Completed |  | Rapid Procurement 29.3.17
| Consulting Firms | [13 empty] | Tannya Gayle 15.01.18
MNS | Delivery of Mediation Sessions & Training |  | Single Source Selection | 18-1112h | 25900000 | 200775.1938 | 100 |  | Component | Ex-Ante | 2018-01-18 | 2018-01-18 | Awarded |  | The Dispute Resolution Foundation is the only entity authourized to conduct mediation training and certify mediators.
MNS | Violence Interruption Services - PMI East |  | Single Source Selection | 1113a | 50010000 | 387674.4186 | 100 |  | Component 1 | Ex-Ante | 2017-04-17 | 2017-05-17 | Awarded |  | PMI East 04.7.2017
MNS | Violence Interruption Services - PMI West |  | Single Source Selection | 1113b | 63479594 | 492089.876 | 100 |  | Component 1 | Ex-Ante | 2017-04-17 | 2017-05-17 | Awarded |  | PMI West 29.3.17
MNS | Conflict Resolution Intervention |  | Single Source Selection | 1114i | 25000000 | 193798.4496 | 100 |  | Component 1 | Ex-Ante | 2017-04-01 | 2017-04-01 | Awarded |  | Dispute Resolution Foundation 24.05.17
MNS | Social Norms Baseline Study |  | Selection Based on the Consultants' Qualifications | 1115j | 24000000 | 186046.5116 | 100 |  | Component 1 | Ex-Ante | 2016-08-01 | 2017-03-01 |  |  | C2M2C2 Evaluation Consulting 21.3.17
MNS | Let's Make Peace TV Series |  | Single Source Selection | 1115k | 2000000 | 15503.876 | 100 |  | Component 1 | Ex-Ante | 2017-07-01 | 2017-07-01 | Awarded |  | Television Jamaica Limited 09.10.17
MNS | Critical Intervention - St. James |  | Single Source Selection | 1117 | 40000000 | 310077.5194 | 100 |  | Component 1 | Ex-Ante | 2017-05-01 | 2017-05-01 | Awarded |  | Violence Prevention Alliance 30.6.17
MNS | Development of Community Profiles |  | Single Source Selection | 1123b | 14950164 | 115892.7442 | 100 |  | Component 1 | Ex-Ante | 2017-01-17 | 2017-03-17 | Awarded |  | SDC 2.3.17
MNS | Safety Plans & Audits |  | Single Source Selection | 1123c | 14492859 | 112347.7442 | 100 |  | Component 1 | Ex-Ante | 2017-01-17 | 2017-03-17 | Awarded |  | VPA 28.2.17
MNS | Engagement of CDCs to Implement Community Based Interventions |  | Single Source Selection | 1123d | 33976878 | 263386.6512 | 100 |  | Component 1 | Ex-Ante | 2017-01-17 | 2017-02-17 | Awarded |  | Canaan Heights CDC 31.07.17
[13 empty] | Awarded |  | Grants Pen/Barbican Consultative Committee 12.12.17
[13 empty] | Awarded |  | HWT CDC 31.07.17
[13 empty] | Awarded |  | Fletchers' Land Management 15.9.17
[13 empty] | Awarded |  | Whitehall Citizen Association 21.9.17
[13 empty] | Awarded |  | Combined District of KGN 4 31.08.17
[13 empty] | Awarded |  | Hannah Town CDC 31.07.17
[13 empty] | Awarded |  | Trench Town CDC 30.06.17
[13 empty] | Awarded |  | Rose Town CDC 31.07.17
[13 empty] | Awarded |  | Waterhouse CDC 13.09.17
[13 empty] | Awarded |  | Olympic Gardens CDC 18.09.17
[13 empty] | Awarded |  | Drewsland CDC 31.07.17
[13 empty] | Awarded |  | Marverley Consultative Committee 20.09.17
[13 empty] | Awarded |  | Parade Gardens CDC 12.09.17
[13 empty] | Awarded |  | Tivoli Gardens CDC 31.07.17
[13 empty] | Awarded |  | Greater Brownstown CDC 31.07.17
[13 empty] | Awarded |  | Bonny Gate CDC 30.08.17
[13 empty] | Awarded |  | Rockfort Development Council 31.07.17
[13 empty] | Awarded |  | Tredegar Park CDC 31.07.17
[13 empty] | Awarded |  | Dela Vega City CDC 31.07.17
[13 empty] | Awarded |  | Greendale CDC 31.07.17
[13 empty] | Awarded |  | Central Village CDC 16.11.17
[13 empty] | Awarded |  | Windsor Heights CDC 31.07.17
[13 empty] | Awarded |  | Mile Gully/Warwick Castle CDC 31.07.17
[13 empty] | Awarded |  | York Town CDC 31.07.17
[13 empty] | Awarded |  | Flanker CDC 16.11.17
[13 empty] | Awarded |  | Norwood CDC 31.07.17
[13 empty] | Awarded |  | Rose Heights CDC 30.11.17
[13 empty] | Awarded |  | Mount Salem CDC 26.09.17
[13 empty] | Awarded |  | Pitfour CDC 16.11.17
[13 empty] | Awarded |  | Whitehall CDC 21.09.17
[13 empty] | Awarded |  | Turners CDC 31.07.17
[13 empty] | Awarded |  | Hunts Town CDC 05.07.17
[13 empty] | Awarded |  | Gordpn Pen CDC 16.11.17
MNS | Engagement of JFLL - Pre-vocational skills training |  | Single Source Selection | 1214e | 21043210 | 163125.6589 | 100 |  | Component 2 | Ex-Ante | 2017-03-01 | 2017-03-01 | Awarded |  | JFLL 30.3.17
MNS | Business Development - Ornamental Fish Farming |  | Single Source Selection | 1223 | 367000 | 2844.9612 | 100 |  | Component 2 | Ex-Ante | 2017-09-01 | 2017-09-01 | Completed |  | The Competitiveness Company 30.10.17
MNS | Advanced Training - Mediation |  | Single Source Selection | 1313c(v) | 1320000 | 10232.5581 | 100 |  | Component 3 | Ex-Ante | 2017-04-01 | 2017-04-01 | Completed |  | Dispute Resolution Foundation 20.2.17
MNS | Mid-term Evaluation |  | Selection Based on the Consultants' Qualifications | 1523b | 17800000 | 137984.4961 | 100 |  | Component 5 | Ex-Ante | 2017-01-17 | 2017-01-01 | Awarded |  | Ernst & Young Services Limited 13.10.17
MNS | Insuarnce of PEU's Fixed Assets |  | Single Source Selection | 1611s | 2000000 | 15503.876 | 100 |  | Programme Management | Ex-Ante | 2017-03-01 | 2017-04-01 | Awarded |  | Marathon Insurance Brokers 31.3.17
Individual Consultants
MNS | Parenting Program -Parent Officers |  | 3CV | 1111a(viii) | 4800000 | 37209.3023 | 100 | 10 | Component 1 | Ex-Post | 2017-05-01 | 2017-05-01 | Awarded |  | Sadie Muirhead 09.11.17
[13 empty] | Awarded |  | Zann Locke 09.11.17
[13 empty] | Awarded |  | Arlene Leslie 09.11.17
[13 empty] | Awarded |  | Peaches Watson Creary 09.11.17
[13 empty] | Awarded |  | Norman Powell 09.11.17
[13 empty] | Awarded |  | Mark Lewis 09.11.17
[13 empty] | Awarded |  | Nicole Dennis Sinclair
[13 empty] | Awarded |  | Mario Reid
[13 empty] | Awarded |  | Erica Atkinson
[13 empty] | Awarded |  | Tamekia Brackett
MNS | Parenting Program - Facilitator |  | Single Source Selection | 1111a | 1740000 | 13488.3721 | 100 | 1 | Component 1 | Ex-Post | 2017-05-01 | 2017-05-01 | Awarded |  | Linda Craigie Brown 05.12.17
MNS | Individual Counselling - Referrals |  | Single Source Selection | 1112g(ii) | 1008000 | 7813.9535 | 100 | 30 | Component 1 | Ex-Post | 2017-01-17 | 2017-01-17 | Awarded |  | Anthony Allen 11.8.17
MNS | SSP - Administrators |  | 3CV | 1114j | 5760000 | 44651.1628 | 100 | 6 | Component 1 | Ex-Post | 2017-05-01 | 2017-05-01 | Awarded |  | Jennifer Lambert 29.8.17
[13 empty] | Awarded |  | Alecia Spence 17.7.17
[13 empty] | Awarded |  | Debbie Ade-Gold Thompson 24.7.17
MNS | SSP - Facilitators |  | 3CV | 1114k | 23670000 | 183488.3721 | 100 | 12 | Component 1 | Ex-Post | 2017-05-01 | 2017-05-01 | Awarded |  | Denise Levein 31.8.17
[13 empty] | Awarded |  | Patrice Dixon 31.8.17
[13 empty] | Awarded |  | Yanique Bailey 6.9.17
[13 empty] | Awarded |  | Leon Thompson 17.7.17
[13 empty] | Awarded |  | Wendy Titus 17.7.17
[13 empty] | Awarded |  | Joan Munroe Green 17.7.17
[13 empty] | Awarded |  | Zann Locke 25.7.17
[13 empty] | Awarded |  | Saashauna Morgan 15.12.17
[13 empty] | Awarded |  | Orlando Hamilton 18.12.17
[13 empty] | Awarded |  | Kadian Anderson 15.12.17
MNS | SSP - Project Manager |  | 3CV | 1114l | 2400000 | 18604.6512 | 100 | 1 | Component 1 | Ex-Post | 2017-05-01 | 2017-05-01 | Awarded |  | Kerry Ann Stewart 21.7.17
MNS | Land Surveyor Services |  | Single Source Selection | 1122e | 68320 | 529.6124 | 100 | 1 | Component 1 | Ex-Ante | 2017-01-01 | 2017-02-01 | Completed |  | Carla Baxter 31.1.17
MNS | Training - Facilitators |  | Single Source Selection | 1312c(iii) | 300000 | 2325.5814 | 100 | 4 | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | Melrose Reid 07.12.17
MNS | Updating of JP Directory |  | Comparison of Qualifications - National Individual Consultant | 1313a(i) | 800000 | 6201.5504 | 100 | 1 | Component 3 | Ex-Post | 2017-04-01 | 2017-04-01 | Awarded |  | Denton East 20.03.17
MNS | Qualifying Training - Facilitators |  | Single Source Selection | 1313b(iv) | 225000 | 1744.186 | 100 | 3 | Component 3 | Ex-Post | 2017-04-01 | 2017-04-01 | Completed |  | Carolyn Reid 05.12.17
[13 empty] | Completed |  | George Belnavis 16.11.17
[13 empty] | Completed |  | Carolyn Reid 17.10.17
[13 empty] | Completed |  | George Belnavis 26.09.17
[13 empty] | Completed |  | Andrea Thomas 01.02.17
[13 empty] | Completed |  | Icolin Reid 10.05.17
[13 empty] | Completed |  | Sandria Wong Small 10.10.17
MNS | Advanced Training - Facilitators |  | Single Source Selection | 1313c(iv) | 1380000 | 10697.6744 | 100 | 10 | Component 3 | Ex-Post | 2017-04-01 | 2017-04-01 | Awarded |  | Sondria Wong Small 20.09.17
George Belvanis 05.01.17
MNS | RJ Week -Note takers |  | Shopping | 1315(xx) | 20000 | 155.0388 | 100 | 4 | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | Awarded |  | 3 individuals
MNS | RJ Week -Rapportuers |  | Shopping | 1315(xxi) | 30000 | 232.5581 | 100 | 2 | Component 3 | Ex-Post | 2017-02-01 | 2017-02-01 | Completed |  | Andrene Hutchinson
MNS | RJ Week - Presenter |  | Single Source Selection | 1315(xxii) | 360000 | 2790.6977 | 100 | 1 | Component 3 | Ex-Ante | 2017-02-01 | 2017-02-01 | Completed |  | Sujatha Baliga 06.02.17
MNS | Centre Managers and Office Attendants |  | Comparison of Qualifications - National Individual Consultant | 1315(xxiii) | 7350000 | 56976.7442 | 100 | 10 | Component 3 | Ex-Ante | 2017-10-01 | 2017-10-01 | Awarded
MNS | RJ Sensitization - Facilitators |  | Single Source Selection | 1315c(iv) | 1260000 | 9767.4419 | 100 | 15 | Component 3 | Ex-Post | 2017-01-01 | 2017-01-01 | Awarded |  | Several awards
MNS | RJ Case Conference - Facilitators |  | Single Source Selection | 1315d | 1080000 | 8372.093 | 100 | 15 | Component 3 | Ex-Post | 2017-01-01 | 2017-01-01 | Awarded |  | Several awards
MNS | Training Consultant |  | Comparison of Qualifications - National Individual Consultant | 1316(xxi) | 2000000 | 15503.876 | 100 | 1 | Component 3 | Ex-Post | 2017-06-01 | 2017-06-01 | Completed |  | Jacqueline Sealy-Burke 17.10.17
MNS | Assessment of CDCs |  | 3CV | 1411a | 1800000 | 13953.4884 | 100 | 1 | Component 4 | Ex-Post | 2017-05-01 | 2017-05-01 | Awarded |  | Bridgette Barrett 17.10.17
MNS | Community Survey Consultants |  | Single Source Selection | 1517f | 18100000 | 140310.0775 | 100 | 2 | Component 5 | Ex-Ante | 2017-04-01 | 2017-06-01 | Completed |  | Randy Seepersad 29.6.17
[13 empty] | Completed |  | Annmarie Barnes 29.6.17
MNS | Community Survey - Data Collectors |  | 3CV | 1517g | 7800000 | 60465.1163 | 100 | 50 | Component 5 | Ex-Post | 2017-09-01 | 2017-09-01 | Completed |  | Carla Williams 3.7.17
[13 empty] | Completed |  | Candist Francis 3.7.17
[13 empty] | Completed |  | Chris Ann Bryan 3.7.17
[13 empty] | Completed |  | Shanique Powell 3.7.17
[13 empty] | Completed |  | Tricia Livermore 3.7.17
[13 empty] | Completed |  | Toni Ann Stewart 3.7.17
[13 empty] | Completed |  | Nastassia Gappour 3.7.17
[13 empty] | Completed |  | Tonere Johnson 3.7.17
[13 empty] | Completed |  | achadae Grant 3.7.17
[13 empty] | Completed |  | Kadrean Green 3.7.17
[13 empty] | Completed |  | Alisiea Buchanan 3.7.17
[13 empty] | Completed |  | Kevon McLeish 3.7.17
[13 empty] | Completed |  | Tricia Clarke 3.7.17
[13 empty] | Completed |  | Kereen Baker 3.7.17
[13 empty] | Completed |  | Ricardo Bruff 3.7.17
[13 empty] | Completed |  | Tameka Ferguson 3.7.17
[13 empty] | Completed |  | Tamara Thomas 3.7.17
[13 empty] | Completed |  | Subrina Hall 3.7.17
[13 empty] | Completed |  | Claudette Nicholson 3.7.17
[13 empty] | Completed |  | Leaith McLeod 3.7.17
[13 empty] | Completed |  | Tanika Thompson 3.7.17
[13 empty] | Completed |  | Tanisha Reid 3.7.17
[13 empty] | Completed |  | Shellon Simpson 3.7.17
[13 empty] | Completed |  | Kerry- Ann Wright 3.7.17
[13 empty] | Completed |  | Juliet McLeod 3.7.17
[13 empty] | Completed |  | Dorsia Allen 3.7.17
[13 empty] | Completed |  | Allan Campbell 3.7.17
[13 empty] | Completed |  | Brian Kelly 3.7.17
[13 empty] | Completed |  | Casandra McKenzie 3.7.17
[13 empty] | Completed |  | Doreen Hall Millwood 3.7.17
[13 empty] | Completed |  | Janice Bent Carr 3.7.17
[13 empty] | Completed |  | Dorret Allen 3.7.17
[13 empty] | Completed |  | David McLaren 3.7.17
[13 empty] | Completed |  | Myrtle Lewis-Wright 3.7.17
[13 empty] | Completed |  | Karen Lawrence 3.7.17
[13 empty] | Completed |  | Wendy Williams 3.7.17
[13 empty] | Completed |  | Lisa Cohen 3.7.17
[13 empty] | Completed |  | Ruhette Dixon 3.7.17
[13 empty] | Completed |  | Stacy Todd 3.7.17
[13 empty] | Completed |  | Sherril Gooden 3.7.17
[13 empty] | Completed |  | Mikel Allen 3.7.17
[13 empty] | Completed |  | Kerrian Allen 3.7.17
[13 empty] | Completed |  | Amunike Peddie 3.7.17
[13 empty] | Completed |  | Shakera Williams 3.7.17
[13 empty] | Completed |  | Shadine Pinnock 3.7.17
[13 empty] | Completed |  | Carlington Lawrence 3.7.17
[13 empty] | Completed |  | Wendy Titus 3.7.17
[13 empty] | Completed |  | Teneisha Cleghorn 3.7.17
[13 empty] | Completed |  | Latoya Dennis 3.7.17
[13 empty] | Completed |  | Lesrine Harvey 3.7.17
[13 empty] | Completed |  | Francesca McGhie 3.7.17
[13 empty] | Completed |  | Keisha Shettlewood 3.7.17
[13 empty] | Completed |  | Stacy Todd 3.7.17
[13 empty] | Completed |  | Stephanie Taylor Francis 3.7.17
[13 empty] | Completed |  | Rochelle powell 3.7.17
[13 empty] | Completed |  | Chantae Smart 3.7.17
[13 empty] | Completed |  | Mellissa Orr 3.7.17
[13 empty] | Completed |  | Shurane Elliott 3.7.17
[13 empty] | Completed |  | Devon Getten 3.7.17
[13 empty] | Completed |  | Renessa Richards 3.7.17
[13 empty] | Completed |  | Aisheka King 3.7.17
[13 empty] | Completed |  | Dennisha Leslie 3.7.17
[13 empty] | Completed |  | Dian Cooke 3.7.17
MNS | Office Attendants- Temporary services |  | 3CV | 1611x | 300000 | 2325.5814 | 100 | 4 | Programme Management | Ex-Post | 2017-01-01 | 2017-12-01 | Completed |  | Deslyn Matthews 31.1.17
Note on G870: Ferguson, Leon Orlando: Must go to Bank's Procurement Committee for approval in H/Q once over USD500,000