## Sheet1
Project: Primary Education Support Project (PESP) Supplementary
Project Number and Loan Contract Number 2100 OC-JA
Period comprised in this Procurement Plan: From September 2009 to January 2011
Ref. No. 1 | Description of and category of procurement contract | Estimated cost in (US$ thousand) | Procure-ment method 2 | Review Ex-ante | Source of financing and percentage |  | Prequali-fication 3 (Yes/No) | Estimated Dates |  | Status 4 (pending, in process, awarded, cancelled) | Comments
[5 empty] | IDB % | Local / Other % |  | Publication of specific procurement notice | Completion of contract
1 | WORKS 1
| Construction of a quadrangle two (2) story concrete structure to form the Hellshire Primary School complex | 2660 | ICB | yes | 100% |  | yes | 2nd Semester 2009 | 1st Semester 2011 | Pending | This project is being retendered
WORKS 2
Construction of two to three story concrete structure to form
| Red Hills Priamry school complex | 3192 | ICB | yes | 100% |  | yes | 2nd Semester 2009 | 2nd Semester 2011 | Pending | This project is being retendered
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labeled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.