## Sheet1
INTER-AMERICAN DEVELOPMENT BANK
PRIMARY EDUCATION SUPPORT PROJECT PROCUREMENT PLAN
| LOAN NUMBER 2100-OC-JA | 2014-04-01
PRIMARY EDUCATION SUPPORT PROJECT
Supplemental
| Description of the contract and category of Procurement | Estimated Cost in (US Thousand) |  | Procurement Method | Review (Prior or Post) | Date of Bank No Objection | Source of Financing and Percentage |  | Prequalification (Yes/No) | Estimated Dates |  | Status (pending, in process, awarded, cancelled) | Comments
|  | Estimated | Actual |  |  |  | IDB % | Local/Other % |  | Publication of Specific Procurement Notice | Completion of Contract
I. | Goods ( Furniture)
1 | Procurement of furniture for expanded schools | 112.64 | - | NCB | ExPost | Pending | 100 | 0 | No | 2014-07-01 | 2014-09-01 | Pending | Subject fiscal space by MoF
| Goods Sub-Total: | 112.64 | -
II. | Works: Expansion Of Primary Schools
1 | Construction of a two (2) classroom block at Hastings Primary, Trelawny, Region 3 | 58.13 | - | PC | Ex-Ante | Pending | 100 | - | No | 3rd Qrt. 14 | 4th Qrt. 14 | Pending
2 | Construction of two (2) classrooms and an admin block at Chester Primary, St. Ann, Region 3 | 128.22 | - | PC | Ex-Ante | Pending | 100 | - | No | 3rd Qrt. 14 | 4th Qrt. 14 | Pending
3 | Construction of an eight (8) classroom block at Breadnut Hill Primary, St Ann, Reg. 3 | 385.23 | - | PC | Ex-Ante | Pending | 100 | - | No | 2nd Qrt. 14 | 4th Qrt. 14 | Pending
4 | Construction of a six (6) classroom block at Parry Town Primary, St. Ann, Region 3 | 226.35 | - | PC | Ex-Ante | Pending | 100 | - | No | 2nd Qrt. 14 | 4th Qrt. 14 | Pending
5 | Construction of four (4) classrooms, canteen and sanitation upgrade at Four Path Primary, Clarendon, Reg. 6 | 160.93 | - | PC | Ex-Ante | Pending | 100 | - | No | 3rd Qrt. 14 | 4th Qrt. 14 | Pending
6 | Construction of an eight (8) classrooms block at McIntosh Primary, Manchester, Region 5 | 385.23 | - | PC | Ex-Ante | Pending | 100 | - | No | 1st Qrt. 14 | 4th Qrt. 14 | Pending
7 | Construction of a four (4) classrooms at Barracks Road Primary, St. James, Region 4 | 160.93 | - | PC | Ex-Ante | Pending | 100 | - | No | 2nd Qrt. 14 | 4th Qrt. 14 | Pending
8 | Construction of a four (4) classroom block at Zion Hill Primary, Manchester, Region 5 | 160.93 | - | PC | Ex-Ante | Pending | 100 | - | No | 1st Qrt. 14 | 3rd Qrt. 14 | Pending
9 | Construction of four (4) classrooms, canteen and sanitary block at Bryce Primary, Manchester, Region 5 | 226.35 | - | PC | Ex-Ante | Pending | 100 | - | No | 2nd Qrt. 14 | 4th Qrt. 14 | Pending
| Works Sub-total | 1892.3
III. | Administrative Services: Salaries & Allowances
1 | Technical Coordinator | 90.45 | - | QCNI |  | ExPost | 100 |  | No | 1st Qrt. 14 | 3rd Qrt. 15 | Awarded | Anthony Thomas
2 | Administrative Assistant | 22.19 | - | QCNI |  | ExPost | 100 |  | No | 1st Qrt. 14 | 3rd Qrt. 15 | Awarded | Shahaney Hamilton
3 | Project Accountant | 68.4 | - | SSS |  | ExPost | 100 |  | No | 1st Qrt. 14 | 3rd Qrt. 15 | Awarded | Phillippa Grant
4 | Contracts Manager | 42.63 | - | QCNI |  | ExPost | 100 |  | No | 1st Qrt. 14 | 4th Qrt. 14 | Awarded | Michael Paul
5 | Contracts Manager | 28.89 | - | SSS |  | ExPost | 100 |  | No | 2nd Qrt. 14 | 4th Qrt. 14 | Pending | Vacant
| Administrative Services Subtotal | 252.56
| GRAND TOTAL | 2257.5
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labeled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.

## Worksheet
2012/13 | 10 | 11 | 12 | 14
- Literacy |  |  |  |  | 0
- Special Education & Support | 93778.86 | 3891.51 | 8012.58 |  | 105682.95
- APSE/ASTEP - Coldax | 220712.5 |  |  | 46357.95 | 267070.45
- APSE/ASTEP |  | 72713 | 18845.03 |  | 91558.03
UWI | 4500 |  | 7000 |  | 11500
Misc | 22311.93 | 3531.92 |  |  | 25843.85
0
- GSAT/PEP-DPK | 18045 | 12030 |  |  | 30075
- GSAT/PEP | 232.59 |  | 3857.9 | 7965.61 | 12056.1
0
0
- Curriculum | 16103.98 | 16313.5 | 3846.63 | 131.9 | 36396.01
| 375684.86 | 108479.93 | 41562.14 | 54455.46 | 580182.39 |  |  | 854546.91 | 900000 | -45453.09
| 535.75 | 2743.37 | 2154.9 | 19274.03 | 24708.05
Costruction Fees | 535.75 | 2743.37 | 2154.9 | 4055.89 | 9489.91
Peter |  |  |  | 3534.07 | 3534.07
Blankson |  |  |  | 8307.49 | 8307.49
Empro |  |  |  | 3376.58 | 3376.58
2011/12 | 9 | 6 | 5 | 4 | 3 | 2
- Literacy | 19817.71 | 12820.63 | [5 empty] | 32638.34
| 448.4 |  |  | 177.14 |  |  |  | 625.54
- Special Education & Support | 67275.07 | 39879.57 | 34374.5 | 70713.13 |  |  |  | 212242.27 |  | 91154.81
- APSE/ASTEP - Coldax | [7 empty] | 0
- APSE/ASTEP | 23893.9 | [6 empty] | 23893.9
UWI |  | 9000 | [5 empty] | 9000
Misc |  | 14383.26 | [5 empty] | 14383.26
Phoenix |  | -18418.79 | [5 empty] | -18418.79
0
0
- GSAT/PEP-DPK | [7 empty] | 0
- GSAT/PEP | [7 empty] | 0
0
0
- Curriculum | [7 empty] | 0
|  | 14383.26 | [5 empty] | 14383.26
Phoenix |  | 6325.52 | [5 empty] | 6325.52
| 111435.08 | 78373.45 | 34374.5 |  |  |  | 0 | 274364.52
|  | 93847.28 | 4789.07 | 3505.42 | 0 | 67394.89 | 0 | 169536.66
Costruction Fees |  | 11502.26 | 23.34 |  |  | 13871.3 |  | 25396.9
Peter | [5 empty] | 21527 |  | 21527
Blankson |  | 3878 | 4765.73 | 3505.42 |  | 29384.04 |  | 41533.19
Empro | [7 empty] | 0
APEC |  | 78467.02 |  |  |  | 2612.55 |  | 81079.57
Peter |  |  |  |  | 18681.0602
| 28/12/12 | 327076 | 92.5493 | 3534.0732
| 26/02/13 | 425488 | 96.3378 | 4416.6257
| 28/003/13 | 212744 | 98.2353 | 2165.6574
| 15/05/13 | 106372 | 98.7356 | 1077.3419
| 14/06/13 | 103132 | 98.7691 | 1044.1727
| 04/07/13 | 103132 | 101.1252 | 1019.8447
| 24/07/13 | 103132 | 101.4961 | 1016.1179
| 22/08/13 | 105082 | 101.6684 | 1033.5758 |  | 15307.4092 | 18681.06 | 3373.6508
| 06/11/13 | 106372 | 104.8735 | 1014.2886
| 05/12/13 | 103132 | 105.536 | 977.221
17298.9189
1382.1413
3373.651
Blankson |  |  |  |  | 47287.72
| 28/12/12 | 768852 | 92.5493 | 8307.4858 |  |  | 1381.19
| 26/02/13 | 358570.8 | 96.3378 | 3722.0157
| 28/003/13 | 395952.2 | 98.2353 | 4030.6509
| 21/06/13 | 549082.8 | 101.1292 | 5429.5179
| 03/09/13 | 609638.4 | 101.6279 | 5998.7307 | 27488.4009 | 19799.3191
| 05/12/13 | 640125 | 105.4427 | 6070.8328
Blankson |  |  |  |  | 25731.77
| 16/04/13 | 1036904.43 | 99.482 | 10423.0356
| 27/05/13 | 97602.22 | 98.8628 | 987.2492
| 28/06/13 | 100482.22 | 101.0287 | 994.5908
| 04/07/13 | 132654 | 101.1252 | 1311.7799
| 24/07/13 | 237212.25 | 101.4961 | 2337.1563
| 22/08/13 | 100482.22 | 101.6684 | 988.3329
| 23/09/13 | 97602.22 | 102.5957 | 951.3286 | 17993.4732 | 7738.2968
| 23/10/13 | 94722.22 | 104.7464 | 904.3005
| 13/12/13 | 94722.22 | 105.8275 | 895.0624