## Awarded Procurement
SECTION 3
PROCUREMENT PLAN - AWARDED
October 2013 - to - April 2016
Ref. No. 1 | Reference to SEPA code | Comp. No. | Description of and Component of procurement contract | Indicative cost (USD) | Procurement Selection method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Pre-qualification 3 (YES/NO) | Estimated Dates |  | Actual dates |  | Status 4 (pending; in process; awarded; cancelled) | Comments
[7 empty] | IDB % | Local/ Other % |  | Publication of specific procurement notice | Completion of Contract | Publication of specific procure-ment notice | Completion of Contract
| TRINIDAD |  | GOODS
1 | CSP-155-SBCC-CF | 2.1.2B | Design & Implement Sport for Development - Fight for Peace | 77640 | QCBS | ex-ante | 100 |  | Yes |  |  |  | 25/10/2015 | Awarded | Contract executed 25th August 2014
2 | CSP-121-SBC-CF | 2.1.1C | Crime Prevention Through Environmental Design Training & Implementation | 93750 | QBS | ex-ante | 100 |  | NO |  |  |  |  | Awarded | Letter of Award issed by CTB; awaiting contract from CSS
3 | CSP-148-SBCC-CF | 2.3.3B | Crime & Violence Surveys : Collective Efficacy | 61979 | QCNI | ex-ante | 100 |  | NO |  |  |  | 28/10/2014 | Awarded | Contrac executed 29th May 2014-Alexa Khan
4 |  | 2.1.2B | Phase 2 - Parent Education - Programme for Fathers | 77640 | SSS |  |  |  | YES |  |  |  | 2016-02-01 | Awarded | Contract executed
5 |  | 2.1.2B | Gender Based Violence Prevention | 77640 | SSS |  |  |  | YES |  |  |  |  | Awarded | At legal department for contract preparation
6 |  | 2.1.2B | Phase 2 - Therapeutic Family Intervention | 77640 | SSS |  |  |  | YES |  |  |  | 25/03/2016 | Awarded | Contract executed 26th September 2014 with Dolly and Associates
7 | CSP-53-AESP-B | 2.3.1D | Automated FingerPrint System for TTPS | 777830 | DC | ex-ante | 100 |  | No |  | 2013-09-30 |  |  | Awarded
8 | CSP-88-LPN-B | 2.3.1D | Acquisition of Portable GIS for TTPS - CAPA | 153727 | DC | ex-ante | 100 |  | No |  | 2014-01-05 |  |  | Awarded
NON-CONSULTING SERVICES
9 |  | 2.2.3C | Production of Video Documentary on CSP | 38556 | QCBS | ex-ante |  | 100 | No |  | 2014-02-17 |  |  | Awarded | Contract awarded to Silverpin Design Co.
10 |  | 2.1.1A | Event Mgt: CSP Sports & Family Day | 75577 | NCB |  |  | 100 | No |  | 2014-01-22 | 2012-09-19 |  | Awarded | Contract executed on 23/7/13 with Buzz Concepts
11 |  | 2.1.1A | Event Mgt: Football Competition | 49690 | NCB |  |  | 100 | No |  | 2014-03-31 | 2012-09-19 |  | Awarded | Contract awarded to Celian Group
12 |  |  | CONSULTING SERVICES
13 | CSP-184-CF | 3.2.1 | Audit of Financial Statements 2013 | 62112 | QCBS | ex-ante | 100 |  | No |  | 2015-03-31 | 2013-09-18 |  | Awarded | Contract awarded to PKF
14 | CSP-164-CD-CF | 2.1.2B | Youth Micro-Entrepreneurship Programme - Dynamic Youth Foundation | 77640 | SSS | ex-ante | 100 |  | Yes |  | 2015-03-01 |  |  | Awarded | Awarded
15 | CSP-163-CD-CF | 2.1.1C | Conflict Management & Mediation Services - Dispute Resolution Centre | 77640 | SSS | ex-ante | 100 |  | Yes |  | 2014-07-12 |  |  | Awarded | Contract executed on 13/9/13
16 | CSP-165-CD-CF | 2.1.2B | Academic Enrichment Programme (NPATT) | 77640 | SSS | ex-ante | 100 |  | Yes |  | 2015-03-01 |  |  | Awarded | Awarded
17 | CSP-167-CD-CF | 2.1.2B | Community Based Social Intervention (Life & vocational Skills Prog.)-Social Justice Foundation | 77640 | SSS | ex-ante | 100 |  | Yes |  | 2014-10-26 |  |  | Awarded | Awarded
18 | CSP-168-CD-CF | 2.1.1C | Community Based Social Interventions (organization Strengthening of CACs) Veni Appwan | 77640 | SSS | ex-ante | 100 |  | Yes |  | 2014-12-15 |  |  | Awarded | Contract executed on 16/10/13
19 | CSP-170-Cd-CF | 2.1.2B | School Based Violence Reduction (ARROW Literacy Prog) | 77640 | SSS | ex-ante | 100 |  | Yes |  | 2014-12-15 |  |  | Awarded | Awarded
20 | CSP-174-SBCC-CF | 2.2.4B | Peer Counselling for TTPS | 35000 | QCBS | ex-ante | 100 |  | Yes | 2013-05-27 | 2014-12-01 |  |  | Awarded | contract executed 10th July 2014
21 | CSP-175-CD-CF | 2.1.2B | Violence Prevention Services (Phase 11) Together We Achieve Growth - (Families in Action) | 61816.78 | SSS | ex-ante | 100 |  | Yes |  | 2014-12-31 |  |  | Awarded | Awarded
22 | CSP-176-CD-CF | 2.1.2B | Violence Prevention Services (Phase 11) Academic Enrichment Prog.- Pinto Rd. (Human Development Programme | 77640 | SSS | ex-ante | 100 |  | Yes |  | 2014-09-06 |  |  | Awarded
23 | CSP-133-CD-CF | 2.1.2A | Technical Oversight - CureViolence (Univ. Of Chicago) | 484568.86 | SSS | ex-ante | 100 |  | No |  | 2017-03-19 |  |  | Awarded | Letter of Award issed by CTB; awaiting contract from CSS
24 | CSP-162-CD-CF | 2.1.2A | Implementing Partner (CeaseFire/Cure Violence) | 1927329 | NCB | ex-ante | 100 |  | NO | 2013-12-10 | 2016-04-01 |  |  | Awarded
25 | CSP-90-SCC-CF | 2.3.1E | M & E Consultancies -Evaluation of CBSIs and other Evaluation assistance M & E (Kairi Consulting) | 69455.29 | QCBS | ex-ante | 100 |  | NO |  | 2014-02-06 |  |  | Awarded
26 | CSP-101-CD-CF | 2.1.2B | Community Based Social Interventions : Sport for Development (CSDA/TTASPE)) | 77640 | SSS | ex-ante | 100 |  | Yes |  | 2013-12-20 |  |  | Awarded
27 | CSP-104-CD-CF | 2.1.2B | Community Based Social Interventions : Micro-enterprise (YBTT) | 77640 | SSS | ex-ante | 100 |  | Yes |  | 2013-10-13 |  |  | Awarded
28 | CSP-105-SBC-CF | 1.2.1F | M & E Consultancies - Evaluation of CSP | 78125 | QCBS | ex-ante | 100 |  | No |  | 2014-04-11 | 2013-09-16 |  | Awarded | Letter of Award issed by CTB; awaiting contract from CSS
29 | CSP-111-CD-CF | 2.1.2C | Training for ICON Applicants - PM - Veni Appwan | 34130 | SSS | ex-ante | 100 |  | Yes |  |  |  |  | Awarded | contract executed 5th June 2014
30 | CSP-130-CD-CF | 2.1.2B | Violence Prevention Services - Women Leadership Programme (WINAD) | 77640 | SSS | ex-ante | 100 |  | Yes |  | 2014-08-21 |  |  | Awarded
31 | CSP-131-CD-CF | 2.1.2B | Violence Prevention Services - Never Dirty Phase 2 (Reaction) | 77640 | SSS | ex-ante | 100 |  | Yes |  | 2014-01-20 |  |  | Awarded
32 | CSP-138-CD-CF | 2.1.2B | Community Based Social Intervention: Parent Education Programme (TTIPS) | 77640 | SSS | ex-ante | 100 |  | Yes |  | 2013-12-13 |  |  | Awarded
33 | CSP-139-CD-CF | 2.1.2B | Community Based Social Interventions: Capacity Building for CBOs - The Rose Foundation | 77640 | SSS | ex-ante | 100 |  | Yes |  | 2013-11-25 |  |  | Awarded
34 | CSP-140-CD-CF | 2.1.2B | Community Based Social Interventions:After School Programme - YMCA | 77640 | SSS | ex-ante | 100 |  | Yes |  | 2014-01-06 |  |  | Awarded
35 | CSP-141-CD-CF | 2.1.2B | Community Based Social Interventions: Adult Literacy Programme - ALTA | 77640 | SSS | ex-ante | 100 |  | Yes |  | 2014-01-20 |  |  | Awarded
36 | CSP-142-CD-CF | 2.1.2B | Community Based Social Interventions: Therapeutic Family Intervention - La Romaine | 77640 | SSS | ex-ante | 100 |  | Yes |  | 2013-10-02 |  |  | Awarded
37 | CSP-154-SBMC | 2.1.1C | Capacity Building (Organizational Strengthening of CACs) | 186481 | CQS | ex-ante | 100 |  | No |  |  |  | 25/01/16 | Awarded | contract executed 26th September 2014 with veni apwann
38 |  | 2.1.2B | CBSI-Phase 2 Youth Micro Entrepreneurship Programme | 77640 | SSS |  |  |  | Yes
39 |  | 2.1.2B | CBSI- Life Skills Programmes | 77640 | sss |  |  |  | Yes
40 |  | 2.1.2B | Phase 2 Parent Education | 77640 | sss |  |  |  | Yes |  |  |  |  | awarded | At legal for contract preparation
41 |  | 2.1.2B | Phase 2 - Therapeutic Family Intervention | 77640 | sss |  |  |  | Yes |  |  |  |  | awarded
42 |  | 2.1.1B | Design of M & E System for NGOs | 62112 | SSS |  |  |  | Yes |  |  |  |  | awarded | At legal for contract preparation
TOBAGO
WORKS
43 |  | 2.1.1D | Bethel RAPID IMPACT PROJECT | 46600 | NCB | ex-ante |  | 100 | No | 2012-09-07 | 2014-04-01 |  |  | Awarded
CONSULTING SERVICES
44 | CSP-159-SBCC-CF | 2.1.2B | Positive Parenting Programme (3) Tobago Communities | 77640 | QCBS | ex-ante | 100 |  | NO |  |  | 2013-07-08 |  | Awarded | At legal for contract preparation
45 | CSP-179-SBCC-CF | 2.1.1B | Capacity Building Training for NGOs in Tobago - Project Mgt. Training | 32609 | QCBS | ex-ante | 100 |  | No |  | 2014-06-30 |  |  | Awarded
46 | CSP-180-SBCC-CF | 2.1.1B | Capacity Building Training for NGOs and CBOs in Tobago | 32609 | QCBS | ex-ante | 100 |  | No |  | 2014-06-30 |  |  | Awarded
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labeled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.
Codes from SEPA

## Procurement Plan
SECTION 3
PROCUREMENT PLAN
October 2014 - to - April 2016
Ref. No. 1 | Reference to SEPA code | Comp. No. | Description of and Component of procurement contract | Indicative cost (USD) | Procurement Selection method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Pre-qualification 3 (YES/NO) | Estimated Dates |  | Actual dates |  | Status 4 (pending; in process; awarded; cancelled) | Comments
[7 empty] | IDB % | Local/ Other % |  | Publication of specific procurement notice | Completion of Contract | Publication of specific procure-ment notice | Completion of Contract
| TRINIDAD |  | GOODS
1 | CSP-76-LPN-B | 2.3.1A | Equip Youth Friendly Spaces | 2239346.2791 | NCB | ex-ante | 100 |  | YES | 2015-05-18 | 2016-03-01 |  |  | Pending | Dependent on MOU with MCD and Services of Design and Construction Consultant.
2 |  | 2.3.1E | Injury Surveillance System this includes | 688537 |  | ex-ante | 100 |  |  |  | 2015-02-01 |  |  | Pending | Guided by MOU between the MNS-MOH & RWRHA. Approval being obtained from CSS.
|  |  | Production of Injury Surveillance Forms | 129231 | PC |  | 100 |  | NO |  | 2015-02-03
|  |  | Injury Surveillance Office Equipment | 28769 | PC |  | 100 |  | NO |  | 2015-02-03
|  |  | Injury Surveillance Staff | 391613 | QCNI |  | 100 |  | NO |  | 2015-02-03
|  |  | Injury Surveillance Training | 92308 | CQS |  | 100 |  | NO | 2015-01-15 | 2015-04-05
|  |  | Communications in Injury Surveillance | 462 | PC |  | 100 |  | NO |  | 2015-02-03
|  |  | Monitoring and Evaluation | 46154 | QCNI |  | 100 |  | NO |  | 2015-02-03
WORKS
3 | CSP-115-LPN-O | 2.2.1 | Refurbishment of (7) Police Stations in Trinidad & Tobago | 419543 | NCB | ex-ante | 100 |  | YES | 2015-06-18 | 2016-01-05 |  |  | In process | This project is dependent on CSP-125-SBCC-CF
NON-CONSULTING SERVICES
CONSULTING SERVICES
4 | CSP-161-SBCC-CF | 2.1.1C | Event Mgt. - Community Safety Planning | 110000 | CQS | ex-ante | 100 |  | NO | 2015-03-04 | 2015-06-05 |  |  | Pending | Dependent on Community Safety Plan Tender
5 | CSP-156-SBCC-CF | 2.1.1C | Champions for Change Leadership & Advocacy Training Programme | 52112 | CQS | ex-ante | 100 |  | NO |  |  | 2014-06-25 |  | In process | Evaluation committee Report is being prepared October 2014
6 | CSP-21-SC-7 | 2.2.2 | Basic IT Training for Police Officers | 50000 | CQS | ex-ante | 100 |  | NO |  | 2015-02-28 |  |  | Pending
7 | CSP-91-SCC-CF | 2.3.1E | Community GIS Mapping | 31250 | QCNI | ex-ante | 100 |  | NO | 2015-01-15 | 2015-05-05 |  |  |  | On hold pending review
8 | CSP-109-3CV-CI | 2.1.1C | Development of Community Safety Plans-16 CSP Communities | 80836 | CQS | ex-ante | 100 |  | No |  |  | 22/09/13 |  | In process | CTB to re-advertise due to poor response.
9 | CSP-120-SBCC-CF | 2.1.2E | Community Based Videography Programme | 500000 | QCBS | ex-ante | 100 |  | No |  |  |  |  | In process | Reinitiated under a selective tendering process
10 | CSP-125-SBCC-CF | 2.2.1 | Hire Design and Construction Supervision Consultants - Refurbishment of 7 Police Stations | 184615 | CQS | ex-ante | 100 |  | YES | 2013-05-25 | 2015-01-06 |  |  | In process | Reinitiated using shortlist
11 | CSP-146-SBCC-CF | 2.3.2C | Communication Plan | 155280 | QCNI | ex-ante | 100 |  |  |  | 2015-02-01 |  |  | In process
12 | CSP-150-SBCC-CF | 2.1.1C | Tobago Mediation & Conflict Mgt. Phase 2 | 46584 | CQS | ex-ante | 100 |  | NO |  | 2015-05-31 |  |  | In process
13 | CSP-183-SBCC-CF | 2.3.3A | National Crime & Victimization Survey | 277127 | QCBS | ex-ante | 100 |  | No |  | 2014-12-12 |  |  | In process | Financial Proposal Evaluation completed at Miniserial tenders Committee for review and approval
14 |  |  | Expansion of CSP - Community Building (4 projects/contracts) | 77519.3798 | CQS |  | 100 |  | YES | [5 empty] | In Development
15 |  |  | Establishment of DV clinics in 16 CSP Communities | 310559 | CQS |  | 100 |  | NO |  | 2015-11-30 |  |  | In process | Request Submitted to Central Tenders Board
16 |  | 2.1.2G | Police Youth Clubs - Training & Development for 75 PYCs | 157822 | CQS |  | 100 |  | NO |  | 2015-05-31 |  |  | In process
17 |  | 2.1.2B | Conflict Management & Mediation Services | 186335 | CQS |  | 100 |  | NO |  | 2015-01-10 | 2014-09-08 |  | In process | Evaluation is in progress, proceeding to end October 2014
| TOBAGO |  | GOODS
WORKS
CONSULTING SERVICES
18 | CSP-178-SB-CF | 2.1.2B | Feasibility Study: Design of Model for the Implementation of a Community Based Drug Rehab. Service | 31056 | CQS | ex-ante | 100 |  | NO |  | 2014-03-19 |  |  | In process | To be restarted
19 | CSP-181-SCC-CF | 2.1.2B | Community Based Social Intervention - Learning Support Programme for Tobago | 62112 | CQS | ex-ante | 100 |  | NO |  | 2015-02-28 |  |  | In process | Tender closed
20 | CSP-158-SBCC-CF | 2.1.1B | Capacity Building Programme for NGO's - Leadership Training TOBAGO | 54348 | CQS | ex-ante | 100 |  | NO | 2013-10-30 | 2014-06-30 |  |  | In process | Negotiation being conducted with UWI
21 | CSP-157-SBCC-CF | 2.1.1C | Community Cognitive Social Intervention - TOBAGO | 77640 | CQS | ex-ante | 100 |  | NO | 2013-10-30 | 2015-01-07 |  |  | In process | Proposal received on 24th October 2014, Evaluation to commemnce.
CSP Expansion
| TRINIDAD |  | GOODS
WORKS
22 |  | 2.1.3.A | Crime Prevention through Environmental Design - Projects in East Port of Spain | 232558 | QCBS |  | 100 | [7 empty] | 5 Projects
23 |  | 2.1.3A | Community Impact Centres - Youth Friendly Spaces | 387597 | QCBS |  | 100 |  | NO |  | 2016-01-06 |  |  |  | Support for five (5) Community Impact Centres.
NON-CONSULTING SERVICES
24 |  | 2.1.1A | Community Meeting: Initiation meetings Procurement of materials for Community Meeting within East Port of Spain | 12403 | PC | ex-post |  | 100 | NO |  | 2015-02-01 |  |  |  | Hosting of 8 Community Meetings
25 |  | 2.1.1A | Community Meeting: Support for monthly meeting and quarterly meetings in East Port of Spain | 12651 | PC | Ex-post |  | 100 | NO |  | 2015-02-02 |  |  |  | Four ( 4) quarterly meetings held with representative
26 |  | 2.1.1A | Community Launches : Procurement of materials for Community Meeting within East Port of Spain | 116279 | PC | Ex-post |  | 100 | NO |  | 2015-02-03 |  |  |  | Community Action Councils established through launches in 65 communities @ say $15K per Community; procurement of tents, materials for engagement activities, entertaiment etc
27 |  | 2.1.2E | Public Education : Procurement of promotional materials, advertising materials | 310077 | PC | Ex-post | 100 |  | NO |  | 2016-01-05 |  |  |  | Procurement of public education materials distribution to 87 communities.
28 |  |  | Public Education : Procurement of promotional materials, advertising materials | 3876 | PC | Ex-post | 100 |  | NO |  | 2016-01-06 |  |  |  | 3000 flyers printed distributed.
29 |  | 2.1.2E | Public Education : 3 Public Education per Community (murals, materials, advertising materials) | 93023 | PC | Ex-post | 100 |  | NO |  | 2016-01-05 |  |  |  | Installation of signs, billboards, murals etc to promote non-violence
CONSULTING SERVICES
30 |  | 2.1.1A | Asset Mapping | 4884 | QCNI | Ex-post |  | 100 | NO |  | 2015-04-03 |  |  |  | One day training, 13 CAO in the development of data base etc.
31 |  | 2.1.1A | Community Engagement | 620155 | QCBS | Ex-ante | 100 |  | NO |  | 2015-12-31 |  |  |  | Engagement of 8 Community Based Organisations, 32 Projects in one year; 2 Phases
32 |  | 2.1.3A | Crime Prevention through Environmental Design - Training at East Port of Spain | 232558 | QCBS |  | 100 |  | NO |  | 2016-01-05 |  |  |  | Training of 50 Persons; 10 East Port of Spain 6 CSP; 20 CAC / CWGs
33 |  | 2.1.1B | Program Planning, monitoring and Evaluation Training for East Port of spain EPOS CBOs / CACs | 77519 | QCBS | Ex-ante | 100 |  | NO |  | 2016-01-05 |  |  |  | 8, 2 day training Workshops for Community Working Groups
34 |  | 2.1.1C | Community Safety Planning | 310077 | QBS | Ex-ante | 100 |  | Yes |  | 2015-08-01 |  |  |  | 20 persons to be trained (5 per CAC)
35 |  | 2.1.1C | Conflict Management & Mediation Services | 155039 | CQS | Ex-ante | 100 |  | YES |  | 2015-12-12 |  |  |  | Training in Two (2) Phases of 50 and 30 residents respectively
36 |  | 2.1.1D | Community Service Projects- Rapid Impact | 124031 | PC | Ex-ante | 100 |  | NO |  | 2015-06-05 |  |  |  | Grants to 4 CACs to implement projects
37 |  | 2.1.1E | Therapeutic , Mediation and Emergency Services | 155000 | PC | Ex-post | 100 |  | NO |  | 2016-01-05 |  |  |  | Emergency relief services
38 |  | 2.1.2C | Inspiring Confidence in Our Neighbour Grants - ICONS | 167441 | PC | Ex-ante |  | 100 | NO |  | 2016-01-05 |  |  |  | 3 projects executed per Community based upon Community Safety Plan
39 |  | 2.1.2B | Community Based Social Interventions | 155039 | SSS | Ex-ante | 100 |  | NO |  | 2016-01-05 |  |  |  | 20 engagements in interventions, estimated at TT$500,000 each, addressing: Parenting, after school, lifer skills., academic enrichment , mentorship etc.
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labelled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.
Codes from SEPA