| Procurement Plan BH- L 1024 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. No. | Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequalification (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) |
|  |  |  |  | IDB % | Local/other % |  | Publication of specific procurement notice | Completion of contract |  |
| A | Consulting Services |  |  |  |  |  |  |  |  |
| 1 | Consultant as Transport Specialist for 2 years to provide technical leadership of the TPPU in implementing the transport initiatives arising from the updated TDP and recommendations of previous consultancies. $360,000. | 3 CV’s | Prior | 100 | 0 | Shortlist | Jul/08 | Dec/10 | Pending |
| 2 | 1 local consultant for 2 years to support the TPPU/ORC in implementing public transport recommendations. $120,000 | 3 C.V. ‘s | Prior | 100 | 0 | No | Nov/08 | Dec/10 | Pending |
| 3 | Consultant to Develop and implement a Routine Maintenance management System for the roads in New Providence (supplemental) $290,000 | 3 CV’s | Prior | 100 | 0 | Shortlist | Dec/08 | Dec/08 | Pending |
| 4 | Organizational capacity assessment of MOWT $30,000 | 3 C.V. ‘s | Prior | 100 | 0 | No | July/08 | Oct/08 | Pending |
| 5 | Implementing of Organizational Strengthening of MOWT $320,000 | QCBS | Prior | 100 | 0 | Shortlist | Oct/08 | Jun/10 | Pending |
| 6 | Engineering Consultancy Services for Supervision of Road Corridor improvements. $6,672,095 | QCBS | Prior | 100 | 0 | Shortlist | May/08 | Dec/11 | In Progress |
| 7 | 2 full-time individual consultants as Project Engineers for the supervision of road corridor improvements $350,000 | 3CV’s | Prior | 100 | 0 | No | Jun/08 | Jun/11 | Pending |
| 8 | Procure Road Safety equipment and train MOWT personnel $120,000 | NCB | Prior | 100 | 0 | No | Sept/08 | Juln/09 | Pending |
| B | Civil Works |  |  |  |  |  |  |  |  |
| 8 | Rehabilitation of existing road corridors and construction of new road corridors in New Providence (12 corridors total) $113,200,000 | LIB/DC | Prior | 100 | 0 | Yes (post) | N/a (LIB) Bid docs issued May 2007 | Sep/11 | Pending |
| 9 | Construct recreational facilities for the development of Big Pond Park $1,800,000 | NCB | Prior | 100 | 0 | No | Nov./08 | Dec/09 | Pending |
| C | Goods & Services |  |  |  |  |  |  |  |  |
| 10 | Procure playground apparatus for Big Pond Park $200,000. | ICB | Prior | 100 | 0 | No | Mar/09 | Nov/09 | Pending |

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality- and cost-based selection QBS: Quality-based selection FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection;  3CV’s: Selection of Individual Consultant based on 3CV’s