## Procurement Plan
PROCUREMENT PLAN
Project Name: Technical Support to Reduce Teenage Pregnancy
Project Number: ATN/OC-15957-JA
FROM April 2018 to December 2019
FROM __JAN/2018______ (month/year) to _JUN/2019_________ (month/year)
Ref. No. 1 | Comp. No. | Description of and Component of procurement contract | Indicative cost (JA$) | Procurement Selection method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Estimated Dates |  | Actual dates |  | Status 4 (pending; in process; awarded; cancelled) | Comments
[6 empty] | IDB % | Local/Other % | Publication of specific procurement notice | Completion of Contract | Publication of specific procurement notice | Completion of Contract
GOODS
1.1 | 1 | Layout and Printing of ASRH Manual | 1600 | Shopping | ex-post | 100 |  | 2019-04-20 | 2019-04-08
1.2 | 1 | Layout and Printing of ASRH Toolkit | 1200 | Shopping | ex-post | 100 |  | 2019-04-20 | 2019-04-08
1.3 | 1 | Procure stationery and office supplies | 6400 | Shopping | ex-post | 100 |  | 2018-06-01 | 2018-06-20
1.4 | 1 | Social Media Materials | 10000 | Shopping | ex-post | 100 |  | 2018-10-23 | 2018-10-23
1.5 | 1 | Stationery for Validation and stakeholders' Workshop | 400 | Shopping | ex-post | 100 |  | 2018-12-17 | 2018-12-17
1.6 | 2 | Stakeholder Workshop Materials | 2800 | Shopping | ex-post | 100 |  | 2019-02-04 | 2019-02-04
1.7 | 3 | Procure Jadelle Implants | 12000 | DC | ex-ante | 100 |  | 2018-05-25 | 2018-06-01 |  |  | In process | Quote requested from supplier
1.8 | 3 | Procure Branded Condoms | 3379.2 | DC | ex-ante | 100 |  | 2018-05-25 | 2018-06-01 |  |  | In process | Quote requested from supplier
1.9 | 3 | Procure Pregnancy Kits | 2136.96 | DC | ex-ante | 100 |  | 2018-05-25 | 2018-06-01 |  |  | In process | Quote requested from supplier
2 | 3 | Branded novelties | 5200 | DC | ex-ante | 100 |  | 2018-06-25 | 2018-07-16 |  |  | In process | Quote requested from supplier
NON-CONSULTING SERVICES
2.1 | 1 | Advert Placement for consultant to develop ASRH manual and toolkit | 312 | Shopping | ex-post | 100 |  | 2018-10-08 | 2018-10-08 |  |  | In process | Draft TOR reviewed by IDB
2.2 | 1 | Advert Placement for consultant to pretest ASRH manual and toolkit | 312 | Shopping | ex-post | 100 |  | 2019-08-10 | 2019-08-10
2.3 | 1 | Advert Placement for consultant to develop social media campaign | 312 | Shopping | ex-post | 100 |  | 2019-10-15 | 2019-10-15 |  |  | In process | Draft TOR prepared to be reviewed by project Steering Committee
2.4 | 2 | ASRH Workshop - Venue and Refreshments | 24000 | Shopping | ex-post | 100 |  | 2019-02-04 | 2019-02-04
2.5 | 2 | ASRH Workshop - Transportation | 1200 | Shopping | ex-post | 100 |  | 2019-02-04 | 2019-02-04
2.6 | 3 | Public Awareness Sessions - Venue and Refreshments | 4851.84 | Shopping | ex-post | 100 |  | 2018-05-25 | 2018-05-25
2.7 | 4 | Advert Placement for Monitoring and Evaluation Consultant | 312 | Shopping | ex-post | 100 |  | 2019-08-10 | 2019-08-10
2.8 | 4 | Advert Placement for Project Financial Audit | 312 | Shopping | ex-post | 100 |  | 2019-10-15 | 2019-10-15
CONSULTING SERVICES
3.1 | 4 | Administrative Support (Procurement/DHHP/Finance/AdminComm) | 16400 | QCNI | ex-post | 100 |  | N/A | N/A | N/A | 2019-12-07 |  | Administrative Support within NFPB to include component persons within the project to Procurement/DHPP/Admin/Finance/Comm). Correspondence submitted to IDB dated July 7, 2017 regarding level of effort of this team member. Letter requesting IDB's permission to pay for the effort from project funds submitted on November 21, 2017.
3.2 | 1 | Consultant to develop the ASRH manual and accompanying toolkit | 55000 | QCNI | ex-ante | 100 |  | 2018-05-03 | 2018-05-25
3.3 | 1 | Consultant to conduct pre-testing of ASRH manual and toolkit | 18000 | QCNI | ex-ante | 100 |  | 2019-01-07 | 2018-01-09
3.4 | 1 | Consultant to develop a social media campaign | 25000 | QCNI | ex-ante | 100 |  | 2018-10-22 | 2018-10-22
3.5 | 3 | Personnel to insert and remove Jadelle | 33872 | DC | ex-ante | 100 |  | 2018-05-30 | 2018-06-08 |  |  |  | The team that works with the Women's Health Network to insert these types of contraceptives will be engaged
3.6 | 4 | Monitoring and Evaluation | 8000 | QCS | ex-ante | 100 |  | 2019-09-01 | 2019-09-01
3.7 | 4 | Financial Audit | 17000 | QCS | ex-ante | 100 |  | 2019-09-01 | 2019-09-01
250000
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labeled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.
Codes from SEPA