INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 1. Goods - Goods 1 ICT – NYS Head Office and Parish Offices including PBX Estimated cost: US$231,750 - Goods 2 Web portal/relational database Estimated cost: US$50,000 - Goods 3 HR Management System Estimated cost: US$75,000 - Goods 4 Furniture & Equipment Estimated cost: US$21,978 | NCB NCB NCB PC | Ex-ante Ex-ante Ex-ante Ex-Post | 100 100 100 100 |  | No No No No | Jul. 2014 Jul. 2014 Jul. 2014 N/A | Mar. 2015 Mar. 2015 Mar. 2015 Sept. 2014 | Pending Pending Pending Pending | For Trelawny and Hanover Parish Offices |
| SUBTOTAL US$378,728 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 1. Goods Cont’d. - Goods 5 Equipment and Furniture Estimated cost: US$27,333 - Goods 6 Additional Equipment & Furniture Estimated cost: US$29,261 Goods 7 Electronic Surveillance & Alarm Systems Estimated cost: US$24,000 - Goods 8 Procure and install air conditioning units and mobile partitioning Estimated cost: US$24,628 | PC PC PC PC | Exante Ex-ante ExPost Ex-Post | 100 100 100 100 |  | No No No No | N/A N/A N/A N/A | Mar. 2014 Jun. 2014 Apr. 2014 & Mar. 2015 Jun. 2014 | Pending Pending Pending In Process | For Spanish Town and May Pen NYS Facilities. Several contracts to be issued and will be under the threshold. For existing Parish Offices. Several contracts to be issued and will be under the threshold. For St. Catherine, Hanover and Trelawny Parish Offices. For remaining Parish Offices. Several contracts will be issued. |
| SUBTOTAL US$105,222 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 1. Goods Cont’d. - Goods 9 Purchase & installation of A/C units Estimated cost: US$10,000 - Goods 10 Procurement of Training Room Desks Estimated cost: US$21,775 Good 11 Electronic Surveillance & Alarm Systems Estimated cost: US$8,000 | PC SSS PC | Ex-Post Ex-post Ex-Post | 100 100 100 |  | No No No | N/A N/A N/A | Jan. 2014 Jan. 2014 Mar. 2014 | In Process In Process In Process | For St. Thomas Parish Office. For Clarendon Facility. Approval granted by the PS to direct contract ModOffice as they were previously contracted to supply these desks and to maintain the uniformity of the desks. For Clarendon Parish Office (new facility). |
| SUBTOTAL US$39,775 |  |  |  |  |  |  |  |  |  |
| TOTAL (Goods 1-11) US$523,725 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services - Consulting Service 1 Evaluation Specialist Estimated cost: US$25,000 - Consulting Service 2 Evaluation Assistant Estimated cost: US$15,000 - Consulting Service 3 Wide Area Network Estimated cost: US$43,956 - Consulting Service 4 Database Upgrade Estimated cost: US$5,000 | QCNI QCNI CQS QCNI | Ex-Post Ex-Post Ex-Post Ex-Post | 100 100 100 100 |  | No No No No | Jan. 2014 May 2014 Mar. 2014 Mar. 2014 | Sept. 2014 Nov. 2014 Mar. 2015 Oct. 2014 | Pending Pending Pending Pending | TOR is being prepared. TOR is being prepared. |
| SUBTOTAL US$88,956 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 5 Project Manager (NWA) Actual cost: US$85,742 Consulting Service 6 - Architect – Trelawny Parish Office Actual cost: US$30,097 Consulting Service 7 - Architect – Hanover Parish Office Actual cost: US$35,307 | SSS SSS SSS | Ex-Post Ex-Post Ex-Post | 100 100 100 |  | No No No | N/A N/A N/A | Mar. 2014 Mar. 2014 Mar. 2014 | In Process In Process In Process | For Trelawny and Hanover NYS Parish Offices: Contract for NWA amended. Contract to be extended to May 2015. Contract for Cornerstone Design amended. Contract to be extended to May 2015. Contract for Plexus Limited amended. Contract to be extended to Jan. 2015. |
| SUBTOTAL US$151,146 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 8 Organizational Review Estimated cost: US$38,461 - Consulting Service 9 HR&A Manual Estimated cost: US$54,945 - Consulting Service 10 Finance & Accounting Manual Estimated cost: US$54,945 - Consulting Service 11 Strategic Plan for NYS Estimated cost: US$38,461 | QCNI QCNI QCNI QCNI | Ex-Post Ex-ante Ex-ante Ex-Post | 100 100 100 100 |  | No No No No | Jan. 2014 Mar. 2014 Mar. 2014 Jan. 2014 | Sept. 2014 Sept. 2014 Sept. 2014 Jun. 2014 | In Process In Process In Process In Process | TORs were sent to IDB for approval. The Bank requested clarification on TORs. NYS to provide clarification. |
| SUBTOTAL US$186,812 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 12 Upgrade of NYS Website Estimated cost: US$40,000 - Consulting Service 13 Follow-on contract for 7 RFOs Actual cost: US$188,400 - Consulting Service 14 Corporate Outreach marketing and mentoring Actual cost: US$426,150 | QCNI QCNI QBS | Ex-Post Ex-ante Ex-ante | 100 100 100 |  | No No No | Jan. 2014 Aug. 2012 Feb. 2010 | Sept. 2014 Mar. 2014 Feb. 2014 | In Process Awarded/ In Process Awarded / In Process | TOR was sent to IDB for approval. The Bank requested clarification on TOR. NYS to provide clarification. Contract awarded to LPD Hall & Associates. Contract was extended to Feb. 28, 2014. |
| SUBTOTAL US$654,550 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 15 Curriculum revision and alignment Actual cost: US$134,532 - Consulting Service 16 Impact evaluation for NYS/CAP Programmes Actual cost: US$249,326 - Consulting Service 17 Chief Technical Advisor, NYS Actual cost: US$50,000 | SSS SSS SSS | Ex-ante Ex-ante Ex-ante | 100 100 100 |  | No No No | N/A N/A N/A | Mar. 2014 Mar. 2014 Mar. 2014 | In Process Awarded / In Process Awarded / In Process | Sixty (60) days’ Notice of Termination of Contract was served to ABU Consult, Berlin. Received the Bank’s no objection to sole source Nancy George & Associates. The justification is to prevent any further delays with start-up of this activity. Contract to be extended to Sept. 2014. Contract awarded to Social Welfare Training Centre, UWI. Contract awarded to Dr. Darrell Hull. |
| SUBTOTAL US$434,501 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| - Consulting Services Cont’d. - Consulting Service 18 Project Management Services – Construction of NYS Facilities Actual cost: US$12,835 - Consulting Service 19 Architect for NYS - St. Catherine Actual cost: US$17,447 - Consulting Service 20 Architect for NYS – Clarendon Actual cost: US$15,845 | SSS SSS SSS | Ex-Post Ex-Post Ex-Post | 100 100 100 |  | No No No | N/A N/A N/A | Mar. 2014 Mar. 2014 Mar. 2014 | Awarded / In Process Awarded / In Process Awarded / In Process | (For St. Catherine & Clarendon) No-objection received to amend NWA contract to include this activity. Cornerstone Design contract amended to include additional reimbursable expenses. No-objection received to amend Plexus Limited contract to include this activity. |
| SUBTOTAL US$46,127 |  |  |  |  |  |  |  |  |  |
| TOTAL (CS 1-20) US$1,584,513 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 3. Works - Works 1 Upgrade NYS and parish offices (Fixed partitioning, tinting and painting) Estimated cost: US$30,000 - Works 2 Construction of NYS Training Facilities at Hanover & Trelawny Estimated cost: US$769,230 - Works 3 Renovation of external bathroom Estimated cost: US$10,000 | PC NCB PC | Ex-ante Ex-ante Ex-Post | 100 100 100 |  | No No No | Feb. 2014 Jan. 2014 & Mar. 2014 N/A | Jun. 2014 Jan. 2015 & May 2015 Mar. 2014 | Pending Pending Pending | Multiple contracts will be awarded. Include sewerage. NYS Parish Offices to be built with YICs. (Final cost to be provided) For St. Catherine Office |
| SUBTOTAL US$819,230 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 3. Works Cont’d. - Works 4 Partitioning of Training Room at St. Catherine Facility Estimated cost: US$10,000 - Works 5 Construction of NYS Training Facilities at Sp. Twn. & May Pen Actual cost: US$1,189,521 | PC NCB | Ex-Post Ex-ante | 100 100 |  | No No | N/A Apr. 2011 | Mar. 2014 Mar. 2014 | Pending Awarded / In Process | Variation costs for both sites added. |
| SUBTOTAL US$1,198,499 |  |  |  |  |  |  |  |  |  |
| TOTAL (Works 1-5) US$1,217,729 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| Non- Consulting Services - Connection to JPS and NWC services for New Parish Offices Estimated cost: US$14,000 - Stakeholder Consultation Estimated cost: US$11,500 | Direct Payments PC | Ex-Post Ex-Post | 100 100 |  | No No | N/A N/A | Mar. 2015 Dec. 2014 | Pending Pending | For Trelawny and Hanover Offices. For Trelawny and Hanover Offices. |
| TOTAL US$25,500 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| Non- Consulting Services - Connection to JPS and NWC services for New Parish Offices Estimated cost: US$14,000 - Stakeholder Consultation Estimated cost: US$10,000 - Stakeholder Consultation Estimated cost: US$10,000 | Direct Payments PC PC | Ex-Post Ex-Post Ex-Post | 100 100 100 |  | No No No | N/A N/A N/A | Apr. 2014 Feb. 2014 Mar. 2014 | In Process In Process In Process | For St. Catherine, Clarendon Offices. Relating to the Corporate Outreach. YICs/NYS Facilities at Spanish Town and May Pen. |
| TOTAL US$34,000 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 1. Goods - Goods 1 Equipment for Youth Information Centres (YICs) Estimated cost: US$3,000 - Goods 2 Electronic Surveillance Security & Alarm Systems Estimated cost: US$8,000 - Goods 3 Furniture for Youth Information Centres (YICs) Estimated cost: US$25,125 | PC PC PC | Ex-Post Ex-Post Ex-Post | 100 100 100 |  | No No No | N/A N/A N/A | Jan. 2014 Mar. 2014 Jan. 2015 | Awarded/ In Process In Process Pending | Project allocation is insufficient as the project amt. required is US$78,000. NCYD obtained support from Universal Access Fund (UAF). Delivery expected by Jan. 2014. For Clarendon YIC (new facility). Hanover YIC. Several contracts to be issued. |
| SUBTOTAL US$36,125 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| - Goods Cont’d. - Goods 4 Equipment for Youth Information Centres (YICs) Estimated cost: US$3,000 Goods 5 - Furniture for Youth Information Centres (YICs) Estimated cost: US$25,125 Goods 6 - Equipment for Youth Information Centres (YICs) Estimated cost: US$3,000 - Goods 7 Workstations for YICs Estimated cost: US$4,863 | PC PC PC PC | Ex- Post Ex-Post Ex-Post Ex-Post | 100 100 100 100 |  | No No No No | N/A N/A N/A N/A | Jan. 2015 Jan. 2015 Jan. 2015 Feb. 2014 | Pending Pending Pending Pending | Hanover YIC. Project allocation is insufficient as the project amt. required is US$78,000. NCYD to obtain support from Universal Access Fund (UAF). Trelawny YIC. Several contracts to be issued. Trelawny YIC. Project allocation is insufficient as the project amt. required is US$78,000. NCYD to obtain support from Universal Access Fund (UAF). St. Catherine and Clarendon YICs. |
| SUBTOTAL US$35,988 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| - Goods Cont’d. - Goods 8 Remainder of ICT equipment for YICs Estimated cost: US$88,455 - Goods 9 Opening of 2 YICs Estimated cost: US$12,000 - Goods 10 Electronic Surveillance Security & Alarm Systems Estimated cost: US$25,707 | PC PC PC | Ex-Post Ex-Post Ex-ante | 100 100 100 |  | No No No | N/A N/A N/A | Jul. 2014 Feb. 2014 & Jul. 2014 Mar. 2014 | Pending Pending In Process | Purchases being done on a phased basis. Several contracts to be issued. Clarendon and St. Catherine YICs. Costs to include logistics, refreshments, ‘Entrepreneurship Fair’ for potential Users. Funds re-directed from allocations for equipment for each YIC. Surveillance system to be installed at St. Catherine, Hanover & Trelawny YICs. |
| SUBTOTAL US$126,162 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| - Goods Cont’d. Institutional Strengthening, Capacity Building (ISCB) Model YIC & Testing of M&E Systems GOODS 11: - Stationery & Office Supplies Estimated cost: US$10,000 - Maintenance and Supplies Estimated cost: US$11,000 - Equipment, Accessories Estimated cost: US$25,000 - Other Goods Estimated cost: US$13,920 - Training and Workshops Estimated cost: US$20,000 - Outreach Activities Estimated cost: US$13,000 | PC PC PC PC PC PC | Ex-Post Ex-Post Ex-Post Ex-Post Ex-Post Ex-Post | 100 100 100 100 100 100 |  | No No No No No No | N/A N/A N/A N/A N/A N/A | Dec. 2014 Dec. 2014 Dec. 2014 Dec. 2014 Mar. 2015 Mar. 2015 | Pending Pending Pending Pending Pending Pending |  |
| SUBTOTAL US$92,920 |  |  |  |  |  |  |  |  |  |
| TOTAL (Goods 1-11) US$291,195 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services - Consulting Service 1 Institutional Strengthening, Capacity Building (ISCB) Model YIC & Testing of M&E System PERSONNEL: - 1 IT Systems Admin/Technician (NCYD) Estimated cost: US$24,811 - 1 M&E Systems Manager (NCYD) Estimated cost: US$$25,666 - 1Website Manager (NCYD) Estimated cost: US$24,811 | QCNI QCNI QCNI | Ex-Post Ex-Post Ex-Post | 100 100 100 |  | No No No | May 2013 Jan. 2014 May 2013 | Mar. 2014 Dec. 2014 Mar. 2014 | In Process In Process Awarded/ In Process | Contract to be awarded to Gavin Rose subject to approval of secondment from NCYD. Contract awarded to Traci-Ann Johns. |
| SUBTOTAL US75,288 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| - Consulting Services Cont’d. - Consulting Service 1 ISCB Model YIC & Testing of M&E System PERSONNEL: - 10 M&E Assistants/Data Clerks – 10 YICs Estimated cost: US$51,253 - Entrepreneurship Promotion/ YICs Events Estimated cost: US$12,237 | QCNI QCNI | Ex-Post Ex-Post | 100 100 |  | No No | May 2013 Mar. 2014 | Aug. 2014 Dec. 2014 | In Process Pending | Data Clerks included for St. Catherine and Clarendon when opened. Note: Projected sums allocated for emoluments package to Project Staff are subject to change and final approval. |
| SUBTOTAL US$63,490 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 2 Consultant for data collection and evaluation of YIC operations Estimated cost: US$2,835 - Consulting Service 3 ICT Upgrade in existing YICs Estimated cost: US$75,346 | QCNI CQS | Ex-ante Ex-Post | 100 100 |  | No No | Jan. 2014 Jan. 2014 | Mar. 2014 Mar. 2015 | Pending Pending | Data Collection and Impact Evaluation Activity to be deferred. Budget reduced to support M&E Consultancy. Deliverables for M&E include In-Process Assessment of the Testing of M&E System implemented in 4 YICs. US$8,000 reallocated to support Stakeholders’ Meetings for 4 YICs. Upgrade activities are being phased. Only a portion of funds have already been spent. Additional upgrades to be done. |
| SUBTOTAL US$78,181 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 4 ICT Training for M&E Implementing Team Estimated cost: US$3,500 - Consulting Service 5 IT Users’ Guideline for YICs Estimated cost: US$3,500 | QCNI SSS | Ex-post Ex-Post | 100 100 |  | No No | Feb. 2014 N/A | Feb. 2014 Apr. 2014 | Pending Awarded/ In Process | Following final hiring of the team members. First draft delivered electronically. Awaiting additional feedback from NCYD/YIC Users. |
| SUBTOTAL US$7,000 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 6 Project Manager (Construction ) (NWA) Actual cost: US$55,814 - Consulting Service 7 Architectural Firm (Plexus Ltd.) Actual cost: US$45,349 - Consulting Service 8 Architect (Heritage sites) (Cornerstone Design) Actual cost: US$27,907 | SSS NCB SSS | Ex-ante Ex-ante Ex-ante | 100 100 100 |  | No No No | N/A Mar. 2010 N/A | Mar. 2014 Mar. 2014 Mar. 2014 | Awarded/ In Process Awarded/ In Process Awarded/ In Process | For St. Catherine and Clarendon YICs. Duration now extended to 2014. Defects Liability period to be included. Projected completion for Clarendon – Dec. 2013 & St. Catherine – Jun. 2014. For Clarendon YIC projected for completion Dec. 2013. Duration to be extended to include 6 months Defects Liability Period (DLP) For St. Catherine YIC. Now extended to 2014. DLP included in extension. Projected completion time to Jun. 2014. |
| SUBTOTAL US$129,070 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 9 Project Manager (Construction ) (NWA) Actual cost: US$46,926 - Consulting Service 10 Architectural Firm (Plexus Ltd.) Actual cost: US$41,940 - Consulting Service 11 Architect (Heritage sites) (Cornerstone Design) Actual cost: US$26,744 | SSS SSS SSS | Ex-ante Ex-ante Ex-ante | 100 100 100 |  | No No No | N/A N/A N/A | Mar. 2014 Mar. 2014 Mar. 2014 | Awarded/ In Process Awarded/ In Process Awarded/ In Process | For Hanover and Trelawny. Services include Land Surveying and Geotechnical Engineering services. Contract Amendment to follow to exclude St. Andrew YIC. Defects Liability period goes beyond March, 2014. For Hanover YIC. Contract amendment to follow to exclude St. Andrew YIC. Defects Liability period goes beyond March 31 2014. For Trelawny YIC. Note: Extension of these contracts is tied to new end date of YDP. |
| SUBTOTAL US$115,610 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 12 Consultant for website maintenance and hosting Actual cost: US$12,500 - Consulting Service 13 Stakeholders’ Forums for 4 YICs and other meetings Estimated cost: US$6,500 | SSS PC | Ex-Post Ex-Post | 100 100 |  | No No | N/A N/A | Mar. 2014 Mar. 2014 | Awarded/ In Process Awarded/ In Process | Follow-on Contract awarded to Web Developer, Trevor Forrest and to be extended to new end date of YDP. Forums to precede Contract Award/Signing for Hanover and Trelawny YICs, respectively. |
| SUBTOTAL US$19,000 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 14 Consultant to develop Monitoring & Evaluation Framework/System and Activities relating to Pilot Project Actual cost: US$26,800 | SSS | Ex-Post | 100 |  | No | N/A | Dec. 2013 | Awarded / In Process | Contract awarded to Moses Peart To include preparation of JDs, TORs for Pilot Project Personnel, training in Monitoring, Data Collection at YICs. Preliminary Assessment of Pilot Project in YICs. Contract amended to reflect end date for December 2013, following IDB’s approval of extension of YDP. Contract to be re-negotiated due to delays from ‘Merger’ announcements. TOR to be revised. |
| SUBTOTAL US$26,800 |  |  |  |  |  |  |  |  |  |
| TOTAL (CS 1-14) US$514,439 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 3. Civil Works - Works 1 Contractor for St. Catherine YIC Actual cost: US$298,536 - Works 2 Contractor for Clarendon YIC Actual cost: US$251,685 | NCB NCB | Ex-ante Ex-ante | 100 100 |  | No No | Mar. 2011 Mar. 2011 | Mar. 2014 Dec. 2013 | Awarded/ In Process Awarded/ In Process | Contract awarded to Rogers Land Development Limited. 12-month construction period. Construction cost of US$823,269 shared with NYS. Contract date to be extended. Contract Variations to be approved (some by Cabinet) prior to continuation of some works. Practical Further extension to be requested. Contract awarded to Rogers Land Development Limited. Construction cost of approx. US$629,213 shared with NYS. (60:40). Practical completion certificate issued at the end of Nov. |
| SUB-TOTAL - US$550,221 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 3. Civil Works Cont’d. - Works 3 Contractor for Hanover YIC Estimated cost: US$298,536 - Works 4 Contractor for Trelawny YIC Estimated cost: US$298,536 | NCB NCB | Ex-ante Ex-ante | 100 100 |  | No No | Dec. 2013 May 2014 | Mar. 2015 May 2015 | In Process Pending | Hanover YIC – full construction. Practical completion projected for March 2015 – 9-month construction period. Defects Liability period extended beyond March 2015. Trelawny YIC – full construction. Additional costs projected for External Works relating to design and construction of a Sewage Disposal System. Scheduled for 80% completion by March 2015. |
| SUB-TOTAL US$597,072 |  |  |  |  |  |  |  |  |  |
| TOTAL (Works 1-4) US$1,147,293 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 4. Non-Consulting Services - Service 1 Utility connections for YICs Estimated cost: US$7,865 | Direct Payments | Ex-Post | 100 |  | No | N/A | Apr. 2014 | In Process | To include Internet, cabling, telephone, Jamaica Public Service 3-phase electricity connections & water. Allocation supported by activity at ‘Consulting Service 2’. |
| TOTAL US$7,865 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme				Component 3 – Sector Management (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services - Consulting Service 1 Programme Support Officer, NCYD Estimated cost: US$27,472 - Consulting Service 2 Consultant to Oversee Youth Policy & Develop Masters Programme for youth development Actual cost: US$31,053 | QCNI SSS | Ex-ante Ex-ante | 100 100 |  | No No | Mar. 2014 N/A | Mar. 2015 Mar. 2014 | Pending Awarded/ In Process | Integration of Mainstreaming recommendations in NCYD programmes. (Preliminary work) Contract issued to Vivienne Williams Thompson. Received the Bank’s approval to hire Mrs. Williams Thompson as she was involved in the preliminary stages of this activity. Her knowledge of the consultancy and what is required is unquestionable. Contract extended to Mar. 2014. |
| SUBTOTAL US$58,525 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme				Component 3 – Sector Management (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 3 Policy Instruments to Support Youth Sector (incl. Youth stakeholder consultation & M&E Plan) Actual cost: US$213,445 | QCBS | Ex-ante | 100 |  | No | Mar. 2012 | Feb. 2014 | Awarded/ In Process | To include Strategic Plan and Cost Benefit Analysis. Contract awarded to UWI Consulting Inc. Contract was amended to include increase in reimbursable expenses. Contract extended to Feb. 2014. |
| SUBTOTAL US$213,445 |  |  |  |  |  |  |  |  |  |
| TOTAL (CS 1-3) US$271,970 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme				Component 3 – Sector Management (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| Non-Consulting Service - Support to multifunctional teams (incl. Youth Ambassador’s Prog.) Estimated cost: US$17,000 - Stakeholder Consultation Estimated cost: US$54,945 | PC PC | Ex-Post Ex-Post | 100 100 |  | No No | N/A N/A | Mar. 2014 Mar. 2014 | Pending In Process | Support to meetings and workshops. Several contracts to be issued. To support workshops, focus group meetings for Youth Policy. Several contracts to be issued and will be under the threshold. |
| TOTAL US$71,945 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme						Project Implementation Unit

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| - Consulting Services - Consulting Service 1 External Auditing Services Estimated cost: US$30,000 - Consulting Service 2 End of Project Evaluation Estimated cost: US$62,837 - Consulting Service 3 Evaluation Phase I (Mid-Term) Actual cost: US$14,762 - Consulting Service 4 Follow-on Contract for Project Driver Actual cost: US$10,035 | SSS QCNI QCNI SSS | Ex-ante Ex-ante Ex-Post | 100 100 100 100 |  | No No No No | N/A Jan. 2015 Oct. 2012 N/A | Jul. 2014 & Jun. 2015 Jun. 2015 Jul. 2013 Mar. 2014 | In Process Pending Terminated Awarded/ In Process | KPMG to carry out audit of the project for two financial years - FY 2013/14 and FY 2014/15. Contract awarded to Joy Moncrieffe was terminated as there will be no Phase II of the project. Contract issued to Winston Clarke. Contract extended. |
| SUBTOTAL US$117,634 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme						Project Implementation Unit

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 5 Follow-on Contract for Programme Manager Actual cost: US$79,920 p.a. - Consulting Service 6 Contract for Financial Specialist Actual cost: US$54,938 p.a - Consulting Service 7 Follow-on Contract for Procurement Specialist Actual cost: US$49,332 p.a. | SSS SSS SSS | Ex-Post Ex-Post Ex-Post | 100 100 100 |  | No No No | N/A N/A N/A | Mar. 2014 Mar. 2014 Mar. 2014 | Awarded/ In Process Awarded/ In Process Awarded/ In Process | Contract awarded to Margery Newland. Contract extended. Contract awarded to Shernette Effs. Contract extended. Contract awarded to Marlene McKessey. Contract extended. |
| SUBTOTAL US$184,190 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme						Project Implementation Unit

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 8 Project Administrator Actual cost: US$24,440 p.a - Consulting Service 9 Project Assistant, Comp. 1 Actual cost: US$19,040 p.a. - Consulting Service 10 Follow-on Contract for Technical Coordinator, Comp. 1 Actual cost: US$56,590 p.a. | SSS QCNI SSS | Ex-Post Ex-Post Ex-Post | 100 100 100 |  | No No No | N/A Feb. 2012 N/A | Mar. 2014 Mar. 2014 Mar. 2014 | Awarded/ In Process Awarded/ In Process Awarded/ In Process | Contract awarded to Geraldine Simmonds. Contract extended. Contract issued to Kerry-Ann Osbourne. Contract amended to include an increase for additional work as Project Accountant. Contract issued to Sonia Francis Contract extended. |
| SUBTOTAL US$100,070 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme						Project Implementation Unit

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 11 Follow-on Contract for Technical Coordinator, Comp. 2 Actual cost: US$56,590 p.a. - Consulting Service 12 Project Assistant, NCYD Actual cost: US$21,477 p.a. | SSS QCNI | Ex-Post Ex-Post | 100 100 |  | No No | N/A Aug. 2011 | Mar. 2014 Mar. 2014 | Awarded/ In Process Awarded/ In Process | Contract issued to Alethia Barker. Contract extended. Contract issued to Beverly Gordon. Contract extended. |
| SUBTOTAL US$78,067 |  |  |  |  |  |  |  |  |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme						Project Implementation Unit

| Description of the contract and estimated cost of procurement | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 13 Clerical Assistant, PIU Actual cost: US$5,457 p.a. - Consulting Service 14 Clerical Assistant, NCYD Actual cost: US$5,081 p.a. - Consulting Service 15 Clerical Assistant, NCYD Actual cost: US$5,081 p.a. | SSS SSS SSS | Ex-Post Ex-Post Ex-Post | 100 100 100 |  | No No No | N/A N/A N/A | Mar. 2014 Mar. 2014 Mar. 2014 | Awarded/ In Process Awarded/ In Process Awarded/ In Process | Contract issued to Anneka Wallace. Contract issued to Tashieka Bailey. Contract issued to Danekia Barnes. |
| SUBTOTAL US$15,619 |  |  |  |  |  |  |  |  |  |
| TOTAL (CS 1-15) US$495,580 |  |  |  |  |  |  |  |  |  |

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment