INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 1. Goods - Goods 1 Procure and install air conditioning units, blinds and mobile partitioning in 14 parish offices Estimated cost: US$90,000 - Goods 2 Partitioning and procure furniture and equipment for NYS Head Office and parish offices Estimated cost: US$170,000 - Goods 3 ICT – NYS Head Office and parish offices including PBX, computers & accessories Estimated cost: US$200,000 | NCB ICB ICB | Prior Prior Prior | 100 100 100 |  | No No No | Mar. 2010 Mar. 2010 Aug. 2010 | Aug. 2010 July 2010 Nov. 2011 | In process In process Pending | NYS Head Office plus 2 parish offices for year 1. Several contracts to be awarded |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 1. Goods Cont’d. - Goods 4 Instructional Equipment Estimated cost: US$60,000 - Goods 5 Procure two 4x4 vehicles Estimated cost: US$120,000 - Goods 6 Furniture and equipment for existing NYS camps Estimated cost: US$15,000 - Goods 7 Printing of Personal Development Manual Actual cost: US$2,348.44 | NCB NCB PC PC | Prior Prior Prior Post | 100 100 100 100 |  | No No No No | Apr. 2011 May 2010 Apr. 2011 Jan. 2010 | Oct. 2011 Jun. 2010 Jul. 2011 Feb. 2010 | Pending Pending Pending Awarded | For existing and new camps Cost based on average quotes received from dealers. Goods delivered |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 1. Goods Cont’d. - Goods 8 Instruments for impact evaluation Estimated cost: US$100,000 | NCB | Prior | 100 |  | No | May 2011 | Jun. 2011 | Pending | The same instruments used for the NYS baseline impact study will be acquired for the this evaluation. |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services - Consulting Service 1 Corporate marketing and alignment of NYS. Alignment with employer needs and demands Estimated cost: US$590,000 - Consulting Service 2 Curriculum revision and alignment Estimated cost: US$300,000 - Consulting Service 3 Development and implementation of Information Management System (WAN) Estimated cost: US$200,000 | ICB ICB QCBS | Prior Prior Prior | 100 100 100 |  | No No No | Feb. 2010 May 2010 May 2010 | Feb. 2012 Aug. 2011 Nov. 2011 | In process Pending Pending | This activity is to include Cost Sharing Mechanisms for Private Sector training. A firm is to be contracted. |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 4 Web portal/relational database Estimated cost: US$50,000 - Consulting Service 5 HR Management System Estimated cost: US$75,000 - Consulting Service 6 Accounting System Estimated cost: US$100,000 | QCNI QCBS FBS | Post Prior Prior | 100 100 100 |  | No No No | Jun. 2011 Sept. 2010 Mar. 2011 | Nov. 2011 Dec. 2010 Jul. 2011 | Pending Pending Pending |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| - Consulting Services Cont’d. - Consulting Service 7 Programme and curriculum development. New initiatives for youth with low literacy levels. Estimated cost: US$331,470 - Consulting Service 8 Piloting of new initiatives Estimated cost: US$1,080,000 - Consulting Service 9 Evaluation of new initiatives Estimated cost: US$96,000 - Consulting Service 10 Recruitment tools Estimated cost: US$150,000 | QCBS QCBS QCII QCII | Prior Prior Prior Prior | 100 100 100 100 |  | No No No No | Jan. 2011 Jun. 2011 Oct. 2011 Jul. 2011 | July 2011 Sept. 2011 Dec. 2011 Oct. 2011 | Pending Pending Pending Pending |  |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| - Consulting Services Cont’d. - Consulting Service 11 Facility expansion plan Estimated cost: US$105,000 - Consulting Service 12 Impact evaluation Estimated cost: US$240,000 - Consulting Service 13 Monitoring and evaluation framework Estimated cost: US$25,000 - Consulting Service 14 Evaluation Specialist Estimated cost: US$110,000 | QCNI QCBS QCII QCNI | Prior Prior Prior Prior | 100 100 100 100 |  | No No No No | Jun. 2010 May. 2011 May 2010 Apr. 2011 | Oct. 2010 Jun. 2011 Sept. 2010 Jun. 2013 | Pending Pending Pending Pending | (Architectural Firm – Q.S., Architect, Engineer, Land Surveyor to be engaged. |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 15 Evaluation Assistant Estimated cost: US$30,000 - Consulting Service 16 Professional Development for NYS Staff (incl. training needs assessment Estimated cost: US$191,800 - Consulting Service 17 Regional Field Officers (6) Estimated cost: US$150,000 - Consulting Service 18 Instructional/Career guidance materials Estimated cost: US$60,000 | QCNI QCBS QCNI NCB | Prior Prior Prior Prior | 100 100 100 100 |  | No No No No | Apr. 2011 Apr. 2010 Dec. 2009 Apr. 2011 | Jun. 2013 Jun. 2013 Jun. 2013 Jul. 2011 | Pending Pending In Process Pending | Several contracts to be awarded. 6 RFOs will be employed for 3 years. |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 19 Instruments for impact evaluation Estimated cost: US$100,000 - Consulting Service 20 Technical Coordinator, NYS Actual cost: J$170,150.90 - Consulting Service 21 Project Assistant Estimated cost: US$80,000 - Consulting Service 22 Chief Technical Advisor, NYS Estimated cost: US$84,000/yr | NCB QCNI QCNI QCII | Prior Prior Prior Prior | 100 100 100 100 |  | No No No No | Jun. 2010 Mar. 2009 Jan. 2010 Apr. 2011 | Jul. 2011 Aug. 2011 Jun. 2013 Jun. 2013 | Pending Awarded In Process Pending | The same instruments used for the NYS baseline impact study will be acquired for the final report. An initial two year contract was issued. Employed full-time to NYS. An initial two year contract to be issued. To be hired on a retainer basis |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme		Component 1 – Quality Improvement & Strengthening (NYS)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 3. Works - Works 1 Upgrade NYS and parish offices (Electrical upgrades, fixed partitioning, tinting and painting) Estimated cost: US$110,000 - Works 2 Rehabilitation. NYS new camp facilities Estimated cost: US$450,000 - Works 3 Construction of Regional Offices in Spanish Town & May Pen Estimated cost: US$300,000 | NCB ICB NCB | Prior Prior Post | 100 100 100 |  | No Yes No | Jan. 2010 Jun. 2010 Aug. 2010 | Dec. 2010 Oct. 2012 Oct. 2010 | Pending Pending Pending | Multiple contracts will be awarded. NYS Parish Offices to be merged with YICs. |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 1. Goods - Goods 1 Laptops & Desktop Computer Actual cost: US$3,346 - Goods 2 ICT, furniture and equipment for Youth Information Centres Estimated cost: US$430,000 | PC ICB | Post Prior | 100 100 |  | No Yes | Sept. 2009 Aug. 2010 | Nov. 2009 Jun. 2013 | Awarded Pending | Goods delivered. Multiple contracts to be executed in tandem with the completion of the YICs. |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services - Consulting Service 1 Project Manager (Construction ) (NWA) Actual cost: US$48,137 - Consulting Service 2 Architectural Firm Actual cost: US$43,605 - Consulting Service 3 Architect (Heritage sites) Actual cost: US$26,867.25 | DC QCBS DC | Prior Prior Post | 100 100 100 |  | No No No | N/A Mar. 2010 Mar. 2010 | Jun. 2013 Mar. 2011 Mar. 2011 | Awarded Awarded Awarded | Contract for first 2 YICs was issued in the amount of J$4.3M. These services will be procured on a retainer basis for each of the 5 YICs, including Land Surveying services Contract was awarded for 1 YIC in the amount of J$3.9M. Firm to be contracted for 2 additional YICs. Contract was awarded for 1 YIC in the amount of J$2.4M. Firm to be contract for 1 additional YICs. (2 YICs to be built in Heritage District). |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 5 Geotechnical Engineer for YICs Actual cost: US$5,625 - Consulting Service 6 Consultant to develop Monitoring & Evaluation Framework Estimated cost: US$10,500 - Consulting Service 7 Consultant for website construction and maintenance Actual cost: US$12,052.74 - Consulting Service 8 Consultant for data collection M&E Estimated cost: US$98,000 | QCNI QCNI QCNI QCNI | Prior Prior Prior Prior | 100 100 100 100 |  | No No No No | Mar. 2010 Apr. 2011 Mar. 2010 Apr. 2011 | Jun. 2010 Jun. 2012 May 2011 Aug. 2011 | Awarded Pending Awarded Pending | For 2 sites. Firm to be contracted for 2 additional YICs where full construction will take place. Project management services on retainer for 3 years Website Consultant on retainer for 3 years |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 9 Technical Coordinator Actual cost: US$170,150 - Consulting Service 10 I.T. Consultant for 5 YICs Actual cost: US$4,800 - Consulting Service 11 Upgrade of internet capacity in 4 existing YIC Estimated cost: US$80,000 - Consulting Service 12 Heritage Impact Assessment Estimated cost: US$2,000 | QCNI QCNI PC DC | Prior Prior Prior Post | 100 100 100 100 |  | No No No No | April 2009 Mar. 2010 Jun. 2010 May 2010 | Aug. 2011 Jun. 2010 Sept. 2010 May 2010 | Awarded Awarded Pending In Process | An initial two year contract was issued. Employed full-time to NCYD. Assessment to be carried out by Jamaica National Heritage Trust (JNHT). |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme			Component 2 – Youth Information Centres (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 3. Civil Works - Works 1 Contractor for Spanish Town YIC Estimated cost: US$300,000 - Works 2 Contractor for Clarendon YIC Estimated cost: US$300,000 - Works 3 Contractor for 3 remaining YICs Estimated cost: US$900,000 | NCB NCB NCB | Prior Prior Prior | 100 100 100 |  | No No No | Jul. 2010 Jul. 2010 Apr. 2011 | Mar. 2011 Mar. 2011 Jun. 2013 | Pending Pending Pending | 3 separate contracts at US$300,000 each. |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme				Component 3 – Sector Management (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 1. Goods - Goods 1 Youth & Stakeholder Consultations Estimated cost: US$65,270 - Goods 2 Support to multifunctional teams (incl. Youth Ambassador’s Prog.) Estimated cost: US$40,000 - Goods 3 National Youth Survey Launch Actual cost: US$3,302.73 | NCB NCB PC | Post Prior Post | 100 100 100 |  | No No No | Oct. 2010 Apr. 2011 Mar. 2010 | Dec. 2010 Mar. 2012 Mar. 2010 | Pending Pending Awarded | Support to meetings and workshops. Purchase Orders issued to various suppliers/contractors. Total cost was J$295,678. |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme				Component 3 – Sector Management (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services - Consulting Service 1 National Youth Survey Actual cost: US$486,188 - Consulting Service 2 Development of indicators for youth policy (M&E) Estimated cost: US$40,000 - Consulting Service 3 Electronic Youth Programmatic Inventory & Gap Analysis Estimated cost: US$60,240 - Consulting Service 4 Situational Analysis Estimated cost: US$22,800 | DC QCNI QCBS QCNI | Prior Prior Prior Prior | 100 100 100 100 |  | No No No No | N/A Apr. 2011 Feb. 2010 Jun. 2010 | Oct. 2010 Sept. 2011 Jun. 2011 Sept. 2010 | Awarded Pending In Process Pending | STATIN was contracted to undertake the youth survey (J$43,756,960) Firm to be contracted 1 Coordinator and 2 Researchers to be contracted. |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme				Component 3 – Sector Management (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 5 Marketing and Communication (Mainstreaming) Estimated cost: US$104,000 - Consulting Service 6 Development of Masters Programme for youth development Estimated cost: US$120,000 - Consulting Service 7 Technical Coordinator Amount: J$15,120,000 | ICB QCBS QCNI | Prior Prior Prior | 100 100 100 |  | No No No | Feb. 2010 Apr. 2011 April 2009 | Jan. 2011 Apr. 2012 Aug. 2011 | In Process Pending Awarded | Firm to be contracted An initial 2 year contract was issued. Employed full-time at NCYD. |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme				Component 3 – Sector Management (NCYD)

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 8 Project Assistant Actual cost: US$50,726 - Consulting Service 9 Professional development for NCYD Staff Estimated cost: US$32,400 - Consulting Service 10 Youth & Stakeholder Consultation Amount: US$41,700 | QCNI QCBS QCNI | Prior Prior Prior | 100 100 100 |  | No No No | Oct. 2009 Apr. 2011 Oct. 2010 | Oct. 2011 Apr. 2012 Dec. 2010 | Awarded Pending Pending | A 2 year contract issued in the amount of J$4,512,480. |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme						Project Implementation Unit

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services - Consulting Service 1 External Auditing Services Actual cost: US$14,115.89 - Consulting Service 2 Programme Manager Actual cost: US$103,486 (2 yrs.) - Consulting Service 3 Financial Specialist Actual cost: US$76,087 (2 yrs.) - Consulting Service 4 Procurement Specialist Actual cost: US$63,683 (2 yrs.) | QCBS DC QCNI DC | Post Prior Prior Prior | 100 100 100 100 |  | No No No No | June 2009 N/A Mar. 2009 N/A | Nov. 2013 Jul. 2011 Sept. 2011 Apr. 2011 | Awarded Awarded Awarded Awarded | Estimated total for 4 annual audits. Contract awarded in the amount of J$1,255,200 for first audit. Non-objection received. A two year contract issued in the amount of J$9,193,000. A two year contract issued in the amount of J$6,756,750. Non-objection received. A two year contract issued in the amount of J$5,640,000 |

INTER-AMERICAN DEVELOPMENT BANK

PROCUREMENT PLAN

Loan Number:  2039/OC-JA

Program Name:  Youth Development Programme						Project Implementation Unit

| Description of the contract and estimated cost of procurement | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/ other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 2. Consulting Services Cont’d. - Consulting Service 5 Project Assistant Estimated cost: US$97,218 (4 yrs.) - Consulting Service 6 Project Accountant Estimated cost: US$91,817 (4 yrs.) - Consulting Service 7 Project Driver Estimated cost: US$35,160 (4 yrs.) - Consulting Service 8 Evaluation Phase I Estimated cost: US$170,000 | QCNI QCNI QCNI QCII | Post Post Post Prior | 100 100 100 100 |  | No No No No | Jan. 2010 Jan. 2010 Jan. 2010 Jan. 2012 | Jun. 2013 Jun. 2013 Jun. 2013 Oct. 2012 | In Process In Process In Process Pending | An initial 2 year contract is to be issued. “ “ “ “ “ “ Evaluation to take place within 6 months. |

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment

ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; QCBS: Quality-and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection

All contracts are pending at the moment