# PROJECT PROCUREMENT PLAN

Model A - for specific projects

General information

Country: Suriname

Borrower: Republic of Suriname

Executing agency: Ministry of Education and Community Development (MOECD)

Project name: Second Basic Education Improvement Program (BEIP) – Phase I

Project and loan contract numbers: SU-L1019

Brief description of the project’s objectives and components:

- The program goal is to increase learning outcomes of students in the education system of Suriname from pre-primary through junior secondary education nationally. The overall program objective is to improve the internal efficiency and quality of the new basic education system. The strategic objective is to eliminate the tracking system and create a new basic education cycle comprised of 11 years from pre-primary through junior secondary school. The program has four components: (i) Component 1: improving student learning outcomes in basic education in grades 1 to 8 (primary level), with an emphasis in Dutch and arithmetic, and in teaching approaches; (ii) Component 2: Researching ICT in education and implementing pilots to test different strategies for utilizing ICT in the classroom; (iii) Component 3: increasing access to education through school construction and expansion, construction of teacher housing in the interior and construction, rehabilitation and refurbishment of MOECD departments; and (iv) Component 4: improving management of the education system at the MOECD and school levels.

Estimated date of project approval by the Board of Executive Directors: June 6, 2012

Estimated date of signature of the loan contract: June 8, 2012

Estimated date of the final disbursement: June 8, 2016

- A. Introduction

Procurements for the proposed project will be carried out in accordance with the Policies for the Procurement of Works and Goods Financed by the Inter-American Development Bank (GN-2349-9), of March 2011; and the Policies for the Selection and Contracting of Consultants Financed by the Inter-American Development Bank (GN-2350-9), of March 2011, and with the provisions established in the loan contract and this procurement plan.

- B. Procurement plan

The procurement plan for the Program for Improved Basic Education covering 48 months of project execution has been agreed between the Bank and MOECD. The plan, which is summarized in Appendix 1, indicates the procedure to be used for the procurement of goods, the contracting of works or services, and the method of selecting consultants, for each contract or group of contracts. It also indicates cases requiring prequalification; the estimated cost of each contract or group of contracts; the requirement for prior or post review by the Bank; and estimated dates for the publication of specific procurement notices and completion of the contracts included in this project. The procurement plan will be updated annually or whenever necessary or as required by the Bank. The detailed procurement plan is available at:

Office of the Permanent Secretary

Ministry of Education and Community Development

Dr. Kafiluddistraat 117

Paramaribo, Suriname

The procurement plan will be made available on the executing agency’s website. is available on the executing agency’s website. The following documents can also be found on the Bank’s website: Project Procurement Information

- C. Project procurement

The following is a general description of the procurement planned for the proposed project.

Works procurement: The works to be contracted include the following: (i) construction of four new schools, renovation/expansion of three schools and upgrading of 10 schools to increase school access and decrease over crowdedness; (ii) renovation and upgrading of MOECD departments and teacher training colleges; and (ii) construction of CENASU; (iii) Construction of new location or rehabilitation of existing MOECD department to house date center for EMIS.

Project works requiring International Competitive Bidding (ICB) will be contracted using the Standard Bidding Documents (SBDs) issued by the Bank. Procurement subject to National Competitive Bidding (NCB) will be undertaken using national bidding documents agreed upon with the Bank [or satisfactory to the Bank in the absence of an agreement].

Goods procurement: The goods to be procured for this project include the following: (i) provision of textbooks and teaching and learning materials for grades 1 to 8 in the new basic education cycle; (ii) upgrading MOECD departments and teacher training colleges by providing equipment/furniture; and ICT equipment for the MOECD and 150 schools selected for EMIS and for 10 schools selected for ICT in education pilot; and (iii) Furniture for 150 schools selected for EMIS.

Project goods requiring ICB will be procured using the SBDs issued by the Bank. Procurement subject to NCB will be undertaken using national bidding documents agreed upon with the Bank.

Procurement of non-consulting services: The non-consulting services planned in the program will utilize the goods policy.

Procurement of consulting services: Consulting services for the project include: (i) to work on the redesign of the curriculum from grades 1 to 8; (ii) to conduct a study on the feasibility and sustainability of the provision of textbooks; (iii) to assist in the reform of the examination system; (iv) to provide teacher training through the program period (in-service and pre-service); and (v) develop, pilot and evaluate ICT in education. These items are related to the reform of the curriculum and professionalization of the education system. In addition, consulting services also include: (i) building capacity of staff within the MOECD and schools, including in use of the EMIS; (ii) continuous social marketing of the program; (iii) additional studies, including on how to restructure the junior secondary education and options for a new assessment system; (iv) formative, mid-term and final evaluations of the program; and (v) the audit of the program.

The consulting firms to be hired for the project will be selected using the Standard Request for Proposals (RFP) issued by the Bank, or an RFP satisfactory to the Bank in cases where the standard RFP is not applicable. Individual consultants will be selected in accordance with the provisions established in chapter V of the policy in document GN-2350-9.

Short lists of consultants for consulting services estimated to cost less than US$100,000 equivalent per contract may consist entirely of national firms.

It is possible that consulting services related to curriculum development, professional development of teachers and other areas of the curriculum reform may include candidates such as universities and NGOs given the extensive experience of such entities in this area.

Operating expenses: The following operating expenses will be financed by the Bank: The program will finance the salaries of the Program Management Unit (PMU) staff throughout the program period. Designated MOECD staff to the program will also receive an incentive based on clear deliverables and for program work outside of their normal responsibilities. This could include the salaries of staff.

Project operating expenses to be financed by the Bank may be contracted using the executing agency’s procedures that have been previously reviewed by the Bank and classified as satisfactory.

Others: MOECD staff will be eligible to receive scholarships to continue their studies at a university. The procurement method used will be that of non-consulting services. Procurement for these non-consulting services will utilize the goods policy.

Advance contracting and retroactive financing: Contracts that are active from the Basic Education Improvement Program (SU0023) will automatically be transferred to the reformulated program, SU-L1019 upon program approval. Since SU-L1019 is a reformulation of the SU0023, current activities are also relevant for the new program.

- D. Bank review of procurement decisions

The following contracts will be subject to prior review by the Bank in accordance with Appendix 1 of the policies for the procurement of works and goods and the selection of consultants, respectively:

- Works contracts with an estimated total cost of US$50,000.00 equivalent or more.

- Goods contracts with an estimated total cost of US$25,000.00 equivalent or more.

- Contracts for Non-Consulting Services with an estimated total cost of US$50,000.00 equivalent or more.

- All direct contracting.

- Contracts for Consulting Services with firms with an estimated total cost of US$25,000.00 equivalent or more.

- Contracts with Individual Consultants with an estimated total cost of US$10,000.00 equivalent or more.

- All Single-Source Selection of Consulting Firms.

The remaining contracts will be subject to ex-post review by the Bank, in accordance with the aforementioned Appendix 1 of the policies.

- E. Domestic preference

Bids offering goods originating in the borrower’s country will receive a 15% price preference in contracts requiring international competitive bidding, as established in Appendix 2 of the procurement policies.

Appendix I

# Procurement Plan

Country: Suriname

Executing agency: Ministry of Education and Community Development (MOECD)

Project name: Second Basic Education Improvement Program (BEIP) – Phase I

Project and loan contract numbers: SU-L1019

Brief description of the project’s objectives and components:

- The program goal is to increase learning outcomes of students in the education system of Suriname from pre-primary through junior secondary education nationally. The overall program objective is to improve the internal efficiency and quality of the new basic education system. The strategic objective is to eliminate the tracking system and create a new basic education cycle comprised of 11 years from pre-primary through junior secondary school. The program has four components: (i) Component 1: improving student learning outcomes in basic education in grades 1 to 8 (primary level), with an emphasis in Dutch and arithmetic, and in teaching approaches; (ii) Component 2: Researching ICT in education and implementing pilots to test different strategies for utilizing ICT in the classroom; (iii) Component 3: increasing access to education through school construction and expansion, construction of teacher housing in the interior and construction, rehabilitation and refurbishment of MOECD departments; and (iv) Component 4: improving management of the education system at the MOECD and school levels.

Estimated date of project approval by the Board of Executive Directors: June 6, 2012

Estimated date of signature of the loan contract: June 8, 2012

Estimated date of the final disbursement: June 8, 2016

Address of the executing agency office responsible for the procurement plan:

Office of the Permanent Secretary

Ministry of Education and Community Development

Dr. Kafiluddistraat 117

Paramaribo, Suriname

| Table 1: Country Thresholds for Procurement (in US$’000s) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Works |  |  | Goods |  |  | Consulting Services |
| International Competitive Bidding | National Competitive Bidding | Shopping/ Price Comparison | International Competitive Bidding | National Competitive Bidding | Shopping/ Price Comparison | Short Lists Solely by Nationals/ NCB |
| ≥1,000 | 100 – 1,000 | <100 | ≥100 | 25 - 100 | <25 | <100 |

Complete Procurement Plan

Project: Program for Improved Basic Education

Project number: SU-L1019 and Loan Contract number:

Period included in this Procurement Plan: From: June 2012 until June 2016

| Ref. No. | Description of and category of procurement contract | Estimated cost in (US$ thousand) | Procurement method | Review (ex-ante or ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated Dates |  |  |  | Status (pending, in process, awarded, cancelled) |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | IDB % | Local / Other % |  | Publication of specific procurement notice |  | Completion of contract |  |  |  |  |
| 1 | GOODS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 1. Improved learning outcomes in basic education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.2 Provision of textbooks and teaching and learning materials. | 2,950 | ICB | Ex-ante | 100% | 0 | No | Jun-12 | Dec-14 |  |  |  |  |  |
| Component 2. ICT in Education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.1 Provision of ICT equipment and furniture to schools in pilot. | 100 | NCB | Ex-ante | 100% | 0 | No | Apr-13 | Dec-13 |  |  |  |  | To be delivered to 10 schools in pilot. |
| Component 3. Increase access to basic education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.1 Provision of furniture and equipment for 4 newly constructed schools, CENASU and teacher housing. | 100 | NCB | Ex-ante | 100% | 0 | No | Apr-13 | Dec-13 |  |  |  |  |  |
| Component 4. Improve management at MOECD and school levels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.1 Capacity building, including university programs, for 25 MOECD staff as part of staff development. | 415 | ICB | Ex-ante | 100% | 0 | No | Oct-12 |  | Jan-15 |  |  |  |  |
|  | 4.2 EMIS expanded. | 300 | ICB | Ex-ante | 100% | 0 | No | Aug-12 |  | Dec-14 |  |  |  |  |
|  | 4.2 Connecting 150 basic education schools to the EMIS. | 200 | ICB | Ex-ante | 100% | 0 | Yes | Aug-12 |  | Dec-14 |  |  |  |  |
| 2 | WORKS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3. Increase access to basic education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3. Construction of 4 schools, teacher housing, and CENASU. | 3,700 | ICB | Ex-ante | 92% | 8% | Yes | Jul-12 |  | Apr-14 |  |  |  | Four new schools in the interior. |
|  | 3. Renovation and upgrading of MOECD departments. | 400 | NCB | Ex-ante | 100% | 0 | No | Jul-12 |  | Oct-14 |  |  |  | Renovation and upgrading of departments of R&P, Curriculum Development, Inspection, Examinations, Teacher Counseling and Support , also Construction and Furnishing. |
| 3 | CONSULTING SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 1. Improve learning outcomes in basic education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1 Re-design of the new basic education cycle curriculum. | 1930 | QBS | Ex-ante | 100% | 0 | Yes | Jun-12 |  | Apr-16 |  |  | Continuous, until end of the program. |  |
|  | 1.1 Reform of existing examination system and training for MOECD staff. | 500 | QCBS | Ex-ante | 100% | 0 | Yes | Jun-13 |  | Mar-16 |  |  |  |  |
|  | 1.1 Development of Strategy for revising junior secondary grades. | 70 | QCBS | Ex-ante | 100% | 0 | No | Jun-13 |  | Dec-13 |  |  |  |  |
|  | 1.1 Teacher training in the new curriculum and pedagogical approaches. | 200 | QCBS | Ex-ante | 100% | 0 | No | Jun-12 |  | Apr-16 |  |  | This includes smaller contracts to local consultants to provide ongoing support. |  |
|  | 1.2 Design Services for textbooks. | 50 | QCNI | Ex-ante | 100% | 0 | No | Jun-12 |  | Apr-14 |  |  |  |  |
| Component 2. ICT in Education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.1 Develop a national ICT in education policy and strategy. | 150 | QCBS | Ex-ante | 100% | 0 | No | Aug-12 |  | Feb-13 |  |  | To be approved by the MOECD, Council of Ministers. |  |
|  | 2.1 Develop and pilot ICT in education models in 10 schools. | 350 | QCBS | Ex-ante | 100% | 0 | No | Dec-12 |  | Aug-14 |  |  | Pilot will take place in 10 schools. |  |
|  | 2.1 Development of legal and regulatory framework for ICT in education. | 100 | QCBS | Ex-ante | 100% | 0 | No | Aug-12 |  | Feb-13 |  |  | To be approved by the MOECD, Council of Ministers. |  |
|  | 2.1 Assessment for ICT use in education in the interior / Action Plan on methods to expand ICT. | 100 | QCBS | Ex-ante | 100% | 0 | No | Dec-12 |  | Aug-14 |  |  |  |  |
|  | Component 3. Increase access to basic education |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3. Diagnostic study on school construction and expansion in the Interior. | 30 | QCNI | Ex-ante | 100% | 0 | No | Jun-12 |  | Jan-13 |  |  |  |  |
| Component 4 Improve management at MOECD and school levels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.1 Capacity building at relevant MOECD departments. | 300 | QCBS | Ex-ante | 100% | 0 | No | Dec-12 |  | Feb-16 |  |  |  |  |
|  | 4.1 School leaders management training. | 100 | QCBS | Ex-post | 100% | 0 | No | Jul-13 |  | Dec-15 |  |  |  |  |
|  | 4.2 Strengthening the EMIS system: training of MOECD-R&P staff. | 50 | QCNI | Ex-ante | 100% | 0 | No | Aug-12 |  | Dec-14 |  |  |  |  |
|  | 4.2 Strengthening the EMIS system: training staff at schools. | 70 | QCII | Ex-post | 100% | 0 | No | Aug-12 |  | Dec-14 |  |  |  |  |
|  | 4.3 Technical assistance in developing and implementing a social marketing campaign. | 185 | QCBS | Ex-ante | 100% | 0 | No | Jun-12 |  | May-16 |  |  | Continuous, until end of the program. |  |
|  | 4.3 Formative evaluation studies of design and implementation of revised curriculum. | 100 | QCBS | Ex-ante | 100% | 0 | No | Jan-13 |  | Mar-16 |  |  | Continuous, and connected to the design of the curriculum. |  |
|  | Project Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Mid-term evaluation | 80 | QCII | Ex-ante | 100% | 0 | Yes | Mar-14 |  | Oct-14 |  |  |  |  |
|  | Final evaluation | 80 | QCII | Ex-ante | 100% | 0 | Yes | Sep-15 |  | May-16 |  |  |  |  |
|  | Project auditing | 71 | QCBS | Ex-ante | 100% | 0 | No | Jun-12 |  | Jun-16 |  |  | Annually |  |
|  | Project administration: PCU/local consultants | 500 | QCNI | Ex-ante | 77% | 23% | No | Jun-12 |  | Jun-16 |  |  | PCU consultants include: Program Manager, Operations Officer, Procurement Officer, Finance Officer, Education Coordinators (2), Social Marketing Officer and IT Officer. |  |

Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms:  QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.

Appendix 2

Capacity of the executing agency and supervision of procurement by the Bank

Assessment of the executing agency’s capacity to administer procurement

Program Management Unit of the Program for Improved Basic Education will be responsible for carrying out project procurements. Having assessed the capacity of the executing agency [or a representative sample thereof if there are several] to carry out the procurement actions, the Bank rates the overall risk to the project arising from the administration of procurement as:

| Goods >US$25,000 (equivalent) | High |
| --- | --- |
| Works >US$50,000 (equivalent) | High |
| Non-consulting Services >US$50,000 (equivalent) | Low (X) |
| Consulting Firms >US$25,000 (equivalent) | Medium |

Significant deficiencies identified and corrective actions agreed upon are summarized below:

| Deficiencies | Corrective action | Completion date |
| --- | --- | --- |
| Formal assignment of functions and responsibilities for procurement processes not documented in operations manual. | Assignment of functions and responsibilities need to be documented and included in operations manual. | 30 June 2012 |
| Formal assignment of functions and responsibilities for processes relating to the receipt, inventory, and maintenance of works, goods and consulting services not documented in operation manual. | Assignment of functions and responsibilities need to be documented and included in operations manual. | 30 June 2012 |
| The procurement procedures do not define a separation of incompatible functions that allow for clearly differentiation of personnel's attributions in each one of the different phases of the process. | To include as part of the Operations Manual the standards and procedures relative to: (i) the levels of procurement, authorization levels, amounts, complexity and source of resources; and (ii) the application, authorization, start of the process and execution of the procurement and contracting for different officials. | 30 June 2012 |
| The system of procurement administration does not allow to identify the commitments and all other transactions from the beginning of the process, and establishes a link among the creation of the obligation, the receipt of the goods, works, and consulting services, and the corresponding payments, thus providing a reasonable assurance on the information system reliability and integrity. | Include in the Operations Manual the standards and procedures for: (i) the handling, conservation and control of inventory; and (ii) the periodic implementation of reconciliations between physical inventories and accounting records by personal independent of the handling and recording of goods. | 30 June 2012 |
| Internal Audit (Internal Control) does not participate in the planning and observation of the verification. | Include in the Operations Manual the Standards and Procedures for: (i) the handling, conservation and control of inventory; and (ii) the periodic implementation of reconciliations between physical inventories and accounting records by personal independent of the handling and recording of goods. | 30 June 2012 |
| There is no insurance plan to protect the goods in general. | Consider an insurance plan for the protection of all goods. | 30 June 2012 |
| There is no general maintenance plan for the acquired works and goods. | Prepare maintenance plans in agreement with the needs determined by the type of fixed asset and generate reports for the records. | 30 June 2012 |
| There is no coding system to identify the fixed assets. | Incorporate in the procedures aspects related with: (i) physical count of the inventory; (ii) registration and movement of fixed assets; (iii) officially assign to each employee the goods under their responsibility; and (iv) physically and financially identify the assets by means of appropriate codes. | 30 June 2012 |

Frequency of procurement supervision

In addition to prior reviews, the Bank will conduct post reviews of procurement. The frequency of post reviews and the thresholds established for the prior review of contracts are consistent with the assessment made of the executing agency’s capacity. These thresholds and the frequency of post reviews may be adjusted in the process of updating and revising the procurement plan, depending on the performance of the executing agency and the progress made in adopting the corrective measures described above.

Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms:  QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.

Appendix 2

Capacity of the executing agency and supervision of procurement by the Bank

Assessment of the executing agency’s capacity to administer procurement

Program Management Unit of the Program for Improved Basic Education will be responsible for carrying out project procurements. Having assessed the capacity of the executing agency [or a representative sample thereof if there are several] to carry out the procurement actions, the Bank rates the overall risk to the project arising from the administration of procurement as:

Goods >US$25,000 (equivalent) High  Works >US$50,000 (equivalent) HighNon-consulting Services >US$50,000 (equivalent)Low (X)Consulting Firms >US$25,000 (equivalent) Medium

Significant deficiencies identified and corrective actions agreed upon are summarized below:

DeficienciesCorrective actionCompletion dateFormal assignment of functions and responsibilities for procurement processes not documented in operations manual.Assignment of functions and responsibilities need to be documented and included in operations manual.

30 June 2012Formal assignment of functions and responsibilities for processes relating to the receipt, inventory, and maintenance of works, goods and consulting services not documented in operation manual.Assignment of functions and responsibilities need to be documented and included in operations manual.

30 June 2012The procurement procedures do not define a separation of incompatible functions that allow for clearly differentiation of personnel's attributions in each one of the different phases of the process.To include as part of the Operations Manual the standards and procedures relative to: (i) the levels of procurement, authorization levels, amounts, complexity and source of resources; and (ii) the application, authorization, start of the process and execution of the procurement and contracting for different officials.30 June 2012The system of procurement administration does not allow to identify the commitments and all other transactions from the beginning of the process, and establishes a link among the creation of the obligation, the receipt of the goods, works, and consulting services, and the corresponding payments, thus providing a reasonable assurance on the information system reliability and integrity.Include in the Operations Manual the standards and procedures for: (i) the handling, conservation and control of inventory; and (ii) the periodic implementation of reconciliations between physical inventories and accounting records by personal independent of the handling and recording of goods. 30 June 2012Internal Audit (Internal Control) does not participate in the planning and observation of the verification.Include in the Operations Manual the Standards and Procedures for: (i) the handling, conservation and control of inventory; and (ii) the periodic implementation of reconciliations between physical inventories and accounting records by personal independent of the handling and recording of goods.30 June 2012There is no insurance plan to protect the goods in general.Consider an insurance plan for the protection of all goods.30 June 2012There is no general maintenance plan for the acquired works and goods.Prepare maintenance plans in agreement with the needs determined by the type of fixed asset and generate reports for the records.30 June 2012There is no coding system to identify the fixed assets.Incorporate in the procedures aspects related with: (i) physical count of the inventory; (ii) registration and movement of fixed assets; (iii) officially assign to each employee the goods under their responsibility; and (iv) physically and financially identify the assets by means of appropriate codes. 30 June 2012

Frequency of procurement supervision

In addition to prior reviews, the Bank will conduct post reviews of procurement. The frequency of post reviews and the thresholds established for the prior review of contracts are consistent with the assessment made of the executing agency’s capacity. These thresholds and the frequency of post reviews may be adjusted in the process of updating and revising the procurement plan, depending on the performance of the executing agency and the progress made in adopting the corrective measures described above.

The first 18 months of project execution are counted from the date of publication of the general procurement notice, or the first specific procurement notice published following approval of the loan, whichever is earlier.

Available at www.iadb.org/procurement.