Technical Cooperation Profile

13 de julio de 2009

- Basic Project Data

| Country: | Regional: Colombia, Chile, Uruguay, Peru, Paraguay and Haiti |  |  |
| --- | --- | --- | --- |
| Project name: | ICT Impact on Education, Knowledge and indicators in Latin America |  |  |
| Project number: | RG-T1709 |  |  |
| Trust fund: | Knowledge Partnership Korea Fund for Technology and Innovation (KPK) |  |  |
| Project team: | Eugenio Severin (SCL/EDU), Team Leader; Carla Jimenez, Ana Santiago and Claudia Cox (SCL/EDU); and Geronimo Frigerio (LEG/SGO) |  |  |
| Date of request: | N/A |  |  |
| Beneficiary: | Latin America and the Caribbean (LAC) Region |  |  |
| Executing agency: | Bank through Education Division (SCL/EDU) |  |  |
| Financing plan: | IDB (KPK): Other contributions: Total: | US$390,000 US$552,000 US$942,000 |  |
| Technical and basic responsibility: | Education Division (SCL/EDU) |  |  |
| Execution timetable: | Disbursement period: |  | 24 months |
|  | Execution period: |  | 24 months |

- Background and Problem Statement

  - One of the main challenges in the use of Information and Communication Technology (ICT) in education is the lack of indicators that offer clear criteria and objective information to allow policy-makers to make the proper decisions on how and why to fund ICT and education related initiatives. Projects have not always considered rigorous evaluation processes and in those instances where they have, ICT impact on learning has not been the focus. Lastly, the project offering is so vast that there is no common framework that can be both flexible and broad enough that would include the diverse nature and contexts where projects are carried out.

  - In cooperation with the Organization for Economic Cooperation and Development (OECD) Centre for Educational Research and Innovation (CERI), Korean Education and Research Information Service (KERIS), World Bank (WB), United Nations Educational Scientific and Cultural Organization (UNESCO) (Paris office, Bangkok, and UIS- UNESCO Institute for Statistics) and Economic Commission for Latin America and the Caribbean (ECLAC), the IDB is currently carrying out research on measuring ICT performance and effectiveness in education, specifically in one-to-one computing initiatives in the region. The IDB has the opportunity to provide LAC countries with a knowledge product that will serve as a framework in the design of ICT for education, and specially, one-to-one computing programs that are aimed at improving educational processes.

  - IDBs compromise with education. Education is a right and a requirement for the equal generation of opportunities. Despite the progress that Latin American and Caribbean countries have achieved in expanding educational coverage, challenges associated with quality and equity still persist.

  - Narrowing the digital divide. The Bank’s goal in the area of ICT and education is to promote equitable access and use of the ICT to improve education and narrow the digital divide. One of the Bank’s key priorities in the area of ICT in education is to provide key elements in terms of access and use.

  - Improving learning through innovation and the use of ICT. The Bank favors initiatives that provide relevant and innovative content for strengthening skill and capacity development through the use of ICT.

- Program Objective and Description

  - The overall objective of this Technical Cooperation (TC) is to provide LAC countries with knowledge products that will serve as a framework in the design, implementation and evaluation of ICT for education projects that are aimed at improving educational processes and a set of indicators for monitoring and evaluation.

  - Component 1. Research

  - This component seeks to finance research on the effectiveness of ICT in education in LAC region, specifically one-to-one computing initiatives. In order to ensure that the information to be generated is comparable to other efforts conducted at the international level by the OECD, KERIS, WB, UNESCO and ECLAC. This study will be conducted within the parameters already established by IDBs’ “General Assessment Framework”, prepared in conjunction with these organizations. The main emphasis will be on students’ learning.

  - Component 2. Dissemination of knowledge products

  - Roundtables on education and the use of ICT. This component will finance different events that will: (i) review the research evidence about the cost-effectiveness of one-to-one computing, the effects on teaching and learning processes, and on educational performance, as well as the wider benefits (local providers, families, communities); (ii) identify the knowledge gaps and suggest opportunities for further research; (iii) discuss the lessons learnt and eventual policy implications; and (iv) provide opportunities for peer-learning among countries and partner institutions.

  - Publication and distribution. A publication will compile the best practices, this publication will include the IDBs’ proposed General Assessment Framework, research reports with best practices from the region and partner institutions on the impact of ICT and education, specifically one-to-one computing assessment and indicators. It is expected that it will provide significant added value to the current knowledge gap, on the topic.

- Budget

  - The total cost of the proposed TC is US$942,000. The operation will be partially financed with resources from the Knowledge Partnership Korea Fund for Technology and Innovation (KPK) for up to US$390,000. Additional contributions, both in-kind and cash, are estimated for a value of U$552,000.

| Table VI-1 Detailed cost US$ |  |  |  |
| --- | --- | --- | --- |
| Description | KPK | Other contributions | Total |
| Component 1. Research | 180,000.00 | 542,000.00 | 722,000.00 |
| Research experts (framework, indicators and evaluation) | 60,000.00 | - | 30,000.00 |
| Korean Case Study | 20,000.00 | - | 20,000.00 |
| Speakers fee +event participation | - | 10,000.00 | 10,000.00 |
| Evaluations |  |  |  |
| Peru | 25,000.00 | 250,000.00 | 275,000.00 |
| Haiti | - | 200,000.00 | 200,000.00 |
| Colombia | - | 32,000.00 | 32,000.00 |
| Paraguay | 25,000.00 | 25,000.00 | 50,000.00 |
| Uruguay | 50,000.00 | 25,000.00 | 75,000.00 |
| Component 2. Dissemination of knowledge products | 210,000.00 | 10,000.00 | 220,000.00 |
| 15 participants travel + accommodation | 52,500.00 | - | 52,500.00 |
| Senior speaker participation + participation | 22,500.00 | 5,000.00 | 27,500.00 |
| Regional conferences |  |  |  |
| Speaker participation | 20,000.00 | - | 20,000.00 |
| 7 Countries Conference hosting and publications (Colombia, Chile, Brazil, Uruguay, Peru, Paraguay and Haiti) | 90,000.00 | - | 60,000.00 |
| Publication and distribution of the Report |  |  |  |
| Editing and coordination | - | 5,000.00 | 5,000.00 |
| Translation | 5,000.00 | 0.00 | 5,000.00 |
| Publication | 10,000.00 | 0.00 | 10,000.00 |
| Distribution | 10,000.00 | 0.00 | 10,000.00 |
| Total | 390,000.00 | 552,000.00 | 942,000.00 |

- Executing Agency and Execution Structure

- A.	Executing agency

  - This operation will be executed by the Bank through SCL/EDU. The Bank will be responsible for all aspects of project management, including the administration of resources and the contracting of specialized consulting services in accordance with IDB Policies for the Contracting of Consultant Services (GN-2350-7).

  - The execution period will be 24 months and the disbursement period will be 24 months.

  - Technical responsibility: SCL/EDU will have the technical responsibility.

  - Responsibility for disbursements: SCL/EDU will have the disbursement responsibility.

- Major Issues

  - This TC will support the participation of IDB Education Department in OECD international research on ICT and their impact on education.

  - The activities included in this operation have been identified by SCL/EDU as key learning opportunities for the Bank to sharpen its knowledge of how programs on ICT in education act as important policy levers to improve the quality of learning. In no case does a previous evaluation exist, and in all cases, the respective counterparts have given their full support to working with the Bank in undertaking rigorous evaluations and using results to form policy recommendations for how best to design and implement ICT programs.

- Action Plan

  - EDU will keep working in collaboration with its partner organizations on the general conceptual framework and indicators presenting it in Seoul, Korea in July, 2009.

- Environmental and Social Strategy

  - The project was reviewed by the Environmental and Social Impact Review (ESR) on June 22, 2009. No negative environmental or social effects were identified and the TC has been classified as a “C” according to the Safeguard Classification Tool.

- (ORIGINAL FIRMADO)

- Approval: __________________________

- Marcelo Cabrol

- Chief SCL/EDU