# LOAN CONTRACT No. BH-L-1027

BAHAMAS AIR TRANSPORT REFORM PROGRAMME

# Procurement Plan

Period January 2012 to June 2013

# SUBMITTED: January 12th, 2012

**Period included in this Procurement Plan: From January 2011 to June 2012**

| **Ref. No.** | **Description and type**  **Of the procurement contract** | **Aggregate/Estimated Contract Cost (US$)** | **Procurement Method** | **Review (ex-ante**  **or**  **ex-post)** | **Source of financing**  **and percentage** | | **Pre-qualification**  **(Yes/No)** | **Estimated dates** | | | **Status (pending, in process, awarded, cancelled)** | **Comments** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **IDB**  **%** | **Local/ Other**  **%** | **Publication of specific procurement notice** | | **Completion of contract** |
| ***icao specification code***: 44-05-000 BHA/10/701 PR 21100905 | **GOODS**  **Component 1:**  **Air Traffic Control Equipment for Lynden Pindling International Airport** | $9,028,000 | ICB | Ex- Ante | 100 |  | No | | 12 Dec. 2011 |  | In process | Purchase, installation and commissioning of a new radar system for LPIA. |
| Lot 1 | Walk Thru Metal Detector |  | ICB | Ex-Ante | 100 |  | No | | January 2012 | July 2012 | Pending | Purchase, installation and commissioning of Walk Thru Metal Detectors at Bimini; San Salvador; and Moss Town, Exuma |
| Lot 2 | X-Ray Machine |  | ICB | Ex –Ante | 100 |  | No | | January 2012 | July 2012 | Pending | Purchase, installation and commissioning of Explosive Detector Machines at Bimini; San Salvador; and Moss Town, Exuma |
| Lot 3 | Explosive Trace Detector machine |  | ICB | Ex –Ante | 100 |  | No | January 2012 | | July 2012 | Pending | Purchase, installation and commissioning of Explosive Detector Machines at Bimini; San Salvador; North Eleuthera and Governor’s Harbour, Eleuthera; and Moss Town, Exuma |
| Lot 4 | Hand Held Metal Detector |  | ICB | Ex –Ante | 100 |  | No | January 2012 | | July 2012 | Pending | Purchase, installation and commissioning of Explosive Detector Machines at Bimini; San Salvador; North Eleuthera; and Moss Town, Exuma |
| Lot 5 | Hold Baggage X-Ray Machine |  | ICB | Ex –Ante | 100 |  | No | | January 2012 | July 2012 | Pending | Purchase, installation and commissioning of Explosive Detector Machines at Moss Town, Exuma |
|  | Project Coordinator for Project Executing Unit |  | NICQ |  |  | 100% | No | January 2012 | | July 2013 |  | Project Coordinator required to supervise the works, goods, and services for the Bahamas Air Transport Reform Programme |
|  | Procurement Officer for Project Executing Unit |  | NICQ |  |  | 100% | No | January 2012 | | July 2013 |  | Assist the Project Coordinator in the procurement of works, goods and services under the IDB Loan |
|  | Consultancy for Preparation of Environment, Health and Safety and Emergency Preparedness Guidelines for Airports in the Bahamas |  | ICB | Ex -Ante | 100 |  | No | March 2012 | | June 2013 | Pending | Consultant required to prepare the Guidelines for Environment Standards, Health and Safety Regulations and Emergency Preparedness Plans for Airports in the Bahamas |
|  | Consultancy for  Preparation of Hazardous Cargo Management procedures for Airports in the Bahamas |  | ICB | Ex-Ante | 100 |  | No | March 2012 | | June 2013 | Pending | Consultant required to prepare the Procedures for Hazardous Cargo Management for Airports in the Bahamas |
|  | Consultancy for Preparation of Energy and Water Use and Conservations Standards for Airports in the Bahamas |  | ICB | Ex-Ante | 100 |  | No | March 2012 | | June 2013 | Pending | Consultant required to prepare the Standards for Energy and Water Use and Conservation for Airports in the Bahams |
|  | Consultancy for Preparation of a Comprehensive Strategy for Family Island Airports Optimization |  | ICB | Ex-Ante | 100 |  | No | March 2012 | | June 2013 | Pending | Consultant required to prepare a Comprehensive Strategy for Family Island Airports Optimization |
|  | Consultancy – External Auditor |  | NICQ | Ex-Ante |  | 100 | No | March 2012 | | June 2013 | Pending | Consultant to audit financial transactions under the terms of the loan agreement. |

**Goods and Works:** ICB: International Competitive Bidding; LIB: Limited International Bidding; NCB: National Competitive Bidding; PC: Price Comparison; DC: Direct Contracting; FA: force account; PSA: Procurement through Specialized Agencies; PA: Procurement Agents; IA: Inspection Agents; PLFI: Procurement in Loans to Financial Intermediaries; BOO/BOT/BOOT: Build, Own, Operate/Build, Operate, Transfer/Build, Own, Operate, Transfer; PBP: Performance-Based Procurement; PLGB: Procurement under Loans Guaranteed by the Bank; CPP: Community participation procurement. **Consulting Firms:** QCBS: Quality-and Cost-Based Selection QBS: Quality-Based Selection FBS: Selection under a Fixed Budget; LCS: Least-Cost Selection; CQS: Selection based on the Consultants’ Qualifications; SSS: Single-Source Selection. **Individual Consultants:** NICQ: National Individual Consultant selection based on Qualifications; IICC: International Individual Consultant selection based on Qualifications.