## Sheet1
PROCUREMENT PLAN FOR BANK EXECUTED OPERATIONS
Country: Brazil |  |  | Executing agency: IDB | [9 empty] | UDR: CBR
Project number:BR-T1412 |  | Title of Project: FINEP Clima: Fostering Climate Technology and Innovation to Deliver Brazil’s NDCs
Period covered by the plan: 24 months |  |  |  |  | Total Project Amount US($): 1,000,000
Component | Procurement Type | Service type | Description (4) | Estimated contract cost (US$) | Selection Method (2) | Type of contract | Source of financing and percentage |  |  |  | Estimated date of the procurement notice | Estimated contract start date | Comments
[7 empty] | IDB/MIF |  | Other External Donor
[7 empty] | Amount | % | Amount | % |  |  |  | Direct Contracting
Select comp | Select Proc. Type | Goods Included in Firm Cons. RFP | Consultant 1: brief description |  | select method | Select Cont. Type |  |  |  |  | 2016-03-01 |  |  | International Competitive Bidding
Component 1 | A. Consulting services: | Firm Consultant (GN-2765) | Analyzing climate technologies: this analysis will be based on the main Brazilian policies and guidelines, especially in MCTIC’s publication about mitigation alternatives to reduce greenhouse gas emissions in strategic sectors , as well as the under construction TNA, and national and international studies related to climate change. The analysis should identify the priority technologies and innovations to be supported by Finep. | 80000 | SC <= $100K | Lump Sum | 80000 | 100 |  |  | 2019-08-02 | 2019-09-02 |  | National Competitive Bidding
Component 1 | A. Consulting services: | Firm Consultant (GN-2765) | Assessment of Finep’s portfolio: by financing instrument (grants and loans), including impact and outcomes (e.g. deployed technologies, GHG reduction). This analysis will be carried out by the Unicamp Development Foundation – Funcamp, which has analyzed Finep’s wider portfolio and developed an assessment methodology to measure its impacts, thus Funcamp can provide valuable inputs. The selected firm will be hired directly as it presents indispensable knowledge to carry out this analysis, consistent with that indicated in OP-1155-4. | 100000 | SSS | Lump Sum | 100000 | 100 |  |  | 2019-08-03 | 2019-10-02
Component 2 | A. Consulting services: | Individual Consultant (AM-650) | Tailored climate mission-oriented policy: evaluation of Finep’s financing and investment model, considering its strengths and weaknesses, to propose a mission-oriented structure for its climate program. It will apply the eight practical steps for creating a mission-oriented organization and this should not only be limited to this specific program, but also be used by the organization as a whole to direct innovation towards solving climate challenges in Brazil. | 100000 | IICQ | Lump Sum | 100000 | 100 |  |  | 2019-12-01 | 2020-03-31 |  | Shopping
Component 2 | A. Consulting services: | Firm Consultant (GN-2765) | Measurement, Reporting and Verification (MRV): MRV Methodology that allows Finep to assess the results and impacts of its financial instruments and to prioritize its pipeline. The MRV will use sustainability criteria such as potential of greenhouse gas mitigation of proposed innovation projects supported by Finep to direct programs and financing to low-carbon activities. | 100000 | SC > $100K and <= $250K | Lump Sum | 100000 | 100 |  |  | 2019-11-01 | 2019-12-01 |  | Least-Cost Selection
Component 2 | A. Consulting services: | Individual Consultant (AM-650) | Design of financial instruments: reorientation of existing mechanisms towards climate innovation to produce attractive conditions for companies investing in climate solutions; this could be lower rates, extended payment deadlines or greater participation from Finep. This will allow Finep to catalyze private investments. | 100000 | IICQ | Lump Sum | 100000 | 100 |  |  | 2020-02-01 | 2020-03-01
Component 2 | A. Consulting services: | Individual Consultant (AM-650) | (i) Building internal and external capacity – design of a capacity building plan for Finep staff aligned with priority areas and delivery of training sessions to support the execution, monitoring and evaluation of climate innovation projects. This will also include targeted sessions with external partners and clients. (ii) Defining a climate portfolio strategy – compilation and systematization of the findings of the previous activities to serve as the guiding action plan for implementation of the Phase 2 of the Innovation for Growth Project. The definition of the missions based on the analysis from Component 1 to be used as reference for strategic actions to promote innovation and expand Finep’s climate portfolio. (iii)Call for bids – design of a call for bids on climate innovation (non-reimbursable call for science and technology institutions, non-reimbursable call for companies or investment call for startups), according to the availability of Finep’s budget and aligned with the climate portfolio strategy. This will take into consideration Green Procurement Criteria to ensure that goods and services to be contracted also promote environmentally sustainable actions. | 220000 | IICQ | Lump Sum | 220000 | 100 |  |  | 2019-11-01 | 2019-12-01
Component 3 | A. Consulting services: | Firm Consultant (GN-2765) | Organizing workshops: stakeholder meetings and consultations to validate findings and recommendations resulting of activities of components 1 and 2. | 50000 | SC <= $100K | Lump Sum | 50000 | 100 |  |  | 2019-10-01 | 2020-01-01
Prepared by: Barbara Brakarz |  |  | Total | 750000 |  |  | 750000
(1) Grouping together of similar procurement is recommended, such as publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection. Selection process to be done in accordance with AM-650.
(2) Consulting firms: Per GN-2765-1, Consulting Firm selection methods for Bank-executed Operations are: Single Source Selection (SSS); Simplified Competitive <= 100K (SC <=100K); Simplified Competitive >100K and <=250K (SC >100K and <=250K); Fully Competitive >250K and Framework Agreement Task Order (FWTO). All Consulting Firm selection processes under this policy must use the electronic module in Convergence.
(2) Goods: Per GN-2765-1, par. A.2.2.c: "The procurement of goods and related services, except when such goods and related services are necessary to achieve the objectives of the Bank-executed Operational Work and are included in the consulting services contract and represent less than ten percent (10%) of the consulting services contract value."
Table for Data Validation
Select comp | Select Proc. Type | select Service type
Component 1 | A. Consulting services: | Individual Consultant (AM-650) | description | amount | select method | Select Cont. Type
Component 2 | B. Goods (2) | Firm Consultant (GN-2765) |  |  | SSS | Lump Sum
Component 3 | C. Non consulting services | Goods Included in Firm Cons. RFP |  |  | IICQ | Framework
Component 4 |  | Corp. Procurement (GN-2303) |  |  | SC <= $100K
Component 5 |  |  |  |  | SC > $100K and <= $250K
FC > $250K
FWTO