# Agreed TRIGGERS FOR THIRD OPERATION vs. triggers AS stated in Loan Proposal for first PBL

| Objective | Triggers for third operation as stated in Loan Proposal for first PBL | Agreed revised triggers for third operation | Comments |
| --- | --- | --- | --- |
| I. Macroeconomic Sustainability |  |  |  |
| To support and facilitate the implementation of the Program. | Maintenance of an appropriate macroeconomic policy framework. | Maintenance of an appropriate macroeconomic policy framework | No Change |
| II. Competitiveness Implementation Framework |  |  |  |
| To promote a sustainable forum for public-private dialogue to improve competitiveness. | Forum holding regular meetings | Partnerships for Jamaica Agreement Signed between Private Sector, Government, Opposition and Labour. Forum holding regular meetings. | Additional outcome since the Agreement was signed after many years of discussion. |
|  | The priority activities for the second year of the Competitiveness Agenda have been carried out. | The priority activities for the second year of the Competitiveness Agenda have been carried out. . | No Change |
|  | . | Monitoring and coordination mechanisms have been set in place and the Secretariat is monitoring the Forum Agenda and the NCC. | New trigger developed during preparation of second operation |
|  |  | Partnerships for Jamaica agreement signed by Government, Private Sector, Trade Unions and Civil Society | New trigger developed during preparation of second operation |
| III. Tax Reform |  |  |  |
| - Reduce distortions in the current tax systems. | Satisfactory progress in implementing legislative initiatives to reduce distortions in tax system, including but not limited to: - Reform of Stamp Duties and CIT rationalization - Rationalization of Labour Taxes. | Satisfactory progress in implementing legislative initiatives to reduce distortions in tax system, including but not limited to: - Corporate Income Tax (CIT) rationalization - Amalgamation of Labor Taxes | The first harmonization of CIT and PIT and the full harmonization of labor taxes were part of a broader tax policy reform included in JA-L1032. CIT and PIT were harmonized at 25% for non regulated companies in February 2013. |
|  | Tax policy modeling being utilized. | Tax policy modeling being utilized | No Change |
|  | . | - Preparation and dissemination of Tax Expenditure Report 2009 (2013) | New Trigger developed during preparation of second operation |
|  |  | - New methodology for collection of income tax information approved | Revised trigger developed during preparation of third operation |
| - Simplification of tax administration. | Remaining tax collection simplification benchmarks achieved. . | Remaining tax collection simplification benchmarks achieved, including but not limited to: - Adjustments in the implementation of Electronic Drop Box to pick up official receipts. - Operation of E-Payment Kiosks. - Broadening of the application of the Third Party Collection Project - Risk Analysis of the Forensic Data Mining Intelligence in operation. | The activities are part of the Action Plan submitted in compliance with the conditions for the first operation. |
| IV. Reduction in Budgetary Burden of State Owned Enterprises |  |  |  |
| Expenditure Rationalization. | Elimination of government budget support for at least one state-controlled enterprise | Elimination of government budget support for at least one state-controlled enterprise | No change. |
|  |  | Cabinet approval for institutional framework for PPPs | New trigger developed in the third operation. |
| V. Improving Access to Finance and Financial Market Development |  |  |  |
| - Reform of the secured transactions framework. | - Remaining secured transactions benchmarks achieved, in building consensus on legislative reforms to enable secured transactions framework and creation of central registry of pledged assets. . | Remaining secured transactions benchmarks achieved, in building consensus on legislative reforms to enable secured transactions framework and creation of central registry of pledged assets, including but not limited to: - Issuance of drafting drafting instructions approved by Cabinet - Consultation with stakeholders - Security Interests in Personal Property Bill Enacted - Awareness Campaign launched - Insolvency Bill Tabled in Parliament. | Additional detail as part of the process of consultation that has initiated the preparation of the law. |
| - Creation of Credit Bureaus. | - Remaining benchmarks achieved for a fully functioning framework for the regulation and supervision of credit bureaus. | Remaining benchmarks achieved for a fully functioning framework for the regulation and supervision of credit bureaus, including but not limited to: - Credit Reporting Bill enacted. - Regulations on Credit Reporting. - Bank of Jamaica has implemented the Action Plan for supervision of Credit Bureaus. - Two licenses for Credit Reporting Operations awarded. - One Credit Bureau operating. - Awareness Campaign launched. | More detail on the nature of the benchmark included. |
| - Facilitating Electronic Transactions | Remaining benchmarks achieved for full implementation of legal, regulatory and institutional framework for use of mobile devices for financial transactions. | Benchmarks achieved for full implementation of legal, regulatory and institutional framework for use of mobile devices for financial transactions, including but not limited to: - Consultation with stakeholders - Elaboration of appropriate Policy Framework - Initiation on the Implementation of pilot project for provision of payments to PATH beneficiaries through m-banking. - Assessment of regulations for addressing money laundering issues in m-banking completed. - Guidelines for Electronic Payment of Retail Services , including provisions for anti-money laundering regarding mobile services in effect. | These initiatives are elements of the MoF&PS Action Plan submitted in compliance with the conditions for the second operation. For the third operation, issuance of the Guidelines for Electronic Payment of Retail Services Regulations was included.. |
|  | National Payment System in effect. | National Payment System in effect. | No Change |
|  | E-payment Regulations in effect. | E-payment Regulations in effect | No Change |
| - Facilitating credit to SMEs (new) |  | White Paper Policy on MSME approved by Cabinet Legislation for recognition fo Registration Form enacted.. | Additional trigger included as part of the updated third operation. |
| VI. Reduction of business costs through expedited land titling |  |  |  |
| Strengthening land property rights. | Remaining land property rights benchmarks achieved, including but not limited to: - Actions for reducing registration and land titling costs - Reductions in fees, commissions and duties for land transactions by 5% | Remaining land property rights benchmarks achieved, including but not limited to: - Actions for reducing registration and land titling costs - Reductions in fees, commissions and duties for land transactions by 5% compared to 2008 baseline - PPP for implementation of LAMP II in place. | - Clarification of the base year for comparison - PPP for LAMP II implementation was initiated after Board approval of first PBL. |