REGIONAL

UPDATE OF THE SUSTAINABLE ENERGY RATING DATABASE WITH UTILITY-LEVEL INFORMATION AND DATA VISUALIZATION

TERMS OF REFERENCE

- Background

  - The Inter-American Development Bank (IDB) aims to support the Regulation and Governance process for the energy sectors in Latin America and the Caribbean (LAC) countries, in order to promote communication, exchange of information and best practices among regulators, policymakers and various stakeholders of the bank.

  - In LAC countries, information harmonization between countries will demand an extra effort. There is an enormous heterogeneity among the countries, some of which are starting to develop a regulatory body and to standardize the governance process, while others (as Chile) has already around 20 years of experience. Moreover, it is not uncommon for countries with higher institutional capability to rely solely on their domestic experiences. The efforts of harmonization and dialogue between market design and regulation to promote markets integration has been quite limited.

  - The Sustainable Energy Rating (SER) database made a first attempt to depict the energy transition progress on a regional level. As a product of Energy Division (INE/ENE) to facilitate the information exchange and comparability among LAC countries, the first rounds of SER project encompass 110 indicators of 153 utilities in 24 countries of the region. The main variables include financial, technical and sustainability issues for all the generation, distribution, transmission and integrated utilities covered, and the data are gathered both through questionnaire and interview process.

  - The objective of this project is to complement the utility-level information gap across the region, building on the existing SER database of the bank, and to develop a solid methodology for data treatment as well as innovative ways for results presentation, for both internal bank staff and external audience, namely academics, regulatory counterparts, utilities and research institutes interested in related areas.

- Consultancy Objectives

  - The overall objective of this project is to improve the current SER database with more complete information for regional application and dissemination. The project shall cover the following countries: Argentina, Bahamas, Barbados, Belize, Bolivia, Brazil, Chile, Colombia, Costa Rica, Dominican Republic, Ecuador, El Salvador, Guatemala, Guyana, Honduras, Jamaica, Mexico, Nicaragua, Panama, Paraguay, Peru, Suriname, Trinidad and Tobago, Uruguay.

  - This project aims to harmonize the current available information in SER, integrate the information with the other databases of the division to increase the comparability between countries and utilities. It will help to provide a comprehensive and sound backup for operations and knowledge products.

  - Specifically, the consultancy should be able to fulfill the following objectives: (1) Diagnose of the current SER database with information gap and complete the database with solid methodology and efficient strategy; (2) Analysis of key factors contributing to the sustainability and performance of utilities; (3) Develop an interactive platform for benchmarking utility performance.

- main activities

  - The consulting firm should perform all the activities needed to achieve the objectives, including but not restricted to:

  - Activity 1: Diagnose of the current SER database with information gap and complete the database with solid methodology and efficient strategy. In the first part of the activity, the current SER database will be analyzed based on its completeness, quality of information, and the existing data structure. In the second part, strategies to complement the data gap should be identified and implemented. The final delivery of this activity should be a complete and harmonized database.

  - Activity 2: Analysis of key factors contributing to the sustainability and performance of utilities. The amount of data collected to create the SER index can be an impressive source of information and potential of statistical analysis. Nevertheless, to get sound results, the data must be aggregated and analyzed to produce insightful findings. Besides that, it is necessary to apply a statistical tool suitable to deal with qualitative data. This database includes information on gender, resilience measures, sustainability (environmental and financial data). The work will include, among other things, an analysis to understand the level of relations between the institutional variables and company’s traditional performances measures, such as EBITDA, work productivity, sales/revenue, Capex/Opex ratio.

  - Activity 3: Develop an interactive platform for benchmarking utility performance. The final objective is to build an interactive platform that allows the electric utilities of the region to see how they are positioned compared to the top performers. The benchmarking exercise will be based on the updated SER database, with possibility to update automatically.

- Reports

  - The consulting firm shall prepare the following reports and products for mutual agreement and Management Group acceptance, prior to payment:

  - Activity 1:

RA1. Work plan;

RA1 a. Diagnostic summary of data quality and missing information of the existing SER database

RA1 b. Strategy to complement the database and detailed methodology review

RA1 c. Potential new data structure to reorganize the information

RA1 d. Possibility for update automation and proposed strategies

RA1 e. Comparison of updated information and previous SER data based on summary statistics and documentation

RA1 f. Final database and documentation.

  - Activity 2:

RA2. Work plan;

RA2 a. Diagnostic summary of improved data quality and key factors

RA2 b. Methodology for building statistical models and results description

RA2 c. Regional and sub-regional results for the Latin American and Caribbean region

RA2 d. Country-level summary results and info-graphs

RA2 e. Detailed manual about the sources of information and potential limitation of the current database

RA2 f. Final report.

  - Activity 3:

RA3. Work plan;

RA3 a. Methodology for building statistical models and results description

RA3 b. Manual for key functions of the interactive platform

RA3 c. Final platform.

  - The work plans should contain the details of the development of each of the subsequent steps, the planning of the services and the description of the main criteria and premises to be used. This Work Plan should contain (at least) the following considerations:

i. Main actions to be developed per step including its criteria and premises;

ii. Individual chronograms per action that make up each activity;

iii. Human resources involved by action of each activity;

iv. Source and database to be used; and

v. Scope of Reports.

  - The final reports should contain a summary of all actions taken in the activities and a summary of the main conclusions. All material developed must be delivered, in two (2) copies and with all files opened and presented at a Technical Meeting to be held at headquarters.

- Schedule of payments

  - The total payment will be USD 70,000. Payment will be disbursed to the Consulting Firm based on the above reports once received or approved to the satisfaction of the Management Group as follows:

  - 5% after the presentation of each product list from RA1a to RA1e (25% in total);

  - 10% after the approval of RA1f.

  - 15% after the presentation of the final report.

  - 2% after the presentation and approval of each product listed from RA2a to RA2e (10%).

  - 15% after the approval of product RA2f.

  - 5% after the presentation and approval of each product listed from RA2a to RA23 (10%).

  - 15% after the approval of product RA2j.

- Coordination

  - The project will be managed by IDB (INE/ENE). The contracted consulting firm will coordinate the actions with the designated IDB’s technical team.

  - In representation of the IDB, the technical coordination for this assignment rests with Energy Specialist, Michelle Hallack, michellecar@iadb.org.

- Characteristics of the consultancy

  - The consultancy will be paid as a lump sum, which will include all the cost necessary for the implementation of the studies.

  - Starting date and duration: The main activities to be carried out under this TOR are expected to be completed in twenty-four (24) months after contract signature. The consulting firm will submit a detailed Work Plan, with staff activities, as a first Inception Report.

  - Place of work: No specific location is required for the nature of work of this project. The designated representatives of the consultancy will need to be travel to Washington DC, USA occasionally.

- Qualifications

  - A core team of at least four (4) members is here suggested:

  - General coordinator of the work, with professional training in economics with at least fifteen (15) years of professional experience in coordinating studies and economic assessment projects related to energy.

  - Two (2) technical Specialists in projects with professional training in data and statistics with hands-on experience in the execution of engineering projects.

  - One (1) Specialist proficient in interactive and graphic design, with experience on building web-based platforms.

Payment and Conditions: Compensation will be determined in accordance with Bank’s policies and procedures. In addition, candidates must be citizens of an IDB member country.

Consanguinity: Pursuant to applicable Bank policy, candidates with relatives (including the fourth degree of consanguinity and the second degree of affinity, including spouse) working for the Bank as staff members or Complementary Workforce contractuals, will not be eligible to provide services for the Bank.

Diversity: The Bank is committed to diversity and inclusion and to providing equal opportunities to all candidates. We embrace diversity on the basis of gender, age, education, national origin, ethnic origin, race, disability, sexual orientation, religion, and HIV/AIDs status. We encourage women, Afro-descendants and persons of indigenous origins to apply.