REGIONAL

SURVEY DESIGN AND DATA COLLECTION OF ENERGY CONSUMERS BEHAVIOR AND PUBLIC PERCEPTION OF INNOVATIVE TECHNOLOGIES

TERMS OF REFERENCE

- Background

  - The Inter-American Development Bank (IDB) will contract a firm to perform (i) a survey design consulting and (ii) a regional survey in, at least, 6 (six) countries of the Latin America and the Caribbean (LAC) region on energy consumption behavior and the willingness to adopt energy innovative technologies.

  - The main objective is to gather data on energy behavior and perception to clarify innovation concerning policy efficiency and policy framing in the LAC region, with focus on household consumption units. This survey can be latter used to identify the obstacles for the affordable adoption of new technologies by households and improve the policy quality.

  - The survey must gather data on four dimensions: (i) household conditions, including housing infrastructure, ownership, localization, income, energy expenditures and number of member; (ii) owned equipment, technologies, acquisition date and frequency of use, including cookstoves, showers, lightbulbs, refrigerators, cooling and heating devices and washing machine; (iii) energy perception and knowledge, including energy grid price, quality of supply (continuity and liability), cost of alternative energy installation, knowledge about innovative technologies, understanding about the bill information, and responsibility for cleaning the energy matrix; (iv) behavioral experiments, including lightbulb color, cost framing, neighborhood effect.

  - The project is financed by the Inter-American Development Bank Strategic Program for Infrastructure Development.

- Consultancy Objectives

  - The general objective of this survey consulting is to cooperate with the IDB in the survey design and to conduct the survey with the approved specifications in the approved countries.

  - The countries to be part of the survey proposal are the IDB’s borrowing member countries, which includes: Argentina, the Bahamas, Barbados, Belize, Brazil, Bolivia, Chile, Colombia, Costa Rica, the Dominican Republic, Ecuador, El Salvador, Guatemala, Guyana, Haiti, Honduras, Jamaica, Mexico Nicaragua, Panama, Paraguay, Peru, Suriname, Trinidad and Tobago, Uruguay and Venezuela.

  - The survey must include, at least, 6 (six) of the above countries, being 3 (three) countries necessarily located in the Central America and the Caribbean.

- main activities

  - The survey firm should perform all the activities needed to achieve the objectives, including but not restricted to:

  - Activity 1: Survey design consulting. The survey company should support the IDB with the design of the surveys and behavioral experiments. This cooperation includes, but is not restricted to, questionnaire design, mode of survey (on-site, by phone, on the streets, etc.), sample size and stratification and language-localized framing. This activity includes a limited-size trial of the survey with a report on the effectiveness of the questions and experiments.

  - Activity 2: Conduct regional survey. Conduct the survey as designed in Activity 1 and provide to the IDB the raw database in comma separated values format (CSV) or other Stata® readable file, aside with a variables dictionary, survey manual and a digital copy of the survey questionnaire.

- Reports

  - The survey consulting firm should provide to the IDB the following reports and products:

  - Survey Questionnaire: the consulting firm must deliver to the IDB’s approval the survey questionnaire before and after the survey trials. The IDB must approve (1) the questions and experiment framing, (2) the questionnaire layout and (3) the sample size of the size before the trials and the final conduction.

  - Survey Design Trials Report: the consulting firm must deliver to the IDB a report on the results of the trial of the survey questionnaire and experiments, including, but not restricted to, the interviewer perception, and re-framing or re-writing recommendations.

  - Dataset of the survey: the survey consulting firm must provide to the IDB the raw database in comma separated values format (CSV) or other Stata® readable file, aside with a manual report of variables dictionary and technical notes of the methodology

  - Presentation of the results: the survey consulting firm must present the survey results at the IDB Headquarters in Washington, DC, including the methodology for sampling and survey mode.

- Schedule of payments

  - Payment will be disbursed to the Consulting Firm based on the above reports once received or approved to the satisfaction of the IDB as follows:

- 20% after the signature of the contract;

- 20% after the trials survey questionnaire approval;

- 20% after the delivery of the survey trials report;

- 20% after the delivery the database of the survey and technical notes;

- 20% after the presentation of the results.

  - The consultancy firm should consider the maximum budget of US$110,000 in order to achieve the consultancy objectives

- Coordination

  - The technical responsibility will be in charge of INE/ENE. The survey consulting firm will coordinate the actions with the designated IDB’s technical team.

  - This project will be coordinated by the Energy Specialist, Michelle Hallack.

- Characteristics of the consultancy

  - The consultancy will be paid as a lump sum, which will include all the cost necessary for the implementation of the studies.

  - Starting date and duration: The main activities to be carried out under this TORs are expected to be completed in twelve (12) months after contract signature. The consulting firm will submit a detailed Work Plan, with staff activities.

  - Place of Work: The work is mainly to be done in the place of work of the Consulting Firm. Presentations and meetings will be held, preferentially, in the IDB’s Headquarters in Washington, DC.

- Qualifications

  - A core team of 2 (two) members is here suggested:

  - A Survey Team Leader with extensive experience in conducting surveys at household level in Latin America and the Caribbean region. The Survey Team Leader is going to be responsible to coordinate the survey technical team, to facilitate the communication between the consulting firm and the IDB, and to deliver the required report to the designated project coordinator. A possible background for this position includes solid formation in economics, statistics, psychology or related fields with at least 15 years of experience in survey planning.

  - A Technical Specialist experienced in survey design and behavioral experiments. The technical specialist is going to be responsible to consult the IDB with the survey design. A possible background for this position includes solid formation in economics, statistics, psychology or related fields with at least 5 years of experience in survey design.

  - If deemed necessary, and not exceeding the suggested budget for the consultancy, the survey consulting firm may propose additional staff as part of the team or may negotiate the option of combining the duties of one or more of the recommended positions

Payment and Conditions: Compensation will be determined in accordance with Bank’s policies and procedures. In addition, candidates must be citizens of an IDB member country.

Consanguinity: Pursuant to applicable Bank policy, candidates with relatives (including the fourth degree of consanguinity and the second degree of affinity, including spouse) working for the Bank as staff members or Complementary Workforce contractuals, will not be eligible to provide services for the Bank.

Diversity: The Bank is committed to diversity and inclusion and to providing equal opportunities to all candidates. We embrace diversity on the basis of gender, age, education, national origin, ethnic origin, race, disability, sexual orientation, religion, and HIV/AIDs status. We encourage women, Afro-descendants and persons of indigenous origins to apply.