## Procurement Plan 23 May 2018
Project Name : Second Basic Education Improvement Program Phase II
Project Number: 3603 OC-SU
Executing Agency: Ministry of Education, Science and Culture
23 May 2018
PROCUREMENT PLAN PERIOD: 23 May 2018 - 31 December 2020
WORKS
| Ref. # | Component | Description/Contract Name: | Procurement Method | Lots Quantity: | Baseline Document | Contract Type | Estimated Amount, in US$ : | Associated Component : (if applicable) | Review Method | Process Status | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency) | Comments
[12 empty] | Bidding Document |  | No objection to the Documents |  | Publication |  | Opening |  | Evaluation |  | No Objection to the Evaluation |  | Contract Signing |  | End of Contract
[12 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
1 | 1W | 2.3 | New Building for the Center for Continuing Education of Suriname (CENASU) | NCB | TBD | Procurement of works | Lump-Sum incl. Bill of Quantities | 900000 |  | Exante | Planned | 2018-06-04 |  | 2018-06-15 |  | 2018-06-18 |  | 2018-08-03 |  | 2018-08-24 |  | 2018-09-07 |  | 2018-10-09 |  | 2019-10-01 |  |  |  | The first delivery of the CENASU building is expected to be 90 days earlier before the estimated contract end date; The enddate of contract included the defects liability period of 3 mnd.
2 | 2W | 2.2 | Rehabilitation of existing schools, teachers housing and TRC's and the construction of new class rooms, media centers and teacher housing in the interior | ICB | TBD | Procurement of works | Lump-Sum incl. Bill of Quantities | 2800000 |  | Exante | Planned | 2019-01-28 |  | 2019-02-11 |  | 2019-02-14 |  | 2019-04-02 |  | 2019-04-20 |  | 2019-05-04 |  | 2019-06-09 |  | 2020-09-20 |  |  |  | The start depends on the execution of CIER. Also, the mapping of the schools. This contract might be splitted according to the conditions defined in the mapping of the schools. The enddate of contract is included the defects liability period of 3 mnd.
3700000
GOODS
| Ref. # | Component | Description/Contract Name: | Procurement Method | Lots Quantity: | Baseline Document | Contract Type | Estimated Amount, in u$s : | Associated Component: | Review Method | Process Status | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency) | Comments
[12 empty] | Bidding Document |  | No objection to the Documents |  | Publication |  | Opening |  | Evaluation |  | No Objection to the Evaluation |  | Contract Signing |  | End of Contract
[12 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
4 | 1G | 1.3 | Printing textbooks and learning materials for grade 1-8 | ICB | TBD | Procurement of goods | Lump-sum | 2525000 |  | Exante | Planned | 2018-07-02 |  | 2018-07-20 |  | 2018-07-24 |  | 2018-09-25 |  | 2018-10-26 |  | 2018-11-09 |  | 2018-12-09 |  | 2020-11-30
5 | 2G | 1.3 | Tactile material and training kits for BE STREAMING program | ICB | TBD | Procurement of goods | Lump-sum | 250000 |  | Exante | Planned | 2018-06-16 |  | 2018-06-26 |  | 2018-07-10 |  | 2018-08-24 |  | 2018-09-25 |  | 2018-10-05 |  | 2018-10-19 |  | 2019-03-18
9 | 9G | 1.2 | Supporting material for Curriculum Development and Guidance Department (speech therapy) of MOESC | Shopping | TBD | Procurement of goods | Lump-sum | 12500 |  | Exante | Planned | 2018-08-31 |  | 2018-09-10 |  | N/A |  | 2018-10-02 |  | 2018-10-19 |  | 2018-10-29 |  | 2018-11-12 |  | 2018-12-12
2787500
NON-CONSULTING SERVICES
| Ref. # | Component | Description/Contract Name: | Procurement Method | Lots Quantity: | Baseline Document | Contract Type | Estimated Amount, in u$s : | Associated Component: | Review Method | Process Status | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency) | Comments
[12 empty] | Bidding Document |  | No objection to the Documents |  | Publication |  | Opening |  | Evaluation |  | No Objection to the Evaluation |  | Contract Signing |  | End of Contract
[12 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
13 | 2NC | 3.1 | Implementation of ICT network improvement plan BEIP office and MOESC BEIP partners | NCB | 1 | Procurement of non consulting services | Lump-Sum | 240000 |  | Exante | Planned | 2018-09-03 |  | 2018-09-14 |  | 2018-09-26 |  | 2018-10-26 |  | 2018-11-20 |  | 2018-11-30 |  | 2018-12-12 |  | 2019-03-12
14 | 3NC | 3.1 | Implementation of Security for MOESC partners | NCB | 1 | Procurement of non consulting services | Lump-sum | 200000 |  | Exante | Planned | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
15 | 5NC | 1.3 | Photocopy training material for training of teachers, grade 1-8 | NCB | 1 | Procurement of non consulting services | Lump-sum | 75000 |  | Exante | Planned | 1139024 |  | 1139034 |  | 1139041 |  | 1139071 |  | 1139088 |  | 1139098 |  | 1139108 |  | 1139139
16 | 7NC | 4.1 | Teambuilding activity BEIP | Shopping | 1 | Request for Quotation | Lump-sum | 4000 |  | Exante | Planned | 2018-08-20 |  | 2018-09-03 |  | N/A |  | 2018-09-24 |  | 2018-10-15 |  | 2018-10-25 |  | 2018-11-04 |  | 2018-12-04
|  |  | Total |  |  |  |  | 519000
CONSULTING FIRMS
| Ref. # | Component | Description/Contract Name:65 | Procurement Method | Process Number: | Contract Type | Estimated Amount, in u$s : | Associated Component: | Review Method | Process Status | Dates (If it does not apply, use N/A) | [21 empty] | Short List Members | Technical Score Assigned | Evaluated Price Proposal (Currency ####) |  | Combined Score | Comments
[11 empty] | Publication of Expression of Interest Notice |  | RFP and Short List |  | No Objection to RFP and Short List |  | RFP Invitation |  | Opening |  | Technical Evaluation |  | No Objection to the Technical Evaluation |  | Final Evaluation and Negotiated Contract |  | No Objection to the negotiated draft Contract |  | Contract Signing |  | End of Contract
[11 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real |  |  |  | Real
17 | 2CF | 1.5 | Reform of lower secondary education | QCBS | TBD | Lump-Sum | 550000 |  | Exante | Planned | 2018-08-08 |  | 2018-08-24 |  | 2018-09-07 |  | 2018-09-11 |  | 2018-10-26 |  | 2018-11-28 |  | 2018-12-18 |  | 2019-01-16 |  | 2019-01-30 |  | 2019-02-13 |  | 2020-02-14
18 | 4CF | 2.2 | Engineering firm to design, tender and supervise the following: rehabilitation of existing schools, teacher housing and TRC's and the construction of new classrooms, media centers and teacher housing in the interior | QCBS | 1 | Lump-Sum | 300000 |  | Exante | Planned | 2018-05-30 |  | 2018-07-02 |  | 2018-07-16 |  | 2018-07-21 |  | 2018-08-13 |  | 2018-08-29 |  | 2018-09-16 |  | 2018-10-08 |  | 2018-09-08 |  | 2018-09-24 |  | 2020-09-23
850000
INDIVIDUAL CONSULTANTS
| Ref. # | Component | Description/Contract Name: | Procurement Method | Process Number: | Estimated Amount, in u$s : | Estimated Number of Consultants: | Associated Component: | Review Method | Process Status | Dates (If it does not apply, use N/A) | [5 empty] | Consultant's Name | Period |  | Title | Comments
[11 empty] | No Objection to the TORs |  | Hiring Deadline |  | End of Activity |  |  | From | Until
[11 empty] | Estimated | Real | Estimated | Real | Estimated | Real
24 | 6IC | 1.3.4 | Conduct a thorough needs assessment (strength and weaknesses) of the LPD Department (Distribution and production of learning material) to strenghten the Department | NICQ | 1 | 25000 | 1 |  | Exante | Planned | 2018-08-01 |  | 2018-09-30 |  | 2018-11-29
29 | 15IC | 1.2 | Task Officer for Training | NICQ | 1 | 42000 | 1 |  | Exante | Planned | 2018-06-21 |  | 2018-06-20 |  | 2019-03-17
|  |  | Total |  | 0 | 67000
TRAINING
| Ref. # | Component | Description/Contract Name: |  | Process Number: | Contract Type | Estimated Amount, in U$S : | Associated Component: | Review Method | Process Status | Dates (If it does not apply, use N/A) | [5 empty] | Detail | Amount (Currency ) | Comments
[11 empty] | Annual Training Plan (ATP) |  | No Objection to the ATP |  | End of Activity
[11 empty] | Estimated | Real | Estimated | Real | Estimated | Real
30 | IT |  | Implementation of the training plan of the management and support staff for the MOESC ( BMC, LPD, Research en Planning, BEIP office, strengthen CENASU etc). | TBD | TBD | Lump-sum | 120000 |  | Exante | Planned | 2018-07-18 |  | 2018-07-28 |  | 2019-07-27
Formulas:
Opening = +[Publication]+46
Opening = [Publication]+9*7
Evaluation = [Opening]+21
Evaluation = +[Opening]+18
No Objection to the Evaluation = +[Evaluation]+14
No Objection to the Evaluation = [Evaluation]+14
Contract Signing = +[No Objection to the Evaluation]+32
Contract Signing = +[No Objection to the Evaluation]+31+5
End of Contract = +[Contract Signing]+14+250+90+3
End of Contract = +[Contract Signing]+365+90+14
No objection to the Documents = +[Dates (If it does not apply, use N/A)]+14
No objection to the Documents = [Dates (If it does not apply, use N/A)]+18
Publication = +[No objection to the Documents]+3
Publication = [No objection to the Documents]+4
Real = +[Process Status]+16
Real = +[Real]+14
Proposal Price (Currency) = +[Real]+14