|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | **Results Statement** | **Indicator** | **Baseline Q1 2014\*** | **Target Q1 2015\*** | **Target Q1 2016\*** | **Data Source** |
| **Intermediate outcome** | Strengthened institutional capacities to implement and participate in activities to promote broadband access, adoption and usage in LAC | Number of public and private institutions strengthened | 1 | 4 | 5 | Lists of participants. |
| Number of participants who become tutors | 0 | 3 | 6 | High and technical-level official contacts with government. |
|  |  |  |  |  |  |  |
| **Immediate outcome** | Improved knowledge and skills among individuals involved in broadband access, adoption and usage promotion initiatives in LAC | Number of professionals successfully trained (receiving a certificate) | 30 | 120 | 150 | Examinations at the end of capacity-building events. |
| Share of women in total persons receiving a certificate (%) | 50 | 50 | 50 | Examinations at the end of capacity-building events. |
|  |  |  |  |  |  |  |
| **Output** | Training delivered to individuals involved in broadband access, adoption and usage promotion initiatives in LAC | Number of professionals who received training | 35 | 140 | 210 | Lists of participants. |
| Number of women who received training | 17 | 70 | 105 | Lists of participants. |
|  |  |  |  |  |  |  |
| **Activity 1** | Developing content on broadband | Number of new courses developed, old courses adjusted and/or translated | 1 | 2 | 2 | INT-INTAL-KNL Capacity-Building Program files. |
| **Activity 2** | Delivering online tutored courses on broadband | Number of online courses delivered. | 1 | 4 | 5 | INT-INTAL-KNL Capacity-Building Program files. |

\*Cumulative results