GUYANA

Primary Education Improvemenet Programme (PEIP)

(Loan 827/SF-GY)

PROJECT COMPLETION REPORT (PCR)

Minutes of the Management Review Committee (MRC)

March 19, 2003

# I.   PARTICIPANTS

1.1	The MRC was presided by Mr. Juan Manuel Fariña (SO3).  Participants included:  Messrs. Marco Nicola (CGY); Carlos Antola (COF/CGY); Rafael Hernandez (RE3); Arne Paulson (RE3); Kristyna Bishop (SO3); Gabriel Castillo (OD6); Adrienne Pratt (OD6); Sergio Campos (EN3); Amparo Omana (SO3); and Ms. Michelle Fryer (SO3), who acted as secretary.

II.   RECOMMENDATIONS

    - Consistent with RE3’s emphasis on results management, MRC requested that CGY revise the PCR to more fully capture project outcomes using the analysis of ex-post data to be collected in June 2003, and the validation of lessons learned during the upcoming project exit workshop.

    - RE3 requested that CGY assess whether any additional consultant resources, beyond those presently available to the country office, are required in order to comply with the recommendations of the MRC by August 2003.

III.   OBSERVATIONS

    - In addition to the above recommendations, the revised PCR should take into consideration oral and written comments received from the MRC, and:

- provide a more detailed description of the historical context of project execution and reprogramming, differentiating between the original project design (1989-1998) and the reprogrammed project design (1998 – 2003) in Section 1;

- review consistency in the documentation of project objectives and achievements, Section 2;

- include additional detail in the analysis of lessons learned from the assessment of :  project assumptions and design, institutional capacity / responsiveness (GOG, MOE, IDB), and the adequacy of basic assumptions, Section 4;

- link outcomes to Millennium Goals, where applicable;

- provide further explanation of enabling factors and obstacles to the achievement and sustainability of outcomes during the project, and over the long-term (i.e.,  project management, reprogramming, HIPC, teacher migration, wages, external decisions, etc.);

- clarify why CGY final ranking of the project differs from that in the PPMR;

- update tables and budgetary data.

(Original signed)					(Original signed)

_________________________________________________________________

Juan Manuel Fariña	     Michelle Fryer

Chief, RE3/SO3	MRCSecretary, RE3/SO3

Project Completion Report (PCR)

Part One

PROJECT NAME:  Primary Education Improvement Programme

PROJECT NUMBER:

LOAN AND TC NUMBER(S): 827/SF – GY

COUNTRY: Cooperative Republic of Guyana

EXECUTING AGENCY: Ministry of Education

SECTOR: Education - PRI

MODALITY: Investment – Specific project

DATE APPROVED: October /13 / /1989 DATE COMPLETED: April 2002

LOAN/TC AMOUNT(S): Loan: $46.4 millions TC: $520,000

FINAL PROJECT IMPLEMENTATION CLASSIFICATION (HS, S, U, VU): S

FINAL PROJECT ASSUMPTIONS CLASSIFICATION (H, L): H

FINAL DEVELOPMENT OBJECTIVES CLASSIFICATION (HP, P, LP, I): P

Prepared By

COF/CGY

I. PROJECT OBJECTIVES AND COMPONENTS

Based on the latest formally agreed-upon statement of project objectives and components (reflected in the most recent version of Annex A of the loan contract and related technical cooperation agreement, if any):

A. Succinctly present the project’s objectives.

The goal of the program was the improvement of Guyana’s primary education sub-sector.

B. Briefly describe the project’s components.

The Original PEIP 1990-1998

The programme comprised three major components as follows:

Component I, Human Resource Development, where the aim was to upgrade the skills of primary school teachers, administrators and supervisors and other staff members of institutions involved in the programme

Component II, Curriculum Development and Education Technology, where the objective was to support and expand activities of NCERD in order to strengthen its capacity, to revise and update curricular contents and methods, to implement the adoption of new curricula to increase the production of textbooks and other instructional materials, and to develop more efficient  teaching and  learning materials.

Component III, Physical Infrastructure and Equipment, through the construction of twenty seven (27) new schools, rehabilitating three (3) schools, provision of furniture to project schools, library books audio visual equipment and science laboratories and the strengthening the physical maintenance service for the system.

In the ninth year (1998), of what was originally a five-year programme, only 33% of the US $46.4 million in loan resources had been disbursed. A change in the design of the school building and in the arrangements for supervision of construction resulted in a saving of USD 23.4 million.

GOG therefore proposed that the funds be used to strengthen MOE’s management capabilities including its regional education entities, to take significant steps to promote quality improvement in the classroom to enhance the human resources available to the Ministry, and to continue a primary school building programme.

The PEIP Reformulated Programme 1998 - 2001

The reformulated programme remained within the objectives of the original project. It aimed at improving the quality of basic education in the classroom through the execution of the following components.

Component I, School Construction, which included:

The construction of 16 new primary schools and one new secondary school, and the rehabilitation of 28;

The design of a permanent ministerial maintenance capacity together with a maintenance survey and database;

A pilot programme incorporating important aspects of school based maintenance to serve as the basis for a greatly enhanced maintenance programme;

# Component II, Quality Improvement in the Classroom Environment,

Activities comprised:

- Learning Strategies Assessment.

- Strengthening NCERD’s testing measurement and assessment capacity.

- Enhancing teacher training for multi-grade classrooms.

- Strengthening regional resource centers’ capacity by training teachers in Reading and Mathematics instruction

- Generating greater parent and community participation in quality improvement efforts together with enhanced school-based management.

- Providing all primary schools with a core package of learning aids such as globes encyclopedias and classroom posters

- Developing distance teaching and information technology as tools for quality improvement through:

Component III, Strengthening the Institutional Capacity of MOE through

- Conducting an organizational assessment;

- Enhancing MOE’s capacity in strategic planning, personnel management

- Assisting with the establishment of an MIS system.

Component IV, Human Resource Development for Teachers and Administrators

- Enhancing the qualifications of Hinterland teachers;

- Providing opportunities for managerial and administrative upgrading in a variety of long and short-term training programme both in Guyana and overseas.

Component V, Strengthening the PIU and Monitoring and Evaluation of the Project

- Strengthening the PEIP Project Implementation Unit included:

- Employing additional staff plus a professional to deal with the several efforts to mobilize communities and schools in initiatives;

- Providing for a continuous monitoring presence to assist in expeditiously moving forward with the plan to work on a bi-monthly basis.

C. Briefly describe the main assumptions on which the successful implementation of project components is based, as well as the assumptions on which the overall achievement of project objectives is based.

There were six key assumptions for the implementations of project components:

- The local construction industry was going to adequately absorb the program works within the execution time.

- The education administrators and teachers in-service were going to be receptive to the training and had the basic academic background to fully benefit from it.

- The Central Tender Board System was going to facilitate the process for major procurement.

- The PIU, NCERD and CPCE were properly and competently staffed with well-remunerated professionals and technicians in the positions critical to project implementation.

- Recommendations made by the institutional strengthening consultants were going to be implemented by MOE.

- SIMS was going to be installed properly and effectively.

There were four assumptions related to the Development objectives:

- No changes in Government education policy.

- Government attains and sustains desired level of expenditure in education.

- Borrower/MOE is committed to ensuring that pilot initiatives in maintenance of school facilities and quality improvements in the classroom environment are sustained post-project.

- Conditions of service are attractive enough to retain teachers and administrators.

II. PROJECT RESULTS AND DEVELOPMENT OBJECTIVES

A. Based on Section I (A, B, C), succinctly describe:

1. The actual level of achievement of project components.

Component 1 - Improvement of the infrastructure of the educational system and the development of a sound maintenance system.

A problem found in schools during the design of Primary Education Improvement Project (PEIP), were their general neglected and overcrowded facilities and absence of textbooks. These were serious constraints, which were directly related to the low average attendance and performance. It was estimated that 56, 919 students (47% student enrolment population) were in schools, which needed to be replaced, or which were in need of major rehabilitation.

Under the program, the school system has benefited from improved and expanded physical services on a much larger scale than originally intended. 72 percent of Guyana’s primary cohort benefited from access to improved and expanded educational facilities.  Schools not built or renovated under the project also received furniture from the project.   Table 1 presents beneficiaries of the programmes across regions.

# Table 1 : Beneficiaries of the School Construction Component of PEIP

| Regions | Original PEIP Programme 1990-1998 |  | 1999-2001 |  |
| --- | --- | --- | --- | --- |
|  | No of Schools Built, Rehabilitated Extended | Beneficiaries | No of Schools Built, Rehabilitated Extended | Beneficiaries |
| 1 | 1 | 400 | 1 | 400 |
| 2 | 7 | 4800 | 4 | 1550 |
| 3 | 9 | 5600 | 7 | 2900 |
| 4 | 6 | 3200 | 19 | 12 300 |
| GT | 7 | 7600 | 10 | 7300 |
| 5 | 3 | 1800 | 3 | 1500 |
| 6 | 8 | 4400 | 9 | 5100 |
| 7 | 1 | 600 | - | - |
| 8 | 1 | 300 | - | - |
| 9 | - |  | 1 | 650 |
| 10 | 3 | 2400 | 1 | 1200 |
| Total | 46 | 30 100 | 55 | 32 900 |
| Grand Total : No of Schools: 101 No of Beneficiaries 63 000 |  |  |  |  |

Component 2 - Quality Improvements in the Classroom Environment.

The effort to improve the Classroom environment was directed to explore the elements of the Model School and then to pilot them.

Fifteen schools across the regions constructed and rehabilitated through PEIP were identified as Model Schools where innovative learning strategies were introduced and refined giving teachers the opportunity to master a number of strategies and develop appropriate instructional materials.

Teachers from each of these schools participated in child centered learning strategies and school based management workshop sessions to help them to acquire skills and techniques that would enhance their capability to inter alia,

- focus on child centered teaching learning approaches;

- create and establish supportive learning environment;

- use a variety of teaching aids;

- cater for individual differences;

- adopt a consensual approach to problem solving; and

- enlist  community members to play a significant  role in school improvement

An analysis of the response of 178 teachers from 12 of the 15 schools, indicates that  ‘Reinforcing Pupils Learning’ was perceived to be the most frequently used skill, while ‘Using a Variety of Learning Aids’ was the least practiced.

Chart 1 shows the mean rating of each category of practices recorded in Tables 2 to 2 (g), which has the mean rating of each practice.

#### Chart 1

An examination of the data in Tables 2 to 2 (e) that deal directly with child centred teaching learning strategy indicates that with the exception of two practices, teachers in the school are practicing most of these techniques they acquired. The mean value ranges from 2.73 for ‘Display of Pupils Efforts on the Wall’, to 3.53 for ‘Using Test Results to Reinforce Learning’ The highest responses are those related to pupil reinforcement practices, which is a good indication of teachers moving away from reinforcing undesirable pupil behaviour, and giving tests just for examination purposes.

For ‘Teachers Keep Attractive Classrooms’, some teachers felt that this was impossible where there are two classes in one classroom, where furniture is not suitable for the pupils’ age.

On the other hand there were some attractive classrooms with up to date teaching aids, interest and learning corners and functioning school libraries.   During plenary sessions teachers reported on the usefulness of the Learning Aids Package distributed to each school through PEIP.

The evidence is high in the practice of sharing ideas and experiences among teachers as shown in Table 2(f) where the mean value for this item is 3.41.

# Table 2 Supportive and Child Friendly Classrooms

| Teaching Practices | Mean |
| --- | --- |
| Teachers keep attractive classrooms | 2.29 |
| Teachers display pupils’ efforts on the wall | 2.73 |
| Teachers provide interest corners in the classroom | 2.96 |

##### Table 2a Child Centered Approach to Learning

| Teaching Practices | Mean |
| --- | --- |
| Pupils work on a variety of projects | 3.0 |
| Teachers allow pupils to share their experiences with each other | 3.33 |
| Teachers ‘chalk and talk’ during lessons | 2.54 |

##### Table 2b Response to Child’s Learning  Needs

| Teaching Practices | Mean |
| --- | --- |
| Teachers attend to the needs of slow learners | 2.96 |
| Teachers address different learning abilities during class lessons | 2.89 |

##### Table 2c Reinforcing Pupils’ Learning

| Teaching Practices | Mean |
| --- | --- |
| Teachers praise pupils’ efforts | 3.51 |
| Teachers give feedback to pupils on their performance | 3.31 |
| Teachers use test results to guide pupil performance | 3.53 |

##### Table 2d Use of a Variety of Learning Materials

| Teaching Practice | Mean |
| --- | --- |
| Teachers use a variety of learning aids during lessons | 2.19 |

##### Table 2e Group Approach to Teaching Learning

| Teaching Practices Teaching Practices | Mean |
| --- | --- |
| Pupils work in groups to complete a given task | 3.1 |
| Teachers stay in front of the class most of the time while teaching | 2.71 |

##### Table 2f Sharing with Peers

| Teaching Practice | Mean |
| --- | --- |
| Teachers share knowledge and experience with each other | 3.41 |

##### Table 2g Teachers and Parents work to improve delivery of education

| Teaching Practices | Mean |
| --- | --- |
| Teachers and parents work together on school improvement plans | 2.51 |
| School improvement plans are implemented in the school | 2.70 |
| Parents are actively involved in school improvement plans | 2.38 |

Component 3 - Strengthening the Institutional Capacity of the MOEDC

The effort to strengthen MOE was effectively launched by an in-depth Organizational Capacity Assessment done by a consulting firm and followed up with work on Strategic Planning, two new efforts in MIS, and exploratory work in Human Resource Development and Financial Management and Budgeting.

As a result of this component, a five-year strategic plan was formulated for the period 2002-2007.  The component financed the implementation of an ongoing planning process, which has allowed the ministry to enhance monitoring an evaluation of its programs.

Component 4 - Human Resource Development for Teachers and Administrators

Over the period 1991-96, 34 persons drawn from the schools and MOE units were trained in advanced courses (mainly overseas) varying in length between three and 18 months, in various educational and management specializations.  All of these returned to the MOE and most of them were placed in the units (NCERD, CPCE and MOE) for which they were trained.  As of the end of 2001, the country received an average of approximately eight years of post-training service in the relevant units for every year of training provided.  The major loss was of six of the 11 trained to the Master’s Degree that suggests the need to improve capacity in personnel management to afford opportunities for well-qualified nationals to make a contribution.

### The Local Training Program was conducted both by foreign and local consultants and by staff trained overseas.   Primary Teachers across all regions were exposed to one-week workshop sessions in Mathematics and Test & Measurement conducted in each region. The objective was to improve the quality of delivery of these subjects with the intent that those trained will work with fellow teachers in their respective schools, and school clusters to achieve a multiplier effect.

The organization of the Reading sessions was a little different. Representatives from all regions met in Georgetown. The training sessions lasted one year.

Chart 2 shows the consistency of the teachers’ responses where they recorded the effectiveness of the sessions and the attainment of objectives of all three-subject areas sessions in strengthening their capability to teach the subjects. The mean value for effectiveness of workshop sessions in enhancing capability ranges from 3.1 in Test Measurement and Assessment (TMA) to 3.6 in Reading; while for achievement of objectives it 4.3 in Reading and Mathematics to 4.4 for TMA.

###### Chart 2

In response for reasons given for rating effectiveness of workshops for enhancing capability, the dominant factor was the acquisition and reinforcement of skills and knowledge, which they were able to share with staff and pupils.

An analysis of the responses and discussions that followed indicates that most of the teachers who participated in the training held staff development sessions with their colleagues on return to their respective schools. The extent to which this happened depended on the support received from the headteachers and staff of the school.

In some schools a culture has developed where there is a coming together of teachers across levels in the region to develop schemes of work and plan term tests.

There were several progressive ideas such as the Teacher Cadet Scheme, the Hinterland Teacher Upgrading Program and the Multi-grade Teaching Workshops. Under the Cadet Scheme, 30 promising teachers were selected and trained over a six-month period of lectures, study and attachments, posted for a year to various offices, and then ‘fast-tracked’ into various management or supervisory roles.  The Hinterland Program helped to make a dramatic difference in the proportion of trained teachers in the Hinterland schools by 1999-2000.  Three pilot initiatives in educational technology were undertaken—Computer Assisted Learning (or Micro-Computer Pilot) in the Original Project and Information Technology (IT) Pilot and Interactive Radio Pilot in the Reformulated Project.

2. The currently expected level of achievement of project objectives.

The aim of improving the primary sub-sector may be regarded as having substantially been achieved, with indications of increases over the period 1995-2000 in the broad indices of public expenditure on education as a percentage of total public expenditure and of GNP, primary school enrolment, enrolment rates, average attendance and declines in grade repetition rates and number of students per teacher (or trained teacher).  In addition, the physical infrastructure (buildings and furniture) and educational materials supplied represent a considerable improvement over the pre-Project situation.

PIEP achieved an overall improvement in the delivery of Education at the primary level.  Using 1987/88 as the base year, education indicators that have been derived from available data, measured changes that have occurred since the implementation of PEIP initiatives. These referred to:

- Government’s Commitment to Increase Expenditure on Education;

- Access to Primary Education;

- Internal Efficiency of the Education System;

- Pupil Absenteeism from School;

- Completion of Primary Education;

- The Teaching Force;

- Access to Textbooks and Instructional Materials;

- The Learning Environment;

- Teacher Capability  - Learning Strategies, Individualized Instruction; and

Output from the Primary  Programme.

The available data reflects a significant improvement in the above mention indicators for the 1989-2000 period. Examples of that are: (i) Government recurrent budget in education has almost increased by two folds since 1996; (ii) repetition rate for grade 1-6 has dropped from 5.7 to 1.5 from 1989 to 2001 and (iii) attendance has increased from 68% in 1989 to 72.8% over the same period.

B. Are there any differences between the current assessment of components or

Objectives, and the latest formal statement of components and objectives agreed

upon with the borrower? If so:

1. Describe and explain differences between planned and attained results with

respect to the components of the project.

Component 1: Improvement of the infrastructure of the educational system and the development of a sound maintenance system.

Due largely to an initial over-estimation of costs and the savings that the PIU was able to achieve, the objectives of this component were clearly surpassed. The original number of schools to be constructed or rehabilitated grew from 30 to 101.

School’s Design considerations and a relatively weak PIU in the first period of implementation caused serious delays. They were overcome in the second period due to a large extent to better planning and a much stronger management.

The weakest link in the performance of this component is the maintenance system that although has made some improvement is still behind the needs and expectations.

Component 2 - Quality Improvements in the Classroom Environment

Some significant efforts took place in this component. Nevertheless some lack of coordination and planning limited the impact. All the elements in the component were implemented with a variety of degrees of success. In general local improvement was felt and overall indicators of system performance have indeed improved.

Component 3 - Strengthening the Institutional Capacity of the MOEDC

A very thorough study was made to identify the weaknesses of the Ministry and to give the necessary recommendation for improvement. To this extent, this element of the component was successful.  The implementation of the envisioned reforms in structure and management are still in progress. In essence, MOE needed more support to be able to change its organizational culture and significantly improve management.

In the second implementation period some consultancies brought some of the needed support to obtain changes in the Management of Information, Financial and Human Resources. These changes, and recommendations based upon the analysis of lessons learned from PEIP implementation, and effectively paved the way to initiate further changes through the design of the new project (BEAMS). The process is on-going and is difficult to predict at this point the extend of the changes that will take place.

MOE was able to produce a Strategic Plan for the period 2003-2007 that Cabinet approved on December 2002. A team from various units in the Ministry received training in Strategic Planning. The Planning Unit is the one that benefited the most.

Component 4 - Human Resource Development for Teachers and Administrators.

The programs took place and had serious impact on MOE and the school system.  However, to take full advantage of the newly trained cohort,  the Ministry needed even more preparation in human resources management, as well as changes in its own internal management and decision-making framework. Hence, although new graduates were absorbed back into the system, the system itself became a limiting factor.

2. Describe and explain differences between planned and currently expected

results with respect to the objectives of the project.

Except for the Infrastructure component, were the total number of new and rehabilitated school increased due to savings, there are not significant differences between planned and currently expected results.

C. Did the project achieve anything of importance that was unexpected? If so,

explain.

Maybe expected by some but surely not included in the formal objectives of the project was the creation in MOE of new expectations after the relatively successful (as compared to the first) implementation of the reformulated project. There is willingness in the majority of administrative officers and teachers to improve the system.

The capability of implementing a program was significantly increased by the experience of the members of the PIU in the second period of implementation.

D. What is the likelihood of achieving the project's agreed objectives and for them to be sustainable? Explain, considering: (i) the degree of completion of the project's components and their use; and (ii) whether the assumptions necessary to achieve the project's objectives are still valid and likely to continue being valid. (Examples of factors that could have an impact on sustainability include: borrower commitment; policy environment; institutional capacity; technical, financial and economic viability; social impact; and incentives for stakeholders to sustain the project.)

There has been no change in the Government’s education policy. Education and in particular basic education, has been clearly articulated as a national policy in the Government’s Poverty Reduction Strategy paper, the National Development Strategy prepared by the civil society and the MOE’s Education Development Strategy Paper 2003-2007.

The PEIP was completed in a relatively successful environment and the experience of the second period of implementation was an invitation to the borrower to become involved in the continuation of the programs through a new loan and different initiatives in the Ministry. The fact that MOE was able to produce a strategic plan with the level of participation in which it was made is a sure indicator of a higher level of commitment by stakeholders and of the establishment of a very positive environment for national and sector-wide policies.

MOE has increased its technical and institutional capacity although still needs a high level of support from external sources.  The future looks promising although many loose ends still remain. The new project BEAMS will be very important to determine the sustainability of the process of change that has started with PEIP.

The country has experienced significant economic improvement in the last five years but there is a recent slow down. Nevertheless, the government remains committed to the process.  GOG’s commitment to education is reflected in the indices of public expenditure as a percentage of total public expenditure and GNP. In spite of the steady decline in the exchange rate of the Guyana Dollar and other inflationary trends, Government spending averaged 3.6% of GDP and 7.5 % of total public expenditure. In 2000 it averaged 14.5 of total public expenditure and  7.3 of GDP (Table 3).

Table 3

| Years | National Expenditure |  |  | Education Expenditure |  |  | Education Expenditure as % of: |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Recurrent | Capital | Total | Recurrent | Capital | Total | Recurrent | Capital | Total | GDP | GNP |
| *1986 |  |  |  |  |  |  |  |  | 5.0 | 5.8 | - |
| 1994 | 29,498.40 | 10,687.40 | 40,185.80 | 2,080.40 | 777.30 | 2,857.70 | 7.05 | 7.3 | 7.11 | - | 4.51 |
| 1995 | 28,538.00 | 11,539.50 | 40,077.50 | 2,545.90 | 721.40 | 3,267.30 | 8.92 | 6.5 | 8.15 | 3.69 | 4.29 |
| 1996 | 29,736.90 | 15,705.50 | 45,442.40 | 2,992.30 | 1,599.60 | 4,591.90 | 10.00 | 10.1 | 10.1 | 4.5 | 5.1 |
| 1997 | 40,414.60 | 16,543.70 | 56,958.30 | 3,458.10 | 1,576.65 | 5,034.75 | 8.50 | 9.5 | 8.8 | 4.7 | 5.2 |
| 1998 | 38,336.30 | 13,086.10 | 51,422.40 | 4,073.00 | 1,832.50 | 5,905.50 | 10.60 | 14 | 11.4 | 5.3 | 5.8 |
| 1999 | 41,909.80 | 12,345.20 | 54,255.00 | 5,150.60 | 1,725.00 | 6,875.60 | 12.20 | 13.9 | 12.6 | 5.6 | 6.3 |
| 2000 | 48,443.08 | 17,132.78 | 65,575.86 | 5,866.06 | 3,661.14 | 9,527.20 | 12.10 | 21.3 | 14.5 | 7.3 | 8.4 |

Guyana Human Development Report 1996 page 57

Source MOE Statistical Digest 1994-2000

The salary situation is still a worrisome factor and the fact that professionals in general and teachers and educational managers are in high demand in other countries is not going to facilitate the development of the system.

Overall the primary objective of the PIEP has been substantially achieved as noted from the education indicators which measured increments of success between 1987 and  2000/01. In general, there has been definite improvement in the physical conditions and learning environments of primary schools, increased access to textbooks and instructional materials, enhanced teaching capability, a definite moving towards child friendly classrooms and improved community/school relationships resulting in better pupil performance at the Secondary School Entrance Examination.  (Table 4)

Table 4: Primary School Performance at SSEE in English & Mathematics,

1995, 1997  & 2000

| Region | English |  |  |  |  |  | Mathematics |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coastland | 1995 |  | 1997 |  | 2000 |  | 1995 |  | 1997 |  | 2000 |  |
|  | Mean | SD | Mean | SD | Mean | S.D. | Mean | SD | Mean | SD | Mean | SD |
| 2 | 21.0 | 11.1 | 26.9 | 12.37 | 27.18 | 15.03 | 19.0 | 12.0 | 23.7 | 13.3 | 24.1 | 11.0 |
| 3 | 19.2 | 10.6 | 24.14 | 12.57 | 28.31 | 14.76 | 16.6 | 10.2 | 21.1 | 11.8 | 24.4 | 10.6 |
| 4 | 22.9 | 12.3 | 26.99 | 13.93 | 28.14 | 15.26 | 16.3 | 12.0 | 22.4 | 13.3 | 25.7 | 11.8 |
| 5 | 19.6 | 10.0 | 22.29 | 11.53 | 24.61 | 13.19 | 15.2 | 9.1 | 18.5 | 10.0 | 22.1 | 9.9 |
| 6 | 17.2 | 9.7 | 21.10 | 11.92 | 23.29 | 13.27 | 13.7 | 8.3 | 17.9 | 9.6 | 20.8 | 10.1 |
| 10 | 23.2 | 10.2 | 27.01 | 11.96 | 27.39 | 13.23 | 18.2 | 10.6 | 21.2 | 11.1 | 25.2 | 9.2 |
| Hinterland |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 14.4 | 6.3 | 18.43 | 9.75 | 17.44 | 7.87 | 12.5 | 6.0 | 15.65 | 7.21 | 18.03 | 7.75 |
| 7 | 16.7 | 9.2 | 20.15 | 10.82 | 21.17 | 10.95 | 11.9 | 6.4 | 14.96 | 7.07 | 21.37 | 10.25 |
| 8 | 11.7 | 7.1 | 15.31 | 8.19 | 14.92 | 7.35 | 10.0 | 6.4 | 12.18 | 4.36 | 14.83 | 7.14 |
| 9 | 18.2 | 9.4 | 20.66 | 9.27 | 18.48 | 8.12 | 12.5 | 7.4 | 15.36 | 7.62 | 18.52 | 8.19 |

The activities helped to develop capacity during the Reformulated Phase were well organized and presented. Based on the responses given by the recipients, there has been marked improvement in the delivery of education in the classroom as a result of these initiatives taken.

Particularly noticeable in the model schools is the transfer of teacher-centered classroom instruction to a child- centered one, where a concerted effort is made to have attractive classrooms, interest corners and classroom organization that reflect a group approach to teaching-learning activities. Note was also taken of the emergence of the headteacher assuming more instructional leadership role, evidenced among other things in the increase in staff development sessions, and corporate planning among similar grades in the schools.

In general parents and the society as a whole are willing to favor an educational reform.

E. In your judgment, are any of the project’s objectives unlikely to ever be achieved and if so, why?

Although the  project objective has been substantially achieved , weaknesses remain, particularly in the area of institutional strengthening,.  This situation can be attributed to a number of causes: the planning process that preceded the implementation of the PEIP had some flaws; the managerial capability of MOE was not correctly assessed and the political environment around the Ministry brought difficult situations that contributed to the delay in the execution of some activities.

Over the long-term, particularly in view of ongoing strengthening activities to be implemented through the new BEAMS project, it is expected that the achievement  of the project’s objective will be further consolidated.

F. If the ex-ante analysis of the project included a calculation of the project’s rate of return or cost-efficiency analysis, what was the rate of return or what were the cost-efficiency estimates? What is the comparable rate of return, or re-estimated cost-efficiency analysis, after project execution? (Note, recalculation of the project’s economic justification should be undertaken in all cases where reliable information is available and where this can be done within the required time frame.)

The project did not include an ex-ante analysis that calculated the project rate of return or cost-efficiency.

III. CHANGES IN ORIGINAL OBJECTIVES, COMPONENTS AND ASSUMPTIONS

A. Did any significant changes occur in the project's objectives, component or assumptions during execution (after project approval)? If so, describe these changes and provide your assessment as to why the changes were required.

In a sense the PEIP became two consecutive projects—the original and the reformulated—with the first one in a state of suspense for some years.  In that context, the 12-year period of implementation does not appear unreasonable. Although the components and implementation benchmarks were modified in 1998 under the reformulation, the assumptions and the overall project objectives remained the same.

C. Based on PPMRs presented to headquarters in connection with the annual Report on Portfolio Management, provide the end-of-year performance classifications for each year the project was in execution.

| End of Year PPMR Performance Classification | ## Years in Execution |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dec 1997 | Jun 1998 | Dec. 1998 | Jun. 1999 | Dec. 1999 | Jun. 2000 | Dec. 2000 | Jun. 2001 | Dec. 2001 | Jun. 2002 |
| Development Objectives (DO) [HP, P, LP, I] | P | P | P | P | P | P | P | P | P | P |
| Implementation Process (IP) [VS, S, U, VU] | U | U | U | U | U | U | U | U | U | U |
| Probability of Assumptions holding true [H, L] | H | H | H | H | H | H | H | H | H | H |

* Year of Board approval

The PPMR assessment of the implementation process as unsatisfactory is mainly based on the long delay experienced by the executor in the implementation on the agreed activities even after the 1998 reformulation of the project.  However, taking into consideration that PEIP became two consecutive programs and all components were successfully completed, an ex-post assessment of the implementation would allow a reclassification to satisfactory implementation.

IV. LESSONS LEARNED FROM THE PROJECT

A. Project Design

1. Were the original objectives of the project (at loan approval) realistically formulated? If not, why not?

The original objective were realistically designed.  Nevertheless, it was not imbedded from the very beginning in a general plan that could better guide the actions of the MOE and the Education sector as a whole.

2. Were the original (at project approval) components of the project appropriate (i.e., necessary and sufficient) for achieving the project’s stated objectives?

The original components were appropriated. However a  noticeable element is what needed to be done to realign the infrastructure component. The initial calculations were over-dimensioned, requiring the adoption of foreign standards and the importation of expensive materials rather than taking into consideration available local resources.  The change into a more suitable and affordable design and the use of more appropriate local materials allowed a substantial expansion of the infrastructure and institutional strengthening components and the addition of two new components.

3. Were project assumptions correctly identified and realistically assessed? Were they adequately covered by conditionality in the loan contract to mitigate risks, or by steps to address risks within the design of the project? Were any assumptions omitted that should have been explicitly considered?

After the reformulation the assumptions were realistically assessed. In fact from all of them already described in the answer to question I C above, only two of the assumptions did not occur at the expected level. The Central Tender Board process was always a difficult one and salaries have not become attractive enough to be able to keep teachers and administrators in the system and the country.

4. Was the planned sequencing of the components adequate?

The sequence of the components seems to have been adequate.

5. Was the institutional capacity of the executing agency and other institutions or agencies involved in the program adequately assessed in the project’s design? If not, explain.

On the whole, the Borrower successfully implemented the Project. However, considerable time overruns, which could have not be completed mitigated during the design of the program, gives the Impression of lack of institutional capacity.

On the other hand, the program was really two consecutive projects—the original and the reformulated—with the first one in a state of suspense for some years.  In that context, the 12-year period of implementation does not appear unreasonable.  Possibly, the original allowance of five years for implementation was unreasonable for a Project of that size and complexity.

.

6. What aspects of the project’s design most contributed to the project’s successes and/or failures?

The Project exhibited many strong points, it focused on one sub-sector – primary; it included due emphasis on improving the skills of the teacher; it provided for piloting ideas with which the country has limited familiarity and its general approach to the sub-sector was reasonably comprehensive in addressing growth and change.  The emphasis on Final Reports and Training Manuals being produced by consultants was a major contribution to retention of some benefits after the departure of the consultants.

The original design guidelines and the management arrangements for construction did not produce the desirable effects.  Changes in the design, permitted to expand the rehabilitation and construction of school to a total of 101.

B. Project Execution

1. What aspects of project execution most contributed to the project’s successes and/or failures?

The Bank demonstrated capacity and flexibility to accept to reformulate the program.  This flexibility allowed the Bank to better understand the nature of problems in the sector and foreseen the need of a second operation to support the underline changes initiated under the PEIP.

2. If significant problems arose during project execution, what were these problems and what measures were taken to solve them? Did these measures have the desired impact?

Most of the problems that delayed PIEP execution were addressed in the reformulation. After he project was redefined and the PIU was strengthened the actions took place in much more satisfactory manner, especially in the area of civil works.

3. Were the quantity, quality and timeliness of components delivered under

the project satisfactory in comparison with original expectations?

The training program was a success in that thousands of teachers received training that would doubtless have improved their skills.  Most of the supervisors of these teachers also received training and orientation in the same fields as their staff in addition to skills essential to their supervisory and managerial roles.

As mentioned above, the Infrastructure Component obtained numbers beyond expectations. In the case of the institutional strengthening the process is well under way although the objectives were not fully obtained.

Even though the additional time that the program took for completion, most of the activities were completed within the given timeframe.    Again, the delay on the execution has to do with some considerable time overruns arising from issues such as: (a) the one year delay in staffing the PIU; (b) protracted discussions leading to the Reformulation of the Project; and (c) considerable expansion in Project scope in terms of physical infrastructure and educational and institutional objectives;

4. If any components have not been completed, what further actions, if any,

Should be taken to complete them?

The program was completed as agreed on the loan contract.  Nevertheless, the next program, BEAMS, will be able to address most of the new aspects identified during PEIP implementation such as the curriculum, testing and evaluation reforms.

C. Borrower/Executor Performance

1. How well did the Borrower/Executor perform throughout the execution phase of the project? (For example, were financial arrangements and procurement carried out effectively? Did the executing agency coordinate effectively with other institutions? Did it have efficient information systems for project execution and monitoring? Did it use this information to improve project management? Did it have an effective analytical and decision-making capacity? Did it identify problems in a timely manner and expeditiously take action to solve them?)

On the whole, the Borrower successfully implemented the Project with, however, some considerable time overruns arising from:

- The one year delay in staffing the PIU;

- Protracted discussions leading to the Reformulation of the Project;

- Considerable expansion in Project scope in terms of physical infrastructure and educational and institutional objectives.

- Chronic understaffing of the PIU in Procurement and Financial management and Education owing to failure to apply agreed salary scales.

- Delays in receiving approvals from the Bank, CTB, and Cabinet in the procurement process and from the Bank on other approvals.

- Unsatisfactory management of the PIU for a critical period 1994-1997.

- Shortfalls in Government’s financing for implementing the Project that curtailed, inter alia, the training program.

In a sense the PEIP became two consecutive projects—the original and the reformulated—with the first one in a state of suspense for some years.  In that context, the 12-year period of implementation does not appear unreasonable.  The original allowance of five years for implementation was not unreasonable.  Nevertheless, some seven years should have been allowed.

Some problems arose from the frequency with which stipulations of the Loan Contract were not adhered to in a timely manner in respect of such items as collection of baseline and comparative data on the sector and submission of Semester Reports.

2. How well did the Borrower/Executor utilize staff and consultants in this project? Were the consultants’ inputs and recommendations appropriate and effective, and were they used by the Borrower/Executor?

The work of most of these consultants appears to have been held in high regard by all persons concerned. The consulting services components of the Reformulated Project reflected a heightened concern with effecting and accelerating change.  The Maintenance of school buildings, for example, extended into a pilot maintenance phase and into computerizing the condition of school plant.   Greater emphasis was placed on the capacity of NCERD and Regional Learning Resources Centres to change Reading and Mathematics teaching.  The consultants prepared Manuals in the teaching of Mathematics and Reading, in Testing and Measurement and in Multigrade Teaching, all indicating directions of desirable improvement. The effort to improve the management and planning of the sector went beyond the original scope of works of the organizational and management consultants, venturing into direct efforts to change procedures and methods of operating in financial management and Human Resources management.

3. Did the Borrower/Executor’s relationship with the other institutions or agencies involved in the project have any significant impact on the outcome of the project? What was the impact?

Yes, the Borrower relationship with other institutions and agencies has had a significant impact on the outcome of the program.  To a great extend, the PEIP experience strength the managerial capacity of the Ministry to work in a larger number of reform issues simultaneously.  The Ministry went from only implementing the PEIP to execute three other large programs financed by the World Bank, the Canadian and British international cooperation Agencies.  This required a greater comprehension of the need for integrating planning to avoid duplication of resources and defining each level of government responsibility.

4. Did the Borrower/Executor significantly improve its institutional capacity during project execution? If yes, explain. If not, why not?

Component III on Strengthening the Institutional Capacity of MOE revolved around an assessment of the capacity of the Ministry, which was very well done by a consulting firm.  A document entitled the Strategic Plan was prepared with contributions by many groups.  Further work was done by three more consultants on the MIS, and consultants also worked on Human Resource Capacity and Financial Management and Budgeting.  In all of these areas, work is scheduled to continue.

The development of NCERD and CPCE was an implicit objective of the overseas and advanced training programme.   Overall, the Ministry has improved its planning and monitoring capacity.

5. Did the Borrower/Executor follow up on critical assumptions and take steps to make necessary adjustments?

Yes in did, The Borrower follow on critical assumptions.  An example of that is the steady increase in recurrent budget of the education sector from 7% to 12% in six years.   Without the commitment of the borrower in this matter none of the changes will be sustainable today.

D. Project Performance Monitoring by the Borrower/Executor

1. Was the way through which project performance would be monitored (and the resource requirements involved clearly established and agreed upon with the borrower/executing agency? If so, at what stage?

The PIU had all the responsibility of implementation and monitoring. Because of all the problems that existed in this unit, the monitoring system was not strong. There was no continual follow-up on the actions of the program and much was dependant on the reports of the consultants and the different units. In general, monitoring of the quality components was not effective. PIU, in the second period was able to monitor very well the construction work.

2. How was project performance actually monitored in practice? Were any difficulties encountered? If so, explain.

The main difficulty was the lack of a previous effective design for a monitoring system and the absence of that capability within MOE.

3. Were the indicators and benchmarks selected to measure the achievement of the project's objectives adequate and useful? If not, explain.

Yes they were.   The borrower has been able to track and measure the entire set of indicator.

E. Bank Supervision

1. How well did the Bank perform throughout the execution phase of the project? (For example, did the Bank correctly anticipate potential problems at the objective, component, and assumption levels? Did it take corrective action to solve problems in a timely manner? Was the Bank an able and efficient supervisor/advisor?)

In this Project, beyond its direct financing, the Bank played an important role at all stages of the Project Cycle.  At the design stage, IDB helped to keep the Project focused on Primary Education.  During the implementation stage, the Bank steered the Reformulation into reinforcing the original goals and discouraged significant departures from these goals.

However, it was at the design stage that the Bank, apparently somewhat unfamiliar with the design and construction supervision practices of the Anglophone Caribbean, played too large a role in determining the design guidelines and the arrangements for design and construction supervision that proved extremely costly and resulted in the Reformulation of the Project on the basis of savings generated by the re-design of schools and the changes in construction management.

While allowing the Borrower ample room in which to implement the Project, the Bank was careful not to allow gross inefficiencies and breaches of the Loan Contract to go unnoticed.  In its Project Performance Monitoring Report following its 1996 Project Review Mission, IDB gave the PIU a rating of “weak institutional capacity.”  The Project Director challenged this.  The Bank, therefore, provided him with an instructive outline of the negatives in the performance of the PIU:

1. The vacancy for the past two years in the posts of Academic and Procurement   Specialists.

- The failure regarding collection of baseline and comparative data since 1991/92.

- The delays in producing camera-ready copy for levels 4-6 textbooks and manuals.

- The several local teacher training programs yet to be implemented.

- The fact that this education program (PEIP) needs an educator – a sine qua non of achieving the project objective of improving the quality of primary education.

- The need to strengthen staffing for physical infrastructure.

- The poor state of the unit’s financial management and reporting with no financial specialist on staff.

In the critical years of indecision--1992-96--the Reformulation discussions dragged on.  The date of final disbursement was extended.  When it became quite clear that the Borrower was taking too long to assess the progress of civil works, estimate the cost of successful completion of the same and identify the cost savings expected from the redesign of the project schools, the Bank took the initiative of engaging a consultant to determine these.  This determination provided the financial basis for finalizing the Reformulation of the Project.  Another very useful measure was the engaging of a consultant to review the management and planning of the sector so as to clarify the institutional issues to be addressed in the Reformulated Project.

On changes in the Project, and extensions of dates of final disbursement, the Bank was generally flexible and positive.  The Bank also offered suggestions such as the hiring of a consultant for procurement and one for compiling baseline and comparative data.  It would have been advantageous, in solving the problem of the prolonged absence of Specialists in Finance and Procurement, to have had a standing arrangement to employ a short-term consultant (i.e. for a maximum of six months) whenever the vacancy persisted for more than a given period such as two months.  The informal advice given on procurement by the Guyana Office was much appreciated by the Procurement Officer.

One of the persistent complaints of the PIU throughout Project implementation was the delay between asking for and receiving IDB approvals on a wide range of matters.  IDB usually either requested that they be supported by fact or replied that the delays were caused by Borrower failure to supply information requested in support of the applications.  It is clear that (1) more informal communication (telephone or visit) before making a request for approval could help IDB to identify in advance some of the data IDB would need and (2) IDB, having received the request, could also use the phone to clarify any data requirements and follow up in writing if necessary.  It is possible that the internal arrangements in PIU, without a central filing system and with attrition of staff, may have contributed to loss of the tracking of requests for more information.  Yet, it would appear that the key to avoiding such delays is the staff at the immediate disposal of the Guyana Office of IDB — in this case the posting of someone with an Education Project background as was done eventually.

2. Did the Bank/Executor relationship, and the Bank’s relationship with other institutions and agencies that were involved in the project, have any significant impact (positive or negative) on the outcome of the project. If so, what was the impact?

The bank relationship with other Agencies and Institutions has helped to facilitate the success of the project.   Having a permanent dialogue with key ministries such as Finance, the Bank has been able to address a number of issues that resulted on internal efficiencies and adequate resources allocation for the program.

V. MAIN LESSONS AND RECOMMENDATIONS FOR FUTURE PROJECTS 10

A. What are the main lessons that have been learned from this project and that could be relevant to other projects? (For example, design flaws that should be avoided in similar operations, institutional issues that were overlooked or inadequately addressed, innovative solutions that resolved problems during execution, successful or unsuccessful attempts to make the project financially sustainable, suggestions regarding better project performance indicators, etc.)

The lessons that are suggested by the design and implementation of this Project can be condensed as follows:

| Problems | Lessons Learned |
| --- | --- |
| Strategic Planning | The importance of a sector plan as the basis for generating a Project. Programs must be designed within an existing strategic planning framework that has been produced with the participation of all relevant stakeholders and approved by the national authorities. |
| Logical framework system | It is important to assess the role of different stakeholder. The need to ensure that all agencies that have some part to play in implementing the Project, including those that appoint Project staff, are briefed as to the content and rationale of the relevant items in the Project. |
| Institutional Assessment Analysis | - The value of scheduling items for implementation in such a way as to avoid over-taxing the implementation capacity of the PIU. - The need to establish within the PIU a unit to monitor adherence to the provisions of the Loan Contract and the adoption of measures for the implementation and completion of the different aspects of the Project. - The importance of absorption of highly trained staff on suitable conditions of work and remuneration. - Condition prior to first disbursement shall include a remuneration analysis and scale as part of the project organization structure. The bank needs to monitor the government adherence to the remuneration scale. |
| Monitoring and Evaluation | - Programs should put greater emphasis on project monitoring through simple reliable data collection combined with an upgraded MIS system, able to generate reports on performance indicators and operational audits. The collection of baseline data should be incorporated into special conditions of the loan contract in order to facilitate the process. - Include a monitoring and evaluation in the design of the program and budget the resources for its implementation. |
| Local Industry Trends and Technology (assumptions) | - Assess the current development of the industries upon which the component will request services from (construction, consultants, etc). Industries practices or lack of capacity could slow down the implementation of the program. |

B. Based on the lessons learned from this project, indicate possible improvements in Bank policies, strategies, practices and procedures. (For example, recommendations for streamlining procurement, improving dialog with borrowers, facilitating timely reformulations, suggested changes in Bank operating policies and strategies, etc.)

The level of remuneration of the PIU should be kept at least to the level suggested in the Project Report with appropriate performance incentives linked to the timely attainment of the milestones in the Plan of Action.

Project monitoring and evaluation should be set from the starting point and be a priority at all times. In fact the design and implementation of the project should be understood as to phases of the same process and project management tools and conceptualizations used at all times in the project cycle.

VI. ADDITIONAL COMMENTS

If there are any additional aspects concerning this operation that have not been covered thus far, present them in this section.

Part Two

Prepared by Ministry of Education

PROJECT NAME: Primary Education Improvement Program

IDB PROJECT NUMBER:

IDB LOAN AND TC NUMBER(S): Loan 827/SF – GY TC:

BORROWER AGENCY(IES) RESPONSIBLE FOR THIS REPORT: Ministry of Education

I. PROJECT OBJECTIVES

A. Although it may be difficult to fully assess all of the results of the project at this stage, please indicate which objectives* you feel have been achieved under the project, and to what extent.

The general objective of the project seems to be achieved. Primary Education in Guyana has been strengthened and while there are a lot of initiatives to be taken on the main indicators show a significant improvement. The coverage of the level is complete and Nursery Education has increased to almost achieve complete coverage too. The number of trained teachers has increase and GOG has shown commitment with Education by continually raising the budget.

B. In your judgment, are there any project objectives that are unlikely ever to be achieved? If so, why?

There are no project objectives that cannot be achieved. Some will take longer because of lack of implementation capabilities and resources, financial and human. Nevertheless, with time and the support of agencies committed to development this will be possible.

II. PROJECT DESIGN AND EXECUTION

A. What aspects of the project’s overall design most contributed to the project’s successes and/or failures? Why?

The original design of the infrastructure component was ill conceived and caused many problems. Also there was the weakness of the PIU created an almost insurmountable difficulty. There is need to pay more attention to this staffing and also to the level of remunerations.

B. What aspects of project execution most contributed to the project’s successes and/or failures? Why?

The lack of a good monitoring system to follow on each of the actions and the fact that the PIU lacked the necessary human resources were significant contributors to problems and failures.

The changes in design made after the first years of the project were necessary. Then, the presence, in the second stage, of a Program Manager with expertise on constructions and civil works was a great addition.

C. Did significant problems arise during project execution? If so, what were these problems and what measures were taken in an attempt to solve them? Were these measures successful?

The problems were many. This is especially at the beginning of the program when several weaknesses in the design (Construction/ Monitoring/PIU) made implementation very difficult. The reformulation of the program was a successful attempt to solve the problem. The new program BEAMS will benefit from this experience.

D. Has the institutional capacity of the institutions and agencies involved in the project been strengthened as a result of the project? If so, how?

Definitely so, MOE is more aware now of its own limitations and can plan better to overcome them. The consultancies on Strategic Planning, Human Resources, Financial Management and Management Information Systems were the starting point of a process that should lead to a change in the organizational culture and its managerial capability.

E. Did any unforeseen events, beyond the control of those directly involved in project execution, adversely affect the project and the likelihood that it will achieve its development objectives? If so, please explain.

Some political unrest and economic problems in the country led to difficulties.

III. BANK PERFORMANCE

A. How well did the Bank perform during the preparation and execution phase of the project? (Was the Bank an able and efficient administrator? Did the Bank provide good and timely advice? Did the Bank maintain an effective dialog with the executing agency and between the institutions or agencies that were involved with the project?)

The Bank was a great support. At a point in time there were some problems because of lack of dialogue. They were solved and the cooperation now is at one of its highest levels.

B. What significant impact, if any, did the Bank’s performance have on the outcome of this project?

The Bank helped very much in the redesign of the project. IDB showed flexibility and honest desire to help. The introduction of new tools of project management was and will be a significant help for the projects.

IV. LESSONS LEARNED

A. Are there any lessons from the Bank’s performance in this project that could be used to improve future projects? If so, what are they?

It is important to stress the need of a clear direction and purpose in the sector. In order for any project to be really successful, the Ministry must know what it wants and needs and be able to think strategically in a way as to be able to be really committed with the actions to take.

The whole Government, all the agencies of the sector, needs to be involved and know the purpose. More so those that will become part of the project need to be fully conscious.

The PIU, to be effective, needs to be strong and have good and capable leadership.

B. Are there any additional comments or recommendations regarding the project and/or the Bank that need to be mentioned and/or that should be taken into account in future projects?

Part Three -- Basic Data

### BASIC PROJECT DATA

Original		Actual

| Project dates (months/year) |  |  |  |
| --- | --- | --- | --- |
| Date of inclusion in the pipeline |  | December 29, 1987 |  |
| Date of Profile II or Loan Request | (Orientation Mission) | January, 1988 |  |
| Date of Analysis Mission |  | April 18-May 5, 1989 |  |
| Date of Loan Committee Approval | October 13,1989 | October 13,1989 |  |
| Date of Contract Effectiveness | Nov 16, 1989 | Jan 12, 1990 |  |
| Date of Compliance with prior conditions | June 12,1990 | Jan 10, 1991 |  |
| Calendar of investments |  |  |  |
| Starting date | Nov 16, 1989 |  | Jan 12, 1990 |
| End date | Jan 12 1995 |  | April 30, 2002 |
| Disbursement calendar |  |  |  |
| First disbursement | Jan 12, 1990 |  | Jan 18, 1991 |
| Last disbursement | Jan 12, 1995 |  | April 30, 2002 |
| For sector loans |  |  |  |
| First tranche | N/A |  | N/A |
| Second tranche | N/A |  | N/A |
| Third tranche | N/A |  | N/A |
| Date of physical initiation of works |  |  | Nov 16, 1993 |
| Date of loan commitment |  |  |  |
| Date(s) of Cancellation(s) |  |  |  |

| Original Actual |  |  |
| --- | --- | --- |
| Mid-term review and evaluation |  |  |
| Date of mid-term review (if required) |  |  |
| Due date of borrower ex-post evaluation (if required) | December 31, 1995 | December 31, 2002 |
| Due date of Bank ex-post evaluation (if required) |  |  |
| Summary cost data |  |  |
| Total amount of IDB financing | 46,400,000.00 | 45,727,749.56 |
| IDB financing as % of total cost |  | 89.0 |
| Total cost of project | 51,600,000 | 52,437,000.00 |
| Cumulative investment as of (month/year) |  |  |
| Reminder required for completion | N/A | N/A |

B. PROJECT COST AND FINANCING (all amounts in millions of US$)

1. Project cost and source of financing

| Original Actual |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Investment category | IDB | Borrower | Total | IDB | Borrower | Total |
| 1. | 1,375,000 | 1,350,000 | 2,725,0010 | 5,416,938.78 | 2,529,714.40 | 7,947,000 |
| 2. | 31,175,000 | 1,745,000 | 32,920,0020 | 28,523,409.46 | 1,610,487.34 | 30,134,000 |
| 3. | 5,171,000 | 0 | 5,171,0030 | 7,354,320.20 | 0 | 7,354,000 |
| 4. | 715,000 | 1,460,000 | 2,175,0040 | 2,686,278.86 | 624,624.03 | 3,311,000 |
| 5. | 6,512,000 | 208,000 | 6,720,0050 | 0 | 0 | 0 |
| 87. | 1,452,000 | 437,000 | 1,889,08700 | 1,746,802.26 | 1,944,348.21 | 3,691,000 |
| TOTAL | 46,400,000 | 5,200,000 | 686,018,8500 | 45,727,749.56 | 6,709,173.98 | 52,437,000 |

2. Schedule of Investments

| Original Actual |  |  |  |  |
| --- | --- | --- | --- | --- |
| Years | IDB | Borrower | IDB | Borrower |
| Year 1 | 900,000 | 600,000 |  | 205,196.00 |
| Year 2 | 7,100,000 | 900,000 | 299,779.00 | 401,610.00 |
| Year 3 | 13,800,000 | 1,200,000 | 788,759.00 | 675,678.00 |
| Year 4 | 17,300,000 | 1,500,000 | 825,827.00 | 548,769.00 |
| Year 5 | 7,300,000 | 1,000,000 | 476,343.00 | 443,556.00 |
| Year 6 |  |  | 1,484,070.00 | 527,651.00 |
| Year 7 |  |  | 4,445,659.00 | 794,714.00 |
| Year 8 |  |  | 6,405,258.00 | 604,400.00 |
| Year 9 |  |  | 4,944,893.00 | 682,632.00 |
| Year 10 |  |  | 3,624,930.79 | 452,413.92 |
| Year 11 |  |  | 9,105,573.22 | 733,131.37 |
| Year 12 |  |  | 10,906,599.33 | 594,860.61 |
| Year 13 |  |  | 2,420,058.22 | 44,562.08 |
| # Total | 46,400,000 | 5,200,000 | 45,727,749.56 | 6,709,173.98 |

C. LOAN/TC DATA

| Original Loan/TC amount | $46,400,000 |
| --- | --- |
| Amount disbursed | $45,727,749.56 |
| Amount cancelled | $672,250.44 |
| First disbursement |  |
| Original date (month/year) | 12 Jan. 1990 |
| Actual date (month/year) | 10 Jan. 1991 |
| Last disbursement |  |
| Original date (month/year) | 12-Jan-1995 |
| Actual date (month/year) | 30-April-2002 |

# Part Four

(To be completed after headquarters review)

This section contains the official observations on the draft PCR resulting from the review process at headquarters. In the case of PCRs that are reviewed at the CRG level, the minutes of that meeting should be attached here. In the case of PCRs that are not reviewed by the CRG, the official comments of the headquarters division assigned to follow the project’s execution, or any other comments deemed relevant by the regional Manager, should be attached here. In either case, these observations become a formal part of the PCR, and should be included in the final version disseminated to Bank staff.

Teachers (178) of the twelve (12) schools responded to a Liker type scale, which required them to rate the frequency with which they observed the teaching behaviors being practiced in their schools. 1 being the lowest and 4 being the highest.

The remaining three were not accessed because of time constraints due to the teachers’ strike and annual examination activities occurring at this time of the year.

A sample of teachers was asked to respond to a questionnaire which sought to ascertain the extent to which: Workshop objectives were achieved; Teachers’ capability in the respective subject areas enhanced; Action taken by the teachers since participation and facilitating and hindering factors.