## Sheet1
Inter-American Development Bank
VPC/FMP
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Ecuador |  |  |  |  | Executing agency: Asociacion Fe y Alegria |  |  |  |  | Public or private sector: Both
Project number: EC-T1307 |  |  |  |  | Title of Project: ICT for Inclusion: Using technology for the inclusion and promotion of technological skills for children and youth with disabilities
Period covered by the plan: September 2015 - September 2017
Threshold for ex-post review of procurements: n/a |  |  |  | Goods and works (in US$):____________ |  | 393500 |  | Consulting services(in US$):____________ | 387500 | 781000
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (ex-ante or ex-post) (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB JPO Fund % | Local/other %
1 |  | Component 1. Curriculum Development and Implementation | 461360
Individual consultants
1.1 |  | Project Manager and Coordinator | 56000 | IICQ | n/a | 100% | 0 | September 10th, 2015 | n/a
1.2 |  | ICT Curriculum design & technical experts | 80000 | IICQ | n/a | 100% | 0% | September 10th, 2015 | n/a | 3 consultants with average individual amount of US$13,500/year
1.3 |  | Training and coordination actitivies | 127177 | IICQ | n/a | 55% | 45% | September 10th, 2015 | n/a | 3 consultants with average individual amount of US$10,000/year (7 units total)
1.4 |  | Capacity bldg / awareness raising / teacher training workshop design and execution | 30000 | IICQ | n/a | 100% | 0% | September 10th, 2015 | n/a | 2 consultants with average individual cost of US$15,000/year
Goods and Works
1.5 |  | Capacity bldg / awareness raising / teacher training workshops | 62683 | CB | n/a | 42.2% | 57.7% | September 10th, 2020 | n/a | Average of 7 workshops per year
1.6 |  | Hardware/Software including software, licenses and tools for people with disabilities (PWD) | 63000 | PC |  | 100% |  | September 10th, 2021
1.7 |  | Materials/printing | 20000 | DC | n/a | 100% | 0 | September 10th, 2022 | n/a
1.8 |  | Travel | 22500 | IICQ | n/a | 100% | 0 | August 10th, 2023 | n/a | Airfare and per diem for 3/year at individual cost of US$2,500
2 |  | Component 2. Collaboration with private sector companies | 95500
Individual consultants
2.1 |  | Design and Identification of private sector partners and collaboration | 16000 | IICQ | n/a | n/a | 0 | August 1st, 2015 | n/a
Goods and Works
2.2 |  | Internship structuring / capacity bldg workshops | 52500 | DC | n/a | 100% | 0 | October 1st, 2015 | n/a
2.3 |  | Dissemination and Sensitization Strategy/Campaign | 27000 | PC | n/a | 100% | 0 | October 1st, 2016 | n/a
3 |  | Component 3: Dissemination, Documentation and Digitalization of Project | 167500
Individual consultants
3.1 |  | Documentary development / production | 40000 | IICQ | n/a | 100% | 0 | August 1st, 2015 | n/a
3.2 |  | Dissemeniation platform development / campaign and strategy with Ministry of Education of Ecuador | 75500 | IICQ | n/a | 100% | 0 | January 1st, 2017 | n/a
Goods and Works
3.3 |  | Digitalization of of classes / sign-language adaptation | 20000 | DC | n/a | 100% | 0 | June 1st, 2016 | n/a
3.4 |  | Dissemnation Materials / Workshop | 32000 | PC | n/a | 100% | 0 | January 1st, 2017 | n/a
4 |  | Component 4: Monitoring and Evaluation | 69000
Consulting firm/Individual consultants
4.1 |  | Evaluation (base line and follow up) | 69000 | IICQ/CQS | n/a | 100% | 0 | August 1st, 2015 | n/a
Total |  |  | 793360 | Prepared by: Carlos Guaipatin (IFD/CTI) |  |  | Date: June 20, 2015
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection under a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical "or "complex "that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.
Note on C35: Test: Pull from C1 in order to add contingencies into the TC