Japan Special Fund (JSF)

Project Profile

December 2006

- Basic Project Information

| Beneficiary country: | Peru |  |  |  |
| --- | --- | --- | --- | --- |
| Project name: | Support the Sustainable Development of the Lower Urubamba |  |  |  |
| Project number: | PE-T1053 |  |  |  |
| Project team: | Kristyna Bishop (RE3/SO3) team leader; Ophelie Chevalier (RE3/SC3), Leonardo Corral (RE3/EN3); Antonio Giuffrida (RE3/SO3), Rafael de la Cruz (RE3/SC3), Ian MacArthur (COF/CPE) and Joseph Milewski (COF/CPE). |  |  |  |
| Executing agency: | Presidencia del Consejo de Ministros (PCM) |  |  |  |
| Target beneficiary population: | Population of the Lower Urubamba and local governments in the region |  |  |  |
| Date of request: | December 2006 |  |  |  |
| Financing plan: | IDB (JSF): | US$ | 750,000 |  |
|  | Local counterpart: | US$ | 190,000 |  |
|  | Total: | US$ | 940,000 |  |
| Technical and basic responsibility: | Technical responsibility: Basic responsibility: | RE3/SO3 COF/CPE |  |  |
| Tentative date: | Approval: | April 2007 |  |  |
| Execution period: | 12 months |  |  |  |
| Disbursement period: | 18 months |  |  |  |

- Background and Rationale

- A.	The Lower Urubamba region

  - The Lower Urubamba is an area of approximately 3 million hectares that is located in the Peruvian Amazon and inhabited primarily by Indigenous peoples. It has been internationally recognized as an area of extreme biological diversity that exhibits “pristine natural conditions allowing for the existence of species already extinct in other areas” and has been recognized nationally through the establishment of a significant number of protected areas including the Otishi National Park and the Megantoni Sanctuary.

  - The Lower Urubamba is also home to 20,886 residents including several Indigenous peoples such as the Machiguenga (56.9%), Ashaninka (8.9%), Caquinte (1.0%), Nanty (11.0%), Nahua (5.2%) and Yine (8.0%). They live in small family groups or clans that occupy particular territories and which enjoy varying levels of interaction amongst themselves and with non-Indigenous communities. Their communities are generally located along the banks of the large rivers including the Urubamba which provide them with access to food sources and transportation. Data from the Inka Region Diagnostic 1997 shows that this area is characterized by a relatively low level of social development. There is high fertility, high infant mortality rate, low life expectancy, high levels of illiteracy and low levels of household income that are combined with limited access to basic services such as education, health and sanitation. The 2002-2006 Development Plan for the Lower Urubamba estimated that the average annual per capita income in the Lower Urubamba was US$60.

- Aggregate Poverty Index for Lower Urubamba Municipal Districts(*)

| Municipal district |  | ECHARATE | RAYMONDI | SEPAHUA |
| --- | --- | --- | --- | --- |
| Province |  | LA CONVENCION | ATALAYA | ATALAYA |
| Department |  | Cusco | Ucayali | Ucayali |
| Access to basic services index (1) |  | 0.6976 | 0.8848 | 0.5802 |
| Quintile of the access to basic services index (2) |  | 1 | 1 | 2 |
| % of the population without access to | Water (3) | 78% | 72% | 51% |
|  | Sanitation (3) | 19% | 38% | 28% |
|  | Electricity (3) | 73% | 74% | 57% |
| Female literacy (%) (3) |  | 24% | 32% | 16% |
| % of child malnutrition (4) |  | 41% | 46% | 30% |
| % of children aged 0-12 (3) |  | 34% | 42% | 39% |
| * Source: “Nueva Mapa de Pobreza del Fondo de Cooperacion para el Desarollo-FONCODES, 2006” Lima, July 2006 http://www.foncodes.gob.pe/mapapobreza 1: It is a value between 0 and 1 constructed using the principal components, factorial analysis of the indicators below 2: Quintile weighted by population size of the municipal district. 1=poorest quintile. 3: Source: 2005 Population Census (INEI) 4: Source: 1999 Student population size Census (MINEDU) |  |  |  |  |

  - In addition, a significant population of colonos (settlers originally from other areas particularly Cuzco) is moving into the region partially as a result of expectations for employment from new economic activities. This population is relatively fluid, however, with high rates of mobility and migration depending on availability of resources, employment and transportation. It is estimated that colonos currently represent approximately 9% of the total population in the Lower Urubamba.

  - The Lower Urubamba is an area of important hydrocarbon reserves which are estimated to be 8.7 trillion cubic feet of natural gas and 545 million barrels of natural gas liquids. In particular, the Camisea gas project which is located in this region is considered by the Government of Peru to have great strategic importance because it expands Peru’s energy base to cleaner, more abundant and more economical sources and gives Peru energy export revenues and the possibility of generating new related business activities. Forestry, both legal and illegal, is another economic activity in the Lower Urubamba that has significant development impacts.

  - The regional and local governments of the Lower Urubamba region, including the municipal districts of Echarati (province of La Convención, Department of Cusco), Raimondi and Sepahua (province of Atalaya, Department of Ucayali), will benefit from the employment and investments generated by the oil and gas projects in the region as well as directly benefit from the taxes and royalties received by the State from the companies involved in gas exploitation. These revenues have enormous potential for the region although various communities and NGOs have complained that the expected financial benefits have not yet reached all the intended beneficiaries. There is also concern that the legal restrictions on the use of the royalties (e.g. only investment projects can be financed), the strict procedures required to unlock the funds (e.g. the need to use the norms established by the National System for Public Investment (Sistema Nacional de Inversión Publica [SNIP]) compounded by the weak institutional capacity of the local governments, low absorption capacity of these governments and the relative lack of coordination between the various levels of government (i.e. national, regional, provincial, district and community levels) have resulted in serious challenges for the effective use of these resources.

- B.	Linkage to other IDB programs

  - The IDB has been actively working in the Lower Urubamba for several years primarily by supporting the Government of Peru to manage the environmental and social impacts of oil and gas exploitation. In particular, the “Program for Institutional Strengthening and Environmental and Social Management Support for the Camisea Project” (PE-0233, 1441/OC-PE) supports the 13 government entities that are directly involved in the environmental and social aspects of the Camisea project by strengthening their institutional and regulatory capacity. This Program has supported the design and implementation of social and environmental management plans and specific programs to promote sustainable development in the area of influence of the Camisea project. Of relevance to the proposed technical cooperation project, the Program also supported the preparation of various studies and plans for the Lower Urubamba including a proposal for a Strategic Environmental Planning System for the Lower Urubamba; a Strategic Environmental Assessment for the hydrocarbon sector in the Lower Urubamba; an access control plan; a plan for the protection of populations living in voluntary isolation in the Reserva Nahua Kugapakori (RNNK); creation of and management plans for four protected areas (Otishi National Park, Ashaninka and Machiguenga Communal Reserves and the Megantoni Sanctuary). The recurrent costs associated with the implementation of these various protection, monitoring and control plans are being financed as part of the Government of Peru’s annual budget.

  - This technical cooperation project also complements work being undertaken as part of a national level project, Modernization of the State and Decentralization (PE-0217; 1437/OC-PE), which focuses on strengthening subnational governance, particularly in the areas of management and technical capacity that is intended to improve the rate and quality of investments at this level.

  - In November 2006, the Peruvian government requested a new program for the sustainable development of the Lower Urubamba. The objectives of the loan operation, Sustainable Development of the Lower Urubamba (PE-L1021), as articulated by the Government of Peru will include: i) increasing the presence of the State in this region (delivery of basic services); ii) institutional strengthening for regional and municipal governments; iii) protection and support for local populations and Indigenous communities; and iv) identifying infrastructure projects in the area that could be financed by future oil and gas revenues. This technical cooperation project will support loan preparation by providing technical assistance and support for key information gathering and project dimensioning activities that will be the main inputs for the design of the loan.

- C.	Linkage to Bank strategies

  - In terms of the priority areas of the Bank’s Strategy with Peru (GN-2205-1), the proposed technical cooperation will contribute primarily to the second objective — i.e., to promote social development and increase social efficiency — by improving the sustainable development of the Lower Urubamba population.

  - The proposed project will also contribute to the third objective of the Bank’s Social Development Strategy (GN-2241-1) — i.e. to promote social inclusion and prevent social ills — by supporting the sustainable development of the Indigenous communities of the Lower Urubamba, who are often excluded from many programs due to their geographic isolation and the high cost of service delivery.

  - In addition, the technical cooperation will contribute to the general objective contained in the Bank’s Modernization of the State Strategy (GN-2235-1) which is to strengthen the capacity of subnational governments in order to improve public sector delivery.

  - The technical cooperation project and the loan operation will also greatly contribute to the implementation of the Bank’s Indigenous Peoples Strategy and Policy (GN-2387-5 and GN-2386-5) that were approved by the Board of Directors in February 2006. The TC will ensure the active participation of Indigenous peoples in the design of the loan operation, which is outlined as a key element in the directives contained in the Policy.

- Project Objectives and Description

- D.	Objective

  - The proposed Technical Cooperation (TC) will support the preparation of the Sustainable Development of the Lower Urubamba Program (PE-L1021) by providing technical assistance and support for key information gathering and project dimensioning activities that will be the main inputs for the design of the loan.

  - The overall objective of the TC and PE-L1021 is to support the sustainable development of the Lower Urubamba region by focusing on the social and economic development of the Indigenous and non-Indigenous communities, improving quality and management of public investment, building local institutional capacity to better manage the environmental and social impacts of natural resource extraction on these populations and enhancing the return of benefits from natural resource exploitation to these areas.

  - Partnerships with well established development organizations that already operate in Peru will be explored in order to expedite project design and piloting of innovative social and economic development interventions. These partnerships would also support capacity building for local institutions in key areas of project management and implementation with the long term goal of transferring responsibility for project implementation and delivery of services to these institutions.

- E.	Components, activities, and products

  - In order to achieve the aforementioned objectives, this technical cooperation project will finance the following components:

  - Component 1 – Socio-economic development and sustainable environmental planning ($775, 950)

  - The objective of this component is to improve the social and economic development opportunities for the Indigenous and non-Indigenous communities living in the Lower Urubamba through a series of targeted activities and pilots. Related objectives are to improve the capacity of local governments to manage the delivery of basic services to these communities and to mitigate the environmental impacts of large scale natural resource extraction projects by improving local participation in environmental monitoring.

    - Design of socio-economic development interventions ($182,650)

  - This sub-component will finance technical assistance including studies and in-depth analysis to define the scale and scope of the interventions needed to address the inadequate socio-economic development of the Lower Urubamba. Initial studies will include but are not limited to: rapid health and education assessments, infrastructure and transportation assessments, feasibility studies regarding productive projects, analysis of sanitation and access to clean water and feasibility studies for alternative and convention energy and connectivity. This component will also support a participatory consultation process among local stakeholders, which includes local communities, central and local governments, civil society organizations, private sector companies involved in the natural resource extraction projects and local NGOs, in order to further define priorities for this subcomponent. The final product for this subcomponent will be a proposed design of the relevant component under the loan operation, Sustainable Development of the Lower Urubamba (PE-L1021), that will be discussed and agreed with the Government of Peru.

    - Sustainable environmental planning ($65,650)

  - The objective of this sub-component is to support sustainable environmental planning in the Lower Urubamba by promoting the establishment of a multisector, representative and participatory planning mechanism. This component will finance the following activities: (i) stakeholder mapping, which includes the identification of all local, regional, and national stakeholders currently operating in the area; (ii) proposal for a mechanism that will ensure the participation of all stakeholders; and (iii) development of the necessary legal instruments to establish the planning mechanism. In addition, specific hands-on training modules for environmental planning will be developed to enhance the capacity of local and regional governments.

  - This component will also compile the numerous environmental studies that have been prepared for the Lower Urubamba, synthesize and share this information with local communities through various communication tools, including modules and training material for schools, in order to improve awareness and respect for the natural environment.

    - Support for Local Governments ($65,650)

  - The objective of this sub-component is to conduct an assessment of the institutional and investment capacity of two regional governments (Cuzco and Ucayali), two provincial municipalities (La Convencion and Atalaya) and three district governments (Echarati, Raymondi and Sepahua). The assessment will include: (i) a description of the organizational structure of the regional and municipal governments and identification of any central government agencies in the territory; (ii) relevant civil service rules, number, characteristic and distribution of positions; (iii) budget analysis: income (transfers, taxes), expenditures (current and investment), and borrowing levels; (iv) analysis of existing capacity for investment/maintenance planning and execution, budgeting; procurement, financial control and data gathering/investment evaluation; (v) institutional arrangements for decision-making and policy implementation; (vi) description of actual responsibilities of the various levels of governments present in the territory; (vii) description and analysis of public services delivered by the various levels of government in the territory; and (viii) analysis of local community participation in setting investment priorities and monitoring government actions. Three consultants will be hired to undertake this work and assist in drafting a proposal for the design of this component for the loan operation.

    - Support for Local Communities ($65, 650)

  - The objective of this sub-component is to assist with the design of the loan operation by strengthening local Indigenous and non-Indigenous communities leaders and institutions including regional representative organizations. All activities undertaken in this sub-component will be highly participatory and will focus on building leadership and negotiation skills within a context of participatory planning in order to ensure the participation of these communities in project-related decisionmaking and priority setting. Activities to be supported by this sub-component will include: i) an assessment of local development initiatives that have already been undertaken and identification of any gaps or needs; ii) strengthening regional networks among Indigenous and non-Indigenous communities and local governments and supporting the work of the Management Committee of the Lower Urubamba (CGBU); iii) participatory planning process to prioritize development needs and prepare this component for the loan operation; iv) creation of a communications plan to increase awareness and information sharing among Indigenous and non-Indigenous communities, leaders and institutions including regional representative organizations; and v) presentation of the results of the sub-component including recommendations for the loan operation to a multistakeholder meeting called for this purpose.

    - Pilots and early implementation of socio-economic development and environmental planning interventions ($280,000)

  - This sub-component will finance pilots and early stage implementation of socio-economic development projects and environmental management in key communities in the Lower Urubamba including: equipment for schools and health centers; improving access to clean water, sanitation and electrification; technical assistance and start-up support for small-scale productive projects; feasibility study on appropriate connectivity technology etc. The objective is to pilot several social and economic development projects before they are scaled up in the loan operation as well as build trust between the government and the communities and increase visibility of the project. Eligible communities will be identified during the Stakeholder’s Meeting scheduled for February 2007 and will represent a geographical and socio-economic balance in the region. It is anticipated that no less than 3 pilots and/or early interventions in each of the identified areas will be implemented.

  - Component 2 – Project administration ($148,000)

  - This component will finance project administration costs including a Project Coordinator, dissemination of awareness building of the activities related to the project and issues relevant in the region as well as the costs of auditing the project.

- Cost and financing

  - The total cost of this operation is US$940,000, with financing from the Japan Special Fund (JSF) in the amount of US$750,000 and US$190,000 in local counterpart funds from the PCM. Below is a preliminary budget for the proposed operation. A more detailed budget is provided as Annex A.

| Component | JSF | Local | Total | Total (%) |
| --- | --- | --- | --- | --- |
| Component 1: Socio-economic development and environmental management | $635,950 | $140,000 | $ 775,950 | 84.8% |
| 1.1 Design of socio-economic development interventions | $132,650 | $50,000 | $182,650 |  |
| 1.2 Environmental management | $65,650 | $10,000 | $75,650 |  |
| 1.3 Support for Local Governments | $65,650 | $10,000 | $75,650 |  |
| 1.4 Support for Local Communities | $92,000 | $20,000 | $112,000 |  |
| 1.5 Pilots and early implementation | $280,000 | $50,000 | $330,000 |  |
| Component 2: Project administration and dissemination | $98,000 | $ 50,000 | $ 148,000 | 13.1% |
| 3.1 Contingencies | $16,050 | $ - | $16,050 | 2.1% |
| GRAND TOTAL | $750,000 | $190,000 | $ 940,000 | 100% |
|  | 80% | 20% |  |  |

- Project execution and Administration

  - The project will have an execution period of 12 months and a disbursement period of 18 months. The beneficiary of this technical cooperation operation will be the Presidencia del Consejo de Ministros (PCM). The PCM was designated by the Government of Peru as the entity responsible for the coordination of the overall implementation of the Sustainable Development of the Lower Urubamba Program (PE-L1021) including this technical cooperation.

- Project Risks

  - The project team has not identified any serious technical or political risks for the preparation or execution of the proposed technical cooperation. They are, however, mindful of the extreme geographical isolation and overall low capacity characteristic in this region which will be taken into consideration when designing the activities, Terms of Reference and components for both the technical cooperation as well as the loan operation.

- Action Plan

  - The action plan for preparing the proposed technical cooperation operation is summarized in the following table:

| - TC operation profile submitted to JSF | - Green light from JSF | - Plan of Operations | - Approval of TC operation |
| --- | --- | --- | --- |
| - December 2006 | - February 2007 | - March 2007 | - April 2007 |

  - An orientation mission to prepare the Plan of Operations for the TC is scheduled to be carried out between February and March 2007 in conjunction with the Stakeholder Meeting also anticipated for this time. The project team is anticipating that the results of the Stakeholder Meeting will provide the primary inputs for the Project Profile and will greatly contribute to further defining the scope of the studies and the eligible communities for the pilot projects that will be undertaken as part of this technical cooperation project.

- Environmental and Social Strategy

  - This technical cooperation is not expected to have any significant negative environmental or social impacts. On the contrary, it will help prepare an environmental and social strategy for the loan operation which is consistent with the Bank’s Indigenous Peoples Policy and Environment Policy and which will focus on improving the quality of life for extremely vulnerable populations within a sustainable environmental context perspective.

- Annex A: Preliminary detailed budget

| Component/Activity | Unit cost | Quantity | JSF | Local | TOTAL | % |
| --- | --- | --- | --- | --- | --- | --- |
| Component 1: Socio-economic development and environmental management |  |  |  |  |  |  |
| 1.1 Design of socio-economic development interventions |  |  |  |  |  |  |
| Rapid basic social investment assessments | $3,000 | 12 | $36,000 |  | $36,000 |  |
| Participatory consultation expert | $2,000 | 5 | $10,000 |  | $10,000 |  |
| Electrification and connectivity analysis | $5,000 | 12 | $60,000 |  | $60,000 |  |
| Travels and per-diem | $26,650 | 1 | $26,650 |  | $26,650 |  |
| Total |  |  | $132,650 | $50,000 | $182,650 |  |
| 1.2 Environmental management |  |  |  |  |  |  |
| Environmental assessment expert | $5,000 | 9 | $45,000 |  | $45,000 |  |
| Travels and per-diem | $20,650 | 1 | $20,650 |  | $20,650 |  |
| Total |  |  | $65,650 | $10,000 | $75,650 |  |
| 1.3 Support for Local Governments |  |  |  |  |  |  |
| Institutional capacity assessment expert | $5,000 | 9 | $45,000 |  | $45,000 |  |
| Travels and per-diem | $20,650 | 1 | $20,650 |  | $20,650 |  |
| Total |  |  | $65,650 | $10,000 | $75,650 |  |
| 1.4 Support for Local Communities |  |  |  |  |  |  |
| Community development expert | $3,000 | 12 | $36,000 |  | $36,000 |  |
| Outreach and participation expert | $2,000 | 4 | $8,000 |  | $8,000 |  |
| Costs for workshops, logistic and materials | $48,000 | 1 | $48,000 |  | $48,000 |  |
| Total |  |  | $92,000 | $20,000 | $112,000 |  |
| 1.5 Pilots and early implementation |  |  |  |  |  |  |
| Pilot implementation of basic social services enhancement | $30,000 | 4 | $120,000 |  | $120,000 |  |
| Pilot implementation of electrification and connectivity | $40,000 | 4 | $160,000 |  | $160,000 |  |
| Total |  |  | $280,000 | $50,000 | $330,000 |  |
| Total Component 1 |  |  | $635,950 | $140,000 | $775,950 | 85% |
| Component 2: Project administration and dissemination |  |  |  |  |  |  |
| 2.1 Administration |  |  |  |  |  |  |
| Project Coordinator | $4,000 | 12 | $48,000 | $0 | $48,000 |  |
| Project Assistant | $2,500 | 12 | $30,000 | $0 | $30,000 |  |
| Office costs | $50,000 | 1 |  | $50,000 | $50,000 |  |
| Total |  |  | $78,000 | $50,000 | $128,000 |  |
| 2.2 Auditing | $10,000 | 1 | $10,000 |  | $10,000 |  |
| 2.3 Dissemination and promotion activities | $10,000 | 1 | $10,000 |  | $10,000 |  |
| Total Component 2 |  |  | $98,000 | $50,000 | $148,000 | 13% |
| 3.1 Contingencies | $16,050 | 1 | $16,050 | $0 | $16,050 | 2.1% |
| GRAND TOTAL |  |  | $750,000 | $190,000 | $940,000 |  |
|  |  |  | 80% | 20% |  |  |

2001 estimate included in the Development Plan for the Lower Urubamba 2002-2006 (June 2002).

See “Canon Gasífero en la provincial de La Convención-Proyecto Camisea”. Centro de Análisis y Resolución de Conflictos, Pontifica Universidad Católica del Peru. October 2005.