Document of the Inter-American Development Bank

Guyana

Enhancing the National Quality Infrastructure for Economic Diversification and Trade Promotion

(GY-L1059)

Draft Operating Manual

This document was prepared by the project team consisting of: Claudia Stevenson (IFD/CTI); Team Leader

TABLE OF CONTENTS

CHAPTER 1: INTRODUCTION								1-10

1.1 Objectives and Scope of the Operations Manual					1-2

1.2 Definitions										2-3

1.3 Introduction										4

1.4 Background										4-10

1.5 Operation Manual’s Use, Duration and Modification					10

CHAPTER 2: PROJECT DESCRIPTION AND BUDGETED COST			11-17

2.1 Project’s Objectives									11

2.2 Project’s Components								11-15

2.3 Expected Outcomes									16

2.4 Cost Structure									16

2.5 Project Duration & Sustainability							17

CHAPTER 3: INSTITUTIONAL FRAMEWORK FOR EXECUTION OF THE 
COMPONENTS										18-34

3.1 Project Management								18

3.2 Organizational Structure								18

3.3 Designation of Signature of Officials							20

3.4 Governance Structure								20-21

3.5 Institutional Roles and Responsibilities						25-29

3.6 Coordination Arrangements								29-30

3.7 Monitoring and Evaluation								31

3.8 Reporting										32-33

3.9 Special Contractual Conditions for the First Disbursement and Execution		33

3.10 Communication Strategy								33

3.11 Correspondence									34

3.12 Project E-Mail Account								34

3.13 Document Management								34

CHAPTER 4: THE CYCLE FOR ACTIVITIES AND WORK				35

4.1 Background										35

4.2 Bidding and Contracting								35

CHAPTER 5: FINANCIAL MANAGEMENT AND DISBURSEMENT			36-49

5.1 Organization of the financial management function					36-37

5.2 Accounting and Information System							37-39

5.3 Annual Audit									39

5.4 Maintaining Records									40

5.5 Exchange Rate									40

5.6 Framework of the Financial Management System					40-43

5.7 Chart of Accounts									43-44

5.8 Bank, Reconciliation, Payments and Deposits					44-46

5.9 Accounts Payable									47-48

5.10 Monthly Reports									48

5.11 Audit										49

5.12 Asset Register									49

CHAPTER 6: PROCUREMENT OF WORKS, GOODS AND SERVICES POLICIES AND PROCEDURES										50-54

6.1 Procurement Description								50

6.2 Procurement Plan									50

6.3 Procurement Methods								50-53

6.4 Advertising of Procurement Processes						53

6.5 Selection and Contracting of Consulting Services					53

6.6 Procurement Monitoring and Evaluation						54

6.7 Obligations for Beneficiaries and Consultants					54

CHAPTER 7: REPORTING, MONITORING AND EVALUATION				55

7.1 Reporting										55

7.2 Summary of IDB Reporting Requirements						55

7.3 Monitoring										55-57

7.4 Indicators										58

7.5 Evaluation										58

7.6 Auditing										59

7.7 Budget Performance								59

ANNEXES										60

Annex I: Terms of Reference for Program Manager					60-63

Annex II: Policy Matrix

Annex III: Results Matrix

Annex IV: Detailed Budget

Annex V: Monitoring and Evaluation Plan

Annex VI: Procurement Plan

List of Tables

Table 1.1: Description of Contents of the Organizational Manual				2

Table 2.1: Budget Table (in million US$)							16

Table 3.1: Overview of Staff Requirements						23-25

Table 3.2: Reporting Requirements to the Relevant Agencies				32-33

List of Figures

Figure 1: MOB’s Organizational Structure						19

Figure 2: Project Execution Arrangements						22

Figure 5.1: Process Flow of Fiduciary Management of IDB Loan Funds			42

List of Acronyms

| Acronyms | Expanded Forms |
| --- | --- |
| AOP | Annual Operation Plan |
| CBGY | Central Bank of Guyana |
| CQS | Selection Based on Consultants’ Qualifications |
| CROSQ | CARICOM Regional Organization for Standards and Quality |
| CS | Country Strategy |
| EA | Executing Agency |
| EDB | Economic Development Board |
| EOIs | Expressions of Interest |
| EU | European Union |
| FS | Financial Specialist |
| FBS | Fixed Budget Selection |
| GDP | Gross Domestic Product |
| GNBS | Guyana National Bureau of Standards |
| GOG | Government of the Republic of Guyana |
| GO-Invest | Guyana Office for Investment |
| GPN | General Procurement Notice |
| ICB | International Competitive Bidding |
| ICT | Information & Communications Technology |
| IDB | Inter-American Development Bank |
| IFRS | Internal Financial and Reporting Standards |
| LAC | Latin America and the Caribbean |
| LCS | Least-Cost Selection |
| LIB | Limited International Bidding |
| M&E | Monitoring and Evaluation |
| MIF | Multilateral Investment Fund |
| MoA | Ministry of Agriculture |
| MoB | Ministry of Business |
| MoF | Ministry of Finance |
| MoH | Ministry of Health |
| NARE | National Agricultural Research and Extension Institute |
| NCB | National Competitive Bidding |
| NPTB | National Procurement Tender Board |
| NQI | National Quality Infrastructure |
| OC | Ordinary Capital |
| OM | Operations Manual |
| PA | Project Administrator |
| PAS | Principal Assistant Secretary |
| PC | Shopping or Price Comparison |
| PEU | Project Execution Unit |
| PM | Program Manager |
| PMR | Project Monitoring Report |
| PP | Procurement Plan |
| PS | Permanent Secretary |
| PSAR | Private Sector Assessment Report |
| QBS | Quality-Based Selection |
| QCBS | Quality-and-Cost-Based Selection |
| SEPA | Procurement Plan Execution System (Sistema de Ejecución de Planes de Adquisiciones) |
| SMEs | Small and Medium-sized Enterprises |
| SOP | Standard Operating Procedures |
| SPN | Specific Procurement Notices |
| SPS | Sanitary and Phytosanitary Measures |
| SSS | Single Source Selection |
| WEF | World Economic Forum |
| WTO | World Trade Organization |

CHAPTER 1

INTRODUCTION

1.1 Objectives & Scope of the Operations Manual

This Operations Manual establishes and regulate the way the “Program enhance the National Quality Infrastructure (NQI) for economic diversification and trade promotion” will operate, by providing guidelines that will support the:

- Achievement of program objectives;

- Maximization of efficiency in the use of program resources; and

- Maximization flexibility and transparency in program management.

The Operations Manual is also intended to help:

- Achieve adequate coordination between the Project Execution Unit (PEU) and the two implementing entities participating in the program;

- Ensure that execution structure and project oversight are appropriate for project design and implementation;

- Ensure program sustainability once the Bank’s financial support has ended.

The scope of this Operations Manual (OM) is, therefore, to define the administrative, institutional and technical framework of the Project and the level of responsibilities of the institutions involved in its implementation, in order to achieve the objectives defined in the Annex of the Contract for Enhancing the National Quality Infrastructure for Economic Diversification and Trade Promotion between the IDB and the Republic of Guyana.

The OM is structured as outlined in Table 1.1.

Table 1.1: Description of the Contents of the OM

| CHAPTERS | DESCRIPTION |
| --- | --- |
| Chapter 1 | Introduces the document |
| Chapter 2 | Presents the conceptual framework and the cost structure of the Project, as well as the description of its components |
| Chapter 3 | Outlines the overview of the institutional and administrative framework, defining the organizational execution scheme and the roles and responsibilities of the Executing Agency |
| Chapter 4 | Describes the project cycle, inclusive of the works and activities |
| Chapter 5 | Gives details on the financial procedures for the Project’s execution |
| Chapter 6 | Describes the policies and procedures for the procurement of Goods and Works and for the Selection and Contracting of Consultants |
| Chapter 7 | Outlines the Project’s reporting requirements in addition to the monitoring, evaluation and auditing mechanisms |

### 1.2 Relevant Definitions

The program will use the following definitions:

    - SMEs: Small and medium-sized Guyanese enterprises that directly employ up to 100 workers and of whom 95.3% hire 15 or less persons.

    - Entity responsible for the program: Ministry of Business (MOB), tasked with program management.

    - Beneficiaries: Main – Guyana National Bureau of Standards (GNBS) and Guyana Office for Investment (GO-Invest); and other strategic members of the NQI such as MoA, through the National Agricultural Research and Extension Institute (NAREI) and the MoH, through the Food and Drug Department.

    - Institutional Capacity Assessment: Activities undertaken to evaluate the readiness and capacity of executing and implementing agencies to execute and to identify levels of development and associated risk to project execution using Bank standard tool.

    - Project preparation: Activities undertaken to prepare and present a project for program financing. These should be in accordance with the results of various project preparation inputs, including the ICAS, Development Effectiveness Matrix (DEM), the Environmental and Social Management Report (ESMR), the Gaps and Needs Assessment and the Analysis of Project Cost and Economic Viability.

    - Project implementation: Execution of projects participating in the program.

    - Project monitoring: Activities to permanently monitor and evaluate implementation of the project’s objectives.

    - National Consultants Register: Database containing information on consultants (both national and international) that have expertise in various business competitiveness issues. This program will only help finance consulting services involving consultants chosen from this register, which will be administered by GO -INVEST.

    - National Standards Council: agency established in section 6 of the GNBS Act to govern the GNBS and which is appointed by the responsible Minister.

    - National Quality Infrastructure (NQI): the ecosystem that supports the development, adoption and compliance of standards to promote product quality which is comprised of the institutions, norms, and regulations, metrology and testing infrastructure and public and private stakeholders that develop, supervise or adopt quality standards

    - Project executing unit: Professional and technical team responsible for program management.

    - Program Manager: Executive who directs the project executing unit.

    - Project Steering Committee: advisory and oversight body convened to provide strategic leadership and management of the project and to whom the Program Manager is accountable for project outcomes.

1.3 Introduction

This OM establishes the policies and procedures to be applied during the execution of the Project “Enhancing the National Quality Infrastructure for Economic Diversification and Trade Promotion (hereafter referred to as “the Project”) financed by the Inter-American Development Bank (hereafter referred to as “the Bank”) pursuant to a Loan Contract (the “Contract”) signed on (insert date of loan contract).

The total cost for the Project is US$9 million, 50% of which will be drawn from the Bank’s Ordinary Capital resources (OC) and the remainder from FSP. The Borrower for the operation is the Republic of Guyana.  The Executing Agency (EA) is the Ministry of Business (MOB) through the Project Execution Unit (PEU), responsible for the overall administration of the proposed operation, including planning, budgeting, and implementation.

  - Background

    - Guyana experienced a 4.5% average economic growth during 2009-2014 primarily due to the expansion of mining and agricultural exports and to the high prices of commodities such as gold. However, in 2015, as the price of international commodities declined, economic growth slowed to 1.6% highlighting the vulnerability of the economy to its high concentration in few sectors. Services (59.7%), Agriculture/Agro-processing (18.1%) and Mining (20.3%) together make up more than 90% of Guyana’s Gross Domestic Product (GDP).

    - Guyana’s private sector is small and fragmented consisting of mainly micro, small, and medium-sized enterprises with a few large enterprises operating in the extractive industries. “As of October 2013 the Small Business Bureau’s database included 6,756 businesses, of which about 2,500 had been validated as active businesses (About 73% of registered businesses in Guyana employ fewer than five people, while 22.3% employ 5-15 people and 4.7% employ more than 15. Most firms sell their goods and services only in the domestic market, with only 15% reporting that they sell to the Caribbean region and a mere 3.8% selling beyond the Caribbean”.

    - Guyana’s has a relatively small local market and growth is dependent on export to the competitive export market. 82% of Guyana exports products are concentrated in less than 10 products, mainly within the mineral and agricultural sectors where 45% of exports were attributed to gold, 18% to rice, 6.6% to raw sugar and 3.5% to crustaceans.,  As the production cost of rice and sugar in Guyana makes it hard to compete with other countries, there is a strong need to diversify exports in other agricultural products. Even though Guyana has a strong advantage as a supplier of agricultural products in the Caribbean region and in other markets, non-traditional exports, including fresh produce and agro-processed goods, have only amounted to 0.6% of all exports in average during the 2011-2014 periods. (see Economic and Export Diversification). Guyana’s exports are concentrated, as five countries make up approximately 63% of its export market.,  . Most firms sell their goods and services only to the domestic market, with 15% reporting that they sell to the Caribbean region and 3.8% selling beyond the Caribbean. Access to international markets, product development and industrial upgrading of Small and Medium Sized Enterprises (SMEs) depend on the adoption of quality standards.

    - There is a growing consensus that patterns of economic development is associated with structural change in exports and increased export diversification. Diversification of exports by transitioning into non-traditional, high productivity, and more knowledge-intense areas may assist Guyana in competing in more value added products and services. Economic diversification, including export diversification, requires a supportive and complementary NQI system. Access to existing and new markets require compliance, in most cases mandatory, with technical requirements that are standards-based and include: food safety, good agricultural practices, good manufacturing practices, quality standards, animal health, plant health, environmental, social, safety, information security, efficiency and certification standards. This requires a quality infrastructure with laboratories that are able to generate precise and accurate results.

    - Guyana’s National Competitiveness Strategy, states the need for economic diversification. The Government has listed the following sectors as key diversification and growth opportunities: (i) Agriculture/Agro-processing; (ii) Forestry; (iii) Mining; (iv) Manufacturing; (v) energy; (vi) tourism; and (vii) information technology and services. Guyana’s private sector is small and fragmented consisting of mainly micro, small, and medium-sized enterprises with a few large enterprises operating in the extractive industries.

    - A National Quality Infrastructure (NQI) is the ecosystem that supports the development, adoption and compliance of standards to promote product quality. It is comprised of the institutions, norms, and regulations, metrology and testing infrastructure and public and private stakeholders that develop, supervise or adopt quality standards. (see Schematic representation of a NQI) In order to facilitate economic diversification in the local and external markets and provide recognition for the Guyanese brand in the international markets, there is a need to modernize the NQI in Guyana. The main institution involved in the NQI, related to export promotion in Guyana is the Ministry of Business (MoB), who has responsibility over the Guyana National Bureau of Standards (GNBS) and Go-Invest (Guyana Office for Investment). The GNBS is the agency responsible for developing national standards and is governed by a National Standards Council, whose members are appointed by the Minister of Business (Chambers of Commerce, the University of Guyana, the Guyana Manufacturers’ Association, Regulatory bodies, etc.). Go-Invest, the Ministry of Agriculture (MoA) and the Ministry of Health (MoH) play an important role in Guyana NQI. The MoA, through the National Agricultural Research and Extension Institute (NAREI) is Guyana's Sanitary and Phytosanitary Measures (SPS) enquiry point and national notification authority to the World Trade Organization. The MoH through the Food and Drug Department has the overall responsibility for issues relating to human health, including food for human consumption and cosmetics. Go-Invest is the agency that promotes and facilitates local and foreign private-sector investment an exports. (see Guyana NQI – Ministries and Agencies).

    - Rationale for intervention and main challenges to be addressed. In an increased global economy, with integrated production and consumer networks, countries need to offer high quality products and to deliver them in a timely manner. The prior requires quality standards and modern accredited testing facilities. Recent studies show that services provided by a NQI are necessary for economic growth, diversification and targeting new markets. In the case of Guyana, the production and trading of goods and services face a number of non-compliance risks in both the local and export markets with significant impact on competitiveness such as: (i) rejection of products at border inspection point; (ii) increased costs due to delays while inspections/test are being done in overseas laboratories; (iii) disruptions in trade, loss or inability to expand into new market; (iv) loss of revenue where inaccurate measurements and test results are used; and (v) inability to command premium price where quality and safety products are not defined. Guyana’s Unit Rejection Rate in the United States market in the 2012 Report was 0.2 per million dollars of export, higher than the average of countries with similar income and is not competitive when compared with the two larger exporters (Jamaica and Trinidad and Tobago) of food from CARICOM to these markets. On the other hand, SMEs in Guyana often lack the knowledge, expertise, and resources to adopt and implement high quality and standards.

    - Guyana does not have a fully developed NQI. The GNBS has the responsibility for standardization which entails a process of formulation and application of standards, technical regulations, conformity assessment procedures and metrology. However, the laboratory facilities of the GNBS are not adequate for performing their role as the central body for developing, promoting and verifying conformity on the adoption of standards as the appropriate metrology, calibration and testing require controlled environments in terms of temperature, humidity, and vibration, among others. The GNBS needs to boost its capacity to support the ecosystem of the NQI by providing the platform for producing competitive goods and services, including the provision of services for testing needs of the exporters (particularly non-traditional exporters and SMEs) to comply with the required standards for internal and external markets. Depending on the product and the market, exporters must comply with standards often established by a large company, or by an organization representing a particular interest (i.e. Fair Trade) or by the Organization for Standardization. In addition, there are mandatory technical regulations such as the ones established by the World Trade Organization. Exporters, in particular SMEs, must use testing services from accredited laboratories in order to acquire the required certifications.,

    - The current laboratories infrastructure and equipment are not adequate for supporting exports or protecting local consumers and the environment. The current laboratory facilities and equipment of the GNBS have severe limitations in terms of space and environmental conditions. Without the proper GNBS infrastructure, all the other laboratories in the system face challenges for accreditation and compliance with conformity. The state of the current laboratory infrastructure is inadequate to allow the GNBS to perform its role as the sector entity that verifies conformity with the adoption of standards with the aim of supporting economic diversification and exports. The provision of services in a more adequate and modern facility will contribute to a more effective and efficient operation of the entire NQI contributing to the achievement of the expected outcomes. The main limitations and gaps of the GNBS laboratories in the system are: (i) unsuitable laboratory facilities, lacking the proper physical conditions to assure reliability; (ii) absence of a laboratory facility to perform tests for consumer protection and for dynamic sectors; (iii) limited calibration capacity in terms of capacity in temperature, moisture, pressure, force, volume and electricity; (iv) lack of adequate equipment and consumables; (v) outdated test methods that no longer meet the needs for the industry requirements; (vi) lack of accreditation and participation in proficiency testing programs; and (vii) insufficient trained staff for performing tests and calibrations and maintenance of the equipment. In addition, asymmetries within the existing laboratories in terms of physical and testing capacity, human resources and information cause an inefficient use of the existing resources.

    - Need to implement an export and investment strategy. The Government of Guyana is pursuing economic diversification, focusing on boosting the more dynamic sectors of Guyana’s economy, in particular: (i) agriculture/agro processing, (ii) forestry, (iii) mining, and (iv) manufacturing. In addition, the government is implementing specific policies to accelerate the development of non-traditional agriculture and non-traditional exports. There is a need to develop further strategic planning in the area of export promotion and investment attraction.

    - Government strategy, priorities and actions. Considering the modernization of traditional sectors such as sugar, rice, forestry, and mining, the MoB has been carrying out actions to support economic diversification and productivity, value added and export readiness, and supporting new growth and diversification in new sectors (specifically in non-traditional agriculture, aquaculture, business process outsourcing/ information technology, and tourism) all encapsulated under a socially and environmentally sustainable framework. Due to the size of the economy, economic diversification actions entail accessing new markets for non-traditional products.

    - Justification. In an increased global economy, with integrated production and consumer networks, countries need to offer high quality products and to deliver them in a timely manner. The prior requires quality, standards and modern accredited testing facilities. Recent studies show that services provided by a NQI are necessary for economic growth, diversification and targeting new markets. In the case of Guyana, due to size of the economy and the local market, economic diversification needs to be encompassed with an effort to access new markets with new products. SMEs in developing countries often lack the knowledge, expertise, and resources to adopt and implement high quality and standards, and thus limit their capacity to grow and access new markets.

    - The modernization of the NQI includes streamlining and implementing procedures for certification, accreditation and conformity, improving the laboratory facilities of the GNBS for metrology, calibration and testing as well as providing support to the main laboratories related to the export/import processes under the MoA and MoH. The modernization of the NQI should also be accompanied by actions to promote export and investment, to boost the participation of domestic firms in international markets, and to encourage actions that promote the adoption of a culture of quality in producers and exporters. In addition, actions to make a more efficient use of the existing resources in the different laboratories of the NQI, share best practices and collaborate will be fostered through a network of laboratories.

1.5 Operation Manual Use, Duration and Modification

The OM is a key requirement in the implementation of the Project and will provide guidance for the achievement of the agreed objectives during the Project’s execution period. The OM will be subject to an annual review by the Program Manager, subject to change based on mutual agreement of the MoB and the Bank. Any modifications to the OM identified as a consequence of Project implementation will have to receive the approval of representatives of the MoB and with the prior non-objection of the Bank.

CHAPTER 2

PROJECT DESCRIPTION AND BUDGETED COST

  - Project Objectives

    - The program's main objective is to support economic diversification and exports through the enhancement of the NQI and through a National Export and Investment Promotion Strategy.

      - Specific objective 1 is to enhance the capacity of the NQI;

      - Specific objective 2 is to improve facilities for the NQI; and

      - Specific objective 3 is to enhance the capability of export and investment promotion.

    - The project will also help to transform the practice of quality standards by supporting and promoting export activity under a modern framework, in which the technical and physical capacity of the NQI, in particular the GNBS, will be brought to a level commensurate to best international practices.

    - In addition, the project will allow the country to be able to respond in a more cost effective manner to the requirements of the new international markets.

    - The Gaps and Needs assessment recommended a state of the art laboratory (SAL); however, the approach proposed is to develop a network with the current laboratories in order to promote the most efficient use of resources

To achieve these objectives, the Project will be implemented through three Project components as follows:

  - Program Components

    - To achieve the proposed objectives, the program has been divided into three components:

      - Modernize the Institutional Framework for the NQI

      - Improving Laboratory Facilities and Equipment

      - Implementing the National Export and Investment Strategy

      - Modernize the Institutional Framework for the NQI (US$1,030,000)

        - The component will support the capacity building of the stakeholders of the NQI, in particular the GNBS, in strengthening the areas of technical regulations, compliance, conformity, accreditation and training, and capacity building of public and private stakeholders.

        - The governance structure of the NQI will be streamlined to include the needs of private sector with priority given to non-traditional exporters and a network of laboratories will be created in order to promote the most efficient use of the current facilities.

        - In addition, the network of laboratories under the GNBS will create a monitoring and evaluation system, in which data of the users of the NQI will be collected. This component will finance:

- activities to support the accreditation process of existing laboratories with best practices and international standards, along with the required processes;

- training and capacity building for laboratories in the network and for the GNBS including the awareness campaigns for stakeholders;

- creation and operation of a network of laboratories; including awareness and sensitization workshops, data collection regarding the services, equipment and status of all laboratories in the network and the operation of the network as well the development of a website in which information can be shared among the participants of the network. The Ministry of Business (through the GNBS) will use the information generated and the website to promote collaboration between laboratories, better use of existing resources and interventions that are better tailored to the needs of the existing labs;

- capacity building activities on SMEs and standards in order to promote a quality culture among the private sector;

- the development of a strategic plan for the GNBS that aligns with both the regional and national policy framework and allows for a more efficient management of the facilities and that incorporated the required mechanism to promote sustainability of the NQI; and

- awareness campaigns on the use of standards and quality among public and private stakeholders of the NQI

        - The expected outcomes from this component are as follows:

- A network of laboratories that are compatible with regional and NQI standards;

- A GNBS Strategic NQI Plan; and

- Enhanced awareness within the public and private sectors on NQI standards;

      - Improving Laboratory Facilities and Equipment (US$5,960,000)

        - This component will help to improve facilities for the NQI. In this regard this component will finance new facilities to house metrology, testing, chemistry and microbiology, and legal metrology, the required equipment for the adequate functioning of the GNBS as well as specific support to the main laboratories related to the export/import processes under the MoH and MoB.

        - Additional requirements, derived from quality value chain analysis that will be conducted on selected sectors and the quality bottlenecks, as part of the activities of Component III will be addressed by this component as well.

        - To ensure the sustainability of the facilities, a business plan for cost recovery through phases and a long term operation, and a maintenance plan will be developed.

        - This component will finance, specifically:

- detailed architecture and engineering designs of the new laboratory facility for the GNBS, including “green building” provisions;

- building of the new facility; consisting of an 1,800 sq. ft. two story building allocated in government owned land. This facility will be built according to international metrology and testing standards as well as with the “green building” standards that are currently being developed in Guyana;

- required equipment for measurement metrology and testing including equipment for small Mass Laboratory, large mass laboratory, humidity and temperature volume, time and frequency, electrical magnitude, length, strength and torque, physics and chemistry. (See detailed budget);

- maintenance contracts to guarantee the long term maintenance of the specialized equipment; and

- specific gaps in other laboratories, consisting of specific equipment for the export related activities in the Ministry of Health and the Ministry of Agriculture.

        - Products expected from this component:

- Engineering and architectural designs for the new GNBS laboratory;

- A completed laboratory fully equipped with modern NQI equipment and technology; and

- Specialized equipment for MoH and MoA labs to address gaps

      - Implementing the National Export and Investment Strategy (US$1,069,285)

        - In order to enhance the capability of export and investment promotion, this component will support:

- technical assistance to design and implement a trade and investment promotion strategy, including mapping major value chains; and

- technical assistance for the strengthening of Go-Invest and its ability to promote exports and attract foreign direct investment, especially in the sectors that will need the operation of modern certified lab facilities that are required for accessing international markets.

        - Products expected from this component:

- A National Export and Investment Strategy inclusive of mapping of value chains; and

- Strengthened capacity of GO-Invest to promote exports and attract foreign direct investment in the areas that will benefit from or are complementary to a modern NQI.

      - Results evaluation and dissemination

        - This activity emphasizes evaluation of project progress under each component. A financial audit will also be conducted.

        - The activities to be undertaken are:

- Project evaluation: Two program evaluations will be performed: the first, midway through implementation, to analyze progress and make any corrections that are needed; and the second, at the end of the program, to measure and disseminate results and whether a successor project is warranted. Both evaluations need to be conducted by an external consultant.

- Results dissemination: A seminar will be held to publicize the overall results of the project and the specific progress achieved by each of the projects implemented through it. This seminar should be organized by the program executing unit, no later than 36 months after the start of the program. The seminar would be attended by the highest authorities of the institutions participating in the National Standards Council, and the country’s top-level public authorities in the economic and business area.

- Final financial audit for program closure.

        - Products expected under Results evaluation and dissemination are:

- Two evaluation documents on project execution (mid-term and final).

- Project financial audit.

2.3 Expected Outcomes

The project’s expected outcomes are: (i) optimization and simplification of foreign trade and business processes required by key government agencies; (ii) reduction of time for foreign trade and business processes; and (iii) enhanced interoperability between national government institutions and with international trading partners.

2.4 Cost Structure

The total cost of the Project is US$9 million. This amount will be financed in its entirety by the Bank, through loan resources; however, this does not preclude the Borrower’s provision of additional resources to ensure the uninterrupted execution of the project. Table 2 provides a breakdown by investment category and source of financing.

- Table 2.1: Project total budget (in US$)

| Description/Source | IDB | % (IDB) |
| --- | --- | --- |
| I. DIRECT COSTS | 8,059,285 | 100.00 |
| Component 1: Modernization of the Institutional Framework of the NQI | 1,030,000 | 78.10 |
| Component 2: Improving Laboratory Facilities and Equipment | 5,960,000 | 66.22 |
| Component 3. Implement National Export and Investment Strategy | 1,069,285 | 11.88 |
| II. PROGRAM ADMINISTRATION | 605,715 | 6.73 |
| III. EXTERNAL AUDITING | 100,000 | 1.11 |
| Independent External Audits | 100,000 | 1.11 |
| IV. MONITORING AND EVALUATION | 115,000 | 1.28 |
| V. CONTINGENCIES | 120,000 | 1.33 |
| T O T A L | 9,000,000 | 100.00 |

Changes to the approved Budget are subject to the Bank’s prior approval. All requests for virements within and across budget lines must be formally submitted to the Bank for consideration and include a technical justification.

2.5 Project Duration & Sustainability

Project Duration

The Project is scheduled for implementation over a five (5) year period, effective from (insert date of loan contract). This timeline may be reduced or extended by mutual agreement of the parties to the loan contract.

Project Sustainability

Execution of this project is expected to improve the national quality infrastructure both in terms of the physical infrastructure as well as the capacity to deliver national quality standards. The project will also deliver a National Export and Investment Strategy.

Based on the success achieved under this project, it is expected that:

- Guyanese SMEs will experience a diversification of exports, especially in non-traditional sectors and that the NQI will facilitate access to non-traditional markets as well given compliance with international standards.

- The network of national laboratories will contribute to business confidence and impact positively on FDI in non-traditional sectors into which the Guyanese private sector have the opportunity to expand.

- A completed National Export and Investment Strategy, in addition to a strengthened NQI, will contribute to GDP growth driven by a growing positive trade balance and new investments that create new employment.

- There will be enhanced capacity within the Government of Guyana to execute IDB-financed projects.

CHAPTER 3

INSTITUTIONAL FRAMEWORK FOR EXECUTION OF THE COMPONENTS

3.1 Project Management

The MoB through its PEU will have overall technical and administrative responsibility for all matters relating to the project and direct responsibility for the administration of loan resources and procurement processes. The Project Steering Committee (PSC) will provide strategic direction and oversight for all matters related to the Project through the assessment and review of the Project’s operations.

3.2 Organizational Structure

The organizational structure for the MoB is delineated in Figure 1 below. This structure depicts the overarching structure in which the institutional arrangements for the project will occur.

Minister

Permanent Secretary

Confidential Secretary

Confidential Secretaries

Deputy Permanent Secretary

Department of

Commerce

Department of

Industry

Department of

Consumer Affairs

National Exhibition

Centre (NEC)

Guyana National Bureau of Standards (GNBS)

GO-Invest

Small Business

Bureau (SBB)

Personnel Department

Accounts Department

Registry

General Administration

Business Strategy & Policy

Personal Assistant

Figure 1: MoB’s Organizational Structure

Key:  Departments            Statutory bodies	 Central government administration   Support staff

- 3.3 	Designation of Official Signatories

- 3.3.1	Operations and administrative transactions

Due authority is vested in the following persons, jointly and severally in their stated areas of responsibility to act on its behalf in the capacities specified below in connection with the execution and implementation of the loan agreement, Enhancing the National Quality Infrastructure for Economic Diversification and Trade Promotion, xxxx/OC-GY and to sign any other documents, all in their responsibilities as follows:

- As to all acts relating to the execution of the loan agreement, including variation to the conditions and terms of the Letter of Agreement, which must first receive the Bank’s no-objection, any one of the following signatories:

- Rajdai Jagernauth	Permanent Secretary

- Kim Stephen		Deputy Permanent Secretary

- As to all acts relating to the execution of the loan agreement, except variations to the conditions and terms of the Letter of Agreement (any one of the following signatories):

- Rajdai Jagernauth	Permanent Secretary

- Kim Stephen		Deputy Permanent Secretary

- TBD			Programme Coordinator of Project Execution Unit

- TBD			Financial Specialist

- 3.3.2	Disbursements

In the case of signatories for the Central Bank Special Account, the following designated officials may act individually, provided that specimen signatures have already been provided to the Bank:

- Rajdai Jagernauth		Permanent Secretary

- Kim Stephen			Deputy Permanent Secretary

3.4 Governance Structure

- 3.4.1 Project Execution Unit

The PEU will be responsible for overall project administration, including planning, budgeting, accounting, procurement, monitoring and evaluation and records management; and will include the existing technical resources which will be utilized in the technical implementation of the Project. The staff of the PIU includes:

- One (1) Program Manager

- Two Component Coordinators – one for Components I and II (GNBS) and one for Component III (GO-Invest)

- 1 Project Engineer (Comp II)

- One (1) Procurement Specialist

- One (1) Financial Specialist

- One (1) Project Administrator

- One (1) Monitoring and Evaluation Specialist

The Program Manager (PM) will report directly to the PS of the MOB.  The PM will act as the liaison with the IDB.

- 3.4.2 Project Steering Committee

Strategic direction and oversight will be provided by the Project Steering Committee comprising the Permanent Secretary and ten other members as outlined in Figure 1. (ToR for PSC should be included as Annex)

The Principal Assistant (PAS) -Finance, PAS-General Administration and the Director of Business Strategy and Policy will also provide expert advice and support on all matters relating to the project’s planning, implementation and review processes. Furthermore, these key staff will review and recommend all decisions relating to procurement, financing and M&E and other related matters for the approval of the Permanent Secretary of the MOB.

Figure 2. PROJECT EXECUTION ARRANGEMENT

BUDGET AUTHORITY		   	 POLICY & STRATEGY		             PROJECT EXECUTION

MINISTER OF BUSINESS

PERMANENT SECRETARY (PS)

National Standards Council

PROJECT STEERING COMMITTEE (PSC)

GNBS & GO-Invest

Principal Assistant Secretary (PAS) - Finance

PROJECT EXECUTION UNIT (PEU)

Program Manager

Comp Coordinator & Engineer

Comp Coordinator 3

Business Strategy & Policy Unit

Monitoring & Evaluation Specialist

Financial Specialist

Designate of PAS –

General Admin)

Procurement Specialist

Note: The Project Steering Committee (PSC) consists of a minimum of eleven (11) members, including the Permanent Secretary, MoB, who is the Chair and her alternate the Deputy Permanent Secretary. The PSC includes one (1) representative each from:

- The PEU, specifically the Program Manager

- National Standards Council

- Guyana National Bureau of Standards

- GO-Invest

- Ministries of Finance, Health & Agriculture

- University of Guyana

- The Private Sector

Table 3.1: Overview of Staff Requirements

| Positions | Description |
| --- | --- |
| Program Manager | - Responsible for providing the strategic, organizational, financial and technical direction of the Project, monitoring the progress of the Project and the day to day operational management of the Project’s funds; - Plan the yearly disbursement request along with the Financial Specialist and ensure timely compliance with this; - Coordinate the timely submission of the appropriate requests to IDB for advances of funds; - When appropriate, liaises with the Ministry of Finance regarding specific financial matters; - Coordinate with stakeholders of the project, including the IDB; and - Provide information to the Permanent Secretary of the MOB regarding the progress in the financial and physical execution of the Project. |
| Component Coordinators | - Responsible for the execution of the activities under the respective components; - Direct link to the heads/CEOs of the implementing entities (GNBS and GO-Invest); - Support financial management and procurement by providing inputs to updates provided by FS and PS; - Report progress and/or risks to project execution to the PM and the implementing entities; and - Mitigate risks associated with respective components to enhance project outputs and results |
| Financial Specialist | - Responsible for the overall financial administration and control of the resources of the Project, including the effective operation of the financial reporting systems, budgeting payments and monitoring all expenditures; - Support financial management strengthening of the MOB through direct reporting and interface with the Principal Assistant Secretary - Finance; - Prepare the justification of expenses from previous disbursement, according to component activities; - Keep updated financial statements and audit reports to support disbursement requests to the Bank and to the Ministry of Finance; - Assist the Program Manager (PM) in the yearly planning of disbursement request to the Bank; - Prepare payments, reports and other documents as necessary; and - Prepare the justification of expenses from local counterpart funds. |
| Procurement Specialist | Leading the procurement function and overseeing all aspects of purchasing, negotiations, strategy, tool and process implementation for procurement related activities of the Project. The specific responsibilities are as follows: - Prepare the Annual Procurement plans and the procurement of goods, works, services and consulting services for the projects; and regular updates of the plan; - Prepare bidding documents, terms of reference and relevant documents required for the procurement of goods, works, services and consulting services; - Identify and screen procurement suppliers; - Develop the PEU’s procurement policy and strategies in conformance with established procurement procedures of the Central Government, the MoB and the IDB; - Provide advice and guidance on interpretation of procurement policy to members of the PEU Team; - In consultation with the PM and FS, establish and maintain appropriate systems for Contract Administration; - Develop and prepare regular reports on the status of contracts; - Maintain computer database for the contract management system; and - Ensure all contractual obligations are fulfilled. - Support procurement management strengthening of the MoB through direct reporting and interface with the PAS – General Administration; |
| Monitoring and Evaluation Specialist | Responsible for the establishment and management of a monitoring and evaluation system for the Project, in keeping with the Monitoring and Evaluation Plan. |
| Project Administrator | Responsible for assisting in the overall administration of this Project. This includes performing non-routine research, technical and administrative tasks related to the coordination and oversight of the Project to ensure timely and effective project development to achieve its targets. The specific responsibilities are as follows: - Assist in the collection, compilation and analysis of data relating to the project; - Assist in the Preparation of all relevant documentations for the disbursement of funds as required by the GOG and the IDB; - Collaborate with the financial specialist to prepare internal and external financial reports, including: disbursement projections, financial performance, follow up on outstanding invoices with clients and report back to consultants, prepare documents and reports required in the process of obtaining funds in accordance to the laws and regulations of the GOG; - Maintain an electronic database consisting of all relevant documentations for all areas of the loan, the procurement, monitoring and evaluation and financial function; - Assist with managing changes to project scope, cost, schedule, and quality; ensures that all changes are documented and approved; - Coordinate meeting arrangements, establish and maintain internal and external contacts as necessary; - Assist the PM in monitoring, managing and responding to project risks and issues; recommending and implementing solutions; and - Perform project post implementation activities such as soliciting feedback from stakeholders, preparing reports; inter alia. |

3.5 Institutional Roles and Responsibilities

3.5.1	Participants

The direct participants in project management will be:

- Entity in charge: The institution responsible for project management.

- Advisory body: A Project Steering Committee, inclusive of representation from the National Standards Council, tasked with supporting the entity in charge during program execution.

- Project executing unit: The professional team responsible for project coordination and management.

3.5.2	Responsibilities

Entity in charge

The Ministry of Business (MOB) will be in charge of project execution.

MOB will:

- Chair the project’s Project Steering Committee;

- Design and conduct a public tender to hire the first Program Manager;

- Provide infrastructure in its offices for the work of the project’s executing unit;

- Second staff to the project for the purpose of project sustainability;

- Participate in all project promotion and dissemination activities;

- Permanently evaluate the work of the Program Manager; and

- Maintain permanent contact with the Bank’s representatives in Guyana, to report on project management.

Advisory body

The project will be supported by a Project Steering Committee which will provide strategic direction, oversight and supervision. The Project Steering Committee (PSC) will consist of a minimum of eleven (11) members, including the Permanent Secretary, MOB, who is the Chair and her alternate the Deputy Permanent Secretary. The PSC includes one (1) representative each from:

- The PEU, specifically the Project Coordinator

- National Standards Council

- GNBS & GO-Invest

- Ministries of Finance, Health & Agriculture

- University of Guyana

- The Private Sector

Entities participating in the Project Steering Committee will each name an incumbent representative and an alternate. In the absence of the incumbent, the alternate will participate with full powers.

The Project Steering Committee will be responsible for:

- Ensure the coordination of the program’s activities with the ongoing activities and policies of the Ministry of Business and other institutions members of the PSC, including private sector.

- Supervising project progress and taking steps to ensure strategic objectives are achieved;

- Periodically reviewing fulfillment of the strategic objectives of the Program;

- Deciding upon project implementation proposals presented by the Program Manager;

- Continuously supervising and evaluating the work done by the Program Manager;

- Resolving any problem or anomaly that may arise during project execution; and

- Reviewing the mid-term and final evaluations;

3.5.3 Functions of the MoB

The specific responsibilities of the MoB will include, among others:

- Ensuring the efficient and transparent management of the resources of the Project;

- Ensuring the overall attainment of the Project’s, institutional and sectorial objectives;

- Providing the necessary inter-institutional coordination and leadership; and

- Acting as the direct counterpart of the IDB with respect to Project implementation, administration, monitoring and evaluation and reporting.

3.5.4 Functions of the PEU

Project management

The project will be managed by a Project Executing Unit, consisting of a Program Manager, a Financial Management, Procurement and Monitoring and Evaluation Specialist as well as two (2) Component Coordinators reporting directly to GNBS and GO-Invest. The executing unit, run by the Program Manager, will be functionally attached to the Permanent Secretary and the PSC, respectively, and accountable to both, individually and collectively, for the annual work programme and project results.

The Program Manager will be selected and hired through a competitive selection process. Where there is secondment, the Bank has to be satisfied and provide its no objection in addition to the Department of the Public Service’s prior approval.

The members of the executing unit will be hired for 42 months, and will work full-time on the program. It will be clearly established that they may not engage in any other activities to support institutions serving on the PSC.

The general functions of the PEU will include, inter alia, the following:

- Ensure the program’s objectives are fulfilled;

- Prepare the program's annual activities plan, including a timetable of activities for each component, the resources needed, the targets to be achieved in each activity, and the actions needed to achieve them;

- Keep an up-to-date timetable of activities for each component, report on this periodically to the public-private committee, and submit any amendments for its consideration;

- Coordinate and supervise all program activities in accordance with the timetable;

- Produce the program's budgetary statements and keep them up to date;

- Keep an up-to-date record of each project under execution (business export readiness assessments and project preparation, and project implementation);

- Propose projects for business export readiness assessments and project preparation and project implementation to the public-private committee;

- Serve as executive secretariat of the program's public-private committee;

- Visit the different projects being implemented at least four times a year, and inform the public-private committee of this in writing;

- Promote the program and disseminate its results continuously; and

- Carry out all administrative and general coordination tasks needed to implement the program.

A detailed profile of the scope of work and competencies required for the post of Program Manager are contained in Annex 1, "Terms of Reference: Program Manager”.

The specific responsibilities of the PEU will include, among others:

- Planning, including the preparation, implementation, coordination and periodic updating of the of the Project Execution Plan (PEP), Annual Operations Plan (AOP) and Procurement Plan (PP);

- Monitoring, including the preparation of technical reports, as well as progress and financial reports, and preparing variance reports of actual results against plans;

- Ensuring proper financial management, including budgeting, accounting, financial reporting, as well as the preparation of requests for advances of funds and other disbursements to the Bank;

- Ensuring appropriate and adequate financial control, including the contracting of the annual external audits of the Project, and ensuring that the approved recommendations are duly and timely implemented;

- Conducting evaluations comprising the contracting of external mid-term and final evaluations of the Project and ensuring, in collaboration with the participating entities, that the approved recommendations are effectively implemented; and

- Serving as a liaison for the Project with the Bank.

3.5.5 Functions of Stakeholders

The relevant stakeholders will be consulted throughout the Project’s duration. For the purposes of project planning, execution, monitoring, close-out and evaluation their participation in workshops will be required.

Stakeholder Management Strategy

The PEU is dedicated towards ensuring an appropriate stakeholder management strategy is developed and maintained by all members of its unit. The PEU will continuously review its stakeholders’ strategy, at least once a year to ensure stakeholders are properly managed to provide support, commitment, technical advice and other relevant assistant for the ease of execution of the project. Stakeholders will be engaged and updated through the process of the Component Coordinators, who provide direct links to GNBS and GO-Invest, as well as through the PSC.

3.6 Coordination Arrangements

3.6.1 Coordination mechanisms between PEU and the MoB

The coordination of the Project with the MOB will be facilitated through the Permanent Secretary, MoB (PS). The PM will report on the progress of the Project to the to the PS. The progress reporting should include but not be limited to issues relating to actual progress achieved as against planned, disbursement status, challenges and issues experienced with corrective actions, procurement matters and risks updates. The reporting will be done on a monthly basis.

## The FS will report to the PAS - Finance of the MoB, in meeting its reporting requirements as a project for which allocations are made annually in the Estimates of Expenditure. The FS is responsible for the preparation of:

## Monthly Status Report, Quarterly Projections;

## Semi-Annual Achievement Reports;

## Annual Draft Estimates of Expenditure; and

## any other reports/documents.

3.6.2 Coordination mechanisms between MoB and Ministry of Finance

Through the use of the standard operating procedures, the Ministry of Finance (MoF) will be notified when the request for funds are being made by the PS, MoB. The Advance for Funds Form will subsequently be forwarded to the MoF. In addition, on a monthly basis the PM will report to the MoF, through the PAS – Finance, on loan funds utilized.

3.6.4 Interaction with the Bank

The Bank will be engaged throughout the implementation of the project. The PEU would seek non-objection from the Country Office team for any modifications to project documents, procurement activities, budget transfers, or other activities requiring non-objection from the bank as outlined in the Loan Contract. The Bank will provide technical support and oversight in the operations of the project where necessary. The Bank requires the Borrower, through the PEU, to prepare and submit financial reports on a periodic basis, refer to 3.8.

3.7 Monitoring and Evaluation

The MOB, through its Director, Business Strategy and Policy in collaboration with the PEU, will be in charge of monitoring the Project’s performance and progress throughout the execution period. The Project monitoring will be based on the Results Framework (also referred as Result Matrix), the Semi-Annual Report to the IDB and the AOP. The MOB will submit two semi-annual progress reports throughout the execution of the Project to the Bank which will include semi-annual financial reports, within 60 days following the end of each semester.

A Monitoring and Evaluation Plan will be prepared by the M&E Specialist who will further guide the monitoring and evaluation activities for the Project. Overall, the MOB through its PEU will be responsible for developing the system for gathering and maintaining the data related to the various indicators included in the Results Framework, as well as for collecting and retaining updated information on the performance indicators and implementation plans. The PM will be responsible for monitoring progress against agreed baselines and assessing the continued viability of the Project.

- Using the loan’s resources, independent evaluators will be hired by MOB to conduct two Project evaluations. These evaluations are as follows:

- a Mid-term evaluation done at the end of 30 months from the date of the loan contract or after 50% commitment of the resources, whichever comes first; and

- a Final evaluation inclusive of an ex-post economic evaluation conducted after 90% of loan resources have been committed.

3.8 Reporting

MOB through the PEU will present to stakeholders a number of reports on the execution of the Project.  Table 3.2 below delineates the reporting requirements to the relevant agencies.

Table 3.2: Reporting Requirements to the Relevant Agencies

| Stakeholder | Report | Periodicity |
| --- | --- | --- |
| Bank, Focal Point, Budgets | Annual Operating Plan (inclusive of the updated Implementation Plan, Procurement Plan, Financial Plan) | Updated Annually |
| Bank, Focal Point, Budgets | Project Execution Plan | Updated as necessary |
| Bank | Project Initial Report (inclusive of AOP, updated PEP, Project Narrative and any other relevant documents) | Once |
| Bank, and PS of MoB | Semi-Annual Progress Reports (inclusive of a financial report and the outcomes and outputs achieved in the execution of the AOP, the Procurement Plan and the Project Results Matrix | Semi-Annually (Within 60 days of each semester) |
| Bank, Treasury, MoF, | Project’s audited financial statements on an annual basis | Annually (within 120 days from fiscal year end) |
| Bank | Statement of Cash Flows | Annually |
| Bank | Statement of Cumulative Investments | Annually |
| Bank | Project Management’s representation on internal control | Annually |
| PEU, MoB and, Budgets | Monthly Status Report | Monthly |
| PEU, MoB | Quarterly Projections of Expenditure | Quarterly |
| PEU, MoB, MoF | Achievement Reports | Semi-Annually |
| PEU, MoB | Estimates of Expenditure (public investments/ capital projects) | Annually |

3.9 Special Contractual Conditions for the First Disbursement and Execution

Special contractual conditions prior (prior conditions) to the first disbursement:

Project duration can be impacted by the time it takes to meet conditions precedent to first disbursement. The following are the special conditions that must be met, as expeditiously as possible.

- evidence of the creation of the project implementation unit within the MoB;

- the appointment of the project manager, the financial management specialist, the procurement specialist, and the monitoring and evaluation specialist according to professional profiles satisfactory to the Bank;

- approval of the operating manual of the program by the MoB, with the prior non-objection of the Bank; and

- presentation of an Initial Report including the updated Execution Plan, the first Annual Operation Plan and Procurement and Financial Plans.

The opening of a special bank account for the project, with the relevant signatories is also a condition that impacts on first disbursement since it must be approved by the Ministry of Finance.

Project duration can be lengthened by the process to procure goods and services. If the project is Bank-executed, these delays can be minimized as much as possible. Delays in implementation can impact project outcomes.

- 3.10 Communication Strategy

The PM will be the direct liaison with the Bank in terms of the management and operations of the project and will provide the requisite progress and status reports on the operations of all resources as outlined in the draft project execution plan. Continuous analysis of stakeholders will be undertaken as different stakeholders will join the project at different times. The PEU will analyze the various levels of project information required, the frequency and the modes of transmission.

- 3.11 Correspondence

All correspondence of the PEU will be stored electronically on the MOB’s server and physically filed in the appropriate manner by the PEU, separate from the Ministry’s general filing, in labelled cabinets that are the responsibility of the PA.

An authorized signatory must sign all official correspondence between MOB, PEU and IDB. The individuals on the list may change from time to time and such change must be communicated in writing and agreed by all the relevant parties, receiving the non-objection from the IDB.

Their designations are as follows:

| - From MoB - Permanent Secretary - Deputy Permanent Secretary | - From PEU - Program Manager - Financial Specialist |
| --- | --- |

- 3.12 Project E-Mail Account

An email account will be established on the Government’s email system for the project and will be managed by the PC.  All communication via this e-mail will be copied to the FS and dispatched to other team members as deemed necessary for the efficient operation of the programme

- 3.13 Document Management

- The PEU will establish a Document Management System for the Project. The electronic filing cabinet will provide a framework for organizing all digital and paper documents. This system will work in tandem with scanners, which convert paper documents into digital versions.

- This document management system will allow for quick access to any document or file. For better Management control, all documents will be scanned and place in this repository. The objective is to keep all the paperwork and electronic files that come into the PEU in a centralized system.  As a Risk Mitigation strategy, files in the systems will be read only and only key personnel will have access and authorization to write or modify.

- Data will be backed up to (location to be determined) and only authorized signatories, e.g. PM, FS, PS and PA will have access.

CHAPTER 4

PROJECT CYCLE FOR ACTIVITIES AND WORK

## 4.1 	Background

The Project will be executed in accordance with the AOP that will include for each programmed annual activity, its goals, terms of reference, budget, source of funding, and responsibility for its execution.

- 4.2 Bidding and Contracting

The procurement of goods, works and non-consulting services will be carried out in accordance with IDB’s procurement   Policies for the Procurement of Goods and Works Financed by the IDB (GN-2349-9) and the selection and contracting of Consulting Services will be carried out in accordance with the Policies for the Selection and Contracting of Consultants financed by the IDB (GN-2350-9).  A more detailed explanation on the requirements of the bidding and award of contracts is presented in Chapter 6 of this document.

CHAPTER 5

FINANCIAL MANAGEMENT AND DISBURSEMENT

5.1 Organization of the financial management function

As stated in the Loan Contract, the fiscal year of the Project is the period between January 1 and December 31 of each year. The MOB’s PEU has the overall responsibility for the financial management of the Project. This includes the overall management of funds and compliance with the relevant terms and conditions of the Loan Contract and the local Laws.

5.1.1 Responsibility of FS

The FS will be responsible for overall management of the financial system which includes but is not limited to:

- the development, implementation and maintenance of a financial information system acceptable to the Bank that enables financial record-keeping, budgeting as well as the generation of periodical financial statements and other reports related to the resources of the Loan and other financial sources, as the case may be;

- an internal control structure that enables efficient and effective day to day operations of the PIU allowing for the achievements of the overall objectives of the Project. The internal control system will be robust enough to minimize and detect occurrence of errors in the financial systems and non-compliance of policies and procedures;

- As indicated in the Loan Contract Section 3.02, the project funds are used to pay expenses that are:

- necessary for the Project and are in accordance with its objectives;

- carried out in accordance with the provisions of the Loan Contract and Bank Policies

- adequately recorded and documented in the Borrower’s or Executing Agency’s system; and

- Incurred after (date to be inserted) and before the expiration of the original Disbursement Period or any extensions thereof.

5.1.2 The Project Accounting Function

The Project’s accounting function falls under the purview of the PEU through the FS, reporting directly to the PM. The Project’s accounting function will maintain records of all financial transactions of the Project using the financial information system. The Project’s financial information system includes:

- Developing expenditure forecast and projections of loan drawdowns;

- Capturing all financial transactions via the use of Sage 50 Accounting Software that will generate and manage a general ledger, chart of accounts, detailed bank and expense accounts and periodic financial statements;

- Entering financial information into the General Ledger;

- Processing Payments; and

- Preparing an annual budget for the next fiscal year, detailing the budgetary provisions related to activities financed under the Project within the final quarter of each current fiscal year of the Project.

5.2 Accounting and Information System

The Accounting Software will form the backbone of the PEU`s accounting system, which will be used for recording all financial transactions under the Project to facilitate basic financial reporting. Details on the Chart of Accounts to be used by the Accounting Software (to be specified when the PEU is operational) are provided at Section 5.7 below. The PM and Financial Specialist will be responsible for the financial reporting and will be guided by the International Financial and Reporting Standards (IFRS), the Financial Regulations set out in the Exchequer and Audit Act Chap. 69:01 and by IDB’s Financial Management Guidelines, as applicable.

The FS will prepare the project’s Budget for the MOF in accordance with the Ministry of Finance’s Budget Call Circular upon request by the Principal Assistant Secretary – Finance of the MOB.

5.2.1 Authorization Process

The Principal Assistant Secretary - Finance will review and recommend for the PS’s approval all financial reports produced, drawdown requests, payment requests, queries and other financial matters.

The PS reviews and authorizes all funding requests, drawdown requests, payment requests, queries and other financial matters.

5.2.2 Disbursement Procedures

The period for final disbursement of the resources of the financing shall expire five (5) years from the effective signature date of the Loan Contract, (insert date).

All the activities related to Disbursement will follow the new IDB Project Disbursement Guide, December 2009. Resources of the Bank will only be used for eligible expenses, including goods, works and services detailed in the procurement plan and AOP and acquired according to Bank procurement policies and procedures. For the Bank to make any disbursement, the MOB through the PEU, will follow the IDB’s Disbursement Guidelines.

5.2.3 Bank Accounts and Financial Procedure

The Bank of Guyana (CBGY) will act as the depository for funds released from the Bank for the execution of this Project. An account shall be established at the CBGY to receive all Bank releases for the Project. The PEU will comply with the terms and conditions outlined by the Comptroller of Accounts upon the establishment of the Special Account at the Central Bank. The FS will perform the reconciliation of the PEU’s records with the records held by the central bank and any other financial reporting requirements.

The authorized signatories for the Bank of Guyana Account for the Investment Loan will be:

- Rajdai Jagernauth	Permanent Secretary

- Kim Stephen		Deputy Permanent Secretary

5.2.4 Roles of PEU in Financial Management

Financial Management is not solely the responsibility of the FS, but all of the PEU is involved, directly or indirectly in the financial management of the Project. The following outlines the specific financial roles of the other members of the PEU:

The Program Manager

- Along with the Financial Specialist, plan the yearly disbursement request and ensure timely compliance;

- Coordinate the timely submission of the appropriate request to IDB for advances of funds;

- Be responsible for providing the strategic, organizational, financial and technical direction of the Project, monitoring the progress of the Project and the day to day operational management of the Project’s Fund;

- When appropriate, liaise with the Ministry of Finance regarding specific financial matters; and

- Provide information to the Permanent Secretary of the MOB regarding the progress in the financial execution of the Project.

Component Coordinators

- Advise the FS on component activities with a view to identifying financial implications for disbursements and draw-downs; and

- Provide justification for any modification of financial projections

The Financial Specialist

- Prepare the justification of expenses from previous disbursement, according to the respective component’s activities;

- Responsible for the overall financial administration and control of the resources of the Project, including the effective operation of the financial reporting systems, budgeting payments and monitoring all expenditures;

- Prepare the justification of expenses from local counterpart funds;

- Keep updated financial statements and audit reports to support disbursement requests to the Bank and to the Ministry of Finance;

- Assist the PM in the yearly planning of disbursement request to the Bank; and

- Prepare payments, reports and other documents as necessary.

Procurement and Contract Management Specialists

- Responsible for leading the overall administrative processes for the contracting of works and purchases of goods, services other than consulting, and consulting services; and

- Responsible for management of all contracts.

Monitoring and Evaluation Specialist

- Responsible for the establishment and management of a monitoring and evaluation system for the Project, in keeping with the Monitoring and Evaluation Plan. This function is provided by the MOB as a “shared services” modality.

Project Administrator

- Responsible for assisting in the overall administration of this Project. This includes performing non-routine research, technical and administrative tasks related to the coordination and oversight of the Project to ensure timely and effective project development to achieve its targets

5.3 Annual Audit

Financial report audits must be conducted in accordance with international standards on auditing. The Audit Office of Guyana will carry out the external financial audit work in accordance with the content and scope established in the contract, the guidelines and the Financial Reports and External Audits Handbook for IDB-Financed Projects.

Within one hundred twenty (120) days following the closing of each fiscal year the Project’s audited financial statements, the PEU should engage the Auditor General of the Republic of Guyana to conduct an annual audit. The last audit report shall be submitted within one hundred twenty (120) days following the expiration of the Original Disbursement Period or any extensions thereof. The PEU may wish to have a Memorandum of Understanding with the Audit Office of Guyana.

5.4 Maintaining Records

For the purpose of record-keeping, the PEU will establish a records management protocol. This protocol will allow for record keeping for a minimum of 7 years. The Accounting Software, utilized solely for the Project’s financial transactions will accommodate data over a period beyond 7 years. The Software’s database and all other relevant information will be supported by the MoB’s server, which is secured through its offsite data storage facility, at the MOF (if the same that applies for IFMAS applies here).

5.5 Exchange Rate

For purposes of justification of expenses to the Bank (including reimbursements), where the project expenses have been incurred in local currency, the equivalent amount to be reported in the project currency, shall be determined using the effective exchange rate on the payment date i.e. the selling rate, without regard to the source of financing used, as published by the Bank of Guyana’s website. For month-end conversions, the average mid-point shall be used.

5.6 Framework of the Financial Management System

The following policies and procedures relate to the drawdown of the loan funds, expenditure of the loan funds on approved activities under the various components and the recording, monitoring and measuring of the respective transactions together with the respective internal controls.

These policies and procedures are designed to facilitate accurate reporting and enhance the efficiency of the operations of the PEU.

5.6.1 Drawdown of Loan Funds

The IDB will disburse funds based on the liquidity needs of the project evidenced by the current and anticipated obligations of the project. In preparation for a request for disbursement the following should initially be updated:

- AOP

- PP

- FP

- Open Purchase Order Report

These would provide evidence of the anticipated expenditure to justify the request.

Financing Conditions

Program funds will be used to finance activities from the three components and their management, including the evaluation and financial audit.

Activities and costs that can be funded with project resources include:

- procurement of advisory and consulting services, consultants and consulting firms registered in the National Consultants Register, requirement under Loan Operation 1750/SF-GY;

- Goods and services required for the new GNBS laboratory; and

- Project execution costs for staff of the PEU

- Two evaluations

- Final audit

Goods and Services Suppliers

Project funds can only be used to purchase goods or contract services that satisfy Bank criteria.

Technical assistance and consulting services will be procured from among consultants or consulting firms included in the National Consultants Register and, where capacity is not evident, external to the register, including either regionally or internationally.

5.6.2 Drawdown of loan funds from the MoF

The release of funds for the project falls under the purview of the MoF.

Prior to the beginning of the GOG’s financial year, the FS will use the latest AOP to complete the templates for the Cash-flow Statement and the Implementation Plan and submit to the Projects unit for verification and submission to Budget Division of the Ministry of Finance.

The FS will request a release of funds (subject to approval by the PS), from the MoF as required via memo to the Projects Unit which will detail the amount and respective IDB disbursement reference.

The memo will be accompanied by the completed templates for the Implementation plan and the Cash-flow Statement. The process flow is illustrated below in Figure 5.1.

Figure 5.1: Process Flow of Fiduciary Management of IDB Loan Funds

Linking Budget Call & Budget Preparation to Accounts

Project Execution Unit (PEU)

(Financial Specialist)

Submits 12-month Budget on IDB Forms (separate IDB account would be opened as a condition precedent for disbursement at Bank of Guyana, pending MOF approval)

ACCOUNTS at MOB receives the IDB General Ledger for IDB Resources and Aligned Expense Accounts which are  approved by the PS and incorporated into MOB budget as a line item and submitted to Finance

ACCOUNTS requests Funds from the IDB, pending Management’s Approval

IDB disburses funds directly to separate IDB US$/GY$ account at Central Bank (set up as a condition precedent to disbursement)

STEP 2

STEP 3

STEP 4

Linking Procurement and Expenditure Management with Records Management

PEU Procurement Specialist

Makes recommendation for expenditure to Fin Specialist with appropriate supporting documentation (completed procurement report) and Fin Specialist gets PM’s approval prior to forwarding to Accounts @ MoB

STEP 2

Accounts expenses the request in the IDB General Ledger Expense Account

STEP 3

The Accountant reviews the request and forwards to PS; if approved, the voucher system is effected

(Voucher # corresponds to check # and the Project Procurement Plan references voucher and cheque numbers)

STEP 4

Accounts issues check for expenditure/procurement activity for GY-L1059 signed by the PS or DPS

5.6.3 Methods of Disbursement:

The following are the approved method of Disbursement:

- Advance of Funds

- Reimbursement of Expenses

- Direct Payments to Third Parties

- Reimbursement under a letter of credit

The main methods to be used are items 1& 2.

5.6.4 Advance of Funds Method

The Advance of Funds method, as the name suggests, is where the funds for budgeted activities are requested in advance of carrying out the activities.

This advance is subject to a liquidity shortfall between the FP of the updated AOP and the balance in the CBGY Special Account. Based on the foregoing, an Advances Disbursement Request can be made.

This would require completion of the IDB request for Disbursement Form and signed by the authorized signatories (See 5.2.1)

In anticipation of the disbursement request the process, at 5.6.2 should be carried out to ensure that sufficient releases are available to cover the disbursement request.

5.6.5 Reimbursement of Expenses

This type of disbursement relates to the reimbursement for expenditure on approved activities under the loan, as stated in Loan Contract par. xxx.

These reimbursements are to be directly to the Consolidated Fund (Treasury Suspense Account). Consequently, they are NOT to be commingled with the IDB funds placed in the Project’s dedicated bank account at the Central Bank. The Name and Number of the Treasury Suspense Account must be included in the request.

This would require the completion of IDB Forms 6.1 and submitted to the IDB with the relevant supporting documents to justify the request for reimbursement.

In preparation for the request the process at 5.6.2 should be carried out.

5.7 Chart of Accounts

The Chart of Accounts is the description of account activities, for components and sub-components, used in the accounting/ financial management software, as stated in 5.2.

The structure is outlined below:

The number has three parts, a 4-2-3 “digit” classification. The first “4” digits reference the PEP and the description. The next “2” digits state whether the funding is IDB or counterpart funding. The final “3” digits describe the actual expenditure purpose.

5.7.1 Editing of Chart of Accounts

New account numbers can be added to the chart of accounts as deemed necessary to enhance reporting requirements, but must receive the prior approval of the IDB

Account numbers set up incorrectly or deemed inactive for a long period of time can be deleted from the chart of accounts by the FS.

5.8 Bank Reconciliation, Payments and Deposits:

Cheque Payments and Wire Transfers from the Special Account CBGY

Sources of Entry:

Cheque Register Book

A note book kept by the Financial Specialist to record incoming cheques from the CBGY, ruled as follows:

| Date | Cheque # | Payee | Received by | Identification # |
| --- | --- | --- | --- | --- |

Data Entry on Sage 50

Once an invoice is due and approved for payment, the FS will conduct relevant verification process and prepare a cheque payment or wire transfer request.

This request will contain:

- Date

- Name of Payee

- Amount & Currency

- PEP Subcomponent Reference Numbers

- Invoice Number Reference

- Banking Details (For Wire Transfer), using a Standard Form, similar to the one used by the MOF

This request will be supported by the original invoice, approved purchase order, copy of the relevant approved contract and IDB non objection.

The above document once put together will be passed to the PM for approval and submission to one of the following signatories:

- Rajdai Jagernauth	Permanent Secretary

- Kim Stephen		Deputy Permanent Secretary

The signed document will be copied and filed by the financial specialist and the original filed with a copy sent to the CBGY for processing. After processing, the CBGY will return cheque and debit advice together with relevant documentation to the PEU. The Financial Specialist will enter the cheque details into the cheque register and stamp PAID on the respective invoice and also note the cheque or wire transfer number on the invoice. The Financial Specialist will subsequently make the necessary data entry into the Accounting software and will refer to the manual for the software for instructions on recording bank payments.

5.8.1 Deposits

Deposits into the Special Account CBGY will originate from the approved disbursement request from the IDB.

Once the credit advice is received from the CBGY, the relevant Inter Departmental Adjustment (IDA) will be sent to the Treasury Division for processing.

This transaction will have to be recorded in the accounting software by firstly generating a sales invoice with the respective amount based on the exchange rate stated on the credit advice and then posting the deposit on the bank account against the respective sales invoice.

Refer to to the manual for the software for instructions on sales and deposit procedures.

5.8.2 Bank Reconciliation of the Special Account CBGY

A bank reconciliation of the Special Account will be done on a monthly basis. It will be prepared by the FS and validated by the internal auditor for the project.

The CBGY will issue monthly bank statements. The transactions recorded in the general ledger of the accounting software will be verified against respective entries in the bank statement.

Once all transactions have been accounted for the bank reconciliation can be performed using the following format:

Ministry of Business

Enhancing the National Quality Infrastructure for Economic Diversification and Trade Promotion Project

IDB project xxxx/ OC/GY

Bank Reconciliation for month ending xxx

Opening GL Balance as at			xxx

Less Total Payments for month		(xxx)

Add Deposits for month			xxx

Closing GL Balance as at                                xxx

Closing Balance as per Bank Statement	(xxx)

Difference                                                          	xxx

Once no difference exists between the balance on the bank statement and the respective balance on the general ledger, the bank reconciliation is to be printed and signed and dated by the FS and passed to the PM with a copy of the bank statement for verification.

The PM will sign and date after verification and return to the FS for filing.

5.9 Accounts Payable:

Sources of Entry:

- Purchases Ledger:

A note book to be kept by the Project Officer which will ruled accordingly:

| Date Received | Invoice Date | Supplier | Invoice Nos. | Amount | Due Date | Account # | Signature |
| --- | --- | --- | --- | --- | --- | --- | --- |

The Purchases Ledger book will be kept and Maintained by the Project Administrator. On a monthly basis the Project Administrator will total and pass the Purchases Ledger Book to the Financial Specialist for verification that all invoices for the respective month have been posted into the project accounting software and the IFMAS. The Financial Specialist will sign under the last entry for the month and return the Purchases ledger book to Project Administrator.

- Data Entry in project accounting software

5.9.1: Set Up of Vendor

- The Procurement Specialist will recommend to the FS the setup of a vendor once the respective contract is approved and issued.

- The vendor key or account number will be the PRISM number given for the activity by the IDB non objection.

- A purchase order will be generated for the vendor (for internal use only) using the project accounting system which will detail each deliverable as a separate line item to be supplied on the purchase order

- The purchase order will be printed by the FS and passed to the Procurement Specialist to verify deliverables on the purchase order against respective contract.

- The Procurement Specialist will sign Purchase order and submit to PM for signature.

- Signed Purchase order will be returned to FS for filing awaiting submission of invoices.

A Purchase Order Report detailing all open purchase orders is to be generated on a monthly basis by the FS and passed to the PM and Procurement Specialists for their verification, information and signature, as well as the PAS-Finance and PAS-General Administration. After signatures, the report is to be returned to the FS for filing.

5.9.2: Recording of Purchases Invoices:

- Invoices will be sent to the PM for information and then passed to the Procurement Specialist and the Procurement Officer at the MOB.

- The Procurement Specialist will verify details of invoice against approved contract and recommend payment and pass to the Project Administrator for recording in the Purchases ledger or rectify any issue with supplier.

- Project Administrator will verify details of invoice and stamp the respective account number related to the invoice, sign and date and pass invoice to the FS.

- FS will verify details of invoice against approved contract and IDB non-objection

- Once details are correct, FS will post into the project accounting system, stamp POSTED, sign and date and send to the PAS-Finance for post in the IFMAS sub-ledger on a monthly basis to reconcile disbursements to the project under the loan.

- PAS – Finance will provide copy to the PAS – General Administration.

5.9.3: Payment of Invoices

Refer to 5.8.

5.10 Monthly Reports

The FS will prepare the following reports on a monthly basis:

- Statement of Cumulative Investment

- Bank Reconciliation

- Variance Analysis Report

- Summary of Open Purchase Orders (List of Outstanding Commitments)

These reports will be circulated to the PS, Deputy PS, PASes Finance and General Administration, Director of Business Strategy and Policy, where the M&E function resides, and all members of the PEU for review. For further reporting requirements, refer to 3.8, Table 3.2.

5.11 Audit

The FS will prepare draft financial statements comprising of:

1) Statement of Cash Flows

2) Statement of Cumulative Investment

3) Respective Notes to the Accounts

This will be done in timely manner submission to the auditors before commencement of the annual audit. These will be accompanied by the relevant requested audit schedules and other information that is required by the auditors.

Refer to 5.3 and IDB Financial and External Audit Handbook.

All schedules and statements for audit are to be updated monthly and reconciled to the General Ledger and the IDB’s LMS1 report.

Prior to the start of an audit, a pre-meeting with the External Auditor and IDB should be convened to clarify needs, assess risks, audit schedule and timelines, etc.

5.12 Asset Register

Assets purchased for use in the PEU are to be recorded in an Asset Register maintained by the FS and reconciled with records maintained by the Principal Assistant Secretary – General Administration.

This would detail the description, location and identification number of the asset.

CHAPTER 6

PROCUREMENT OF WORKS, GOODS AND SERVICES, POLICIES AND PROCEDURES

6.1 Procurement Description

The procurement of works, goods and consulting services will be conducted in accordance with the Bank’s procurement policies and procedures for the Procurement of Goods and Works (GN-2349-9) and for the Selection and Contracting of Consultants (GN-2350-9).

6.2 Procurement Plan

The Procurement Plan (PP) is the administrative planning tool that will allow the PS MOB to formulate and agree with the Bank on the procurement of consulting firms, individual consultants, goods, works, and non-consulting services necessary for the fulfillment of the objectives of the Project. Its formulation allows for the necessary programming of procurement processes to achieve the results set out in the Annual Operating Plan (AOP).

The PP will be prepared by the Procurement and Contract Management Specialist and shall receive the Bank’s non-objection prior to the commencement of any procurement process included in the PP. The PEU will update the PP procurement plan at least annually or as needed throughout the duration of the Project. Any modification to the PP will be submitted to the Bank for review and approval.

The PP will contain the following information:

- A brief description of the goods, works and service required to execute the Project;

- The estimated amounts of the different tenders for bids, under which the procurements will be grouped;

- The source of financing and the procurement method anticipated for each bid, on the basis of the norms established for the various methods of procurement; and

- The estimated dates for the publication of the first notice for pre-qualification or bidding and completion of contract.

The PEU will only undertake procurement activities that are listed in the procurement plan and have received their respective no-objection. The finalized plan will be uploaded in the Procurement Plan Execution System (SEPA) and the Bank’s website for viewing by the general public.

6.3 Procurement Methods

All procurement processes to be done under the Project will be part of the approved PP prior to the commencement of the process. The selection methods used in the execution of the Project will be in accordance with the Bank’s policies and considering the IDB and thresholds on the Procurement of Goods and Works and Selection of Consulting Services.

- 6.3.1 Preparation of Bid Documents for Procurement of Works and Goods

The bidding documents will be prepared by the PEU and then sent to the Bank for ex-ante no objection. Procurement methods through which Goods and Works can be contracted are as follows:

- International Competitive Bidding (ICB);

- Limited International Bidding (LIB);

- National Competitive Bidding (NCB);

- Shopping or Price Comparison (PC);

- Direct Contracting (DC); and

- Force Account

The Bank’s standard documents for the procurement of goods and works will be used as the basis of any Bid Documents required.

6.3.2 Preparation of Bid Documents for Procurement of Contractors/Consultants’ Services

The bidding documents for the procurement of contractors/consultant services will be prepared by the PIU and then sent to the Bank for ex-ante no objection. The Bank’s Standard request for proposals (July, 2013) and the Simplified form of Contract for Consulting Services Small Assignments (June, 2013) will be used for the procurement of consultant services pursuant to the Policy for Selecting and Contracting Consultants financed by the Inter-American Development Bank (GN-2350-9).

The procurement of consulting services will be carried out according to the Bank’s Policy for the Procurement of Consultants (GN-2350-9). Methods of selection that can be used for Consultant’s services are:

- Quality-and-Cost-Based Selection (QCBS);

- Quality-Based Selection (QBS);

- Selection under a Fixed Budget (FBS);

- Least-Cost Selection (LCS); and

- Selection Based on Consultants’ Qualifications (CQS).

6.3.3 Financial Limits of Procurement Activities

Individual consultants are selected on the basis of their qualifications for the assignment.

The PP shall include the procurement and selection methods considered for the procurement of works and goods, consulting services or non-consulting services. In accordance with the IDB’s Procurement Policies applicable to the Project, the IDB will not finance expenditures for goods, works, consulting and non-consulting services which have not been procured in accordance with the Bank Procurement Policies and as the approved PP. In such cases, the Bank will declare mis-procurement, and the portion of the loan allocated to the goods and works that have been mis-procured will be cancelled.

In compliance with the regulations of the National Procurement Board and Tender Administration’s Financial Limits, the Project will be guided by the following Financial Limits for the:

- Permanent Secretary 			any amount below GY$250,000 to be

accompanied by a report within 5 days if the amount is above GY$200,000 as per Regulation 4(2) of the Procurement Act Regulations of 2004

- Ministerial Tender Board, on Permanent Secretary’s recommendation

Goods & Services

from GY $250,000 to GY $600,000

Works

from GY $250,000 to GY $1,000,000

Consulting Services

from GY $250,000 to GY $400,000

- National Procurement Tender Board (NPTB) (upper threshold of GY$15,000,000)

Goods & Services

Any amount exceeding GY$600,000

Works

Any amount exceeding GY$1,000,000

Consulting Services

Any amount exceeding GY$500,000

- Cabinet

Goods, Services, Works, Consulting Services

> GY$15,000,000

6.3.4 National Procurement Tender Board Involvement

The PEU will prepare the relevant documents for the procurement activity, in collaboration with the Procurement Officer or responsible officer under the Principal Assistant Secretary – General Services, and submit to the Bank for the Bank’s no-objection. Upon receipt of no-objection, the PEU, through the MoB’s Procurement Officer or designate, will engage the National Procurement Tender Board of the Government of Guyana to facilitate the procurement of Goods, Services, Works or Consulting Services where cost of the Procurement activity exceeds GY$15 Million. Other information to be submitted includes but are not limited to:

- Members of the individuals on the Evaluation Committee;

- Assign a senior technical employee for vendors to engage for clarification or queries; and

- Confirm funds are available for the Procurement.

The NPTB will prepare the package and the Chair will be responsible for arranging a date to evaluate the bids. The NPTB is not responsible for post-contractual activities; however after the completion of the contract, the PEU is responsible for reporting on the contract’s performance to the NPTB.

6.4 Advertising of Procurement Processes

Advertising is an important element of the procurement process, to enable broad participation of eligible bidders and publicize the various procurement processes to be performed under the Project. Advertising will be performed according to the IDB Procurement Policies GN-2349-9, and GN2350-9.

The Bank will establish a General Procurement Notice (GPN) in United Nations Development Business (UNDB) Online upon approval of the project to generally indicate the categories of major procurements to be made ​​under the Project over the life of the project. All procurement by ICB shall be published in Development Business (UNDB Online) as well as in a newspaper of national circulation.

Procurement subject to NCB will be published in a local newspaper of national circulation and may be advertised internationally if there is need to widen to sourcing. The PEU will also publish opportunities on the SPN on the website of the MOB, GNBS and GO-Invest.

6.5 Selection and Contracting of Consulting Services

As stated in Section 4.03 of the Loan Contract, any method of selection used, has to be identified in the Procurement Plan approved by the bank.

6.6 Procurement Monitoring and Evaluation

Procurement of goods, works and consulting services will be reviewed using ex-ante modality by the IDB to ensure that the documents and selection procedures satisfy the IDB’s policies and are consistent with the approved procurement plan.

## 6.7 Obligations for Beneficiaries and Consultants

The direct beneficiaries as well as consultants and any other institution that performs activities with IDB’s resources from the Contract and administered by PEU, must agree with the Bank’s policies, which will be included in the contract documents.

CHAPTER 7

REPORTING, MONITORING

AND EVALUATION

7.1 Reporting

The MoB, through the PEU, will present to the Bank Project Execution Reports, including Semi-Annual Progress Reports, and Financial Reports.

7.2 Summary of IDB Reporting Requirements

The MoB, through the PEU, will submit specific reports to the IDB in accordance with the IDB’s reporting requirements.

- 7.3 Monitoring

The MoB, through its Monitoring and Evaluation Specialist, who will liaise with the PEU, as per the project execution arrangements, will be responsible for monitoring the Project’s performance and progress throughout the execution period. Project monitoring and evaluation will be based on:

- The PEP, which include a comprehensive planning of the Project, the critical path of milestones or actions that must be taken to ensure that the Loan is disbursed within the period indicated and a detailed Financial Plan. The PEP shall be updated as necessary;

- The AOP, which will be prepared each year by the Executing Agency on the basis of the PEP and presented to the Bank for its non-objection. The AOP will contain detailed project execution activities, and for each activity it will detail annual goals, budget and implementation schedule. The first AOP will cover the Project’s first eighteen-month period, commencing from the (insert date of loan contract upon approval);

- The Project’s Results Matrix, includes the indicators for the Project’s results with respective baselines and targets to achieve, outputs for each component, and the expected impact of the Project in the long term;

- Semi-annual progress reports, which should be presented to the Bank within (60) days following the end of each calendar semester (every six months) during Project execution of the AOP, and will include a financial report and the outcomes and outputs achieved in the execution of the AOP, the Procurement Plan and the Project Results Matrix.

The PEU will use the project supervision and monitoring system which will include:

- analysis of the technical and financial reports;

- annual monitoring meetings; and

- midterm evaluation, carried out by an independent external consultant upon fifty percent (50%) of the loan resources;

- Final evaluation, carried out by an external consultant upon ninety percent (90%) of the loan resources;

- In addition, the system will include routine inspection visits normally carried out by the IDB’s Guyana Country Office and the IDB Team in Washington, DC.

The MoB will present semiannual technical and financial progress reports. In addition, it will present annually:

- an assessment of the AOP for the year;

- the AOP for the upcoming year; and

- audited financial statements.

The information from these documents will serve as input for the annual monitoring meetings and inspection visits.

Information Technology System

The project’s executing unit will procure an information technology system to monitor and supervise project progress including fiduciary management. The information system will allow for supervision and monitoring of project implementation in the following aspects at least:

- Administrative management of the project

- financial management of the project: quantify the expenditure and the project's budgetary status;

- In carrying out each activity under the project: measure the costs and time taken to achieve the objectives of each activity, using a work breakdown structure.

Once the information system has been designed and put into operation, the program’s executing unit will be responsible for maintaining it and keeping it up to date to inform the preparation of semi-annual and annual progress reports as well as annual and final audits.

7.3.1 Semi-Annual Progress Report

The Semi-Annual Progress reports regarding the implementation of the activities of the Project within sixty (60) days after the end of each Semester. The content of these reports will include the following elements:

- descriptions of the executed activities per component;

- accounts of the contractors’, consultants’ and the supervision firm’s performances;

- description of the procurement processes carried out during the reported period and any update to the procurement plan;

- updated schedule of physical progress and disbursements;

- level of compliance with the performance indicators;

- review of critical determinants of the socioeconomic feasibility of the Project, particularly actual investments costs;

- description of the elements that are affecting the Project’s implementation, and identification and proposal of corrective measures;

- identification of new risks/events that may potentially affect the future implementation of the Project, and update of the Matrices produced within the Project’s Risk Management process;

- execution plan to be completed in the following two six month periods;

- a summarized Project financial statement, and

- the estimated cash flow for the next two six-month periods

- 7.4 Indicators

During project preparation, process and success indicators will be established, for achievement in the project implementation stage through a detailed Results Matrix.

    - Process indicators

Process indicators measure the efficiency and effectiveness with which project activities are undertaken during implementation. Setting their level requires identifying specific quantitative targets for attainment by each project activity.

    - Success indicators

Success indicators measure achievement of the proposed objectives to be attained by GNBS and GO-Invest as a result of project implementation. Based on information obtained during project preparation, a quantitative baseline situation will be defined (the current or without-project situation). This quantification will be compared with the targets in the Results Matrix as the project is implemented to measure the degree to which the proposed outputs and outcomes are attained.

7.5 Evaluation

The project will entail both a mid-term and final evaluation. Independent evaluators will be procured. At the end of 30 months from the date of the Contract or after 50% commitment of the resources, whichever comes first, the mid-term review will take place with the help of an external consultant who will focus on, among other things:

- the level of progress in attaining the Project’s objectives, as explicitly stated in the Results Framework;

- the level of acceptance of procedures developed under the Project, including environmental and social issues, on safeguards compliance, as well as ex-post economic assessments; and

- the degree of effectiveness of the internal controls and the Bank’s monitoring and supervision system.

The final evaluation, to be carried out with the help of an external consultant will take place after 90% of loan resources have been committed.

The result of this final evaluation will be used as an input for the Project Completion Report (PCR) to be prepared by the Bank.

- 7.6 Auditing

- 7.7.1 External Audit

The annual and final external audits will be carried out by the Auditor General of Guyana, and in accordance with International Accounting and Reporting Standards, and presented to the Bank. The external audit will not require the use of Project’s resources.

7.7.2 MoB’s Internal Audit

The Ministry of Business will procure an independent auditor to audit the Project. This is required given that the MoB does not have an internal auditor and project requires this in order to establish an internal control system, at a minimum for the project, in order to provide assurance that:

- GY-L1059’s funds are used for the intended purposes and are consistent with the project Procurement Plan, to achieve cost effectiveness, value for money and efficient allocation of project resources;

- The Project’s assets, especially with regard to Component II, are properly safeguarded;

- The Project’s transactions, decisions, and activities are properly authorized and documented, consistent with the project execution structure outlines in Figure 1; and

- The Project’s transactions are executed in accordance with the established policies and procedures of the Bank as prescribed in the Loan Contract.

7.7 Budget Allocation

The budget assigned to monitoring, evaluation, and auditing is US$215,000.

ANNEX 1

# TERMS OF REFERENCE: Program Manager

### I.	Background

  - The Government of Guyana, supported by the Inter-American Development Bank (IDB), is implementing a program for improving the National Quality Infrastructure in Guyana (NQI), Enhancing the National Quality Infrastructure for Economic Diversification and Trade Promotion.

The program’s main objective is to support economic diversification and exports through the enhancement of the NQI and through a National Export and Investment Promotion Strategy. Specific objectives are: (i) to enhance the capacity of the NQI; (ii) to improve facilities for the NQI; and (iii) to enhance the capability of export and investment promotion.

  - In order to strengthen the institutional framework to facilitate quality improvements, activities will be conducted in two fronts (supply and demand related): through the enhancement of the National Quality Infrastructure (NQI) and through a National Export and Investment Promotion Strategy. The program will be implemented in three sub components. In particular, the specific components of the intervention are:

  - Component I. Modernization of the Institutional Framework for the NQI (US$1.03MM). The component will support the capacity building of the stakeholders of the NQI, in particular the GNBS, by strengthening the areas of technical regulations, compliance, conformity, accreditation and training, and capacity building of public and private stakeholders. The governance structure of the NQI will be streamlined to include the needs of private sector with priority given to non-traditional exporters and a network of laboratories will be created in order to promote the most efficient use of the current facilities. In addition, the network of laboratories under the GNBS will create a monitoring and evaluation system, in which data of the users of the NQI will be collected. This component will finance: (i) activities to support the accreditation process of existing laboratories; (ii) training and capacity building for laboratories in the network and for the GNBS; (iii) creation and operation of a network of laboratories; (iv) capacity building activities on SMEs and standards (v) the development of a strategic plan for the GNBS that aligns with both the regional and national policy framework; and (v) awareness campaigns on the use of standards and quality.

  - Component II: Improving Laboratory Facilities and Equipment (US$5.96MM). The objective of this component is to improve facilities for the NQI.  This component will finance specifically: (i) architecture and engineering designs of the new laboratory facility for the GNBS, including "green building" provisions; (ii) building of the new facility (the facility will house metrology, testing, chemistry and microbiology, and legal metrology); (iii) required equipment for the adequate functioning of the GNBS; (iv) maintenance contracts; (v) specific support to the main laboratories related to the export/import processes under the MoH and MoB filling specific gaps in those laboratories; and (vi) a sustainability plan (to guarantee the sustainability of the investment, the development of the facilities will be concentrated in the core functions of the GNBS - metrology, calibration and testing - and will provide specific support to the Food and Drug and Agriculture facilities related to export promotion). Additional requirements, derived from quality value chain analysis that will be conducted on selected sectors and the quality bottlenecks, as part of the activities of Component III will be addressed by this component as well.

  - Component III: Implementing the National Export and Investment Strategy (US$1.07MM). In order to enhance the capability of export and investment promotion, this component will support: (i) technical assistance to design and implement a trade and investment promotion strategy, including mapping major value chains; and (ii) technical assistance for the strengthening of Go Invest and its ability to promote exports and attract foreign direct investment, especially in the sectors that will need the operation of modern certified lab facilities that are required for accessing international markets.

  - Program implementation will be the responsibility of MoB; it will be managed by a program executing unit consisting of a Program Manager and Technical Coordinators.

  - The program executing unit, headed by the Program Manager, will be a suitably qualified technical team, with technical knowledge of issues of quality, standards, exports and investment, and capacity to help achieve the program objectives.

### II.	Functions

  - The Program Manager will have the following functions:

- Ensure program goals are fulfilled;

- Inform the Steering Committee on the progress of the Program and incorporate the suggestions regarding strategic direction of the program.

- Prepare an annual plan of program activities that includes a detailed timetable of activities per component, the resources needed, targets to be achieved in each activity, and the actions needed to achieve them.

- Keep an up-to-date timetable of activities for each component, report periodically to the program’s Steering Committee on its progress, and submit any changes for its consideration;

- Coordinate with the MoB, GNBS and Go-Invest all execution related matters.

- Coordinate and supervise the development of all program activities in accordance with the timetable.

- Produce the program's budgetary statements and keep them up to date;

- Serve as executive secretariat of the program's Steering Committee

- Oversee project execution, involving in site supervision of works, quality of goods and services.

- Provide technical inputs to the outputs of the program.

- Promote the program and disseminate results continuously

- Oversee and support on the preparation of Terms of Reference and procurement material.

- Perform all administrative and general coordination tasks needed for program implementation

- Review and submit to the Steering Committee and the Ministry of Business other relevant Program documents, including procurement evaluation reports, financial reports, and the progress reports of the IFS Task Manager;

- Provide support in preparing the TORs, and supervise the procurement process itself with the help of a procurement specialist;

- Monitor and update the results Matrix of the Program;

- Provide support to the entities involved in the implementation of program’s initiatives;

- Collect and document evidence of compliance with the program’s targets; and

- Assist with the procurement and processing of the contracts required for the implementation of the agreed program interventions

### III.	Profile

  - The job will be based in the city of Georgetown.

  - The contract will last for 42 months and will require full-time work on the program.

Academic requirements

  - The Program Manager will have a professional qualification in management, economics or engineering, or similar career, with at least 10 years of experience in project preparation, evaluation and management. Experience with multilateral organizations or donor organizations will be preferred

Work experience

  - The candidate needs to provide evidence of at least four years’ experience in project administrative management.

  - The candidate will provide evidence of at least three years’ experience in project preparation and evaluation.

  - He or she should demonstrate knowledge of the business, economic and export reality in Guyana.

### VI.	Reports

  - During the course of the program, the Manager will submit bimonthly progress reports on its activities to Steering Committee and the Ministry of Business.

### VII.	Supervision and Coordination

  - The program's Steering Committee and the Ministry of Business will monitor the functions and activities of the Program Manager.

See Economic and Export Diversification reference to the Small Business Bureau 2013 data.

This is Guyana's Sanitary and Phytosanitary Measures (SPS) enquiry point and national notification authority to the World Trade Organization

Food and Drug has the overall responsibility for issues relating to human health, including food for human consumption and cosmetics

The Bank’s standard tool is the ICAS – Institutional Capacity Assessment System (SECI in Spanish).

Guyana Private Sector Assessment Report (PSAR). 2014. Bureau of Statistics Data.

Figures are for year 2013 as determined from Bureau of Statistics 2014 Report on GDP at Current Basic Prices.

Guyana Private Sector Assessment Report.

Ibid.

Observatory of Economic Complexity 2016.

The economy is highly dependent on raw materials and unprocessed foods, as the main contributors to the economy are agriculture, forestry and fishing (19% of GDP), mining and quarrying (10%), agroindustry (7%) and services (66%). Source: Bureau of Statistics.

Wenner. 2016. Guyana’s PetroCaribe Rice Compensation Scheme has Ended. Assessment and Policy Implications.

Export penetration in overseas markets, as measured by an index of export market penetration of 1.49 WITS. 2014.

United States, 26.9%; United Kingdom, 12%; Venezuela, 9.6%; Canada, 8.4%; and Jamaica, 5.86%.

Ibid.

Samen, Salomon. World Bank. 2010. Export Diversification: Key Concepts, Theoretical Underpinnings, and Empirical Evidence.

Needs Assessment Report for SAL.

Kandhi, R. and Edmondson, H. 2014. Consultancy for Needs Assessment for State of the Art Testing Metrology Facilities.

Guyana Private Sector Assessment Report.

It is comprised of (i) National Standard Bodies, in charge of developing and adopting standards; (ii) certification bodies in charge of assurance that a product conforms to standards; (iii) testing laboratories (both public and private); (iv) inspection bodies; (v) calibration laboratories; and (vi) accreditation bodies in which an organization or a person is recognized as competent to carry out certain tasks. Guasch, Racine, Sanchez and Diop. 207. Quality Systems and Standards for a Competitive Edge. World Bank Publication.

Needs Assessment for the State of the Art Testing and Metrology Facilities. 2014.

The formal recognition of the technical competence of the certifying body and testing or calibration laboratories. (Sanetra. 20017. A National Quality Infrastructure)

Guasch, Racine, Sanchez and Diop. 2007. Quality Systems and Standards for a Competitive Edge. Directions in Development. World Bank Publication.

Gonzales, Gothner and Rovira. 2014. Midiendo el impacto de la infraestructura de la calidad en América Latina: experiencias, alcances y limitaciones. Documento CEPAL. PTB.

UNIDO. 2012. Trade Standards and Compliance Report

Gutierrez, J.J. 2015 Economic Sector Work: Sistema Nacional de la Calidad. Bien Público para la Competitividad( Draft). Guash 2007.

GNBS Strategy. 2011.

There are various quality services for evaluating whether manufacturers produce and deliver their products in accordance with the corresponding specifications. These include testing laboratories, equipment calibration laboratories, and certification and inspection bodies. There are other specific standards to ensure the technical competence of these services and their correct implementation is confirmed by an accreditation. In Guyana, the GNBS is the only laboratory conducting calibration of measuring devices for mass, electrical measurements and temperature but does not have the physical conditions to control temperature and humidity, among others.

The GNBS Standards Catalogue 2012 lists 20 standards as having mandatory status. The World Trade Organization Report by Measures 2009, states that Guyana makes minimal use of technical regulations.

In Guyana, Metrology support is required by at least 20 agencies, and testing in at least 39 instances to determine compliance with regulations. In the case of metrology, ministries/agencies use external service provided by the GNBS.

There are 20 existing main national laboratories (public and private) that provide different testing services. There are only two accredited labs in Guyana: the Guyana Rice Board Laboratory and the Eureka Medical Lab got accredited on May 2015 and March 20016 respectively. (ISO/IEC 17025).

Unsuitable type of construction materials to ensure a sterile environment, layouts that may conduce to cross contamination, locations subject to flooding, poor ventilation, humidity and direct sunlight. Needs Assessment Report, 2014.

Ibid.

Gutierrez, J.J. 2015 Economic Sector Work: Sistema Nacional de la Calidad. Bien Público para la Competitividad (Draft). Guasch, Racine, Sanchez and Diop. 2007. Quality Systems and Standards for a Competitive Edge. Directions in Development. World Bank Publication.

Gonzales, Gothner and Rovira. 2014. Midiendo el impacto de la infraestructura de la calidad en América Latina: experiencias, alcances y limitaciones. Documento CEPAL. PTB.

Guash 2007.

The current GNBS provides the services of metrology, calibration and testing in a facility that is insufficient in terms of space and environmental requirements. Some tests that are required to be carried out under controlled conditions are being currently carried out in the same room as others.

Services include legal requirements, consumer health, safety and protection, facilitation of priority sectors to market, research, innovation and services to promote competitiveness, interoperability and cost savings.

The possibility to engage into public/private partnerships will be explored.

Initial layout designs are being currently being financed through C&D funds.

The Guyana Lands and Surveys Commission approved the Application to lease 1 acre of State Lan situated at plantation Pattensen, Block XXX at Liliendall East Coast Demerara.

To be determined and updated on determination.

The M&E Specialist reports to the Director, Business Strategy and Policy.

The scale of the Project allows financing activities and outputs oriented to enable the improvements of quality but it does not finance the quality enhancements themselves.