Document of the Inter-American Development Bank

Trinidad and Tobago

Support to Strengthen Trinidad and Tobago’s Public Financial Management System

(TT-L1042)

Monitoring and Evaluation Plan

This document was prepared by: Dana King (IFD/ICS), Project Team Leader, Marcio Cracel (consultant), and Martin Rossi (consultant).

Content

I.	Introduction	2

II.	Monitoring	4

A.	Data collection and instruments	7

B.	Reporting	7

C.	Monitoring Coordination, Work Plan and Budget	8

D.	Main Monitoring Questions	8

III.	Evaluation	11

A.	Reflective Evaluation	12

B.	Financial Evaluation 	14

| Abbreviations |  |
| --- | --- |
| COTS; Commercial, off-the-shelf. GFS; Government Finance Statistics. IFMIS; Integrated Financial Management Information System. IM; Information Management. IPSAS; International Public Sector Accounting Standards. IT; Information Technology. MoFE; Ministry of Finance and the Economy. PEFA; Public Expenditure and Financial Accountability. PFM; Public Financial Management. PFMMU; Public Financial Management Modernization Unit. PIU; Project Implementing Unit. PPRD; Project Planning and Reconstruction Division. PSR; Public Sector Reform. STTFMS; Support to Strengthen TT’s Financial Management System. TT; Trinidad and Tobago. |  |

- Introduction

  - The general objective of this project is to improve the efficiency and effectiveness of the Government of the Republic of Trinidad and Tobago to allocate public resources for public service delivery. The project’s specific objectives are improved: (i) strategic allocation of public resources; (ii) independence in the control and stewardship of public resources; and (iii) information management. Direct beneficiaries of the project are TT’s 34 ministries as well as, more broadly, the population of TT. This Project will finance the following components:

  - Component I: Support for Public Financial Management Modernization (PFM). This component seeks to contribute to the modernization of PFM procedural and legal frameworks for budget preparation and execution. To do so, the component will finance the following products:

    - Development and implementation of a new budget classification based on a GFS-compliant Chart of Accounts (COA). This will include: (i) support for the implementation of the new COA and budget classification system, including training Ministry of Finance and the Economy (MoFE) staff on its use; and (ii) preparation of an IPSAS-compliant Treasury accounting framework to operate with the new concepts introduced by the new COA, including update of Accounting manuals as well as delivery of training courses on the new accounting framework and bookkeeping.

    - Development and implementation of institutional instruments to sustain PFM modernization efforts. This will include: (i) development and implementation of a Sustainability Strategy for PFM continual improvement; (ii) development and implementation of a Change Management strategy, including stakeholder coordination and communication; (iii) train-the-Trainer programs within core PFM areas including Project Planning and Reconstruction Division and the MoFE’s Budget and Treasury Divisions, as well as establishment of an e-Learning platform; and (iv) hiring of a chief technical advisor to the Public Financial Management Modernization Unit (PFMMU) to direct and coordinate Project activities.

    - Design and implementation of an internal audit framework to improve PFM control, transparency, and reporting. This will include support for the implementation of recommendations of the Internal Audit report, and the corresponding training.

    - Review of, and preparation of recommendations to strengthen, the PFM legal framework. This will include the review of the Exchequer and Audit Act, existing PFM regulation, and recommendations on legislative and regulatory amendments to strengthen internal audit, budget classification, automation, and reporting standards.

    - Business process reengineering for budget preparation and execution processes. This will include the revision of existing business processes in view of automation and to prepare procedures manuals for Budget and Treasury Divisions personnel; with the aim of streamlining procedures including payment processing times.

  - Component II: Support for Integrated Financial Management Information System implementation. This component seeks to improve information management for PFM through implementation of an IFMIS. To do so, the component will finance the following products:

    - Establishment of a centralized IT governance framework within MoFE. This will include: (i) the development of the documentation of IT governance practices and procedures for PFM IT management; and (ii) the establishment of a training program for MoFE IT staff, including training for development and implementation of an IT strategic plan.

    - Implementation of a commercial, off-the-shelf (COTS) IFMIS solution with government-wide coverage, including customization, data migration, and integration services. This will include: (i) the operationalization of the COTS IFMIS solution comprising the IFMIS software package; training for users and IT staff in the operation of the IFMIS solution including a train-the-trainers program; purchase of Data Center Hardware, and training of business analysts to analyze IFMIS-aggregated data; (ii) laptops and printers to operate the IFMIS; and (iii) implementation and roll out of a cash receipting system.

  - The Borrower is the Republic of Trinidad and Tobago. The Executing Agency (EA) is the MoFE, which will be responsible for the administration of the resources and procurement processes of the Program. The Public Financial Management Modernization Unit, established in the MoFE, will serve as the Project Implementing Unit (PIU) and oversee project execution. The PIU will be responsible for overall project administration, including planning, budgeting, accounting, procurement implementation, and monitoring; and will include a full-time, dedicated financial specialist, financial assistant, and procurement specialist. Project coordination will be carried out by the PFMMU’s chief technical advisor.

  - This operation is the third IDB-financed project to be led by MoFE and the second operation to be implemented by the PFMMU. The MoFE has demonstrated the administrative capacity and familiarity with IDB requirements and procedures to oversee this operation. Notwithstanding, as this operation is the first investment loan to be implemented by the MoFE and the IDB will provide training and guidance to support execution.

  - PIU responsibilities include: (i) Annual Operating Plan (AOP) preparation and implementation; (ii) financial administration, accounting, and preparation of budgets and disbursement requests; (iii) annual procurement plan preparation and procurement of works, goods and services; (iv) preparation of technical reports and financial statements; (v) monitoring of project activity progress, environmental and social safeguards compliance, and actual and planned results variance; (vi) selection and hiring of the external audit firm and implementation of recommendations; (vii) hiring of consultants to conduct external evaluations; and (viii) serving as liaison to IDB.

- Monitoring

  - Project monitoring will be conducted by the PIU, using the (i) Results Framework; (ii) Project Execution Plan (PEP); (iii) this Monitoring and Evaluation Plan (M&E Plan); (iv) the detailed budget; (v) the Risk Matrix; and (vi) Procurement Plan. The PIU shall prepare and submit semi-annual progress reports for review and no objection by the Bank. The Borrower agrees to use the Results Framework to monitor the operation.

  - Tables 1 and 2 present output indicators and budget allocation, including annual targets and sources of verification.

- Table 1. Output Indicators

| Output | Cost (US$) | Unit of measure | Baseline | 2015 Cost US$ | 2015opt. | 2016 Cost US$ | 2016 opt | 2017 Cost US$ | 2017 opt | 2018 Cost US$ | 2018 opt | 2019 Cost US$ | 2019 opt | Target | Sources/Means of Verification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2013 |  |  |  |  |  |  |  |  |  |  | 2019 |  |
| 1.1 Chart of Accounts (COA) with Government Financial Statistics (GFS) -compliant budget classification implemented. | 1.7 million | COA GFS-compliant | 0 | 170,000 | 0 | 340,000 | 0 | 510,000 | 1 | 340,000 | 0 | 340,000 | 0 | 1 | IMF Article IV - 2017 attesting that TT adopted a COA GFS-compliant. |
| 1.2(a) PFM train-the-trainer program for budget preparation, budget execution, and project planning and management designed. | 6,3 Million | Package (methodology and materials) | 0 | 630,000 | 1 | 1,260,000 | 0 | 1,890,000 | 0 | 1,260,000 | 0 | 1,260,000 | 0 | 1 | MoFE-approved course package (with the methodology and materials), presented to the Bank. |
| 1.2(b) PFM train-the-trainer courses for budget preparation, budget execution, and project planning and management held. |  | Number of courses | 0 |  | 0 |  | 5 |  | 5 |  | 0 |  | 0 | 10 | Report from the MoFE attesting that the courses have been held (including the expenses report of the courses). |
| 1.3 Internal audit framework elaborated | 397,500 | Internal audit framework | 0 | 39,750 | 1 | 79,500 | 0 | 119,250 | 0 | 79,500 | 0 | 79,500 | 0 | 1 | Internal Audit Framework presented to the Bank. |
| 1.4 Amendments to the Exchequer and Audit Act and package with all other regulatory changes needed for allowing the implementation of a GFS-compliant COA drafted | 353,500 | Regulatory package | 0 | 35,350 | 1 | 70,700 | 0 | 106,050 | 0 | 70,700 | 0 | 70,700 | 0 | 1 | Amendment and regulatory changes package presented to the Bank. |
| 1.5 IFMIS designed | 588,000 | IFMIS | 0 | 58,800 | 1 | 117,600 | 0 | 176,400 | 0 | 117,600 | 0 | 117,600 | 0 | 1 | External expert report evaluating the new IFMIS (the new IFMIS conceptual design should satisfy the different requirements dictated by each jurisdiction’s budget and accounting). |

| Table 2. Project Annual Budget |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Total | 40.000.000 | 10,81 | 4.324.221 | 20,00 | 8.000.000 | 29,19 | 11.675.779 | 20,00 | 8.000.000 | 20,00 | 8.000.000 |
| Outputs | Total Product | % | year 1 | % | year 2 | % | year 3 | % | year 4 | % | year 5 |
|  | 9.339.000 | 10,00 | 933.900 | 20,00 | 1.867.800 | 30,00 | 2.801.700 | 20,00 | 1.867.800 | 20,00 | 1.867.800 |
| 1.1 Chart of Accounts (COA) with Government Financial Statistics (GFS) -compliant budget classification implemented. | 1.700.000 | 10 | 170.000 | 20 | 340.000 | 30 | 510.000 | 20 | 340.000 | 20 | 340.000 |
| 1.2 (a) PFM train-the-trainer program for budget preparation, budget execution, and project planning and management designed and (b) PFM train-the-trainer courses for budget preparation, budget execution, and project planning and management held. | 6.300.000 | 10 | 630.000 | 20 | 1.260.000 | 30 | 1.890.000 | 20 | 1.260.000 | 20 | 1.260.000 |
| 1.3 Internal audit framework elaborated | 397.500 | 10 | 39.750 | 20 | 79.500 | 30 | 119.250 | 20 | 79.500 | 20 | 79.500 |
| 1.4 Amendments to the Exchequer and Audit Act and package with all other regulatory changes needed for allowing the implementation of a GFS-compliant COA drafted | 353.500 | 10 | 35.350 | 20 | 70.700 | 30 | 106.050 | 20 | 70.700 | 20 | 70.700 |
| 1.5 IFMIS designed | 588.000 | 10 | 58.800 | 20 | 117.600 | 30 | 176.400 | 20 | 117.600 | 20 | 117.600 |
| Implementation of IFMIS (intermediate outcome) | Total Product | % | year 1 | % | year 2 | % | year 3 | % | year 4 | % | year 5 |
|  | 27.418.803 | 10 | 2.741.880 | 20 | 5.483.761 | 30 | 8.225.640 | 20 | 5.483.761 | 20 | 5.483.761 |
| Evaluation, Audit, Project Administration, and Contingencies | Total Product | % | year 1 | % | year 2 | % | year 3 | % | year 4 | % | year 5 |
|  | 3.242.197 | 20 | 648.439 | 20 | 648.439 | 20 | 648.439 | 20 | 648.439 | 20 | 648.439 |
| Monitoring | 860.000 | 20 | 172.000 | 20 | 172.000 | 20 | 172.000 | 20 | 172.000 | 20 | 172.000 |
| Evaluation | 120.000 | 20 | 24.000 | 20 | 24.000 | 20 | 24.000 | 20 | 24.000 | 20 | 24.000 |
| Auditing | 200.000 | 20 | 40.000 | 20 | 40.000 | 20 | 40.000 | 20 | 40.000 | 20 | 40.000 |
| Contingency | 2.062.197 | 20 | 412.439 | 20 | 412.439 | 20 | 412.439 | 20 | 412.439 | 20 | 412.439 |

- A.	Data collection and instruments

  - The data for monitoring output and outcome indicators will be extracted from the administrative systems and records provided by the PIU.

- B.	Reporting

  - Multiple mechanisms and instruments will be used to report project monitoring findings. The following tools and mechanisms will be a source of information for the Progress Monitoring Report (PMR): (i) the Results Framework; (ii) the Annual Operating Plan (AOP); (iii) the Procurement Plan (PP); (iv) the PEP; and (v) Semi-annual Progress Reports.

- C.	Monitoring Coordination, Work Plan and Budget

  - The objective of project monitoring is to detect factors that can facilitate or obstruct the project achievement of expected results, as presented in the Results Framework.

- D.	Main Monitoring Questions

  - Conformity Monitoring: Are financed activities and processes aligned with the project objectives and methodology?

  - Financial monitoring: Are project funds timely available and expended in line with project financial plans?

  - Activity monitoring: Are project activities executed in accordance with the implementation plan and established timetable?

  - Output monitoring: Are the primary, intermediate, and final outputs delivered in accordance with the PEP and AOP?

  - Risk monitoring: What risks may affect project execution and achievement of project objectives? How can the project best address these opportunities and threats? What are mitigation measures are proposed to address threats?

  - Data collection and compilation for monitoring will be conducted by the PIU. To collect relevant data, the PIU will use the following instruments:

      - The Results Framework (RF). Included as Annex II of this document, the Results Framework will be used to guide project planning, monitoring, and final assessment. The RF includes: (i) project outcome indicators with respective baselines and targets; and (ii) outputs for each component. The Results Framework will be referenced in the AOP, and modifications thereof, and will serve as an instrumental tool for the design, monitoring and evaluation of each of the project components and subcomponents.

      - Financial Audit: As detailed in Annex III of the Loan Proposal, the PIU is responsible for engaging an independent auditor each year to conduct a financial audit of the project. Annual Financial Statements for the previous 12 month period must be submitted to the Bank no later than January 30th each year of project execution and a final audit submitted within 180 days of project closure.

      - Annual Operating Plan (AOP). The AOP is included as an Optional Electronic Link to the Loan Proposal. This instrument provides projections of project activity and financial execution (including disbursement). The first AOP will cover the Program’s first 18 months, which initiates upon the signing of the Loan Contract. Subsequent AOPs will be presented by November 30th of the given year and cover project execution plans from that date through December 5th of the following year.

      - Procurement Plan (PP). Included as a Mandatory Electronic Link of the Loan Proposal, this instrument lists all works, goods, and training, as well as non-consulting and consulting services that will be procured during project implementation. The PP defines for each item to be procured: (i) procurement method; (ii) estimated cost; and (iii) the timeframe estimated for completion of the procurement process. Terms of Reference will be elaborated for each consulting service (consultants and firms). The procurement of works, goods and services will be conducted in accordance with the Bank's Policies and Procedures for the Procurement of Goods and Works (GN-2349-9) and for the Selection and Contracting of Consultants (GN-2350-9). Procurement of goods, works and consulting services will be subject to ex-ante review and no objection by the IDB. This review method may be periodically assessed by the Bank through procurement inspection visits and performance reviews. The Procurement Specialist of the PIU will be responsible for updating the PP on an annual basis in conjunction with the PIU’s preparation of the AOP, or when substantial changes are proposed. Any proposed revision of the PP should be presented to the Bank for its approval. The procedures applied by the Bank for the revision of the procurement are further elaborated in Annex III of the Loan Proposal.

      - Project Execution Plan (PEP). Presented as a Mandatory Electronic Link of the Loan Proposal, this instrument lists all the activities to be conducted under the project during the project execution period, along with required financial resources and time required to carry out each project activity. If the AOP indicates significant variance from the project execution plan presented in the PEP, the Bank may require update and resubmission of the PEP in order to understand how such changes will affect the multi-year execution plan and corrective actions to be taken to ensure timely project execution. If the revised PEP includes acceleration of implementation of specific activities, the PEP will detail (i) the main implementation difficulties giving rise to the need for project execution acceleration; (ii) the mitigation measures; and (iii) the timetable and costs for implementing mitigation measures.

      - Semi-Annual Progress Reports: The PIU will submit two semi-annual progress reports per year during project execution. The Semi-Annual Progress Report will be submitted within 60 days following the end of each semester. The progress reports will contain the following elements: (i) narrative description of activities executed under each component, including a description of the procurement processes carried out and issues affecting implementation during the reported period; (ii) update on attainment of Results Framework indicators; (iii) statement of costs incurred by component activities as well as Results Framework indicator; and (iv) identification of risks/events that may potentially affect the future implementation of the program, as well as proposed mitigation measures. The Semi-Annual Progress Reports will provide inputs for the Bank’s Project Monitoring Reports.

      - Project Monitoring Report (PMR): This instrument, prepared internally by the Bank, will be used by the Bank to track achievement of project outputs and outcomes as well as project costs during implementation. The PMR will be prepared semi-annually by the Bank and provide information on the 6-month period prior to its preparation. Specifically, the PMR will track: (i) delivery of annual targets for output indicators over the 6-month period; (ii) total amount expended for each expected output during the 6-month period; and (iii) total sum of amounts expended for all outputs. Baseline figures will be drawn from the RF and detailed budget prepared as part of project preparation; but may be updated over the course of project execution, upon EA request and Bank no objection.

  - Bank supervision of project execution will be carried out by specialists from the Institutional Capacity of the State (IFD/ICS) and the Fiscal and Municipal Management (IFD/FMM) divisions; with support from the Office of Fiduciary Monitoring and Procurement for Operations (VPC/FMP) and the Country Office of the Bank in Trinidad and Tobago (CCB/CTT). In coordination with the PIU, the Bank will convene semi-annual meetings to monitor technical issues and the pace of the project execution; as well as conduct at least one inspection mission per year to review PIU fiduciary management during project execution.

  - The project team responsible for the design of the Program will continue to be involved during implementation.

  - The collection and compilation of data from the different sources will be monthly carried out in-house by the MoFE, in partnership with the component’s team leaders and will be consolidated by the PIU in the Semiannual Progress Report. These reports will be used to update the Project Monitoring Report (PMR). The products’ annual costs are detailed in a spreadsheet prepared by the project team.

  - For data collection will be necessary to identify all sources/systems and responsible from where the information will be extracted, aiming at to create a direct relation with the supervisors of the corresponding entities, aiming at to facilitate the collection of the information according to the timetable presented in Table 3.

  - The information will be registered using a set of forms (questionnaires), according to the indicators presented in the Result Matrix, which will provide timely progress information for consultation. The information will be consolidated by year and the distortion will justified. The data collection forms are available in the Annex 1 of this document.

  - Additionally, in a trimestral basis, the PIU coordinator will carry out interviews with the main stakeholders to review the collection and consolidation of information, as well as will evaluate the objective’s deviations and possible actions for mitigation.

| Table 3 – Data Collection Activities and Timetable |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Monitoring Activities/Products per Activity | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Responsible | Project Cost (US$) | Funding |
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |  |  |  |
| 1. Identification of the sources/systems/responsible from where the information will be collected |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MoFE, PIU Monitoring Specialist, Bank Project Team |  | TT-L1042 (Program Administration) |
| 2. Preparation of the control forms to consolidate and evaluate the information |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  |  | PIU, and Bank Project Team |  | TT-L1042 (Program Administration) |
| 3. Information collection |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x |  | x |  | x | PIU |  | TT-L1042 (Program Administration) |
| 2. AOP |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x | PIU | 0* | TT-L1042 (Program Administration) |
| 3. Procurement Plan |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x | PIU | 0* | TT-L1042 (Program Administration) |
| 4. PEP | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PIU | 0* | TT-L1042 (Program Administration) |
| 5. Semi-annual Progress Reports |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x | PIU | 50,000 | TT-L1042 (Program Administration) |
| 6. Project Monitoring Report |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x | IDB | 0 | TT-L1042 (Program Administration) |
| *Total Cost (the cost of PIU staff is not reflected herein, as these costs are recurrent over project execution): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 250,000 | TT-L1042 (Program Administration) |

- Evaluation

  - Three evaluations will be carried out periodically during project execution: a Project Completion Report (PCR), to be prepared by the Bank; and mid-term and final evaluations, to be prepared by the PIU.

  - Project Completion Report: The PCR will be prepared by the Bank when 95% of project financing has been disbursed and presented within 180 days of project closure. The final evaluation report described below will be an annex to the PCR. The PCR will use the reflective evaluation methodology described below and seek to augment the information provided by the Government in its evaluations by including analysis of Bank performance in the execution of the project.

  - Mid-term and Final Evaluations. When 60% and 90% of the loan resources have been disbursed, respectively, the PIU will hire an independent consultant to conduct mid-term and final evaluations of the project, respectively. The Final Evaluation will include a Reflective Evaluation and a Financial Analysis. Potential users of the mid-term and final evaluations include Bank personnel, the MoFE, and relevant stakeholders. These evaluations will serve as inputs in the preparation of the PCR. The main objective of the evaluations is to determine whether project activities and outputs contributed to the delivery of expected outcomes, as presented in the Results Framework.

  - The approach for the mid-term and final evaluations has been agreed to by the Bank and the Government of the Republic of Trinidad and Tobago. The PIU will oversee the planning, administration and execution of financial resources necessary for the elaboration and submission of evaluation reports. The PIU will hire 3 independent consultants to carry out the mid-term and final evaluations. Annex I presents the Terms of reference for these consultancies. The mid-term evaluation will comprise a reflective evaluation solely, while the final evaluation will comprise both reflective and financial evaluations. The reflective evaluation methodology entails review and analysis of actions and resulting outputs and outcomes to assess performance and factors contributing to quality of the performance, methods for improving performance, and lessons learned. The financial evaluation methodology is presented in Optional Electronic Link #2 of the Loan Proposal.

- A.	Reflective Evaluation

  - Indicators to be evaluated:

Table 4- Reflective Evaluation Indicators

| Indicators | Unit of Measure | Baseline |  |  | Targets |  |  |  |  | Source/Means of verification | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Value |  | Year | 2015 | 2016 | 2017 | 2018 | 2019 |  |  |
| 1. Increase strategicness in the allocation of public resources |  |  |  |  |  |  |  |  |  |  |  |
| PEFA Performance Indicator 5 Classification of the budget | PEFA PI-5 Score | C | 2014 |  |  |  | C+ |  | B | Public Financial management Performance Measurement Frame work (PEFA) Report to be provided by the MoFE |  |
| PEFA Performance Indicator 12 Multiyear Perspective in fiscal planning, expenditure policy, and budgeting | PEFA PI-12 Score | C+ | 2014 |  |  |  | B |  | B+ | Public Financial management Performance Measurement Frame work (PEFA) Report to be provided by the MoFE |  |
| 2. Increase independence in the control and stewardship of public resources |  |  |  |  |  |  |  |  |  |  |  |
| PEFA Performance Indicator 21 Effectiveness of Internal Audit | PEFA PI-21Score | C | 2014 |  |  |  | C+ |  | B | Public Financial management Performance Measurement Frame work (PEFA) Report to be provided by the MoFE |  |
| 4. Increase the effectiveness of information management |  |  |  |  |  |  |  |  |  |  |  |
| PEFA Performance Indicator 22 Timeliness and Regularity of Bank reconciliation | PEFA PI-22 Score | C | 2008 |  |  |  | C+ |  | B | Public Financial management Performance Measurement Frame work (PEFA) Report to be provided by the MoFE | According to the definition of the PEFA indicator the suspense account is part of the measurement |
| Annual balance of the Suspense Account in constant prices | TT$ billion | 6.241 | Average 2001 to 2014 |  |  |  |  |  | 0.0 FY 2019/2020 | Annual Financial Statement Report prepared by the Auditor General Office |  |
| Intermediate Outcome |  |  |  |  |  |  |  |  |  |  |  |
| LM using the Integrated Financial Management System (IFMIS) | Percentage | 0 | 2015 |  | IFMIS functional specification and bidding process performed | 10 IFMIS implemented as a pilot in 10% LM | 50 | 40 | 100 | Report from the MoFE generated using IFMIS, showing the Financial Statement of the 34 LM. In 2017, the IFMIS will be piloted in three Ministries prior to full roll out. |  |

  - Reflective evaluation methodology is recommended for programs that involve complex, long-term reforms as it captures both quantitative and qualitative changes. The reflective evaluation will provide critical information regarding what works and what doesn’t work, as well as lessons learned that will be useful for future projects.

  - The following main questions will be asked by the independent consultant, hired to conduct the mid-term and final reflective evaluations to guide the evaluation process:

    - Did the Government increase the efficacy of public financial management processes through automation to better plan, allocate, and report the use of public resources? Did this contribute to an increase in the PEFA indicator scores in the 4 PFM areas addressed by the operation?

    - Did the project contribute to a reduction in the time necessary to consolidate the information required to prepare the annual Public Accounts report from 15 days to 1 day?

    - Did the project contribute to the Government expanding the length of planning perspective period from 1 to 3 years?

    - Did the project contribute to increasing the percentage of Line Ministry overpayments recovered by internal audit, raising the percent amount of number of overpayments recovered/amount of total overpayments from 59.6% to 90%?

    - Did the Program provide sufficient resources to the GoTT to be able to decrease the annual average percentage between the balances of the suspense and the exchequer accounts, reducing annual average balance of the suspense account / annual average balance of the exchequer account from 21% to 5%?

    - Did the Program provide enough institutional capacity to the GoTT to increase the IT governance quality score of the Central IT Unit (CITU), Budget and Treasury Divisions, rising the IT governance quality Score from 2 to 4? (out of 5)?

- B.	Financial Evaluation

  - Indicators to be evaluated:

| Table 5 - From the Result Matrix |  |  |  |
| --- | --- | --- | --- |
| Outcome Indicator | Unit of measurement | Frequency of Measurement | Source |

| Annual balance of the Suspense Account in constant prices. | TT$ billion | On a biannual basis | Annual Financial Statement Report prepared by the Auditor General Office |
| --- | --- | --- | --- |

  - In addition to applying the methodology used in the Financial Analysis presented as Optional Electronic Link #2 of the Loan Proposal, the financial evaluation will seek to identify benefits it was not possible to quantify during project preparation. The ex-post evaluation will update the current controls/tables with information related to the year of the evaluation. In this context, an ex-ante Financial Evaluation will be carried out presenting the following estimation and recommendation:

    - The Financial Analysis prepared during project design presented the estimated financial benefits to be generated by the project. According to the baseline financial estimate presented in the analysis, the project was expected to generate a total financial benefit of TT$4.78 million accrued in 2018.

    - The Financial Analysis estimates the project’s Internal Rate of Return as 5%, an estimated Net Present Value of US$21.57 million in 2045 (20 years), and a cost-benefit ratio of 2.36, using the IDB standard discount rate of 12%.

    - Based on these estimates and the sensitivity analysis, the project was deemed to have strong economic viability, justifying the project’s US$40 million investment.

    - Additional costs associated with IT infrastructure were taken into consideration. From 2016 onwards, a maintenance cost will be included (licenses, upgrades, and program management). It is estimated that those costs are a 5% of the total cost of Component 2 (representing approximately US$1.2 million).

  - Working plan and costs for the evaluation. Table 6 presents evaluation timelines and budget. Annual budget targets are presented in Tables 1 and 2.

| Table 6 - Work Plan for ex-post Evaluation (Reflective and Financial Analysis) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Main Activities | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Responsible |  | Cost (US$) | Funding |
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |  |  |  |  |
| 1. Reflective Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 Consultants Hiring |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  | x |  |  |  |  | PIU |  | 60,000 | TT-L1042 |
| 1.2 Fine Tune of the Instruments and methodology |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  | x |  |  |  |  | Consultant |  |  |  |
| 1.3 Data Collection |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  | x |  |  |  |  |  |  |  |
| 1.4 Data Analysis |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  | x |  |  |  |  |  |  |  |
| 1.5 Draft Report |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  | x |  |  |  |  |  |  |
| 1.6 Final Report |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  | x |  |  |  |  |  |  |
| 1.7 Dissemination of information |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  | x |  |  | PIU |  |  |  |
| 2. Financial Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 Consultants Hiring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  | PIU |  | 60,000 | TT-L1042 |
| 2.2 Fine Tune of the Instruments and methodology |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  | Consultant |  |  |  |
| 2.3 Data Collection |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  | x |  |  |  |  |  |
| 2.4 Data Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  | x |  |  |  |  |
| 2.5 Draft Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  | x |  |  |  |  |
| 2.6 Final Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  | x |  |  |  |  |
| 2.7 Dissemination of information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  | x | PIU |  |  |  |
| 3. PCR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 Consultants Hiring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  | IDB |  | 0 | TT-L1042 |
| 4.2 Fine Tune of the Instruments and methodology |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x |  |  |  |  |  |  |
| 4.3 Data Collection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x |  |  |  |  |  |  |
| 4.4 Data Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x |  |  |  |  |
| 4.5 Draft Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |
| 4.6 Final Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |
| 4.7 Dissemination of information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | PIU |  |  |  |
| Total cost (the cost of PIU staff is not reflected herein, as these costs are recurrent over project execution) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 120,000 |  | TT-L1042 |

ANNEX I

EVALUATION CONSULTANCY

DRAFT TERMS OF REFERENCE

- OBJECTIVE OF THE CONSULTANCY

  - Perform the Program evaluation using: (i) Reflective and (ii) Ex-post Financial Analysis; as well as the preparation of the respective reports for review and submission to the Division. These reports will be an input to the Project Completion Report (PCR).

- ACTIVITIES

  - In direct coordination with sector specialists, review the documentation for the execution of the program. In particular, assess the results achieved according to the targets in the Results Framework and Financial Analysis.

  - Perform a Reflective evaluation, based on the results related to the Program components’ activities, taking into account the baselines established in the Result Matrix.

  - Perform an Ex-Post Financial Analysis using the same methodology applied to estimate the project return benefits comparing and justifying the deviations.

  - Preparation of the respective reports, highlighting deviations, and related recommendations for improvement.

- EXPECTED OUTPUTS

  - Intermediate Evaluation Report comprising the 3 mentioned methodologies, with text and graphics, to be reviewed by the sector specialist who oversees the project. The report should include all areas specified in the format, with special emphasis on the project results and lessons learned.

- CHARACTERISTICS OF THE CONSULTANCY

  - Consultancy type: International individual consultant.

  - Duration: 120 non consecutives days in a period of 5 years.

  - Place of work: Place of residence and Trinidad and Tobago

  - Qualifications: Graduate degree in economics with a career spanning over 5 years in evaluation of projects, including PEFA evaluations. Preference will be given to consultants with prior experience in the preparation of IDB projects or projects funded by multinational agencies.

  - Payment: the consultant will be paid in the following manner:

- A first payment of 15% of the contract amount 15 days after signing it, upon delivery of a work plan to the satisfaction of the IDB.

- A second payment 30% upon delivery and approval of the interim evaluation including the 3 methodologies to the satisfaction of the IDB.

- A final payment of 55% upon delivery and approval of the final evaluation including the 3 methodologies to the satisfaction of the IDB.

  - Budget: The evaluations will be covered by Program funds. The cost of the evaluation is estimated at approximately 120 days during the five-year period between 2015 and 2019. There is no extra budget needed for data collection. All costs are detailed in Tables 3 and 6, under the assumption of that the daily rate of the consultant is USD 500.

The ministries will receive training and equipment under the project to use the IFMIS. No formal agreements are required for the ministries to participate in or benefit from project activities.

The AOP, presented by November 30th each year, will detail implementation plans for the following year; and include annual goals, budget, and implementation schedule for each programmed activity. The AOP for the first year is contained in the Project Execution Plan.

GFS is the budget classification system recommended by the IMF and is considered the best practice for budget classification.

As determined by the Project-financed report analyzing all the regulatory changes required to allow for the implementation of a GFS-compliant COA

Requirements as defined in an approved report carried out by the MoFE in 2012 and presented to the Bank  (IDBDocs #39373855).

GFS is the budget classification system recommended by the IMF and is considered the best practice for budget classification.

As determined by the Project-financed report analyzing all the regulatory changes required to allow for the implementation of a GFS-compliant COA

Only one outcome from Component II was considered in the Financial Analysis, because it easier to quantify and the return benefits completely justify the investment.