## Sheet1
Inter-American Development Bank
ORP/GCM
PROCUREMENT PLAN FOR BANK EXECUTED OPERATIONS
Country: Paraguay | [5 empty] | Executing Agency: IDB | [7 empty] | UDR: HQ
Project number: PR-T1249 |  |  |  |  | Title of Project: Support to structure and implement an energy efficiency financing strategy for PYMES with AFD; as an operational support to loan PR-L1146
Period covered by the Plan: [36 months] |  |  |  |  | Total Project Amount: |  | 2300000
Component | Procurement Type (1) (2) | Service type (1) (2) | Description | Estimated contract cost (US$) | Selection Method (2) | Type of Contract | Source of Financing and Percentage |  |  |  | Estimated date of the procurement notice | Estimated contract start date | Estimated contract length | Comments
[7 empty] | IDB/MIF |  | Other External Donor
[7 empty] | Amount | % | Amount | % |  |  |  |  | Direct Contracting
Select comp | Select Proc. Type | Goods Included in Firm Cons. RFP | Consultant 1: brief description |  | select method | Select Cont. Type |  |  |  |  | 2016-03-01 |  |  |  | International Competitive Bidding
Component 1 | A. Consulting services | Individual Consultant (AM-650) | Consultant 1 Development of a standard performance contract for risk sharing between SMEs and ESTPs | 60600 | IICQ | Lump Sum | 60600 | 100% | 0 | 0% |  | Q1 2019 | 12 months |  | National Competitive Bidding
Component 1 | A. Consulting services | Individual Consultant (AM-650) | Consultant 2 Development of insurance policy covering energy savings | 55600 | IICQ | Lump Sum | 55600 | 100% | 0 | 0% |  | Q1 2019 | 12 months |  | Shopping
Component 1 | A. Consulting services | Individual Consultant (AM-650) | Consultants 3,4 Develop methodologies accounting for technology / project level energy savings | 347900 | IICQ | Lump Sum | 347900 | 100% | 0 | 0% |  | Q1 2019 | 12 months |  | Least-Cost Selection
Component 1 | A. Consulting services | Individual Consultant (AM-650) | Consultant 5 Development of a Business Plan for the Project promotion and execution | 118900 | IICQ | Lump Sum | 118900 | 100% | 0 | 0% |  | Q1 2019 | 10 months |  | Quality and Cost Based Selection
Component 1 | A. Consulting services | Consulting Firm (GN-2765) | Consulting firm Hiring and operationalization of validators | 170000 | SSS | Lump Sum | 170000 | 100% | 0 | 0% |  | Q1 2019 | 12 months |  | Quality Based Selection
Component 1 | A. Consulting services | Individual Consultant (AM-650) | Consultant Establishment at AFD of a business unit dedicated for EE financing | 198900 | IICQ | Lump Sum | 198900 | 100% | 0 | 0% |  | Q3 2019 | 12 months |  | Selection Based on the Consultants' Qualifications
Component 1 | A. Consulting services | Individual Consultant (AM-650) | Consultants 7,8,9 support for projects (Including Project and Pipeline Development resources.) | 500000 | IICQ | Lump Sum | 500000 | 100% | 0 | 0% |  | Q1 2020 | 18 months |  | Selection under a Fixed Budget
Component 1 | A. Consulting services | Consulting Firm (GN-2765) | Consulting firm Establishment of electronic registry system for monitoring and evaluation of projects and program’s results | 89000 | SSS | Lump Sum | 89000 | 100% | 0 | 0% |  | Q1 2020 | 24 months |  | Individual Consultant
Component 2 | A. Consulting services | Individual Consultant (AM-650) | Consultant 10 Training of AFD staff on Project mechanisms and methodologies | 69600 | IICQ | Lump Sum | 69600 | 100% | 0 | 0% |  | Q1 2020 | 6 months
Component 2 | C. Non consulting services | Goods included in Cons. Firm RFP | Training activities (workshops, seminars, etc.) to inform and train five LFIs and its staff on financing EE projects | 65300 |  | Framework Agreement | 65300 | 100% | 0 | 0% |  | Q1 2020
Component 2 | A. Consulting services | Individual Consultant (AM-650) | Consultants 11, 12 Two local technical validators informed and trained about Project methodology. | 16300 | IICQ | Lump Sum | 16300 | 100% | 0 | 0% |  | Q1 2020 | 12 months
Component 2 | C. Non consulting services | Goods included in Cons. Firm RFP | Training technology solution providers about Program mechanisms | 38300 |  | Framework Agreement | 38300 | 100% | 0 | 0% |  | Q1 2020
Component 2 | C. Non consulting services | Goods included in Cons. Firm RFP | Training of SMEs on Program mechanisms | 76600 |  | Framework Agreement | 76600 | 100% | 0 | 0% |  | Q1 2020
Component 2 | A. Consulting services | Individual Consultant (AM-650) | Consultant 13 Development of products/publications, knowledge sharing events, country market reports published, and webinars | 193000 | IICQ | Lump Sum | 193000 | 100% | 0 | 0% |  | Q4 2020 | 6 months
Component 3 | A. Consulting services | Individual Consultant (AM-650) | Consultant 14 Develop methodology for monitoring the program results and of fuel wood market developments and informing market actors | 80000 | IICQ | Lump Sum | 80000 | 100% | 0 | 0% |  | Q3 2019 | 12 months
Component 3 | A. Consulting services | Individual Consultant (AM-650) | Consultant 15 Complement and develop in inclusive dialogue round table discussions | 80000 | IICQ | Lump Sum | 80000 | 100% | 0 | 0% |  | Q3 2019 | 12 months
Component 3 | A. Consulting services | Individual Consultant (AM-650) | Consultants 16, 17 Capacity Building and Awareness Campaign to inform on financial, economic, and environmental risks of unsustainable fuel wood use for industry and collect lessons learned from the program. | 140000 | IICQ | Lump Sum | 140000 | 100% | 0 | 0% |  | Q3 2019 | 12 months
Prepared by: | Maria Netto (IFD/CMF) |  | TOTALS | 2300000 |  |  | 2300000 | 100% | 0 | 0%
(1) Grouping together of similar procurement is recommended, such as publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) (i) Individual consultants: ICQ: Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection. Selection process to be done in accordance with AM-650.
(2) (ii) Consulting firms: Per GN-2765-1, Consulting Firm selection methods for Bank-executed Operations are: Single Source Selection (SSS); Simplified Competitive Selection (<=250K) (SCS); Fully Competitive (>250K) (FCS); and Framework Agreement Task Order (TO). All Consulting Firm selection processes under this policy must use the electronic module in Convergence.
(2) (iii) Goods: Per GN-2765-1, par. A.2.2.c: "The procurement of goods and related services, except when such goods and related services are necessary to achieve the objectives of the Bank-executed Operational Work and are included in the consulting services contract and represent less than ten percent (10%) of the consulting services contract value."
Table for Data Validation
Select Comp: | Select Procurement Type: | Select Service Type: | description | amount | Select Method: | Select Cont. Type:
Component 1 | A. Consulting services | Individual Consultant (AM-650) |  |  | SSS | Lump Sum
Component 2 | B. Goods (2)(iii) | Consulting Firm (GN-2765) |  |  | IICQ | Framework Agreement
Component 3 | C. Non consulting services | Goods included in Cons. Firm RFP |  |  | SCS
Component 4 |  | Corporate Procurement (GN-2303) |  |  | FCS
Component 5 |  |  |  |  | TO