## PEP
PEP CLIMATE VULNERABILITY REDUCTION PROGRAM (BL-L1028) | Costo |  |  | 2017 |  | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
|  | Start | Finish | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April
Board Approval |  | Wed 06/12/17 | Wed 06/12/17
Loan Efectivnes |  | Thu 15/03/18 | Fri 16/03/18
Conditions Before the First Disbursement |  | Thu 18/01/18 | Tue 17/04/18
Contratación personal |  | Thu 18/01/18 | Tue 17/04/18
Validacion Manual Operativo |  | Fri 16/03/18 | Tue 03/04/18
Elegibilidad |  | Tue 17/04/18 | Wed 18/04/18
First disbursement |  | Wed 18/04/18 | Thu 03/05/18
Last disbursement |  | Mon 14/03/22 | Tue 15/03/22
Inclusion of steering comitee as part of the Program Operational Manual |  | Fri 16/03/18 | Tue 27/03/18
Appropiatte planning to implement the works during the dry season. |  | Tue 17/04/18 | Mon 08/11/21
Signing of agreements with the beneficiaries for the maintenance of the works (CCVC, BCC, CZMAI) |  | Thu 14/12/17 | Fri 15/12/17
Implement a traning program with the MoW |  | Thu 17/10/19 | Thu 09/04/20
Start-up workshop that includes review of risk management and mitigation actions of the program, regularization of land, actions associated with the implementation of the environmental and social management plan, resettlement, compensation processes, etc. |  | Mon 16/04/18 | Tue 17/04/18
Component 1: Risk Reduction |  | Tue 12/09/17 | Mon 11/04/22
Protective Works Package 1 (Belize) |  | Thu 16/11/17 | Thu 01/07/21
Delivery final design Package 1 |  | Wed 22/11/17 | Thu 23/11/17
Request environmental clearance from DOE |  | Fri 02/02/18 | Thu 03/05/18
Construction Works Package 1 |  | Wed 07/03/18 | Mon 28/06/21
Procurement process |  | Wed 07/03/18 | Wed 05/09/18
(Preparation of Tech. Specs) and bidding docs. |  | Wed 07/03/18 | Thu 15/03/18
Non objection IADB |  | Thu 15/03/18 | Tue 20/03/18
Invites to pre-qualified firms |  | Tue 20/03/18 | Thu 29/03/18
Interest bidders request bidding docs. And prepare offer |  | Thu 29/03/18 | Mon 04/06/18
Bid opening meeting |  | Mon 04/06/18 | Tue 05/06/18
Evaluation of proposals |  | Tue 05/06/18 | Tue 17/07/18
Non-Objection from IDB (evaluation and contract draft) |  | Tue 17/07/18 | Fri 20/07/18
Negotiation of Contract |  | Fri 20/07/18 | Fri 03/08/18
Approval from Financial Sec |  | Fri 03/08/18 | Fri 17/08/18
Aproval Contractor General |  | Fri 17/08/18 | Tue 21/08/18
Signature of contract (including time for performance guaratee and insurances) |  | Tue 21/08/18 | Tue 04/09/18
Award of contract notification sent to short-listed bidders and publication |  | Tue 04/09/18 | Wed 05/09/18
Execution of works: Package 1 | 3478348 | Tue 11/09/18 | Thu 01/07/21 | [11 empty] | 674218 | 147262 | 214524 | 0 | 100000 | 100000 | 200000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 103400 | 0 | 167262 | 107262 | 107262 | 107262 | 114521 |  | 183744 | [11 empty] | 551631
Works Supervision Package 1 |  | Thu 16/11/17 | Wed 29/07/20
Procurement process |  | Thu 16/11/17 | Wed 29/08/18
TORs preparation (selection criteria) |  | Thu 16/11/17 | Thu 14/12/17
Preparation of Request for expression of interest |  | Thu 14/12/17 | Thu 21/12/17
Seek Non-Objection for TOR and Request for Expressions of Interest |  | Thu 21/12/17 | Tue 26/12/17
Non-Objection from IADB |  | Tue 26/12/17 | Wed 03/01/18
Publication of Request for Expression of interest |  | Wed 03/01/18 | Tue 23/01/18
Prepare and submit draft request for proposal for informal review |  | Tue 23/01/18 | Tue 23/01/18
Receive and evaluate expressions of interest |  | Tue 23/01/18 | Tue 06/02/18
Submit to IDB draft request for proposals including shortlist of firms |  | Tue 06/02/18 | Tue 13/02/18
Non-Objection from IADB |  | Tue 13/02/18 | Tue 20/02/18
Issue RFP to shortlisted firms |  | Tue 20/02/18 | Thu 22/02/18
Notify evaluators of the evaluation committee |  | Thu 22/02/18 | Fri 23/02/18
Reciept of proposals and opening of technical proposal |  | Fri 23/02/18 | Thu 03/05/18
Evaluation of technical proposals |  | Thu 03/05/18 | Thu 17/05/18
Preparation of Evaluation Report and finalization |  | Thu 17/05/18 | Fri 25/05/18
Request non'objection to technical evaluation report and to open financial proposal |  | Fri 25/05/18 | Tue 29/05/18
Non-Objection from IADB |  | Tue 29/05/18 | Tue 05/06/18
Public opening of financial proposals |  | Tue 05/06/18 | Wed 06/06/18
Preparation of combined technical and financial report |  | Wed 06/06/18 | Wed 13/06/18
Request non'objection to enter negotiations with selected firm |  | Wed 13/06/18 | Fri 15/06/18
Non-Objection from IADB |  | Fri 15/06/18 | Fri 22/06/18
Conduct negotiations and prepare draft contract |  | Fri 22/06/18 | Fri 29/06/18
Request approval of draft contract from Ministry of Finance and Contractor General |  | Fri 29/06/18 | Tue 03/07/18
MOF and CG´s approval |  | Tue 03/07/18 | Mon 23/07/18
Draft negotiatied contract to be initalled and submitted to IDB |  | Mon 23/07/18 | Mon 30/07/18
Non-Objection from IADB |  | Mon 30/07/18 | Mon 06/08/18
Finalization of contract |  | Mon 06/08/18 | Mon 13/08/18
Award of contract and request for any advance payment guarantee |  | Mon 13/08/18 | Mon 27/08/18
Notification of award sent to short-listed bidders and publication |  | Mon 27/08/18 | Wed 29/08/18
Execution of supervision: Package 1 | 403109.2 | Thu 30/08/18 | Wed 29/07/20 | [11 empty] | 33592.2 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 |  |  | 33592 | 16796 | 16796 | 50388 | 16796 | 16796 | 16801
Protective Works Package 2 (Belize) |  | Fri 13/07/18 | Mon 11/04/22
Delivery final design Package 2 |  | Fri 13/07/18 | Mon 16/07/18
Request environmental clearance from DOE |  | Mon 16/07/18 | Wed 10/10/18
Construction Work Package 2 |  | Fri 29/11/19 | Thu 27/03/22
(Preparation of Tech. Specs) and bidding docs. |  | Fri 27/03/20 | Fri 03/04/20
Non objection IADB |  | Fri 03/04/20 | Wed 08/04/20
Invites to pre-qualified firms |  | Wed 08/04/20 | Wed 15/04/20
Interest bidders request bidding docs. And prepare offer |  | Wed 15/04/20 | Thu 18/06/20
Bid opening meeting |  | Thu 18/06/20 | Fri 19/06/20
Evaluation of proposals |  | Fri 19/06/20 | Fri 31/07/20
Non-Objection from IDB (evaluation and contract draft) |  | Fri 31/07/20 | Wed 05/08/20
Negotiation of Contract |  | Wed 05/08/20 | Wed 19/08/20
Approval from Financial Sec |  | Wed 19/08/20 | Wed 02/09/20
Aproval Contractor General |  | Wed 02/09/20 | Fri 04/09/20
Signature of contract (including time for performance guaratee and insurances) |  | Fri 04/09/20 | Tue 22/09/20
Award of contract notification sent to short-listed bidders and publication |  | Tue 22/09/20 | Wed 23/09/20
Execution of works: Package 2 | 2739330.07 | Wed 23/09/20 | Thu 27/03/22 | [34 empty] | 80467.82 | 218391.07 | 72511.68 | 47585.79 | 128707.91 | 225692.05 | 159525.3 | 159525.3 | 145023 | 159525.3 | 159525.3 | 159525.3 | 145023 | 145023 | 152274.15 | 166776.45 | 146654.97 | 139949.8 | 127622.88
Works Supervision Package 2 |  | Wed 29/01/20 | Mon 29/03/22
Procurement process |  | Wed 29/01/20 | Mon 09/11/20
TORs preparation (selection criteria) |  | Wed 29/01/20 | Wed 26/02/20
Preparation of Request for expression of interest |  | Wed 26/02/20 | Wed 04/03/20
Seek Non-Objection for TOR and Request for Expressions of Interest |  | Wed 04/03/20 | Tue 10/03/20
Non-Objection from IADB |  | Tue 10/03/20 | Tue 17/03/20
Publication of Request for Expression of interest |  | Tue 17/03/20 | Mon 06/04/20
Prepare and submit draft request for proposal for informal review |  | Mon 06/04/20 | Mon 06/04/20
Receive and evaluate expressions of interest |  | Mon 06/04/20 | Mon 20/04/20
Submit to IDB draft request for proposals including shortlist of firms |  | Mon 20/04/20 | Mon 27/04/20
Non-Objection from IADB |  | Mon 27/04/20 | Tue 05/05/20
Issue RFP to shortlisted firms |  | Tue 05/05/20 | Thu 07/05/20
Notify evaluators of the evaluation committee |  | Thu 07/05/20 | Fri 08/05/20
Reciept of proposals and opening of technical proposal |  | Fri 08/05/20 | Fri 10/07/20
Evaluation of technical proposals |  | Fri 10/07/20 | Fri 24/07/20
Preparation of Evaluation Report and finalization |  | Fri 24/07/20 | Fri 31/07/20
Request non'objection to technical evaluation report and to open financial proposal |  | Fri 31/07/20 | Tue 04/08/20
Non-Objection from IADB |  | Tue 04/08/20 | Tue 11/08/20
Public opening of financial proposals |  | Tue 11/08/20 | Wed 12/08/20
Preparation of combined technical and financial report |  | Wed 12/08/20 | Wed 19/08/20
Request non'objection to enter negotiations with selected firm |  | Wed 19/08/20 | Fri 21/08/20
Non-Objection from IADB |  | Fri 21/08/20 | Fri 28/08/20
Conduct negotiations and prepare draft contract |  | Fri 28/08/20 | Fri 04/09/20
Request approval of draft contract from Ministry of Finance and Contractor General |  | Fri 04/09/20 | Tue 08/09/20
MOF and CG´s approval |  | Tue 08/09/20 | Wed 30/09/20
Draft negotiatied contract to be initalled and submitted to IDB |  | Wed 30/09/20 | Wed 07/10/20
Non-Objection from IADB |  | Wed 07/10/20 | Thu 15/10/20
Finalization of contract |  | Thu 15/10/20 | Thu 22/10/20
Award of contract and request for any advance payment guarantee |  | Thu 22/10/20 | Thu 05/11/20
Notification of award sent to short-listed bidders and publication |  | Thu 05/11/20 | Mon 09/11/20
Execution of supervision: Package 2 | 339932.72 | Mon 09/11/20 | Thu 27/03/22 | [36 empty] | 14045.85 | 20773.54 | 2950.78 | 31868.44 | 23724.28 | 20773.5 | 18885 | 20773.5 | 20773.5 | 20773.5 | 18885 | 18885 | 19829.25 | 21717.75 | 25613.25 | 18885 | 20775.58
Protective Works Package 3 (Caye Caulker y Cayo Goff) |  | Tue 12/09/17 | Fri 24/09/21
Preparing biding documents |  | Thu 23/11/17 | Fri 24/11/17
Inform the Local Tourism Comitee about the interventions planned and coordination activities |  | Fri 22/12/17 | Mon 25/12/17
Requesting to Ministry of Natural Resources for the Village Council to have fill permit to use the Palapa beach area |  | Tue 12/09/17 | Tue 05/12/17
Management of agreements with sellers and verification of legal ownership of land |  | Fri 24/11/17 | Thu 29/03/18
Construction Work Package 3 |  | Mon 08/06/20 | Fri 24/09/21
Procurement process |  | Mon 08/06/20 | Mon 11/01/21
Specific notice for pre- qualification documents and requirements for pre-qualification proposals |  | Mon 08/06/20 | Mon 15/06/20
Non objection IADB |  | Mon 15/06/20 | Mon 22/06/20
Publication |  | Mon 22/06/20 | Mon 06/07/20
Proposal reception |  | Mon 06/07/20 | Mon 17/08/20
Proposal evaluation for pre-qualification |  | Mon 17/08/20 | Tue 15/09/20
Non objection IADB |  | Tue 15/09/20 | Wed 23/09/20
(Preparation of Tech. Specs) and bidding docs. |  | Wed 23/09/20 | Wed 30/09/20
Non objection IADB |  | Wed 30/09/20 | Wed 07/10/20
Invites to pre-qualified firms |  | Wed 07/10/20 | Thu 15/10/20
Interest bidders request bidding docs. And prepare offer |  | Thu 15/10/20 | Thu 12/11/20
Bid opening meeting |  | Thu 12/11/20 | Fri 13/11/20
Evaluation of proposals |  | Fri 13/11/20 | Mon 30/11/20
Non-Objection from IDB (evaluation and contract draft) |  | Mon 30/11/20 | Mon 07/12/20
Negotiation of Contract |  | Mon 07/12/20 | Mon 14/12/20
Approval from Financial Sec |  | Mon 14/12/20 | Tue 29/12/20
Aproval Contractor General |  | Tue 29/12/20 | Thu 31/12/20
Signature of contract (including time for performance guaratee and insurances) |  | Thu 31/12/20 | Fri 08/01/21
Award of contract notification sent to short-listed bidders and publication |  | Fri 08/01/21 | Mon 11/01/21
Execution of works: Package 3 | 874000 | Mon 11/01/21 | Fri 24/09/21 | [39 empty] | 87400 | 98325 | 98325 | 98325 | 196650 | 98325 | 98325 | 98325
Works Supervision Package 3 |  | Mon 13/04/20 | Fri 24/09/21
Procurement process |  | Mon 13/04/20 | Mon 08/02/21
TORs preparation |  | Mon 13/04/20 | Mon 20/04/20
Non-Objection from IADB |  | Mon 20/04/20 | Mon 27/04/20
Ad posting with request for expressions of interest |  | Mon 27/04/20 | Tue 12/05/20
Reception of Expressions of Interest |  | Tue 12/05/20 | Tue 23/06/20
Analysis of expressions of interest |  | Tue 23/06/20 | Tue 21/07/20
Elaboration of short list |  | Tue 21/07/20 | Tue 04/08/20
Preparation of proposal request document |  | Tue 04/08/20 | Tue 18/08/20
Non-Objection from IADB |  | Tue 18/08/20 | Tue 01/09/20
Notification of results to participants |  | Tue 01/09/20 | Tue 08/09/20
Referral of SP to the best evalada of the short list |  | Tue 08/09/20 | Fri 23/10/20
Presentation of proposals |  | Fri 23/10/20 | Mon 26/10/20
Evaluation of technical and economic proposals |  | Mon 26/10/20 | Tue 08/12/20
Non-Objection from IADB |  | Tue 08/12/20 | Tue 22/12/20
Notification of results to participants |  | Tue 22/12/20 | Thu 07/01/21
Publication of the award |  | Thu 07/01/21 | Thu 21/01/21
Contract subscription |  | Thu 21/01/21 | Mon 25/01/21
Sending of signed contract to the IDB |  | Mon 25/01/21 | Mon 08/02/21
Execution of supervision: Package 3 | 87400 | Mon 08/02/21 | Fri 24/09/21 | [39 empty] | 10925 | 10925 | 10925 | 10925 | 10925 | 10925 | 10925 | 10925
Environmental measures | 200000.01 | Thu 14/06/18 | Wed 28/10/20 | [7 empty] | 10958.33 | 14666.66 | 14666.67 | 12666.67 | 15000 | 7000 | 20333.33 | [7 empty] | 7333.33 | 6666.67 | 7666.67 | 6666.67 | 6666.67 | 7333.33 | 6666.67 | 7000 | 7333.33 | 6666.67 | 7333.33 | 7666.67 | 7000 | 6666.67 | 6041.67
Coastal monitoring for Goff's Caye (erosion and coral reef) |  | Fri 19/06/20 | Fri 17/12/21
Procurement process |  | Fri 19/06/20 | Fri 02/04/21
TORs preparation (selection criteria) |  | Fri 19/06/20 | Fri 17/07/20
Preparation of Request for expression of interest |  | Fri 17/07/20 | Fri 24/07/20
Seek Non-Objection for TOR and Request for Expressions of Interest |  | Fri 24/07/20 | Wed 29/07/20
Non-Objection from IADB |  | Wed 29/07/20 | Wed 05/08/20
Publication of Request for Expression of interest |  | Wed 05/08/20 | Tue 25/08/20
Prepare and submit draft request for proposal for informal review |  | Tue 25/08/20 | Tue 25/08/20
Receive and evaluate expressions of interest |  | Tue 25/08/20 | Tue 08/09/20
Submit to IDB draft request for proposals including shortlist of firms |  | Tue 08/09/20 | Wed 16/09/20
Non-Objection from IADB |  | Wed 16/09/20 | Thu 24/09/20
Issue RFP to shortlisted firms |  | Thu 24/09/20 | Mon 28/09/20
Notify evaluators of the evaluation committee |  | Mon 28/09/20 | Tue 29/09/20
Reciept of proposals and opening of technical proposal |  | Tue 29/09/20 | Thu 03/12/20
Evaluation of technical proposals |  | Thu 03/12/20 | Thu 17/12/20
Preparation of Evaluation Report and finalization |  | Thu 17/12/20 | Thu 24/12/20
Request non'objection to technical evaluation report and to open financial proposal |  | Thu 24/12/20 | Tue 29/12/20
Non-Objection from IADB |  | Tue 29/12/20 | Wed 06/01/21
Public opening of financial proposals |  | Wed 06/01/21 | Thu 07/01/21
Preparation of combined technical and financial report |  | Thu 07/01/21 | Thu 14/01/21
Request non'objection to enter negotiations with selected firm |  | Thu 14/01/21 | Mon 18/01/21
Non-Objection from IADB |  | Mon 18/01/21 | Mon 25/01/21
Conduct negotiations and prepare draft contract |  | Mon 25/01/21 | Mon 01/02/21
Request approval of draft contract from Ministry of Finance and Contractor General |  | Mon 01/02/21 | Wed 03/02/21
MOF and CG´s approval |  | Wed 03/02/21 | Tue 23/02/21
Draft negotiatied contract to be initalled and submitted to IDB |  | Tue 23/02/21 | Tue 02/03/21
Non-Objection from IADB |  | Tue 02/03/21 | Wed 10/03/21
Finalization of contract |  | Wed 10/03/21 | Wed 17/03/21
Award of contract and request for any advance payment guarantee |  | Wed 17/03/21 | Wed 31/03/21
Notification of award sent to short-listed bidders and publication |  | Wed 31/03/21 | Fri 02/04/21
Execution | 303691.6 | Mon 31/05/21 | Fri 17/12/21 | [43 empty] | 60738.2 |  |  | 121476.4 |  |  | 121477
Management plans for Palapa beach (Caye Caulker) and Goff's Caye |  | Wed 02/05/18 | Thu 29/11/18
Procurement process |  | Wed 02/05/18 | Fri 03/08/18
TORs preparation |  | Wed 02/05/18 | Wed 16/05/18
Non-Objection from IADB |  | Wed 16/05/18 | Thu 17/05/18
Ad posting with request for expressions of interest |  | Thu 17/05/18 | Tue 22/05/18
Reception of Expressions of Interest |  | Tue 22/05/18 | Wed 23/05/18
Analysis of expressions of interest |  | Wed 23/05/18 | Mon 04/06/18
Elaboration of short list |  | Mon 04/06/18 | Thu 14/06/18
Preparation of proposal request document |  | Thu 14/06/18 | Mon 18/06/18
Non-Objection from IADB |  | Mon 18/06/18 | Wed 20/06/18
Notification of results to participants |  | Wed 20/06/18 | Mon 25/06/18
Referral of SP to the best evalada of the short list |  | Mon 25/06/18 | Mon 02/07/18
Presentation of proposals |  | Mon 02/07/18 | Tue 03/07/18
Evaluation of technical and economic proposals |  | Tue 03/07/18 | Wed 04/07/18
Non-Objection from IADB |  | Wed 04/07/18 | Fri 13/07/18
Notification of results to participants |  | Fri 13/07/18 | Fri 20/07/18
Publication of the award |  | Fri 20/07/18 | Wed 25/07/18
Contract subscription |  | Wed 25/07/18 | Wed 01/08/18
Sending of signed contract to the IDB |  | Wed 01/08/18 | Fri 03/08/18
Execution | 113650 | Fri 03/08/18 | Thu 29/11/18 | [9 empty] | 22730 |  | 45460 | 45460
Component 2: Governance for Disaster Risk Management and Adaptation to Climate Change |  | Fri 14/08/20 | Mon 14/02/22
Risk information system |  | Fri 14/08/20 | Fri 31/12/21
Procurement process |  | Fri 14/08/20 | Mon 31/05/21
TORs preparation (selection criteria) |  | Wed 08/01/20 | Wed 05/02/20
Preparation of Request for expression of interest |  | Wed 05/02/20 | Wed 12/02/20
Seek Non-Objection for TOR and Request for Expressions of Interest |  | Wed 12/02/20 | Mon 17/02/20
Non-Objection from IADB |  | Mon 17/02/20 | Mon 24/02/20
Publication of Request for Expression of interest |  | Mon 24/02/20 | Mon 16/03/20
Prepare and submit draft request for proposal for informal review |  | Mon 16/03/20 | Mon 16/03/20
Receive and evaluate expressions of interest |  | Mon 16/03/20 | Mon 30/03/20
Submit to IDB draft request for proposals including shortlist of firms |  | Mon 30/03/20 | Mon 06/04/20
Non-Objection from IADB |  | Mon 06/04/20 | Mon 13/04/20
Issue RFP to shortlisted firms |  | Mon 13/04/20 | Wed 15/04/20
Notify evaluators of the evaluation committee |  | Wed 15/04/20 | Thu 16/04/20
Reciept of proposals and opening of technical proposal |  | Thu 16/04/20 | Fri 19/06/20
Evaluation of technical proposals |  | Fri 19/06/20 | Fri 03/07/20
Preparation of Evaluation Report and finalization |  | Fri 03/07/20 | Fri 10/07/20
Request non'objection to technical evaluation report and to open financial proposal |  | Fri 10/07/20 | Tue 14/07/20
Non-Objection from IADB |  | Tue 14/07/20 | Tue 21/07/20
Public opening of financial proposals |  | Tue 21/07/20 | Wed 22/07/20
Preparation of combined technical and financial report |  | Wed 22/07/20 | Wed 29/07/20
Request non'objection to enter negotiations with selected firm |  | Wed 29/07/20 | Fri 31/07/20
Non-Objection from IADB |  | Fri 31/07/20 | Fri 07/08/20
Conduct negotiations and prepare draft contract |  | Fri 07/08/20 | Fri 14/08/20
Request approval of draft contract from Ministry of Finance and Contractor General |  | Fri 14/08/20 | Tue 18/08/20
MOF and CG´s approval |  | Tue 18/08/20 | Mon 07/09/20
Draft negotiatied contract to be initalled and submitted to IDB |  | Mon 07/09/20 | Tue 15/09/20
Non-Objection from IADB |  | Tue 15/09/20 | Wed 23/09/20
Finalization of contract |  | Wed 23/09/20 | Wed 30/09/20
Award of contract and request for any advance payment guarantee |  | Wed 30/09/20 | Thu 15/10/20
Notification of award sent to short-listed bidders and publication |  | Thu 15/10/20 | Mon 19/10/20
Execution of the Consulting | 478241 | Mon 19/10/20 | Fri 21/05/21 | [36 empty] | 127531 | 127531 |  | 0 | 95648 |  | 127531
Designing of building codes |  | Fri 02/04/21 | Mon 14/02/22
Procurement process |  | Fri 02/04/21 | Tue 27/07/21
TORs preparation (selection criteria) |  | Fri 02/04/21 | Fri 16/04/21
Request Non-Objection for TOR and evaluation criteria |  | Fri 16/04/21 | Wed 21/04/21
Non-Objection from IADB |  | Wed 21/04/21 | Wed 28/04/21
Draft the Request for Expressions of interest |  | Wed 28/04/21 | Thu 29/04/21
Non-Objection of expression of interest |  | Thu 29/04/21 | Thu 06/05/21
Publication of Request for Expressions of Interest |  | Thu 06/05/21 | Thu 27/05/21
Receive and evaluate CVs |  | Thu 27/05/21 | Thu 03/06/21
Non-Objection from IADB |  | Thu 03/06/21 | Thu 17/06/21
Request approval of draft contract from Ministry of Finance and Contractor General |  | Thu 17/06/21 | Thu 08/07/21
Prepare report and Request Non-Objection to selected candidate and the draft contract |  | Thu 08/07/21 | Tue 13/07/21
MOF and CG´s approval |  | Tue 13/07/21 | Tue 20/07/21
Negotiation and finalisation of Contract |  | Tue 20/07/21 | Tue 27/07/21
Execution of the Consulting | 70000 | Tue 27/07/21 | Mon 14/02/22 | [45 empty] | 14000 |  | 21000 |  | 14000 |  | 21000
Climate risk financing strategy for the tourism and agriculture sectors |  | Thu 04/02/21 | Mon 17/01/22
Procurement process |  | Thu 04/02/21 | Tue 01/06/21
TORs preparation (selection criteria) |  | Thu 04/02/21 | Thu 18/02/21
Request Non-Objection for TOR and evaluation criteria |  | Thu 18/02/21 | Tue 23/02/21
Non-Objection from IADB |  | Tue 23/02/21 | Tue 02/03/21
Draft the Request for Expressions of interest |  | Tue 02/03/21 | Wed 03/03/21
Non-Objection of expression of interest |  | Wed 03/03/21 | Thu 11/03/21
Publication of Request for Expressions of Interest |  | Thu 11/03/21 | Wed 31/03/21
Receive and evaluate CVs |  | Wed 31/03/21 | Wed 07/04/21
Non-Objection from IADB |  | Wed 07/04/21 | Wed 21/04/21
Request approval of draft contract from Ministry of Finance and Contractor General |  | Wed 21/04/21 | Wed 12/05/21
Prepare report and Request Non-Objection to selected candidate and the draft contract |  | Wed 12/05/21 | Mon 17/05/21
MOF and CG´s approval |  | Mon 17/05/21 | Tue 25/05/21
Negotiation and finalisation of Contract |  | Tue 25/05/21 | Tue 01/06/21
Execution of the Consulting | 70000 | Tue 01/06/21 | Mon 17/01/22 | [43 empty] | 14000 |  |  | 28000 |  |  |  | 28000
Project Management |  | Thu 14/06/18 | Wed 06/04/22
Technical Unit |  | Thu 14/06/18 | Wed 06/04/22
PEU Team Recruitment |  | Thu 14/06/18 | Wed 06/04/22
Procurement process |  | Thu 14/03/18 | Thu 29/06/18
Project coordinator |  | Thu 14/03/18 | Thu 29/06/18
Project Manager |  | Thu 14/03/18 | Thu 29/06/19
Coastal engineer |  | Thu 14/03/18 | Thu 29/06/20
Planning and Monitoring Specialist |  | Thu 14/03/18 | Thu 29/06/21
Procurement and Contracting Specialist |  | Thu 14/03/18 | Thu 29/06/22
Financial Management Specialist |  | Thu 14/03/18 | Thu 29/06/23
Specialist in environmental and social issues |  | Thu 14/03/18 | Thu 29/06/24
Account Clerk |  | Thu 14/03/18 | Thu 29/06/25
Driver |  | Thu 14/03/18 | Thu 29/06/26
Payment process | 471600.37 | Thu 19/07/18 | Wed 06/04/22 | [8 empty] | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 12654.17 | 12654.17 | 12654.17 | 12654.17 | 12654.17 | 12654.17 | 12654.17 | 12654.17 | 12654.17 | 12654.17 | 12654.17 | 6395 | 9457 | 6395 | 6395 | 6395 | 6395 | 6395 | 6395 | 6395 | 6395 | 6395 | 5116 | 5116 | 5116 | 5116 | 5116 | 5116 | 5116 | 5116 | 5116 | 5116
Furniture & Equipment |  | Thu 05/07/18 | Mon 01/10/18
Preparation of technical specifications |  | Thu 05/07/18 | Thu 12/07/18
Preparation of CP document and offer request |  | Thu 12/07/18 | Thu 19/07/18
Preparation and delivery of quotes |  | Thu 19/07/18 | Thu 26/07/18
Price comparison and revision of technical specifications |  | Thu 26/07/18 | Mon 30/07/18
IDB Non-Objection Request |  | Mon 30/07/18 | Tue 31/07/18
No IDB objection |  | Tue 31/07/18 | Fri 03/08/18
Notification to bidders |  | Fri 03/08/18 | Tue 07/08/18
Subscription of purchase order |  | Tue 07/08/18 | Thu 09/08/18
Delivery of furniture and equipment |  | Thu 09/08/18 | Thu 30/08/18
Furniture & Equipment | 40000 | Thu 30/08/18 | Mon 01/10/18 | [10 empty] | 4000 | 36000
Vehicle Acquisition |  | Thu 05/07/18 | Mon 01/10/18
Preparation of technical specifications |  | Thu 05/07/18 | Thu 12/07/18
Preparation of CP document and offer request |  | Thu 12/07/18 | Thu 19/07/18
Preparation and delivery of quotes |  | Thu 19/07/18 | Thu 26/07/18
Price comparison and revision of technical specifications |  | Thu 26/07/18 | Mon 30/07/18
IDB Non-Objection Request |  | Mon 30/07/18 | Tue 31/07/18
No IDB objection |  | Tue 31/07/18 | Fri 03/08/18
Notification to bidders |  | Fri 03/08/18 | Tue 07/08/18
Subscription of purchase order |  | Tue 07/08/18 | Thu 09/08/18
Delivery of furniture and equipment |  | Thu 09/08/18 | Thu 30/08/18
Vehicle Delivery | 40000 | Thu 30/08/18 | Mon 01/10/18 | [10 empty] | 4000 | 36000
Operating Expenses (Office Supplies and others) |  | Wed 28/11/18 | Wed 11/08/21
Year 1 | 24957 | Wed 28/11/18 | Wed 19/12/18 | [12 empty] | 10957 | 14000
Year 3 | 50740 | Fri 17/07/20 | Fri 07/08/20 | [32 empty] | 25000 | 25740
Year 4 |  | Wed 21/07/21 | Wed 11/08/21
Annual Evaluations and Audits |  | Thu 12/07/18 | Mon 18/04/22
Reviews |  | Fri 14/08/20 | Tue 05/04/22
Intermediate evaluation |  | Fri 14/08/20 | Tue 23/02/21
Procurement process |  | Fri 14/08/20 | Fri 27/11/20
Payment process | 35000 | Fri 27/11/20 | Tue 23/02/21 | [37 empty] | 15000 | 0 | 20000
Final evaluation |  | Thu 15/07/21 | Fri 18/02/22
Procurement process |  | Thu 15/07/21 | Fri 26/11/21
Payment process | 30000 | Fri 26/11/21 | Fri 18/02/22 | [49 empty] | 15000 |  | 15000
Impact evaluation |  | Mon 19/07/21 | Tue 05/03/22
Procurement process |  | Mon 19/07/21 | Fri 12/11/21
Payment process | 50000 | Fri 12/11/21 | Tue 05/03/22 | [49 empty] | 10000 |  | 20000 | 20000
Annual audits |  | Thu 12/07/18 | Mon 18/03/22
Audit Year 1 | 20000 | Thu 12/07/18 | Fri 28/12/18 | [11 empty] | 6400 | 6800 | 6800
Audit Year 2 | 20000 | Tue 08/10/19 | Mon 06/01/20 | [23 empty] | 5958.33 | 6666.67 | 6666.67 | 708.33
Audit Year 3 | 20000 | Fri 09/10/20 | Thu 07/01/21 | [35 empty] | 4958.33 | 6666.67 | 7333.33 | 1041.67
Audit Year 4 | 40000.33 | Tue 14/09/21 | Mon 18/03/22 | [46 empty] | 3166.67 | 5333.33 | 5600 | 6133.33 | 5600 | 5333.33 | 8833.67
TOTAL BUDGET | 10000000.3
Monthly Expense | [10 empty] | 10958.33 | 30654.16 | 53384.17 | 36654.17 | 862657.7 | 250262.5 | 288440.83 | 32783.5 | 132783.5 | 132783.5 | 232783.5 | 132783.5 | 132783.5 | 132783.5 | 136783.5 | 136116.84 | 143075.17 | 129387.51 | 25987.51 | 221549.83 | 143378.84 | 143712.17 | 177637.5 | 150637.84 | 36783.5 | 239606.67 | 42197 | 93529.49 | 235786.07 | 227150.2 | 224618.66 | 139095.36 | 382280.49 | 394542.58 | 295943.8 | 407084 | 467728 | 846295.8 | 308664.8 | 430917.07 | 195357.33 | 182819.4 | 360220.53 | 210984.22 | 225284.13 | 182348.13
Cumulative Expensive | [10 empty] | 10958.33 | 41612.49 | 94996.66 | 131650.83 | 994308.53 | 1244571.03 | 1533011.86 | 1565795.36 | 1698578.86 | 1831362.36 | 2064145.86 | 2196929.36 | 2329712.86 | 2462496.36 | 2599279.86 | 2735396.7 | 2878471.87 | 3007859.38 | 3033846.89 | 3255396.72 | 3398775.56 | 3542487.73 | 3720125.23 | 3870763.07 | 3907546.57 | 4147153.24 | 4189350.24 | 4282879.73 | 4518665.8 | 4745816 | 4970434.66 | 5109530.02 | 5491810.51 | 5886353.09 | 6182296.89 | 6589380.89 | 7057108.89 | 7903404.69 | 8212069.49 | 8642986.56 | 8838343.89 | 9021163.29 | 9381383.82 | 9592368.04 | 9817652.17 | 10000000.3
Annual Disbursement | [10 empty] | 1533011.86 | [6 empty] | 1500835.03 | [11 empty] | 1936587.77 | [11 empty] | 4410949.16 | [11 empty] | 618616.48
% accumulated | [10 empty] | 15.33% | [6 empty] | 30.34% | [11 empty] | 49.7% | [11 empty] | 93.81% | [11 empty] | 100%
AOP CLIMATE VULNERABILITY REDUCTION PROGRAM (BL-L1028) | Costo |  |  | 2017 |  | 2018 | [11 empty] | 2019
|  | Start | Finish | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December
Board Approval |  | Wed 06/12/17 | Wed 06/12/17
Loan Efectivnes |  | Thu 15/03/18 | Fri 16/03/18
Conditions Before the First Disbursement |  | Thu 18/01/18 | Tue 17/04/18
Contratación personal |  | Thu 18/01/18 | Tue 17/04/18
Validacion Manual Operativo |  | Fri 16/03/18 | Tue 03/04/18
Elegibilidad |  | Tue 17/04/18 | Wed 18/04/18
First disbursement |  | Wed 18/04/18 | Thu 03/05/18
Last disbursement |  | Mon 14/03/22 | Tue 15/03/22
Inclusion of steering comitee as part of the Program Operational Manual |  | Fri 16/03/18 | Tue 27/03/18
Appropiatte planning to implement the works during the dry season. |  | Tue 17/04/18 | Mon 08/11/21
Signing of agreements with the beneficiaries for the maintenance of the works (CCVC, BCC, CZMAI) |  | Thu 14/12/17 | Fri 15/12/17
Implement a traning program with the MoW |  | Thu 17/10/19 | Thu 09/04/20
Start-up workshop that includes review of risk management and mitigation actions of the program, regularization of land, actions associated with the implementation of the environmental and social management plan, resettlement, compensation processes, etc. |  | Mon 16/04/18 | Tue 17/04/18
Component 1: Risk Reduction |  | Tue 12/09/17 | Mon 11/04/22
Protective Works Package 1 (Belize) |  | Thu 16/11/17 | Thu 01/07/21
Delivery final design Package 1 |  | Wed 22/11/17 | Thu 23/11/17
Request environmental clearance from DOE |  | Fri 02/02/18 | Thu 03/05/18
Construction Works Package 1 |  | Wed 07/03/18 | Mon 28/06/21
Procurement process |  | Wed 07/03/18 | Wed 05/09/18
(Preparation of Tech. Specs) and bidding docs. |  | Wed 07/03/18 | Thu 15/03/18
Non objection IADB |  | Thu 15/03/18 | Tue 20/03/18
Invites to pre-qualified firms |  | Tue 20/03/18 | Thu 29/03/18
Interest bidders request bidding docs. And prepare offer |  | Thu 29/03/18 | Mon 04/06/18
Bid opening meeting |  | Mon 04/06/18 | Tue 05/06/18
Evaluation of proposals |  | Tue 05/06/18 | Tue 17/07/18
Non-Objection from IDB (evaluation and contract draft) |  | Tue 17/07/18 | Fri 20/07/18
Negotiation of Contract |  | Fri 20/07/18 | Fri 03/08/18
Approval from Financial Sec |  | Fri 03/08/18 | Fri 17/08/18
Aproval Contractor General |  | Fri 17/08/18 | Tue 21/08/18
Signature of contract (including time for performance guaratee and insurances) |  | Tue 21/08/18 | Tue 04/09/18
Award of contract notification sent to short-listed bidders and publication |  | Tue 04/09/18 | Wed 05/09/18
Execution of works: Package 1 | 2139404 | Tue 11/09/18 | Thu 01/07/21 | [11 empty] | 674218 | 147262 | 214524 | 0 | 100000 | 100000 | 200000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 103400 | 0
Works Supervision Package 1 |  | Thu 16/11/17 | Wed 29/07/20
Procurement process |  | Thu 16/11/17 | Wed 29/08/18
TORs preparation (selection criteria) |  | Thu 16/11/17 | Thu 14/12/17
Preparation of Request for expression of interest |  | Thu 14/12/17 | Thu 21/12/17
Seek Non-Objection for TOR and Request for Expressions of Interest |  | Thu 21/12/17 | Tue 26/12/17
Non-Objection from IADB |  | Tue 26/12/17 | Wed 03/01/18
Publication of Request for Expression of interest |  | Wed 03/01/18 | Tue 23/01/18
Prepare and submit draft request for proposal for informal review |  | Tue 23/01/18 | Tue 23/01/18
Receive and evaluate expressions of interest |  | Tue 23/01/18 | Tue 06/02/18
Submit to IDB draft request for proposals including shortlist of firms |  | Tue 06/02/18 | Tue 13/02/18
Non-Objection from IADB |  | Tue 13/02/18 | Tue 20/02/18
Issue RFP to shortlisted firms |  | Tue 20/02/18 | Thu 22/02/18
Notify evaluators of the evaluation committee |  | Thu 22/02/18 | Fri 23/02/18
Reciept of proposals and opening of technical proposal |  | Fri 23/02/18 | Thu 03/05/18
Evaluation of technical proposals |  | Thu 03/05/18 | Thu 17/05/18
Preparation of Evaluation Report and finalization |  | Thu 17/05/18 | Fri 25/05/18
Request non'objection to technical evaluation report and to open financial proposal |  | Fri 25/05/18 | Tue 29/05/18
Non-Objection from IADB |  | Tue 29/05/18 | Tue 05/06/18
Public opening of financial proposals |  | Tue 05/06/18 | Wed 06/06/18
Preparation of combined technical and financial report |  | Wed 06/06/18 | Wed 13/06/18
Request non'objection to enter negotiations with selected firm |  | Wed 13/06/18 | Fri 15/06/18
Non-Objection from IADB |  | Fri 15/06/18 | Fri 22/06/18
Conduct negotiations and prepare draft contract |  | Fri 22/06/18 | Fri 29/06/18
Request approval of draft contract from Ministry of Finance and Contractor General |  | Fri 29/06/18 | Tue 03/07/18
MOF and CG´s approval |  | Tue 03/07/18 | Mon 23/07/18
Draft negotiatied contract to be initalled and submitted to IDB |  | Mon 23/07/18 | Mon 30/07/18
Non-Objection from IADB |  | Mon 30/07/18 | Mon 06/08/18
Finalization of contract |  | Mon 06/08/18 | Mon 13/08/18
Award of contract and request for any advance payment guarantee |  | Mon 13/08/18 | Mon 27/08/18
Notification of award sent to short-listed bidders and publication |  | Mon 27/08/18 | Wed 29/08/18
Execution of supervision: Package 1 | 235144.2 | Thu 30/08/18 | Wed 29/07/20 | [11 empty] | 33592.2 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796
Protective Works Package 2 (Belize) |  | Fri 13/07/18 | Mon 11/04/22
Delivery final design Package 2 |  | Fri 13/07/18 | Mon 16/07/18
Request environmental clearance from DOE |  | Mon 16/07/18 | Wed 10/10/18
Construction Work Package 2 |  | Fri 29/11/19 | Thu 27/03/22
(Preparation of Tech. Specs) and bidding docs. |  | Fri 27/03/20 | Fri 03/04/20
Non objection IADB |  | Fri 03/04/20 | Wed 08/04/20
Invites to pre-qualified firms |  | Wed 08/04/20 | Wed 15/04/20
Interest bidders request bidding docs. And prepare offer |  | Wed 15/04/20 | Thu 18/06/20
Bid opening meeting |  | Thu 18/06/20 | Fri 19/06/20
Evaluation of proposals |  | Fri 19/06/20 | Fri 31/07/20
Non-Objection from IDB (evaluation and contract draft) |  | Fri 31/07/20 | Wed 05/08/20
Negotiation of Contract |  | Wed 05/08/20 | Wed 19/08/20
Approval from Financial Sec |  | Wed 19/08/20 | Wed 02/09/20
Aproval Contractor General |  | Wed 02/09/20 | Fri 04/09/20
Signature of contract (including time for performance guaratee and insurances) |  | Fri 04/09/20 | Tue 22/09/20
Award of contract notification sent to short-listed bidders and publication |  | Tue 22/09/20 | Wed 23/09/20
Execution of works: Package 2 | 0 | Wed 23/09/20 | Thu 27/03/22
Works Supervision Package 2 |  | Wed 29/01/20 | Mon 29/03/22
Procurement process |  | Wed 29/01/20 | Mon 09/11/20
TORs preparation (selection criteria) |  | Wed 29/01/20 | Wed 26/02/20
Preparation of Request for expression of interest |  | Wed 26/02/20 | Wed 04/03/20
Seek Non-Objection for TOR and Request for Expressions of Interest |  | Wed 04/03/20 | Tue 10/03/20
Non-Objection from IADB |  | Tue 10/03/20 | Tue 17/03/20
Publication of Request for Expression of interest |  | Tue 17/03/20 | Mon 06/04/20
Prepare and submit draft request for proposal for informal review |  | Mon 06/04/20 | Mon 06/04/20
Receive and evaluate expressions of interest |  | Mon 06/04/20 | Mon 20/04/20
Submit to IDB draft request for proposals including shortlist of firms |  | Mon 20/04/20 | Mon 27/04/20
Non-Objection from IADB |  | Mon 27/04/20 | Tue 05/05/20
Issue RFP to shortlisted firms |  | Tue 05/05/20 | Thu 07/05/20
Notify evaluators of the evaluation committee |  | Thu 07/05/20 | Fri 08/05/20
Reciept of proposals and opening of technical proposal |  | Fri 08/05/20 | Fri 10/07/20
Evaluation of technical proposals |  | Fri 10/07/20 | Fri 24/07/20
Preparation of Evaluation Report and finalization |  | Fri 24/07/20 | Fri 31/07/20
Request non'objection to technical evaluation report and to open financial proposal |  | Fri 31/07/20 | Tue 04/08/20
Non-Objection from IADB |  | Tue 04/08/20 | Tue 11/08/20
Public opening of financial proposals |  | Tue 11/08/20 | Wed 12/08/20
Preparation of combined technical and financial report |  | Wed 12/08/20 | Wed 19/08/20
Request non'objection to enter negotiations with selected firm |  | Wed 19/08/20 | Fri 21/08/20
Non-Objection from IADB |  | Fri 21/08/20 | Fri 28/08/20
Conduct negotiations and prepare draft contract |  | Fri 28/08/20 | Fri 04/09/20
Request approval of draft contract from Ministry of Finance and Contractor General |  | Fri 04/09/20 | Tue 08/09/20
MOF and CG´s approval |  | Tue 08/09/20 | Wed 30/09/20
Draft negotiatied contract to be initalled and submitted to IDB |  | Wed 30/09/20 | Wed 07/10/20
Non-Objection from IADB |  | Wed 07/10/20 | Thu 15/10/20
Finalization of contract |  | Thu 15/10/20 | Thu 22/10/20
Award of contract and request for any advance payment guarantee |  | Thu 22/10/20 | Thu 05/11/20
Notification of award sent to short-listed bidders and publication |  | Thu 05/11/20 | Mon 09/11/20
Execution of supervision: Package 2 | 0 | Mon 09/11/20 | Thu 27/03/22
Protective Works Package 3 (Caye Caulker y Cayo Goff) |  | Tue 12/09/17 | Fri 24/09/21
Preparing biding documents |  | Thu 23/11/17 | Fri 24/11/17
Inform the Local Tourism Comitee about the interventions planned and coordination activities |  | Fri 22/12/17 | Mon 25/12/17
Requesting to Ministry of Natural Resources for the Village Council to have fill permit to use the Palapa beach area |  | Tue 12/09/17 | Tue 05/12/17
Management of agreements with sellers and verification of legal ownership of land |  | Fri 24/11/17 | Thu 29/03/18
Construction Work Package 3 |  | Mon 08/06/20 | Fri 24/09/21
Procurement process |  | Mon 08/06/20 | Mon 11/01/21
Specific notice for pre- qualification documents and requirements for pre-qualification proposals |  | Mon 08/06/20 | Mon 15/06/20
Non objection IADB |  | Mon 15/06/20 | Mon 22/06/20
Publication |  | Mon 22/06/20 | Mon 06/07/20
Proposal reception |  | Mon 06/07/20 | Mon 17/08/20
Proposal evaluation for pre-qualification |  | Mon 17/08/20 | Tue 15/09/20
Non objection IADB |  | Tue 15/09/20 | Wed 23/09/20
(Preparation of Tech. Specs) and bidding docs. |  | Wed 23/09/20 | Wed 30/09/20
Non objection IADB |  | Wed 30/09/20 | Wed 07/10/20
Invites to pre-qualified firms |  | Wed 07/10/20 | Thu 15/10/20
Interest bidders request bidding docs. And prepare offer |  | Thu 15/10/20 | Thu 12/11/20
Bid opening meeting |  | Thu 12/11/20 | Fri 13/11/20
Evaluation of proposals |  | Fri 13/11/20 | Mon 30/11/20
Non-Objection from IDB (evaluation and contract draft) |  | Mon 30/11/20 | Mon 07/12/20
Negotiation of Contract |  | Mon 07/12/20 | Mon 14/12/20
Approval from Financial Sec |  | Mon 14/12/20 | Tue 29/12/20
Aproval Contractor General |  | Tue 29/12/20 | Thu 31/12/20
Signature of contract (including time for performance guaratee and insurances) |  | Thu 31/12/20 | Fri 08/01/21
Award of contract notification sent to short-listed bidders and publication |  | Fri 08/01/21 | Mon 11/01/21
Execution of works: Package 3 | 0 | Mon 11/01/21 | Fri 24/09/21
Works Supervision Package 3 |  | Mon 13/04/20 | Fri 24/09/21
Procurement process |  | Mon 13/04/20 | Mon 08/02/21
TORs preparation |  | Mon 13/04/20 | Mon 20/04/20
Non-Objection from IADB |  | Mon 20/04/20 | Mon 27/04/20
Ad posting with request for expressions of interest |  | Mon 27/04/20 | Tue 12/05/20
Reception of Expressions of Interest |  | Tue 12/05/20 | Tue 23/06/20
Analysis of expressions of interest |  | Tue 23/06/20 | Tue 21/07/20
Elaboration of short list |  | Tue 21/07/20 | Tue 04/08/20
Preparation of proposal request document |  | Tue 04/08/20 | Tue 18/08/20
Non-Objection from IADB |  | Tue 18/08/20 | Tue 01/09/20
Notification of results to participants |  | Tue 01/09/20 | Tue 08/09/20
Referral of SP to the best evalada of the short list |  | Tue 08/09/20 | Fri 23/10/20
Presentation of proposals |  | Fri 23/10/20 | Mon 26/10/20
Evaluation of technical and economic proposals |  | Mon 26/10/20 | Tue 08/12/20
Non-Objection from IADB |  | Tue 08/12/20 | Tue 22/12/20
Notification of results to participants |  | Tue 22/12/20 | Thu 07/01/21
Publication of the award |  | Thu 07/01/21 | Thu 21/01/21
Contract subscription |  | Thu 21/01/21 | Mon 25/01/21
Sending of signed contract to the IDB |  | Mon 25/01/21 | Mon 08/02/21
Execution of supervision: Package 3 | 0 | Mon 08/02/21 | Fri 24/09/21
Environmental measures | 130291.67 | Thu 14/06/18 | Wed 28/10/20 | [7 empty] | 10958.33 | 14666.66 | 14666.67 | 12666.67 | 15000 | 7000 | 20333.33 | [7 empty] | 7333.33 | 6666.67 | 7666.67 | 6666.67 | 6666.67
Coastal monitoring for Goff's Caye (erosion and coral reef) |  | Fri 19/06/20 | Fri 17/12/21
Procurement process |  | Fri 19/06/20 | Fri 02/04/21
TORs preparation (selection criteria) |  | Fri 19/06/20 | Fri 17/07/20
Preparation of Request for expression of interest |  | Fri 17/07/20 | Fri 24/07/20
Seek Non-Objection for TOR and Request for Expressions of Interest |  | Fri 24/07/20 | Wed 29/07/20
Non-Objection from IADB |  | Wed 29/07/20 | Wed 05/08/20
Publication of Request for Expression of interest |  | Wed 05/08/20 | Tue 25/08/20
Prepare and submit draft request for proposal for informal review |  | Tue 25/08/20 | Tue 25/08/20
Receive and evaluate expressions of interest |  | Tue 25/08/20 | Tue 08/09/20
Submit to IDB draft request for proposals including shortlist of firms |  | Tue 08/09/20 | Wed 16/09/20
Non-Objection from IADB |  | Wed 16/09/20 | Thu 24/09/20
Issue RFP to shortlisted firms |  | Thu 24/09/20 | Mon 28/09/20
Notify evaluators of the evaluation committee |  | Mon 28/09/20 | Tue 29/09/20
Reciept of proposals and opening of technical proposal |  | Tue 29/09/20 | Thu 03/12/20
Evaluation of technical proposals |  | Thu 03/12/20 | Thu 17/12/20
Preparation of Evaluation Report and finalization |  | Thu 17/12/20 | Thu 24/12/20
Request non'objection to technical evaluation report and to open financial proposal |  | Thu 24/12/20 | Tue 29/12/20
Non-Objection from IADB |  | Tue 29/12/20 | Wed 06/01/21
Public opening of financial proposals |  | Wed 06/01/21 | Thu 07/01/21
Preparation of combined technical and financial report |  | Thu 07/01/21 | Thu 14/01/21
Request non'objection to enter negotiations with selected firm |  | Thu 14/01/21 | Mon 18/01/21
Non-Objection from IADB |  | Mon 18/01/21 | Mon 25/01/21
Conduct negotiations and prepare draft contract |  | Mon 25/01/21 | Mon 01/02/21
Request approval of draft contract from Ministry of Finance and Contractor General |  | Mon 01/02/21 | Wed 03/02/21
MOF and CG´s approval |  | Wed 03/02/21 | Tue 23/02/21
Draft negotiatied contract to be initalled and submitted to IDB |  | Tue 23/02/21 | Tue 02/03/21
Non-Objection from IADB |  | Tue 02/03/21 | Wed 10/03/21
Finalization of contract |  | Wed 10/03/21 | Wed 17/03/21
Award of contract and request for any advance payment guarantee |  | Wed 17/03/21 | Wed 31/03/21
Notification of award sent to short-listed bidders and publication |  | Wed 31/03/21 | Fri 02/04/21
Execution | 0 | Mon 31/05/21 | Fri 17/12/21
Management plans for Palapa beach (Caye Caulker) and Goff's Caye |  | Wed 02/05/18 | Thu 29/11/18
Procurement process |  | Wed 02/05/18 | Fri 03/08/18
TORs preparation |  | Wed 02/05/18 | Wed 16/05/18
Non-Objection from IADB |  | Wed 16/05/18 | Thu 17/05/18
Ad posting with request for expressions of interest |  | Thu 17/05/18 | Tue 22/05/18
Reception of Expressions of Interest |  | Tue 22/05/18 | Wed 23/05/18
Analysis of expressions of interest |  | Wed 23/05/18 | Mon 04/06/18
Elaboration of short list |  | Mon 04/06/18 | Thu 14/06/18
Preparation of proposal request document |  | Thu 14/06/18 | Mon 18/06/18
Non-Objection from IADB |  | Mon 18/06/18 | Wed 20/06/18
Notification of results to participants |  | Wed 20/06/18 | Mon 25/06/18
Referral of SP to the best evalada of the short list |  | Mon 25/06/18 | Mon 02/07/18
Presentation of proposals |  | Mon 02/07/18 | Tue 03/07/18
Evaluation of technical and economic proposals |  | Tue 03/07/18 | Wed 04/07/18
Non-Objection from IADB |  | Wed 04/07/18 | Fri 13/07/18
Notification of results to participants |  | Fri 13/07/18 | Fri 20/07/18
Publication of the award |  | Fri 20/07/18 | Wed 25/07/18
Contract subscription |  | Wed 25/07/18 | Wed 01/08/18
Sending of signed contract to the IDB |  | Wed 01/08/18 | Fri 03/08/18
Execution | 113650 | Fri 03/08/18 | Thu 29/11/18 | [9 empty] | 22730 |  | 45460 | 45460
Component 2: Governance for Disaster Risk Management and Adaptation to Climate Change |  | Fri 14/08/20 | Mon 14/02/22
Risk information system |  | Fri 14/08/20 | Fri 31/12/21
Procurement process |  | Fri 14/08/20 | Mon 31/05/21
TORs preparation (selection criteria) |  | Wed 08/01/20 | Wed 05/02/20
Preparation of Request for expression of interest |  | Wed 05/02/20 | Wed 12/02/20
Seek Non-Objection for TOR and Request for Expressions of Interest |  | Wed 12/02/20 | Mon 17/02/20
Non-Objection from IADB |  | Mon 17/02/20 | Mon 24/02/20
Publication of Request for Expression of interest |  | Mon 24/02/20 | Mon 16/03/20
Prepare and submit draft request for proposal for informal review |  | Mon 16/03/20 | Mon 16/03/20
Receive and evaluate expressions of interest |  | Mon 16/03/20 | Mon 30/03/20
Submit to IDB draft request for proposals including shortlist of firms |  | Mon 30/03/20 | Mon 06/04/20
Non-Objection from IADB |  | Mon 06/04/20 | Mon 13/04/20
Issue RFP to shortlisted firms |  | Mon 13/04/20 | Wed 15/04/20
Notify evaluators of the evaluation committee |  | Wed 15/04/20 | Thu 16/04/20
Reciept of proposals and opening of technical proposal |  | Thu 16/04/20 | Fri 19/06/20
Evaluation of technical proposals |  | Fri 19/06/20 | Fri 03/07/20
Preparation of Evaluation Report and finalization |  | Fri 03/07/20 | Fri 10/07/20
Request non'objection to technical evaluation report and to open financial proposal |  | Fri 10/07/20 | Tue 14/07/20
Non-Objection from IADB |  | Tue 14/07/20 | Tue 21/07/20
Public opening of financial proposals |  | Tue 21/07/20 | Wed 22/07/20
Preparation of combined technical and financial report |  | Wed 22/07/20 | Wed 29/07/20
Request non'objection to enter negotiations with selected firm |  | Wed 29/07/20 | Fri 31/07/20
Non-Objection from IADB |  | Fri 31/07/20 | Fri 07/08/20
Conduct negotiations and prepare draft contract |  | Fri 07/08/20 | Fri 14/08/20
Request approval of draft contract from Ministry of Finance and Contractor General |  | Fri 14/08/20 | Tue 18/08/20
MOF and CG´s approval |  | Tue 18/08/20 | Mon 07/09/20
Draft negotiatied contract to be initalled and submitted to IDB |  | Mon 07/09/20 | Tue 15/09/20
Non-Objection from IADB |  | Tue 15/09/20 | Wed 23/09/20
Finalization of contract |  | Wed 23/09/20 | Wed 30/09/20
Award of contract and request for any advance payment guarantee |  | Wed 30/09/20 | Thu 15/10/20
Notification of award sent to short-listed bidders and publication |  | Thu 15/10/20 | Mon 19/10/20
Execution of the Consulting | 0 | Mon 19/10/20 | Fri 21/05/21
Designing of building codes |  | Fri 02/04/21 | Mon 14/02/22
Procurement process |  | Fri 02/04/21 | Tue 27/07/21
TORs preparation (selection criteria) |  | Fri 02/04/21 | Fri 16/04/21
Request Non-Objection for TOR and evaluation criteria |  | Fri 16/04/21 | Wed 21/04/21
Non-Objection from IADB |  | Wed 21/04/21 | Wed 28/04/21
Draft the Request for Expressions of interest |  | Wed 28/04/21 | Thu 29/04/21
Non-Objection of expression of interest |  | Thu 29/04/21 | Thu 06/05/21
Publication of Request for Expressions of Interest |  | Thu 06/05/21 | Thu 27/05/21
Receive and evaluate CVs |  | Thu 27/05/21 | Thu 03/06/21
Non-Objection from IADB |  | Thu 03/06/21 | Thu 17/06/21
Request approval of draft contract from Ministry of Finance and Contractor General |  | Thu 17/06/21 | Thu 08/07/21
Prepare report and Request Non-Objection to selected candidate and the draft contract |  | Thu 08/07/21 | Tue 13/07/21
MOF and CG´s approval |  | Tue 13/07/21 | Tue 20/07/21
Negotiation and finalisation of Contract |  | Tue 20/07/21 | Tue 27/07/21
Execution of the Consulting | 0 | Tue 27/07/21 | Mon 14/02/22
Climate risk financing strategy for the tourism and agriculture sectors |  | Thu 04/02/21 | Mon 17/01/22
Procurement process |  | Thu 04/02/21 | Tue 01/06/21
TORs preparation (selection criteria) |  | Thu 04/02/21 | Thu 18/02/21
Request Non-Objection for TOR and evaluation criteria |  | Thu 18/02/21 | Tue 23/02/21
Non-Objection from IADB |  | Tue 23/02/21 | Tue 02/03/21
Draft the Request for Expressions of interest |  | Tue 02/03/21 | Wed 03/03/21
Non-Objection of expression of interest |  | Wed 03/03/21 | Thu 11/03/21
Publication of Request for Expressions of Interest |  | Thu 11/03/21 | Wed 31/03/21
Receive and evaluate CVs |  | Wed 31/03/21 | Wed 07/04/21
Non-Objection from IADB |  | Wed 07/04/21 | Wed 21/04/21
Request approval of draft contract from Ministry of Finance and Contractor General |  | Wed 21/04/21 | Wed 12/05/21
Prepare report and Request Non-Objection to selected candidate and the draft contract |  | Wed 12/05/21 | Mon 17/05/21
MOF and CG´s approval |  | Mon 17/05/21 | Tue 25/05/21
Negotiation and finalisation of Contract |  | Tue 25/05/21 | Tue 01/06/21
Execution of the Consulting | 0 | Tue 01/06/21 | Mon 17/01/22
Project Management |  | Thu 14/06/18 | Wed 06/04/22
Technical Unit |  | Thu 14/06/18 | Wed 06/04/22
PEU Team Recruitment |  | Thu 14/06/18 | Wed 06/04/22
Procurement process |  | Thu 14/03/18 | Thu 29/06/18
Project coordinator |  | Thu 14/03/18 | Thu 29/06/18
Project Manager |  | Thu 14/03/18 | Thu 29/06/19
Coastal engineer |  | Thu 14/03/18 | Thu 29/06/20
Planning and Monitoring Specialist |  | Thu 14/03/18 | Thu 29/06/21
Procurement and Contracting Specialist |  | Thu 14/03/18 | Thu 29/06/22
Financial Management Specialist |  | Thu 14/03/18 | Thu 29/06/23
Specialist in environmental and social issues |  | Thu 14/03/18 | Thu 29/06/24
Account Clerk |  | Thu 14/03/18 | Thu 29/06/25
Driver |  | Thu 14/03/18 | Thu 29/06/26
Payment process | 271108.35 | Thu 19/07/18 | Wed 06/04/22 | [8 empty] | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 12654.17 | 12654.17 | 12654.17 | 12654.17 | 12654.17
Furniture & Equipment |  | Thu 05/07/18 | Mon 01/10/18
Preparation of technical specifications |  | Thu 05/07/18 | Thu 12/07/18
Preparation of CP document and offer request |  | Thu 12/07/18 | Thu 19/07/18
Preparation and delivery of quotes |  | Thu 19/07/18 | Thu 26/07/18
Price comparison and revision of technical specifications |  | Thu 26/07/18 | Mon 30/07/18
IDB Non-Objection Request |  | Mon 30/07/18 | Tue 31/07/18
No IDB objection |  | Tue 31/07/18 | Fri 03/08/18
Notification to bidders |  | Fri 03/08/18 | Tue 07/08/18
Subscription of purchase order |  | Tue 07/08/18 | Thu 09/08/18
Delivery of furniture and equipment |  | Thu 09/08/18 | Thu 30/08/18
Furniture & Equipment | 40000 | Thu 30/08/18 | Mon 01/10/18 | [10 empty] | 4000 | 36000
Vehicle Acquisition |  | Thu 05/07/18 | Mon 01/10/18
Preparation of technical specifications |  | Thu 05/07/18 | Thu 12/07/18
Preparation of CP document and offer request |  | Thu 12/07/18 | Thu 19/07/18
Preparation and delivery of quotes |  | Thu 19/07/18 | Thu 26/07/18
Price comparison and revision of technical specifications |  | Thu 26/07/18 | Mon 30/07/18
IDB Non-Objection Request |  | Mon 30/07/18 | Tue 31/07/18
No IDB objection |  | Tue 31/07/18 | Fri 03/08/18
Notification to bidders |  | Fri 03/08/18 | Tue 07/08/18
Subscription of purchase order |  | Tue 07/08/18 | Thu 09/08/18
Delivery of furniture and equipment |  | Thu 09/08/18 | Thu 30/08/18
Vehicle Delivery | 40000 | Thu 30/08/18 | Mon 01/10/18 | [10 empty] | 4000 | 36000
Operating Expenses (Papeleria and others) |  | Wed 28/11/18 | Wed 11/08/21
Year 1 | 24957 | Wed 28/11/18 | Wed 19/12/18 | [12 empty] | 10957 | 14000
Year 3 | 0 | Fri 17/07/20 | Fri 07/08/20
Year 4 |  | Wed 21/07/21 | Wed 11/08/21
Annual Evaluations and Audits |  | Thu 12/07/18 | Mon 18/04/22
Reviews |  | Fri 14/08/20 | Tue 05/04/22
Intermediate evaluation |  | Fri 14/08/20 | Tue 23/02/21
Procurement process |  | Fri 14/08/20 | Fri 27/11/20
Payment process | 0 | Fri 27/11/20 | Tue 23/02/21
Final evaluation |  | Thu 15/07/21 | Fri 18/02/22
Procurement process |  | Thu 15/07/21 | Fri 26/11/21
Payment process | 0 | Fri 26/11/21 | Fri 18/02/22
Impact evaluation |  | Mon 19/07/21 | Tue 05/03/22
Procurement process |  | Mon 19/07/21 | Fri 12/11/21
Payment process | 0 | Fri 12/11/21 | Tue 05/03/22
Annual audits |  | Thu 12/07/18 | Mon 18/03/22
Audit Year 1 | 20000 | Thu 12/07/18 | Fri 28/12/18 | [11 empty] | 6400 | 6800 | 6800
Audit Year 2 | 19291.67 | Tue 08/10/19 | Mon 06/01/20 | [23 empty] | 5958.33 | 6666.67 | 6666.67
Audit Year 3 | 0 | Fri 09/10/20 | Thu 07/01/21
Audit Year 4 | 0 | Tue 14/09/21 | Mon 18/03/22
TOTAL AOP | 3033846.89
Monthly Expense | [10 empty] | 10958.33 | 30654.16 | 53384.17 | 36654.17 | 862657.7 | 250262.5 | 288440.83 | 32783.5 | 132783.5 | 132783.5 | 232783.5 | 132783.5 | 132783.5 | 132783.5 | 136783.5 | 136116.84 | 143075.17 | 129387.51 | 25987.51
Cumulative Expensive | [10 empty] | 10958.33 | 41612.49 | 94996.66 | 131650.83 | 994308.53 | 1244571.03 | 1533011.86 | 1565795.36 | 1698578.86 | 1831362.36 | 2064145.86 | 2196929.36 | 2329712.86 | 2462496.36 | 2599279.86 | 2735396.7 | 2878471.87 | 3007859.38 | 3033846.89
Annual Disbursement | [10 empty] | 1533011.86 | [6 empty] | 1500835.03

## AOP
AOP CLIMATE VULNERABILITY REDUCTION PROGRAM (BL-L1028) | Costo |  |  | 2017 |  | 2018 | [11 empty] | 2019
|  | Start | Finish | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December
Board Approval |  | Wed 06/12/17 | Wed 06/12/17
Loan Efectivnes |  | Thu 15/03/18 | Fri 16/03/18
Conditions Before the First Disbursement |  | Thu 18/01/18 | Tue 17/04/18
Contratación personal |  | Thu 18/01/18 | Tue 17/04/18
Validacion Manual Operativo |  | Fri 16/03/18 | Tue 03/04/18
Elegibilidad |  | Tue 17/04/18 | Wed 18/04/18
First disbursement |  | Wed 18/04/18 | Thu 03/05/18
Last disbursement |  | Mon 14/03/22 | Tue 15/03/22
Inclusion of steering comitee as part of the Program Operational Manual |  | Fri 16/03/18 | Tue 27/03/18
Appropiatte planning to implement the works during the dry season. |  | Tue 17/04/18 | Mon 08/11/21
Signing of agreements with the beneficiaries for the maintenance of the works (CCVC, BCC, CZMAI) |  | Thu 14/12/17 | Fri 15/12/17
Implement a traning program with the MoW |  | Thu 17/10/19 | Thu 09/04/20
Start-up workshop that includes review of risk management and mitigation actions of the program, regularization of land, actions associated with the implementation of the environmental and social management plan, resettlement, compensation processes, etc. |  | Mon 16/04/18 | Tue 17/04/18
Component 1: Risk Reduction |  | Tue 12/09/17 | Mon 11/04/22
Protective Works Package 1 (Belize) |  | Thu 16/11/17 | Thu 01/07/21
Delivery final design Package 1 |  | Wed 22/11/17 | Thu 23/11/17
Request environmental clearance from DOE |  | Fri 02/02/18 | Thu 03/05/18
Construction Works Package 1 |  | Wed 07/03/18 | Mon 28/06/21
Procurement process |  | Wed 07/03/18 | Wed 05/09/18
(Preparation of Tech. Specs) and bidding docs. |  | Wed 07/03/18 | Thu 15/03/18
Non objection IADB |  | Thu 15/03/18 | Tue 20/03/18
Invites to pre-qualified firms |  | Tue 20/03/18 | Thu 29/03/18
Interest bidders request bidding docs. And prepare offer |  | Thu 29/03/18 | Mon 04/06/18
Bid opening meeting |  | Mon 04/06/18 | Tue 05/06/18
Evaluation of proposals |  | Tue 05/06/18 | Tue 17/07/18
Non-Objection from IDB (evaluation and contract draft) |  | Tue 17/07/18 | Fri 20/07/18
Negotiation of Contract |  | Fri 20/07/18 | Fri 03/08/18
Approval from Financial Sec |  | Fri 03/08/18 | Fri 17/08/18
Aproval Contractor General |  | Fri 17/08/18 | Tue 21/08/18
Signature of contract (including time for performance guaratee and insurances) |  | Tue 21/08/18 | Tue 04/09/18
Award of contract notification sent to short-listed bidders and publication |  | Tue 04/09/18 | Wed 05/09/18
Execution of works: Package 1 | 2139404 | Tue 11/09/18 | Thu 01/07/21 | [11 empty] | 674218 | 147262 | 214524 | 0 | 100000 | 100000 | 200000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 103400 | 0
Works Supervision Package 1 |  | Thu 16/11/17 | Wed 29/07/20
Procurement process |  | Thu 16/11/17 | Wed 29/08/18
TORs preparation (selection criteria) |  | Thu 16/11/17 | Thu 14/12/17
Preparation of Request for expression of interest |  | Thu 14/12/17 | Thu 21/12/17
Seek Non-Objection for TOR and Request for Expressions of Interest |  | Thu 21/12/17 | Tue 26/12/17
Non-Objection from IADB |  | Tue 26/12/17 | Wed 03/01/18
Publication of Request for Expression of interest |  | Wed 03/01/18 | Tue 23/01/18
Prepare and submit draft request for proposal for informal review |  | Tue 23/01/18 | Tue 23/01/18
Receive and evaluate expressions of interest |  | Tue 23/01/18 | Tue 06/02/18
Submit to IDB draft request for proposals including shortlist of firms |  | Tue 06/02/18 | Tue 13/02/18
Non-Objection from IADB |  | Tue 13/02/18 | Tue 20/02/18
Issue RFP to shortlisted firms |  | Tue 20/02/18 | Thu 22/02/18
Notify evaluators of the evaluation committee |  | Thu 22/02/18 | Fri 23/02/18
Reciept of proposals and opening of technical proposal |  | Fri 23/02/18 | Thu 03/05/18
Evaluation of technical proposals |  | Thu 03/05/18 | Thu 17/05/18
Preparation of Evaluation Report and finalization |  | Thu 17/05/18 | Fri 25/05/18
Request non'objection to technical evaluation report and to open financial proposal |  | Fri 25/05/18 | Tue 29/05/18
Non-Objection from IADB |  | Tue 29/05/18 | Tue 05/06/18
Public opening of financial proposals |  | Tue 05/06/18 | Wed 06/06/18
Preparation of combined technical and financial report |  | Wed 06/06/18 | Wed 13/06/18
Request non'objection to enter negotiations with selected firm |  | Wed 13/06/18 | Fri 15/06/18
Non-Objection from IADB |  | Fri 15/06/18 | Fri 22/06/18
Conduct negotiations and prepare draft contract |  | Fri 22/06/18 | Fri 29/06/18
Request approval of draft contract from Ministry of Finance and Contractor General |  | Fri 29/06/18 | Tue 03/07/18
MOF and CG´s approval |  | Tue 03/07/18 | Mon 23/07/18
Draft negotiatied contract to be initalled and submitted to IDB |  | Mon 23/07/18 | Mon 30/07/18
Non-Objection from IADB |  | Mon 30/07/18 | Mon 06/08/18
Finalization of contract |  | Mon 06/08/18 | Mon 13/08/18
Award of contract and request for any advance payment guarantee |  | Mon 13/08/18 | Mon 27/08/18
Notification of award sent to short-listed bidders and publication |  | Mon 27/08/18 | Wed 29/08/18
Execution of supervision: Package 1 | 235144.2 | Thu 30/08/18 | Wed 29/07/20 | [11 empty] | 33592.2 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796 | 16796
Protective Works Package 2 (Belize) |  | Fri 13/07/18 | Mon 11/04/22
Delivery final design Package 2 |  | Fri 13/07/18 | Mon 16/07/18
Request environmental clearance from DOE |  | Mon 16/07/18 | Wed 10/10/18
Construction Work Package 2 |  | Fri 29/11/19 | Thu 27/03/22
(Preparation of Tech. Specs) and bidding docs. |  | Fri 27/03/20 | Fri 03/04/20
Non objection IADB |  | Fri 03/04/20 | Wed 08/04/20
Invites to pre-qualified firms |  | Wed 08/04/20 | Wed 15/04/20
Interest bidders request bidding docs. And prepare offer |  | Wed 15/04/20 | Thu 18/06/20
Bid opening meeting |  | Thu 18/06/20 | Fri 19/06/20
Evaluation of proposals |  | Fri 19/06/20 | Fri 31/07/20
Non-Objection from IDB (evaluation and contract draft) |  | Fri 31/07/20 | Wed 05/08/20
Negotiation of Contract |  | Wed 05/08/20 | Wed 19/08/20
Approval from Financial Sec |  | Wed 19/08/20 | Wed 02/09/20
Aproval Contractor General |  | Wed 02/09/20 | Fri 04/09/20
Signature of contract (including time for performance guaratee and insurances) |  | Fri 04/09/20 | Tue 22/09/20
Award of contract notification sent to short-listed bidders and publication |  | Tue 22/09/20 | Wed 23/09/20
Execution of works: Package 2 | 0 | Wed 23/09/20 | Thu 27/03/22
Works Supervision Package 2 |  | Wed 29/01/20 | Mon 29/03/22
Procurement process |  | Wed 29/01/20 | Mon 09/11/20
TORs preparation (selection criteria) |  | Wed 29/01/20 | Wed 26/02/20
Preparation of Request for expression of interest |  | Wed 26/02/20 | Wed 04/03/20
Seek Non-Objection for TOR and Request for Expressions of Interest |  | Wed 04/03/20 | Tue 10/03/20
Non-Objection from IADB |  | Tue 10/03/20 | Tue 17/03/20
Publication of Request for Expression of interest |  | Tue 17/03/20 | Mon 06/04/20
Prepare and submit draft request for proposal for informal review |  | Mon 06/04/20 | Mon 06/04/20
Receive and evaluate expressions of interest |  | Mon 06/04/20 | Mon 20/04/20
Submit to IDB draft request for proposals including shortlist of firms |  | Mon 20/04/20 | Mon 27/04/20
Non-Objection from IADB |  | Mon 27/04/20 | Tue 05/05/20
Issue RFP to shortlisted firms |  | Tue 05/05/20 | Thu 07/05/20
Notify evaluators of the evaluation committee |  | Thu 07/05/20 | Fri 08/05/20
Reciept of proposals and opening of technical proposal |  | Fri 08/05/20 | Fri 10/07/20
Evaluation of technical proposals |  | Fri 10/07/20 | Fri 24/07/20
Preparation of Evaluation Report and finalization |  | Fri 24/07/20 | Fri 31/07/20
Request non'objection to technical evaluation report and to open financial proposal |  | Fri 31/07/20 | Tue 04/08/20
Non-Objection from IADB |  | Tue 04/08/20 | Tue 11/08/20
Public opening of financial proposals |  | Tue 11/08/20 | Wed 12/08/20
Preparation of combined technical and financial report |  | Wed 12/08/20 | Wed 19/08/20
Request non'objection to enter negotiations with selected firm |  | Wed 19/08/20 | Fri 21/08/20
Non-Objection from IADB |  | Fri 21/08/20 | Fri 28/08/20
Conduct negotiations and prepare draft contract |  | Fri 28/08/20 | Fri 04/09/20
Request approval of draft contract from Ministry of Finance and Contractor General |  | Fri 04/09/20 | Tue 08/09/20
MOF and CG´s approval |  | Tue 08/09/20 | Wed 30/09/20
Draft negotiatied contract to be initalled and submitted to IDB |  | Wed 30/09/20 | Wed 07/10/20
Non-Objection from IADB |  | Wed 07/10/20 | Thu 15/10/20
Finalization of contract |  | Thu 15/10/20 | Thu 22/10/20
Award of contract and request for any advance payment guarantee |  | Thu 22/10/20 | Thu 05/11/20
Notification of award sent to short-listed bidders and publication |  | Thu 05/11/20 | Mon 09/11/20
Execution of supervision: Package 2 | 0 | Mon 09/11/20 | Thu 27/03/22
Protective Works Package 3 (Caye Caulker y Cayo Goff) |  | Tue 12/09/17 | Fri 24/09/21
Preparing biding documents |  | Thu 23/11/17 | Fri 24/11/17
Inform the Local Tourism Comitee about the interventions planned and coordination activities |  | Fri 22/12/17 | Mon 25/12/17
Requesting to Ministry of Natural Resources for the Village Council to have fill permit to use the Palapa beach area |  | Tue 12/09/17 | Tue 05/12/17
Management of agreements with sellers and verification of legal ownership of land |  | Fri 24/11/17 | Thu 29/03/18
Construction Work Package 3 |  | Mon 08/06/20 | Fri 24/09/21
Procurement process |  | Mon 08/06/20 | Mon 11/01/21
Specific notice for pre- qualification documents and requirements for pre-qualification proposals |  | Mon 08/06/20 | Mon 15/06/20
Non objection IADB |  | Mon 15/06/20 | Mon 22/06/20
Publication |  | Mon 22/06/20 | Mon 06/07/20
Proposal reception |  | Mon 06/07/20 | Mon 17/08/20
Proposal evaluation for pre-qualification |  | Mon 17/08/20 | Tue 15/09/20
Non objection IADB |  | Tue 15/09/20 | Wed 23/09/20
(Preparation of Tech. Specs) and bidding docs. |  | Wed 23/09/20 | Wed 30/09/20
Non objection IADB |  | Wed 30/09/20 | Wed 07/10/20
Invites to pre-qualified firms |  | Wed 07/10/20 | Thu 15/10/20
Interest bidders request bidding docs. And prepare offer |  | Thu 15/10/20 | Thu 12/11/20
Bid opening meeting |  | Thu 12/11/20 | Fri 13/11/20
Evaluation of proposals |  | Fri 13/11/20 | Mon 30/11/20
Non-Objection from IDB (evaluation and contract draft) |  | Mon 30/11/20 | Mon 07/12/20
Negotiation of Contract |  | Mon 07/12/20 | Mon 14/12/20
Approval from Financial Sec |  | Mon 14/12/20 | Tue 29/12/20
Aproval Contractor General |  | Tue 29/12/20 | Thu 31/12/20
Signature of contract (including time for performance guaratee and insurances) |  | Thu 31/12/20 | Fri 08/01/21
Award of contract notification sent to short-listed bidders and publication |  | Fri 08/01/21 | Mon 11/01/21
Execution of works: Package 3 | 0 | Mon 11/01/21 | Fri 24/09/21
Works Supervision Package 3 |  | Mon 13/04/20 | Fri 24/09/21
Procurement process |  | Mon 13/04/20 | Mon 08/02/21
TORs preparation |  | Mon 13/04/20 | Mon 20/04/20
Non-Objection from IADB |  | Mon 20/04/20 | Mon 27/04/20
Ad posting with request for expressions of interest |  | Mon 27/04/20 | Tue 12/05/20
Reception of Expressions of Interest |  | Tue 12/05/20 | Tue 23/06/20
Analysis of expressions of interest |  | Tue 23/06/20 | Tue 21/07/20
Elaboration of short list |  | Tue 21/07/20 | Tue 04/08/20
Preparation of proposal request document |  | Tue 04/08/20 | Tue 18/08/20
Non-Objection from IADB |  | Tue 18/08/20 | Tue 01/09/20
Notification of results to participants |  | Tue 01/09/20 | Tue 08/09/20
Referral of SP to the best evalada of the short list |  | Tue 08/09/20 | Fri 23/10/20
Presentation of proposals |  | Fri 23/10/20 | Mon 26/10/20
Evaluation of technical and economic proposals |  | Mon 26/10/20 | Tue 08/12/20
Non-Objection from IADB |  | Tue 08/12/20 | Tue 22/12/20
Notification of results to participants |  | Tue 22/12/20 | Thu 07/01/21
Publication of the award |  | Thu 07/01/21 | Thu 21/01/21
Contract subscription |  | Thu 21/01/21 | Mon 25/01/21
Sending of signed contract to the IDB |  | Mon 25/01/21 | Mon 08/02/21
Execution of supervision: Package 3 | 0 | Mon 08/02/21 | Fri 24/09/21
Environmental measures | 130291.67 | Thu 14/06/18 | Wed 28/10/20 | [7 empty] | 10958.33 | 14666.66 | 14666.67 | 12666.67 | 15000 | 7000 | 20333.33 | [7 empty] | 7333.33 | 6666.67 | 7666.67 | 6666.67 | 6666.67
Coastal monitoring for Goff's Caye (erosion and coral reef) |  | Fri 19/06/20 | Fri 17/12/21
Procurement process |  | Fri 19/06/20 | Fri 02/04/21
TORs preparation (selection criteria) |  | Fri 19/06/20 | Fri 17/07/20
Preparation of Request for expression of interest |  | Fri 17/07/20 | Fri 24/07/20
Seek Non-Objection for TOR and Request for Expressions of Interest |  | Fri 24/07/20 | Wed 29/07/20
Non-Objection from IADB |  | Wed 29/07/20 | Wed 05/08/20
Publication of Request for Expression of interest |  | Wed 05/08/20 | Tue 25/08/20
Prepare and submit draft request for proposal for informal review |  | Tue 25/08/20 | Tue 25/08/20
Receive and evaluate expressions of interest |  | Tue 25/08/20 | Tue 08/09/20
Submit to IDB draft request for proposals including shortlist of firms |  | Tue 08/09/20 | Wed 16/09/20
Non-Objection from IADB |  | Wed 16/09/20 | Thu 24/09/20
Issue RFP to shortlisted firms |  | Thu 24/09/20 | Mon 28/09/20
Notify evaluators of the evaluation committee |  | Mon 28/09/20 | Tue 29/09/20
Reciept of proposals and opening of technical proposal |  | Tue 29/09/20 | Thu 03/12/20
Evaluation of technical proposals |  | Thu 03/12/20 | Thu 17/12/20
Preparation of Evaluation Report and finalization |  | Thu 17/12/20 | Thu 24/12/20
Request non'objection to technical evaluation report and to open financial proposal |  | Thu 24/12/20 | Tue 29/12/20
Non-Objection from IADB |  | Tue 29/12/20 | Wed 06/01/21
Public opening of financial proposals |  | Wed 06/01/21 | Thu 07/01/21
Preparation of combined technical and financial report |  | Thu 07/01/21 | Thu 14/01/21
Request non'objection to enter negotiations with selected firm |  | Thu 14/01/21 | Mon 18/01/21
Non-Objection from IADB |  | Mon 18/01/21 | Mon 25/01/21
Conduct negotiations and prepare draft contract |  | Mon 25/01/21 | Mon 01/02/21
Request approval of draft contract from Ministry of Finance and Contractor General |  | Mon 01/02/21 | Wed 03/02/21
MOF and CG´s approval |  | Wed 03/02/21 | Tue 23/02/21
Draft negotiatied contract to be initalled and submitted to IDB |  | Tue 23/02/21 | Tue 02/03/21
Non-Objection from IADB |  | Tue 02/03/21 | Wed 10/03/21
Finalization of contract |  | Wed 10/03/21 | Wed 17/03/21
Award of contract and request for any advance payment guarantee |  | Wed 17/03/21 | Wed 31/03/21
Notification of award sent to short-listed bidders and publication |  | Wed 31/03/21 | Fri 02/04/21
Execution | 0 | Mon 31/05/21 | Fri 17/12/21
Management plans for Palapa beach (Caye Caulker) and Goff's Caye |  | Wed 02/05/18 | Thu 29/11/18
Procurement process |  | Wed 02/05/18 | Fri 03/08/18
TORs preparation |  | Wed 02/05/18 | Wed 16/05/18
Non-Objection from IADB |  | Wed 16/05/18 | Thu 17/05/18
Ad posting with request for expressions of interest |  | Thu 17/05/18 | Tue 22/05/18
Reception of Expressions of Interest |  | Tue 22/05/18 | Wed 23/05/18
Analysis of expressions of interest |  | Wed 23/05/18 | Mon 04/06/18
Elaboration of short list |  | Mon 04/06/18 | Thu 14/06/18
Preparation of proposal request document |  | Thu 14/06/18 | Mon 18/06/18
Non-Objection from IADB |  | Mon 18/06/18 | Wed 20/06/18
Notification of results to participants |  | Wed 20/06/18 | Mon 25/06/18
Referral of SP to the best evalada of the short list |  | Mon 25/06/18 | Mon 02/07/18
Presentation of proposals |  | Mon 02/07/18 | Tue 03/07/18
Evaluation of technical and economic proposals |  | Tue 03/07/18 | Wed 04/07/18
Non-Objection from IADB |  | Wed 04/07/18 | Fri 13/07/18
Notification of results to participants |  | Fri 13/07/18 | Fri 20/07/18
Publication of the award |  | Fri 20/07/18 | Wed 25/07/18
Contract subscription |  | Wed 25/07/18 | Wed 01/08/18
Sending of signed contract to the IDB |  | Wed 01/08/18 | Fri 03/08/18
Execution | 113650 | Fri 03/08/18 | Thu 29/11/18 | [9 empty] | 22730 |  | 45460 | 45460
Component 2: Governance for Disaster Risk Management and Adaptation to Climate Change |  | Fri 14/08/20 | Mon 14/02/22
Risk information system |  | Fri 14/08/20 | Fri 31/12/21
Procurement process |  | Fri 14/08/20 | Mon 31/05/21
TORs preparation (selection criteria) |  | Wed 08/01/20 | Wed 05/02/20
Preparation of Request for expression of interest |  | Wed 05/02/20 | Wed 12/02/20
Seek Non-Objection for TOR and Request for Expressions of Interest |  | Wed 12/02/20 | Mon 17/02/20
Non-Objection from IADB |  | Mon 17/02/20 | Mon 24/02/20
Publication of Request for Expression of interest |  | Mon 24/02/20 | Mon 16/03/20
Prepare and submit draft request for proposal for informal review |  | Mon 16/03/20 | Mon 16/03/20
Receive and evaluate expressions of interest |  | Mon 16/03/20 | Mon 30/03/20
Submit to IDB draft request for proposals including shortlist of firms |  | Mon 30/03/20 | Mon 06/04/20
Non-Objection from IADB |  | Mon 06/04/20 | Mon 13/04/20
Issue RFP to shortlisted firms |  | Mon 13/04/20 | Wed 15/04/20
Notify evaluators of the evaluation committee |  | Wed 15/04/20 | Thu 16/04/20
Reciept of proposals and opening of technical proposal |  | Thu 16/04/20 | Fri 19/06/20
Evaluation of technical proposals |  | Fri 19/06/20 | Fri 03/07/20
Preparation of Evaluation Report and finalization |  | Fri 03/07/20 | Fri 10/07/20
Request non'objection to technical evaluation report and to open financial proposal |  | Fri 10/07/20 | Tue 14/07/20
Non-Objection from IADB |  | Tue 14/07/20 | Tue 21/07/20
Public opening of financial proposals |  | Tue 21/07/20 | Wed 22/07/20
Preparation of combined technical and financial report |  | Wed 22/07/20 | Wed 29/07/20
Request non'objection to enter negotiations with selected firm |  | Wed 29/07/20 | Fri 31/07/20
Non-Objection from IADB |  | Fri 31/07/20 | Fri 07/08/20
Conduct negotiations and prepare draft contract |  | Fri 07/08/20 | Fri 14/08/20
Request approval of draft contract from Ministry of Finance and Contractor General |  | Fri 14/08/20 | Tue 18/08/20
MOF and CG´s approval |  | Tue 18/08/20 | Mon 07/09/20
Draft negotiatied contract to be initalled and submitted to IDB |  | Mon 07/09/20 | Tue 15/09/20
Non-Objection from IADB |  | Tue 15/09/20 | Wed 23/09/20
Finalization of contract |  | Wed 23/09/20 | Wed 30/09/20
Award of contract and request for any advance payment guarantee |  | Wed 30/09/20 | Thu 15/10/20
Notification of award sent to short-listed bidders and publication |  | Thu 15/10/20 | Mon 19/10/20
Execution of the Consulting | 0 | Mon 19/10/20 | Fri 21/05/21
Designing of building codes |  | Fri 02/04/21 | Mon 14/02/22
Procurement process |  | Fri 02/04/21 | Tue 27/07/21
TORs preparation (selection criteria) |  | Fri 02/04/21 | Fri 16/04/21
Request Non-Objection for TOR and evaluation criteria |  | Fri 16/04/21 | Wed 21/04/21
Non-Objection from IADB |  | Wed 21/04/21 | Wed 28/04/21
Draft the Request for Expressions of interest |  | Wed 28/04/21 | Thu 29/04/21
Non-Objection of expression of interest |  | Thu 29/04/21 | Thu 06/05/21
Publication of Request for Expressions of Interest |  | Thu 06/05/21 | Thu 27/05/21
Receive and evaluate CVs |  | Thu 27/05/21 | Thu 03/06/21
Non-Objection from IADB |  | Thu 03/06/21 | Thu 17/06/21
Request approval of draft contract from Ministry of Finance and Contractor General |  | Thu 17/06/21 | Thu 08/07/21
Prepare report and Request Non-Objection to selected candidate and the draft contract |  | Thu 08/07/21 | Tue 13/07/21
MOF and CG´s approval |  | Tue 13/07/21 | Tue 20/07/21
Negotiation and finalisation of Contract |  | Tue 20/07/21 | Tue 27/07/21
Execution of the Consulting | 0 | Tue 27/07/21 | Mon 14/02/22
Climate risk financing strategy for the tourism and agriculture sectors |  | Thu 04/02/21 | Mon 17/01/22
Procurement process |  | Thu 04/02/21 | Tue 01/06/21
TORs preparation (selection criteria) |  | Thu 04/02/21 | Thu 18/02/21
Request Non-Objection for TOR and evaluation criteria |  | Thu 18/02/21 | Tue 23/02/21
Non-Objection from IADB |  | Tue 23/02/21 | Tue 02/03/21
Draft the Request for Expressions of interest |  | Tue 02/03/21 | Wed 03/03/21
Non-Objection of expression of interest |  | Wed 03/03/21 | Thu 11/03/21
Publication of Request for Expressions of Interest |  | Thu 11/03/21 | Wed 31/03/21
Receive and evaluate CVs |  | Wed 31/03/21 | Wed 07/04/21
Non-Objection from IADB |  | Wed 07/04/21 | Wed 21/04/21
Request approval of draft contract from Ministry of Finance and Contractor General |  | Wed 21/04/21 | Wed 12/05/21
Prepare report and Request Non-Objection to selected candidate and the draft contract |  | Wed 12/05/21 | Mon 17/05/21
MOF and CG´s approval |  | Mon 17/05/21 | Tue 25/05/21
Negotiation and finalisation of Contract |  | Tue 25/05/21 | Tue 01/06/21
Execution of the Consulting | 0 | Tue 01/06/21 | Mon 17/01/22
Project Management |  | Thu 14/06/18 | Wed 06/04/22
Technical Unit |  | Thu 14/06/18 | Wed 06/04/22
PEU Team Recruitment |  | Thu 14/06/18 | Wed 06/04/22
Procurement process |  | Thu 14/03/18 | Thu 29/06/18
Project coordinator |  | Thu 14/03/18 | Thu 29/06/18
Project Manager |  | Thu 14/03/18 | Thu 29/06/18
Coastal engineer |  | Thu 14/03/18 | Thu 29/06/18
Planning and Monitoring Specialist |  | Thu 14/03/18 | Thu 29/06/18
Procurement and Contracting Specialist |  | Thu 14/03/18 | Thu 29/06/18
Financial Management Specialist |  | Thu 14/03/18 | Thu 29/06/18
Specialist in environmental and social issues |  | Thu 14/03/18 | Thu 29/06/18
Account Clerk |  | Thu 14/03/18 | Thu 29/06/18
Driver |  | Thu 14/03/18 | Thu 29/06/18
Payment process | 271108.35 | Thu 19/07/18 | Wed 06/04/22 | [8 empty] | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 15987.5 | 12654.17 | 12654.17 | 12654.17 | 12654.17 | 12654.17
Furniture & Equipment |  | Thu 05/07/18 | Mon 01/10/18
Preparation of technical specifications |  | Thu 05/07/18 | Thu 12/07/18
Preparation of CP document and offer request |  | Thu 12/07/18 | Thu 19/07/18
Preparation and delivery of quotes |  | Thu 19/07/18 | Thu 26/07/18
Price comparison and revision of technical specifications |  | Thu 26/07/18 | Mon 30/07/18
IDB Non-Objection Request |  | Mon 30/07/18 | Tue 31/07/18
No IDB objection |  | Tue 31/07/18 | Fri 03/08/18
Notification to bidders |  | Fri 03/08/18 | Tue 07/08/18
Subscription of purchase order |  | Tue 07/08/18 | Thu 09/08/18
Delivery of furniture and equipment |  | Thu 09/08/18 | Thu 30/08/18
Furniture & Equipment | 40000 | Thu 30/08/18 | Mon 01/10/18 | [10 empty] | 4000 | 36000
Vehicle Acquisition |  | Thu 05/07/18 | Mon 01/10/18
Preparation of technical specifications |  | Thu 05/07/18 | Thu 12/07/18
Preparation of CP document and offer request |  | Thu 12/07/18 | Thu 19/07/18
Preparation and delivery of quotes |  | Thu 19/07/18 | Thu 26/07/18
Price comparison and revision of technical specifications |  | Thu 26/07/18 | Mon 30/07/18
IDB Non-Objection Request |  | Mon 30/07/18 | Tue 31/07/18
No IDB objection |  | Tue 31/07/18 | Fri 03/08/18
Notification to bidders |  | Fri 03/08/18 | Tue 07/08/18
Subscription of purchase order |  | Tue 07/08/18 | Thu 09/08/18
Delivery of furniture and equipment |  | Thu 09/08/18 | Thu 30/08/18
Vehicle Delivery | 40000 | Thu 30/08/18 | Mon 01/10/18 | [10 empty] | 4000 | 36000
Operating Expenses (Papeleria and others) |  | Wed 28/11/18 | Wed 11/08/21
Year 1 | 24957 | Wed 28/11/18 | Wed 19/12/18 | [12 empty] | 10957 | 14000
Year 3 | 0 | Fri 17/07/20 | Fri 07/08/20
Year 4 |  | Wed 21/07/21 | Wed 11/08/21
Annual Evaluations and Audits |  | Thu 12/07/18 | Mon 18/04/22
Reviews |  | Fri 14/08/20 | Tue 05/04/22
Intermediate evaluation |  | Fri 14/08/20 | Tue 23/02/21
Procurement process |  | Fri 14/08/20 | Fri 27/11/20
Payment process | 0 | Fri 27/11/20 | Tue 23/02/21
Final evaluation |  | Thu 15/07/21 | Fri 18/02/22
Procurement process |  | Thu 15/07/21 | Fri 26/11/21
Payment process | 0 | Fri 26/11/21 | Fri 18/02/22
Impact evaluation |  | Mon 19/07/21 | Tue 05/03/22
Procurement process |  | Mon 19/07/21 | Fri 12/11/21
Payment process | 0 | Fri 12/11/21 | Tue 05/03/22
Annual audits |  | Thu 12/07/18 | Mon 18/03/22
Audit Year 1 | 20000 | Thu 12/07/18 | Fri 28/12/18 | [11 empty] | 6400 | 6800 | 6800
Audit Year 2 | 19291.67 | Tue 08/10/19 | Mon 06/01/20 | [23 empty] | 5958.33 | 6666.67 | 6666.67
Audit Year 3 | 0 | Fri 09/10/20 | Thu 07/01/21
Audit Year 4 | 0 | Tue 14/09/21 | Mon 18/03/22
TOTAL AOP | 3033846.89
Monthly Expense | [10 empty] | 10958.33 | 30654.16 | 53384.17 | 36654.17 | 862657.7 | 250262.5 | 288440.83 | 32783.5 | 132783.5 | 132783.5 | 232783.5 | 132783.5 | 132783.5 | 132783.5 | 136783.5 | 136116.84 | 143075.17 | 129387.51 | 25987.51
Cumulative Expensive | [10 empty] | 10958.33 | 41612.49 | 94996.66 | 131650.83 | 994308.53 | 1244571.03 | 1533011.86 | 1565795.36 | 1698578.86 | 1831362.36 | 2064145.86 | 2196929.36 | 2329712.86 | 2462496.36 | 2599279.86 | 2735396.7 | 2878471.87 | 3007859.38 | 3033846.89
Annual Disbursement | [10 empty] | 1533011.86 | [6 empty] | 1500835.03