Korea Poverty Reduction Fund (KPF)

TC PROFILE

### June 2006

- Basic project data

| Beneficiary Country: | Argentina |  |
| --- | --- | --- |
| Project name: | Support for the design of a technical education program |  |
| Project number: | AR-T1017 |  |
| Project team: | Hugo Flórez-Timorán (RE1/SO1), Team Leader; María Deni Sánchez (RE1/SO1), and Claudia Pévere (RE1/SO1) |  |
| Executing agency: | National Ministry of Education, Science and Technology (MECyT), through the National Institute of Education and Technology (INET) |  |
| Beneficiaries: | Post-Secondary school age youths |  |
| Date of request: |  | May 15 2006 |
| Financing plan: | IDB (KPF): | US$ 104,000 |
|  | Local Counterpart / SO1: | US$ 26,000 |
|  | Total: | US$ 130,000 |
| Tentative dates: |  |  |
|  | Korean Fund Approval | ###### June 2006 |
|  | Division Chief’s approval | June 2006 |
| Execution period: | 9 months |  |
| Disbursement period: | 12 months |  |

- Background and problem statement

- Education in Argentina

  - The education system of Argentina is one of the most comprehensive in the region (enrollment in primary education is almost universal -92,2%- and literacy rate has reached 97,4%). However, the quality and efficiency of education is heterogeneous and needs to be improved for students from the poorest households who are at risk of dropping out or repeating, especially at the secondary and post-secondary level.

  - This heterogeneity becomes clear when analyzing education indicators by age structure.  Sixty five percent of the younger population that is about to enter the labor market has not completed secondary education. The variations among jurisdictions are striking, while 40,3% of young people have not completed secondary school in the City of Buenos Aires, 76,6% have not achieved this level in the province of Misiones.

  - In addition to having a strong negative impact on the access and use of education services, the economic crisis of 2001 deteriorated the delivery of services and key education indicators. Household survey analyses demonstrate the effects of the social impact of the crisis: net enrolment rate of young people who were 15 years old in 1998 dropped by 9.3 percentage points by 2000, while the drop for those who were 17 in 1998 was much larger, 28 percentage points by 2000.  Also, 16 year olds in 1998 had a drop in net enrolment of 17 percentage points by 2000, while 16 year olds in 2000 had a drop of 27 percentage points by 2002.

  - In 2003, young people enrolled in secondary school level had a 24,8% annual repetition rate, and 18,4% had abandoned school previous to completing secondary education. Household surveys projections revealed that 19,1% of these youths (1.271.945) are inactive  (neither study nor work, or seek employment). Even though the situation differs when disaggregating by region, these percentages are high in general. In the provinces of Tucumán and San Juan, inactive people represent 23,9% and 23.7% respectively.  In Buenos Aires, Santa Fe and Entre Ríos young inactive people reaches 20%. Given the right incentives and activities, this group could be potentially reinserted into the educational system.

- Poverty and Inequality of young people

  - Poverty analyses show that approximately 54,6% of the population lives below the poverty line, and almost 25% of the population in extreme poverty. Slightly over half of the poor reside in urban areas and 20% of rural population is living under extreme poverty conditions. This situation is not homogenous across the country, while in provinces such as Neuquén the poor represent 47.5%, in Greater Buenos Aires they represent 69%.

Households under the extreme poverty line

Households under the poverty line

Persons under the extreme poverty line

Persons under the poverty line

  - Moreover, income inequality has increased considerably in the last decade. This is reflected in the Gini coefficient, which increased significantly from around 45% in the mid 1990s to 53% by 2003. In 2004, the 10% richest households received 30.1% of the income, while those households in the poorest decile only received 1.8%.

  - There are also severe differences in terms of the incidence of poverty according to age groups. While 18.8% of the population aged 65 and over is poor, 56% of the individuals aged 0 to 13 and 49% of those aged 14 to 22 are poor. Almost half of the population of secondary and post-secondary school age is poor, and 20% of that population segment is living in extreme poor conditions.

| #### Poverty levels by age group |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | #### Age Groups |  |  |  |
|  | Total | 0 a 13 | 14 a 22 | 23 a 64 | 65 and over |
| Total (thousands) | 23,402 | 5,585 | 3,747 | 11,607 | 2,463 |
| Poor (%) | 40.2 | 56.4 | 49.0 | 34.0 | 18.8 |
| Poor | 25.1 | 32.3 | 30.6 | 22.3 | 13.9 |
| Extreme Poor | 15.0 | 24.1 | 18.4 | 11.7 | 4.9 |
| Source: INDEC, EPH 2003 |  |  |  |  |  |

  - Studies demonstrate that the poorest segments of the population have a greater propensity to drop out of education regardless whether or not they have access to adequate supply. According to flow analysis, out of every 100 students that enter secondary education, only half finishes the cycle. Most of the children that drop out before finishing belong to the poorest segments of the population. According to the EPH, only 27% of the poorest quintile had completed secondary education, compared with 83% of the richest quintile. Such context of social inequity hinders the conditions to promote school retention, thus, limiting the possibility of ending with the poverty cycle.

- Technical Education as a vehicle to promote labor market participation

  - The high level of repetition and drop out rates of the population at risk at the secondary level has placed the education system in the need to design innovative strategies to promote labor market inclusion of this population. Technical education represents an opportunity for young people to acquire the necessary tools and basic skills to adapt to labor market demands.

  - In response to the changing needs, the Government of Argentina (GOA) has provided a New Technical Education Law (Law 26.058, 2005) which recognizes the key role of the National Technical Education Institute (INET) as a means to provide a technical education that: (i) organizes the national technical education (NTE) system; (ii) provides instruments to regulate and organize the system; 
(iii) strengthens local technical education provision; and (iv) promotes equity and quality of education as a means to support social inclusion, economic development and the encouragement of labor competitiveness, among others.

  - Moreover, the GOA believes that, within a framework of economic development with higher levels of equity and social inclusion, technical education constitutes –at the national and local levels-  a key factor for sustainable economic growth due to its importance in affecting job creation, productivity and competitiveness.

  - Nowadays, the technical education system in Argentina suffers from the lack of institutional differentiation to accommodate diverse and growing demands, the lack of an institutional homogeneous framework, inefficient allocation of resources, lack of supply information of all technical schools, lack of common competencies and incipient labor market relation.

  - Thus, the importance of supporting the reorganization and strengthening of the technical education in Argentina to foster activities to better respond rapidly to the changing labor market needs by contributing to training a qualified and adaptable labor force, generating new knowledge, and providing education in accordance to the productive sectors.

  - As a first step to create a solid institutional framework, article 32 of the Technical Education Law promotes the development of three key instruments for the quality improvement of education: (i) the Homologation of Titles and Certifications, (ii) the creation of a National Title and Certification Catalogue and (iii) the creation of a Federal Registry of Technical Education Institutes. This TC will promote the development of these actions.

- Relationship to Bank’s strategy

  - The Country Strategy for Argentina (CP-2785) mandates that the Bank support government efforts in promoting a more equitable education, and the retention of young adults in schools, particularly of those belonging to the poorest segments of the population. The strategy stresses the importance of strengthening education activities to better articulate the link with the labor market sector.

  - Moreover, the Bank promotes the development of advanced skills which are critical determinants of a country's economic growth and improvement of standard of living. Good quality, merit-based, equitable, efficient technical education and research are essential parts of a country’s competitiveness.

  - The Bank’s Strategy on Poverty Reduction and Promotion of Social Equity (CP-1894-7) supports actions aimed at achieving universal enrollment at the primary level, improving its quality and gradually expanding access of the poor to quality secondary and post-secondary education. These activities will seek to improve efficiency and equity of education systems in order to guarantee learning and development of the skills necessary for youths to become active citizens and to participate effectively in economic development.

  - The proposed TC provides a mechanism that allows carrying out the recommendations of the Bank in order to support the efforts of the government in achieving equity and quality in education and a better link to the labor market sector.

- Links with Banks programs in the education sector

  - This program will strengthen the activities financed under other IDB education projects such as the PROMSE loan (Education System Improvement Program (1345/OC-AR)). The PROMSE promotes activities to reform the secondary education by targeting schools that have a majority of poor students. The objective of the loan is to support the improvement of the quality, equity and efficiency of the education system, contributing to a more pertinent supply and a reduction in social inequity through more years of schooling for young people from poor families, which will improve their employability. The program focuses on attaining the objectives of secondary school education reform, which has not yet been fully implemented in most of the provinces, and on targeting support for students at greatest social and educational risk.

  - The Bank is preparing the Strengthening of the Technical Education Loan (AR-L1018). The objective of this program is to strengthen the Technical Education System by supporting the activities mentioned in the Technical Education Law. This TC will provide key inputs for the design and implementation of the project and in laying the basis for the reorganization of the system by creating a Title and Certification Catalogue for the National Technical Education System.

- Program objective and description

  - The objective of this TC is to support the preparation of the Technical Education loan by designing a national title and certification catalogue which will provide the basis to organize the Technical Education System.

  - The specific objectives of the technical education catalogue are: (i) to identify the contents and specifications of the technical education curricula, (ii) to provide a systematized and updated system of the technical education supply, (iii) to provide input for developing the teacher training curricula, (iv) to provide information on the education supply, (v) to provide information of the technical education supply to potential students, and (vi) to provide the basis for an integrated information system with data related to the monitoring of graduate students.

  - The TC will benefit youths that attend post-secondary education, and prospective students to technical education institutions. The program consists of two components: (i) Catalogue of Titles and Certifications; and (ii) International Workshop on Technical Education Systems.

  - Component 1. National Catalogue of Titles and Certification of Technical Education Institutions.  The objective of this component is to design a national catalogue of titles and certifications of all the technical education institutions, at the provincial and municipal levels. Such catalogue should identify information on: productive sectors and sub-sectors, professional family, professional profile, curricula, eligibility criteria, hours per course, type of institution, title or certificate offered, information’s needs assessment, among others. Once this information is standardized, the catalogue will provide key input for the development of the teacher training curricula for in-training service and initial teacher formation. Furthermore, the loan will implement a system for monitoring graduate students and their insertion into the labor market. This system will provide input to the catalogue by verifying the relevance of the curricula offered and ensure the link between labor market demand and technical education supply.

  - The following activities will be financed: (i) consultancy services for developing an implementation plan for the catalogue, (ii) technical assistance for the staff of the INET in the technical aspects for maintaining and updating the information system, (iii) a review of international experiences and best practices, (iii) consultancy services for developing a plan for in-service teacher formation, and (iv) a consultancy for designing a graduate monitoring system. These consultancies 
(iii) and (iv) will be financed with counterpart funding.

  - The expected outputs are: (i) an action plan for establishing a national catalogue of titles and certifications, (ii) an implementation plan to systematize the information system that provides information of the supply of technology education, 
(iii) identification of institutional strengthening activities to implement the catalogue at the three governmental levels, (iv) a strategy to implement in-service teacher formation, and (v) an action plan to implement an integrated information system that provides data on technical education supply and monitors graduate insertion into the labor market.

  - Component 2.  International Workshop on Technical Education Systems.  The objective of this component is to provide knowledge on lessons learned of international experiences and best practices of technical education systems with a special emphasis on catalogue and information system’s maintenance.

  - This TC will finance international experts in the field to provide an overview of experiences from Asia, Europe and Latin America. The following thematic areas have been pre-identified for this workshop: (i) characterization of the technical education system, (ii) best practices in the development of a technical education catalogue; and (iii) systematization and integration of information at local and federal levels, among others.

  - Each international expert will be expected to provide a case study on the technical education system of their expertise and a thorough analysis on best practices for developing a technical education catalogue, or in-service teacher formation or other specific topics related to strengthening technical education. Such studies along with the results from the workshop will be published and disseminated among relevant actors.

  - The expected outputs are: (i) comprehensive knowledge of international best practices of technical education systems, (ii) increased awareness on the importance of participation of local governments and institutions, (iii) acquaintance of activities that promote to the sustainability of similar projects, and (iv) awareness on the uses and capabilities of a catalogue of titles and certifications.

- Cost and financing

  - The total budget for the current TC proposal is estimated at US$130,000, of which US$104,000 will be financed with KPF non-reimbursable resources. The local counterpart funding will be financed by SO1 administrative budget (US$24,000) and the INET in kind (US$2,000) and is a total estimated at US$ 26.000. The following table presents a detailed budget:

Project Costs (in US$ dollars)

KPF

Total

Component 1. Catalogue of Titles and Certification

Design of a technical education catalogue

70 days

500

35,000

35,000

Travel and Per Diem

1

1,500

1,500

1,500

15 days

176

2,640

2,640

Teacher Development and Training

1

12,000

12,000

12,000

Development of a follow up system for graduates

1

12,000

12,000

12,000

International Experts Case Study

6

5,500

33,000

33,000

International Experts from Asia

Air Fare

2

5,000

10,000

10,000

Per Diem

4

528

2,112

2,112

International Experts from Europe

Air Fare

2

2,000

4,000

4,000

Per Diem

4

528

2,112

2,112

International Experts from LAC

Air Fare

2

1,000

2,000

2,000

Per Diem

4

528

2,112

2,112

Workshop (materials, logistics, etc)

100 participants

70

5,000

2,000

7,000

Publications

3,524

3,524

Contingencies

1,000

1,000

1,000

TOTAL

104,000

26,000

130,000

TOTAL

Component 2.  International Workshop

Activity

Quantity

Cost per

Unit

Counterpart

- V.	Execution

  - Hugo Flórez-Timorán (RE1/SO1) (hugof@iadb.org - Tel. (202)6233275 – Fax (202)6233831) will be responsible for the technical, financial and procurement management of the proposed TC. The INET will act in cooperation with the different entities of the MECyT for supporting the technical aspects of the execution.

  - The execution period will be 9 months, with 12 months allowed for the last disbursement.

- Major issues

  - The main risks that can affect the performance of the project are: (i) lack of active participation of the jurisdictions in order to guarantee the fulfillment of the goals; and (ii) poor information systems within the jurisdictions needed to carry out the components of the project.

  - The measures to mitigate such risks are, in each case: (i) constant dialogue and communication with the provincial jurisdictions to generate awareness on the importance of a National Catalogue of Titles and Certification, and (ii) to promote knowledge of international best practices to provide key inputs for the sustainability and efficiency on information systems for technical education.

- Recommendation

- 7.1	Hugo Florez-Timoran, designated team leader for the project of the reference, recommends the approval of this operation and the use of resources from the Poverty Reduction Korea Fund (KPR) totaling up to US$104,000 in order to finance the corresponding project.

- Certification

8.1	I certify that this operation was approved for financing by the donor of the Poverty Reduction Korea Fund (KPR) and communicated through a memo dated June 7, 2006 signed by the RE2/FSS. Also, I certify that resources from the Poverty Reduction Korea Fund (KPR) are available for up to US$104,000 in order to finance the activities described and budgeted in this document. The commitment and disbursement of these resources shall be made only by the Bank in US Dollars. The same currency shall be used to stipulate the remuneration and payments to consultants, except that local consultants working in their own borrowing member country shall have their remuneration defined and paid in the currency of that country.  No resources of the Fund shall be made available to cover amounts greater than the amount certified herein above for the implementation of this TC Brief. Amounts greater than the certified amount may arise from commitments on contracts denominated in a currency other than the Fund currency, resulting in currency exchange rate differences, for which the Fund is not at risk.

| (original firmado) |  |
| --- | --- |
| ## Arnoldo Medeiros da Fonseca Jr. | Date |
| ### Chief, Technical Cooperation Coordination Unit |  |

- Approval

Approved: _____(original firmado)_____			 _____16 junio 2006___

Juan Manuel Fariña					     Date

RE1/SO1/CHF

20 years or more

EPH, May 2003

World Bank data from SEDLAC

Poverty analyses demonstrate that school completion is important in reducing the risk of poverty as indicated by the estimates of the household survey. For household heads, according to 2003 data, having completed secondary schooling decreased the chances of poverty by 40 percentage points. For non-household members, that reduction was of 10 percentage points.