## AOP_PEP
|  |  |  | 2017 |  |  |  |  | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
|  |  |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Solution
Component 1. Violent crime prevention and management (US$12,176,676 million). |  |  | Total Costs for Five years in US$
Subcomponent 1.1. Support for the implementation of problem-oriented policing for crime prevention, including hot-spot policing |  |  | 7486062
|  | Procure handheld devices for CIB investigators (x 1800) | 1080000
|  | Provide user training on use of equipment (application) | 30140
| 1 | Technical Specialist Consultant - Georeferencing (24 months) | 120000
|  | Fleet management, GEONODE and Front End System Integration for Emergency Phone Calls | 3000000
| 2 | Technical Specialist Consultant - Fleet Management (28 months) | 170000
|  | Surveillance equipment procured | 1372922
|  | DCS Surveillance equipment procured (Cameras - CCTV) | 407000
|  | Monitoring Center (1) | 500000
|  | Hardware, Software, Professional Services, Documentation and Configuration Services. | 590600
|  | Provide user training on use of equipment | 45400
| 3 | Technical Specialist Consultant - Surveillance (28 months) | 170000
Subcomponent 1.2. Equip and connect police stations, prisons, and the National Police College of Jamaica |  |  | 4300000
|  | Connecting 45 (of 178) Police Stations (kma, 45, 11 prisons and parole offices, mobay) | 2000000
|  | 4G LTE CORE & Base Stations | 600000
|  | Building access (5 model location) | 250000
|  | (Prior options review for DCS) Prison model review | 60000
|  | Procure hardware (special monitors, printers, UPS, computers, digital signature pads, scanners), Maintenance, Support and Installation / Implementation, Configuration, among others) | 1200000
| 4 | Technical Specialist Consultant - Connectivity (36 months) | 190000
Subcomponent 1.3. Share information with the public through open data |  |  | 390614
|  | Open data initiative | 336296
| 5 | Technical Specialist Consultant - Open Data Initiative (11 months) | 54318
Total Component 1 |  |  | 12176676
Component 2 - Improving investigative capabilities for violent crimes (US$1,811,324 million).
Subcomponent 2.1. Increase the quality of casefiles |  |  | 1510000
|  | Procure e-case management system (automating manual processes and other functionalities to improve efficiency and accountability) | 500000
|  | Implement e-case management system | 250000
|  | Engraving machine for FLA | 50000
|  | Ballistic identifier | 350000
|  | Technical Specialist Consultant - Case Management & Digital Registries (60 months) | 360000
Subcomponent 2.2. Design and implementation of digital registries |  |  | 181324
|  | Design of digital registries, including adaptation to capture data con domestic violence | 74981
|  | Implement registries and design of protocols to handle domestic violence cases | 29000
|  | User training for digital registries | 52343
|  | Maintenance and Support (5 years) | 25000
Subcomponent 2.3. Design and implement a data sharing exchange protocol |  |  | 120000
| 7 | Technical Specialist Consultant - Data Sharing (24 months) | 120000
Total Component 2 |  |  | 1811324
Component 3 - Change Management & Training (US$3,212,000 million).
Subcomponent 3.1. Change Management and Communications |  |  | 1200000
|  | Communications Plan | 500000
|  | Change Management Plan | 400000
| 8 | Technical Specialist Consultant - Change Management & Communications (60 months) | 300000
Subcomponent 3.2. Training in collaboration with the National Police College of Jamaica |  |  | 2012000
|  | Assessment test and remedial training for new recruits | 20000
|  | Assessment test and remedial training for existing members of the Force | 120000
| 9 | Technical Specialist Consultant - Assessment Training (30 months) | 147000
|  | College hardware (laptops and desktops) | 95000
|  | VC equipment in divisional HQ, NPCJ, MNS and Commissioners Office | 50000
|  | Technical Specialist Consultant - NPCJ & VC Equipment (24 months) | 120000
|  | Review of curricula to include technology | 180000
|  | Training on use of digital registries and case management system for existing members of the Force | 80000
|  | Data analytics training for MNS, JCF/CIB, JCF/CSRP | 500000
|  | PICA training | 200000
|  | Provide training on use of data for evidence-based policing strategies | 90000
|  | Training on new protocols for handeling domestic violence for existing members of the Force | 200000
| 11 | Technical Specialist TRAINING Consultant for Sub-component 3114 and provide management over all other training components (38 months) | 210000
Total Component 3 |  |  | 3212000
Project Administration and Coordination |  |  | 2000000.1742
|  | Project Execution Unit | 207438
| 1 | Project Director | 407751.938
| 2 | Procurement Specialist - Manager | 276000
| 3 | Financial Specialist - Manager | 314700
| 4 | Monitoring & Evaluation Specialist | 276000
| 5 | Administrative & Procurement Officer | 170000
| 6 | Finance & Logistics Officer | 170000
| 7 | Project Coordinator Assistant (PCA) & HR Liaison | 118110.2362
|  | Audit | 60000
Audits and M&E |  |  | 300000 | bar: 2018 Jun to 2022 Dec
Contingency |  |  | 500000
Program Total |  |  | 20000000.1742

## Budget
SECURITY STRENGTHENING PROJECT (SSP)
FIVE YEAR BUDGET
[7 empty] | Month #1 | Month #2 | Month #3 | Month #4 | Month #5 | Month #6 | Month #7 | Month #8 | Month #9 | Month #10 | Month #11 | Month #12 | Month #13 | Month #14 | Month #15 | Month #16 | Month #17 | Month #18
[6 empty] | 725935.8674 | Month #1: Retroactive Financing Period
[6 empty] | 4871161.7444 | Month #1: First 18 Months
[7 empty] | Month #1: 2017; Month #5: 2018 |  |  |  | 2018 |  |  |  | 2019
[7 empty] | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October |  |  | November | December | January | February | March | April | May | June | July | August | September | October |  |  | November | December | January | February | March | April | May | June | July | August | September | October |  |  | November | December | January | February | March | April | May | June | July | August | September | October
Outputs | Unit of measure | # of units for 5 years | Cost per unit | Total Cost 5 Years US$) | # of units per year (year 1) | Year 1 (annual costs in US$) |  |  | Year 1 - Month 1 | Year 1 - Month 2 | Year 1 - Month 3 | Year 1 - Month 4 | Year 1 - Month 5 | Year 1 - Month 6 | Year 1 - Month 7 | Year 1 - Month 8 | Year 1 - Month 9 | Year 1 - Month 10 | Year 1 - Month 11 | Year 1 - Month 12 | Year 2 - Month 1 | Year 2 - Month 2 | Year 2 - Month 3 | Year 2 - Month 4 | Year 2 - Month 5 | Year 2 - Month 6 | Year 2 - Month 7 | Year 2 - Month 8 | Year 2 - Month 9 | Year 2 - Month 10 | Year 2 - Month 11 | Year 2 - Month 12 | # of units per year (year 2) | Year 2 (annual costs in US$) | Year 3 - Month 1 | Year 3 - Month 2 | Year 3 - Month 3 | Year 3 - Month 4 | Year 3 - Month 5 | Year 3 - Month 6 | Year 3 - Month 7 | Year 3 - Month 8 | Year 3 - Month 9 | Year 3 - Month 10 | Year 3 - Month 11 | Year 3 - Month 12 | # of units per year (year 3) | Year 3 (annual costs in US$) | Year 4 - Month 1 | Year 4 - Month 2 | Year 4 - Month 3 | Year 4 - Month 4 | Year 4 - Month 5 | Year 4 - Month 6 | Year 4 - Month 7 | Year 4 - Month 8 | Year 4 - Month 9 | Year 4 - Month 10 | Year 4 - Month 11 | Year 4 - Month 12 | # of units per year (year 4) | Year 4 (annual costs in US$) | Year 5 - Month 1 | Year 5 - Month 2 | Year 5 - Month 3 | Year 5 - Month 4 | Year 5 - Month 5 | Year 5 - Month 6 | Year 5 - Month 7 | Year 5 - Month 8 | Year 5 - Month 9 | Year 5 - Month 10 | Year 5 - Month 11 | Year 5 - Month 12 | # of units per year (year 5) | Year 5 (annual costs in US$) | TOTAL OF FIVE YEARS (US$)
Component 1. Violent crime prevention and management (US$12,176,676 million).
Procure handheld devices for CIB investigators (x 1800) with installation and maintenance (replacements) | # of handheld devices | 1800 | 600 | 1080000 | 900 | 0 | [19 empty] | 540000 | [6 empty] | 900 | 540000 | [12 empty] | 900 | 540000 | [26 empty] | 0 | 0
Provide user training on use of equipment (application) | # of training instrument | 1 | 30140 | 30140 | 1 | 0 | [19 empty] | 15070 | [6 empty] | 1 | 15070 | [12 empty] | 1 | 15070 | [26 empty] | 0 | 0
Technical Specialist Consultant - Georeferencing (24 months) | # of consultants | 1 | 120000 | 120000 | 1 | 0 | [19 empty] | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 0 | 35000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 0 | 60000 | 5000 | 5000 | 5000 | 5000 | 5000 | [21 empty] | 0 | 25000
Fleet management, GEONODE and Front End System Integration for Emergency Phone Calls | # of enterprise fleet management, system | 1 | 3000000 | 3000000 | 1 | 0 | [26 empty] | 1 |  | 1500000 | [11 empty] | 1 | 1500000 | 1500000 | [12 empty] | 1500000 | [12 empty] | 1 | 0
Technical Specialist Consultant - Fleet Management (28 months) | # of consultants | 1 | 170000 | 170000 | 1 | 0 | [24 empty] | 6071.4286 | 6071.4286 | 1 | 12142.8571 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 1 | 72857.1429 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 |  | 72857.1429 | 6071.4286 | 6071.4286 | [10 empty] | 1 | 12142.8571
Surveillance equipment | # of surveillance equipment (implementation and maintenance (replacements) included) | 300 | 4576.4067 | 1372922 | 100 | 457640.6667 | Month #5: 183056.2667 |  | 274584.4 | [8 empty] | 457640.6667 | [6 empty] | 100 | 457640.6667 |  |  | 457640.6667 | [9 empty] | 100 | 457640.6667 | [26 empty] | 0 | 0
DCS Surveillance equipment (Cameras - CCTV) | # of dcs surveillance equipment by Lot (implementation and maintenance (replacements) included | 1 | 407000 | 407000 | 0 | 0 | [14 empty] | 203500 | [11 empty] | 1 | 203500 | 203500 | [11 empty] | 1 | 203500 | [26 empty] | 0 | 0
Monitoring Center (1) | # of monitoring center | 1 | 500000 | 500000 | 1 | 250000 | [9 empty] | 250000 | [9 empty] | 250000 | [6 empty] | 1 | 250000 | [12 empty] | 1 | 0 | [26 empty] | 0 | 0
Hardware, Software, Professional Services, Documentation and Configuration Services. | # of hardware & professional services by Lot | 1 | 590600 | 590600 | 1 | 126557.1429 | Month #5: 42185.7143 |  | 84371.4286 | [8 empty] | 126557.1429 | [6 empty] | 1 | 126557.1429 |  |  | 337485.7143 | [9 empty] | 1 | 337485.7143 | [26 empty] | 0 | 0
Provide user training on use of equipment | # of training instrument | 1 | 45400 | 45400 | 1 | 22700 | Month #5: 11350 | 11350 | [9 empty] | 22700 | [6 empty] | 1 | 22700 | [12 empty] | 1 | 0 | [26 empty] | 0 | 0
Technical Specialist Consultant - Surveillance (28 months) | # of technical specialist consultant for sub-components 1113 (28 months) | 1 | 170000 | 170000 | 1 | 12142.8571 | [12 empty] | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 1 | 72857.1429 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 6071.4286 | 1 | 72857.1429 | 6071.4286 | 6071.4286 | [11 empty] | 12142.8571 | [12 empty] | 0 | 0
Subcomponent 1.1. Support for the implementation of problem-oriented policing for crime prevention, including hot-spot policing |  |  |  | 7486062 |  | 869040.6667 | [27 empty] | 1735467.8095 | [13 empty] | 3259410.6667 | [13 empty] | 1585000 | [13 empty] | 37142.8571 | 7486062
Connecting 45 (of 178) Police Stations (kma, 45, 11 prisons and parole offices, mobay) | # of connecting 50 (of 178) police stations (kma, 45, 11 prisons and parole offices, mobay) by Lot | 1 | 2000000 | 2000000 | 1 | 666666.6667 | [12 empty] | 666666.6667 | [10 empty] | 666666.6667 |  |  | 1 | 666666.6667 | [6 empty] | 666666.6667 | [5 empty] | 1 | 666666.6667 | [26 empty] | 0 | 0
4G LTE CORE & Base Stations | # of 4g lte core & base stations by Lot | 1 | 600000 | 600000 | 1 | 200000 | [12 empty] | 200000 | [10 empty] | 200000 |  |  | 1 | 200000 | [6 empty] | 200000 | [5 empty] | 1 | 200000 | [26 empty] | 1 | 1
Building access (5 model location) | # of building access (5 model location) by Lot | 1 | 250000 | 250000 | 1 | 83333.3333 | [12 empty] | 83333.3333 | [10 empty] | 83333.3333 |  |  | 1 | 83333.3333 | [6 empty] | 83333.3333 | [5 empty] | 1 | 83333.3333 | [26 empty] | 2 | 2
(Prior options review for DCS) Prison model review | # of consultants | 1 | 60000 | 60000 | 1 | 30000 | Month #8: 30000 | [5 empty] | 30000 | [11 empty] | 1 | 30000 | [12 empty] | 1 | 0 | [26 empty] | 3 | 3
Procure hardware (special monitors, printers, UPS, computers, digital signature pads, scanners), Maintenance, Support and Installation / Implementation, Configuration, among others) | # of procure hardware (special monitors, printers, ups, computers, digital signature pads, scanners), maintenance, support and installation / implementation, configuration, among others) by Lot | 1 | 1200000 | 1200000 | 1 | 0 | [14 empty] | 300000 | [11 empty] | 1 | 300000 | 300000 | [11 empty] | 1 | 300000 | 300000 | [10 empty] | 300000 |  | 300000 | 300000 | [12 empty] | 300000
Technical Specialist Consultant - Connectivity (36 months) | # of consultants | 1 | 190000 | 190000 | 1 | 52777.7778 | Month #5: 5277.7778; Month #6: 5277.7778; Month #7: 5277.7778; Month #8: 5277.7778; Month #9: 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 1 | 63333.3333 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 5277.7778 | 1 | 63333.3333 | 5277.7778 | 5277.7778 | [10 empty] | 1 | 10555.5556 | [12 empty] | 0 | 0
Subcomponent 1.2. Equip and connect police stations, prisons, and the National Police College of Jamaica |  |  |  | 4300000 |  | 1032777.7778 | Month #5: 241869.7587; Month #6: 5277.7778; Month #7: 5277.7778; Month #8: 35277.7778; Month #9: 5277.7778 | 266627.7778 | 364233.6063 | 5277.7778 | 961349.2063 | 11349.2063 | [13 empty] | 1343333.3333 | [13 empty] | 1313333.3333 | [12 empty] | 1 | 310555.5556 | [13 empty] | 300000 | 4300000
Open data initiative | # of open data initiative (professional services) by Lot | 1 | 336296 | 336296 | 1 | 168148 | [10 empty] | 168148 | [7 empty] | 168148 | [7 empty] | 1 | 168148 | [12 empty] | 1
Technical Specialist Consultant - Open Data Initiative (11 months) | # of consultants | 1 | 54318 | 54318 | 1 | 19752.0736 | [10 empty] | 4938 | 4938.0245 | 4938.0245 | 4938.0245 | 4938.0245 | 4938.0245 | 4938.0245 | 4938.0245 | 4938.0245 | 4938.0245 | 4938.0245 | [5 empty] | 1 | 34566.1718 | [12 empty] | 1
Subcomponent 1.3. Share information with the public through open data |  |  |  | 390614 |  | 187900.0736 | [27 empty] | 202714.1718 | [13 empty] | 0 | [13 empty] | 0 | [13 empty] | 0 | 390614.2455
TOTAL Component 1 |  |  |  | 12176676 |  | 2089718.5181 | [27 empty] | 3281515.3147 | [13 empty] | 4572744 | [13 empty] | 1895555.5556 | [13 empty] | 337142.8571 | 12176676.2455
Component 2 - Improving investigative capabilities for violent crimes (US$1,811,324 million).
Procure e-case management system (automating manual processes and other functionalities to improve efficiency and accountability) | # of Enterprise Case Management System by Lot | 1 | 500000 | 500000 | 1 | 0 | [21 empty] | 500000 | [5 empty] | 500000 | [12 empty] | 1 | 0 | [12 empty] | 1 | 0 | [12 empty] | 1 | 0
Implement e-case management system | # of implementation | 1 | 250000 | 250000 | 1 | 0 | [27 empty] | 0 | 250000 | [11 empty] | 1 | 250000 | [12 empty] | 1 | 0 | [12 empty] | 1 | 0
Engraving machine for FLA | # of Engraving Machine | 1 | 50000 | 50000 | 1 | 0 | [18 empty] | 50000 | [8 empty] | 50000 | [12 empty] | 1 | 0 | [12 empty] | 1 | 0 | [12 empty] | 1 | 0
Ballistic identifier | # of Ballistic Identifier | 1 | 350000 | 350000 | 1 | 0 | [27 empty] | 0 |  |  | 350000 | [9 empty] | 1 | 350000 | [12 empty] | 1 | 0 | [12 empty] | 1 | 0
Technical Specialist Consultant - Case Management & Digital Registries (60 months) | # of Consultants | 1 | 360000 | 360000 | 1 | 56842.1053 | Month #6: 6315.7895; Month #7: 6315.7895; Month #8: 6315.7895; Month #9: 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 |  | 75789.4737 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 1 | 75789.4737 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 1 | 75789.4737 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 1 | 75789.4737
Subcomponent 2.1. Increase the quality of casefiles |  |  |  | 1510000 |  | 56842.1053 | [27 empty] | 625789.4737 | [13 empty] | 675789.4737 | [13 empty] | 75789.4737 | [13 empty] | 75789.4737 | 1510000
Design of digital registries | # of digital registry | 1 | 74981 | 74981 | 1 | 74981 | [10 empty] | 74981 | [16 empty] | 0 | [13 empty] | 0 | [12 empty] | 1 | 0 | [13 empty] | 0
Implement registries | # of implementation | 1 | 29000 | 29000 | 1 | 29000 | [13 empty] | 29000 | [27 empty] | 0 | [12 empty] | 1 | 0 | [13 empty] | 0
User training for digital registries | # of training instruments | 1 | 52343 | 52343 | 1 | [15 empty] | 52343 | [12 empty] | 52343 | [13 empty] | 0 | [12 empty] | 1 | 0 | [13 empty] | 0
Maintenance and Support (5 years) | # of maintenance support | 1 | 25000 | 25000 | 1 | 25000 | [10 empty] | 25000 | [16 empty] | 0 | [13 empty] | 0 | [12 empty] | 1 | 0 | [13 empty] | 0
Subcomponent 2.2. Design and implementation of digital registries) |  |  |  | 181324 |  | 128981 | [27 empty] | 52343 | [13 empty] | 0 | [13 empty] | 0 | [14 empty] | 181324
Technical Specialist Consultant - Data Sharing (24 months) | # of Consultants | 1 | 120000 | 120000 | 1 | 45000 | Month #6: 5000; Month #7: 5000; Month #8: 5000; Month #9: 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 |  | 60000 | 5000 | 5000 | 5000 | [10 empty] | 15000 | [12 empty] | 1 | 0 | [13 empty] | 0
Subcomponent 2.3. Design and implement a data sharing exchange protocol |  |  |  | 120000 |  | 45000 | [27 empty] | 60000 | [13 empty] | 15000 | [13 empty] | 0 | [13 empty] | 0 | 181324
Sub-TOTAL Component 2 |  |  |  | 1811324 |  | 230823.1053 | [27 empty] | 738132.4737 | [13 empty] | 690789 | [13 empty] | 75789.4737 | [13 empty] | 75789.4737 | 1811323.5263
Component 3 - Change Management & Training (US$3,212,000 million)
Communications Plan | # of Communication Plans by Lot | 1 | 500000 | 500000 | 1 | 125000 | Month #7: 125000 | [5 empty] | 125000 | [11 empty] | 1 | 125000 | 125000 | [11 empty] | 1 | 125000 | 125000 | [11 empty] | 1 | 125000 | [13 empty] | 0
Change Management Plan | # of Change Management Plan by Lot | 1 | 400000 | 400000 | 1 | 100000 | Month #5: 100000 | [5 empty] | 100000 | [11 empty] | 1 | 100000 | 100000 | [11 empty] | 1 | 100000 | 100000 | [11 empty] | 1 | 100000 | [13 empty] | 0
Technical Specialist Consultant - Change Management & Communications (60 months) | # of C | 1 | 300000 | 300000 | 1 | 65000 |  | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 1 | 60000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 1 | 60000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 1 | 60000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 |  |  | 55000
Subcomponent 3.1. Change Management and Communications |  |  | 1200000 | 1200000 |  | 290000 | [27 empty] | 285000 | [13 empty] | 285000 | [13 empty] | 285000 | [13 empty] | 55000 | 1200000
Assessment test and remedial training for new recruits | # of training instruments | 1 | 20000 | 20000 | 1 | 0 | [15 empty] | 20000 | [10 empty] | 1 | 20000 | [12 empty] | 1 | 0 | [12 empty] | 1 | 0
Assessment test and remedial training for existing members of the Force | # of training instruments | 1 | 120000 | 120000 | 1 | 0 | [14 empty] | 40000 | [11 empty] | 1 | 40000 | 40000 | [11 empty] | 1 | 40000 | 40000 | [11 empty] | 1 | 40000
Technical Specialist Consultant - Assessment Training (30 months) | # of consultants | 1 | 147000 | 147000 | 1 | 0 | [14 empty] | 49000 | [11 empty] | 1 | 49000 | 49000 | [11 empty] | 1 | 49000 | 49000 | [11 empty] | 1 | 49000
College hardware (laptops and desktops) | # of hardware by Lot | 1 | 95000 | 95000 | 1 | 0 | [14 empty] | 95000 | [11 empty] | 1 | 95000
VC equipment in divisional HQ, NPCJ, MNS and Commissioners Office | # of VC equipment by Lot | 1 | 50000 | 50000 | 1 | 0 | [14 empty] | 50000 | [11 empty] | 1 | 50000
Technical Specialist Consultant - NPCJ & VC Equipment (24 months) | # of consultants | 1 | 120000 | 120000 | 1 | 60000 | [12 empty] | 60000 | [11 empty] | 60000 |  | 1 | 60000
Review of curricula to include technology | # of training instruments | 1 | 180000 | 180000 | 1 | 120000 | Month #8: 60000 |  |  |  |  | 60000 | [5 empty] | 60000 | [6 empty] | 1 | 60000 | [12 empty] | 1 | 0 | [12 empty] | 1 | 0 | [13 empty] | 0
Training on use of digital registries and case management system for existing members of the Force | # of training instruments | 1 | 80000 | 80000 | 1 | 0 | [21 empty] | 40000 |  |  |  |  | 1 | 40000 | 40000 | [11 empty] | 1 | 40000 | [12 empty] | 1 | 0 | [13 empty] | 0
Data analytics training for MNS, JCF/CIB, JCF/CSRP | # of training instruments | 1 | 500000 | 500000 | 1 | 0 | [26 empty] | 1 | 0 |  |  |  | 166666.6667 | [8 empty] | 1 | 166666.6667 |  |  |  | 166666.6667 | [8 empty] | 1 | 166666.6667 |  |  |  | 166666.6667 | [9 empty] | 166666.6667
PICA training | # of training instruments | 1 | 200000 | 200000 | 1 | 0 | [16 empty] | 100000 |  |  |  | 100000 | [5 empty] | 1 | 200000 | [12 empty] | 1 | 0 | [12 empty] | 1 | 0 | [13 empty] | 0
Provide training on use of data for evidence-based policing strategies | # of training instrument | 1 | 90000 | 90000 | 1 | [20 empty] | 0 | [6 empty] | 0 | 0 | 90000 | [11 empty] | 0 | 90000
Training on new protocols for domestic violence for existing members of the Force | # of training instruments | 1 | 200000 | 200000 | 1 | 0 | [23 empty] | 100000 |  |  | 1 | 100000 |  | 100000 | [10 empty] | 1 | 100000 | [12 empty] | 1 | 0 | [13 empty] | 0
Technical Specialist TRAINING Consultant for Sub-component 3114 and provide management over all other training components (38 months) | # of consultants | 1 | 210000 | 210000 | 1 | 70000 | Month #5: 70000 | [6 empty] | 70000 | [10 empty] | 1 | 70000 | 70000 | [11 empty] | 1 | 70000 | [12 empty] | 1 | 0 | [13 empty] | 0
Subcomponent 3.2. Training in collaboration with the National Police College of Jamaica |  |  |  | 2012000 |  | 250000 | [27 empty] | 784000 | [13 empty] | 555666.6667 | [13 empty] | 255666.6667 | [13 empty] | 166666.6667 | 2012000
Sub-TOTAL Component 3 |  |  |  | 3212000 |  | 540000 | [27 empty] | 1069000 | [13 empty] | 840666.6667 | [13 empty] | 540666.6667 | [13 empty] | 221666.6667 | 3212000
Sub-Total (before PEU, Contingency & M&E) |  |  |  | 17200000 |  | 2860541.6233 | [27 empty] | 5088647.7884 | [13 empty] | 6104199.6667 | [13 empty] | 2512011.6959 | [13 empty] | 634598.9975 | 17199999.7718
Project Administration and Coordination
Project Execution Unit | # of offices | 1 | 207438 | 207438 | 1 | 207438 | Month #1: 207438 | [17 empty] | 1 | 0 | [12 empty] | 1 | 0 | [12 empty] | 1 | 0 | [12 empty] | 1 | 0
Programme Coordinator | # of individual consultants | 1 | 407751.938 | 407751.938 | 1 | 81550.3876 |  |  | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 1 | 81550.3876 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 1 | 81550.3876 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 1 | 81550.3876 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 6795.8656 | 1 | 81550.3876
Procurement Specialist - Manager | # of individual consultants | 1 | 276000 | 276000 | 1 | 55200 |  |  | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 1 | 55200 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 1 | 55200 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 1 | 55200 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 1 | 55200
Financial Specialist - Manager | # of individual consultants | 1 | 314700 | 314700 | 1 | 62940 |  |  | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 1 | 62940 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 1 | 62940 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 1 | 62940 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 5245 | 1 | 62940
Monitoring & Evaluation Specialist | # of individual consultants | 1 | 276000 | 276000 | 1 | 55200 |  |  | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 1 | 55200 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 1 | 55200 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 1 | 55200 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 1 | 55200
Administrative & Procurement Officer | # of individual consultants | 1 | 170000 | 170000 | 1 | 34000 |  |  | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 1 | 34000 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 1 | 34000 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 1 | 34000 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 1 | 34000
Finance & Logistics Officer | # of individual consultants | 1 | 170000 | 170000 | 1 | 34000 |  |  | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 1 | 34000 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 1 | 34000 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 1 | 34000 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 1 | 34000
Project Coordinator Assistant (PCA) & HR Liaison | # of individual consultants | 1 | 118110.2362 | 118110.2362 | 1 | 23622.0472 |  |  | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1 | 23622.0472 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1 | 23622.0472 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1 | 23622.0472 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1968.5039 | 1 | 23622.0472
Audit | # of individual consultants | 1 | 60000 | 60000 | 1 | 12000 | [9 empty] | 12000 | [11 empty] | 12000 |  |  |  |  | 1 | 12000 | [7 empty] | 12000 |  |  |  |  | 1 | 12000 | [7 empty] | 12000 |  |  |  |  | 1 | 12000 | [7 empty] | 12000 |  |  |  |  | 1 | 12000
Audits and M&E |  |  |  | 300000 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 150000 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Contingency |  |  |  | 500000 | 1 | 0
Sub-Total PEU, Contingency & M&E) |  |  |  | 2800000.1742 |  | 565950.4348 | 207438 |  | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 40876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 40876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 |  | 358512.4348 | 178876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 40876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 |  | 508512.4348 | 28876.0362 | 28876.0362 | 178876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 40876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 |  | 508512.4348 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 40876.0362 | 28876.0362 | 28876.0362 | 28876.0362 | 28876.0362 |  | 358512.4348
Total Overall Project including PEU, Contingency & M&E) | [5 empty] | 3426492.0582 | [27 empty] | 5447160.2232 | [13 empty] | 6612712.1015 | [13 empty] | 3020524.1307 | [13 empty] | 1493111.4323 | 19999999.946
Project Total |  |  |  | 20000000.1742 |  |  | Month #1: 207438; Month #2: 5000; Month #3: 33876.0362; Month #4: 33876.0362; Month #5: 445745.795
[7 empty] | Month #1: Retroactive Financing Period; Month #6: 50469.6035; Month #7: 175469.6035; Month #8: 140469.6035; Month #9: 50469.6035 | 318574.6035 | 682492.4321 | 55407.628 | 1071479.0566 | 148510.5527 | 1077446.0204 | 151479.0566 | 161479.0566 | 61479.0566
First 18 Months

## Procurement Plan
PROCUREMENT PLAN INITIAL LOAD INFORMATION (ONGOING AND/OR LAST PRESENTED)
SERVICES/GOODS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity output): | Process Number: | Amount in US$ : |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments
[6 empty] | Estimated Amount, in US$ : | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  | Specific Procurement notice | Contract Signature
Component 1. Violent crime prevention and management (US$12,176,676 million).
Subcomponent 1.1. Support for the implementation of problem-oriented policing for crime prevention, including hot-spot policing
MNS | Procure handheld devices for CIB investigators (x 1800) |  | ICB | LOT 1 |  | 1080000 |  |  | Component 1 | Ex-ante
MNS | Provide user training on use of equipment (application) |  | NCB | LOT 1 |  | 30140 |  |  | Component 1 | Ex-ante
MNS | Fleet management, GEONODE and Front End System Integration for Emergency Phone Calls |  | ICB | LOT 2 |  | 3000000 |  |  | Component 1 | Ex-ante
MNS | Surveillance equipment procured |  | ICB | LOT 3 |  | 1372922 |  |  | Component 1 | Ex-ante
MNS | DCS Surveillance equipment procured (Cameras - CCTV) |  | ICB | LOT 3 |  | 407000 |  |  | Component 1 | Ex-ante
MNS | Monitoring Center (1) |  | ICB | LOT 4 |  | 500000 |  |  | Component 1 | Ex-ante
MNS | Hardware, Software, Professional Services, Documentation and Configuration Services. |  | ICB | LOT 5 |  | 590600 |  |  | Component 1 | Ex-ante
MNS | Provide user training on use of equipment |  | NCB | LOT 3 |  | 45400 |  |  | Component 1 | Ex-ante
7026062
Subcomponent 1.2. Equip and connect police stations, prisons, and the National Police College of Jamaica
MNS | Connecting 45 (of 178) Police Stations (kma, 45, 11 prisons and parole offices, mobay) |  | ICB | LOT 1 |  | 2000000 |  |  | Component 1 | Ex-ante
MNS | 4G LTE CORE & Base Stations |  | ICB | LOT 2 |  | 600000 |  |  | Component 1 | Ex-ante
MNS | Building access (5 model location) |  | ICB | LOT 3 |  | 250000 |  |  | Component 1 | Ex-ante
MNS | (Prior options review for DCS) Prison model review |  | NCB | LOT 4 |  | 60000 |  |  | Component 1 | Ex-ante
MNS | Procure hardware (special monitors, printers, UPS, computers, digital signature pads, scanners), Maintenance, Support and Installation / Implementation, Configuration, among others) |  | ICB | LOT 5 |  | 1200000 |  |  | Component 1 | Ex-ante
4110000
Subcomponent 1.3. Share information with the public through open data
MNS | Open data initiative |  | ICB | LOT 1 |  | 336296 |  |  | Component 1 | Ex-ante
336296
Component 2 - Improving investigative capabilities for violent crimes (US$1,811,324 million).
Subcomponent 2.1. Increase the quality of casefiles
MNS | Procure e-case management system (automating manual processes and other functionalities to improve efficiency and accountability) |  | ICB | LOT 1 |  | 500000 |  |  | Component 2 | Ex-ante
MNS | Implement e-case management system |  | ICB | LOT 1 |  | 250000 |  |  | Component 2 | Ex-ante
MNS | Engraving machine for FLA |  | NCB | LOT 2 |  | 50000 |  |  | Component 2 | Ex-ante
MNS | Ballistic identifier |  | ICB | LOT 3 |  | 350000 |  |  | Component 2 | Ex-ante
1150000
Subcomponent 2.2. Design and implementation of digital registries
MNS | Design of digital registries |  | NCB | LOT 1 |  | 74981 |  |  | Component 2 | Ex-ante
MNS | Implement registries |  | NCB | LOT 1 |  | 29000 |  |  | Component 2 | Ex-ante
MNS | User training for digital registries |  | NCB | LOT 1 |  | 52343 |  |  | Component 2 | Ex-ante
MNS | Maintenance and Support (5 years) |  | NCB | LOT 1 |  | 25000 |  |  | Component 2 | Ex-ante
181324
Component 3 - Change Management & Training (US$3,212,000 million).
Subcomponent 3.1. Change Management and Communications
MNS | Communications Plan |  | ICB | LOT 1 |  | 500000 |  |  | Component 3 | Ex-ante
MNS | Change Management Plan |  | ICB | LOT 1 |  | 400000 |  |  | Component 3 | Ex-ante
900000
Subcomponent 3.2. Training in collaboration with the National Police College of Jamaica
MNS | Assessment test and remedial training for new recruits |  | NCB | LOT 1 |  | 20000 |  |  | Component 3 | Ex-ante
MNS | Assessment test and remedial training for existing members of the Force |  | NCB | LOT 1 |  | 120000 |  |  | Component 3 | Ex-ante
MNS | College hardware (laptops and desktops) |  | NCB | LOT 2 |  | 95000 |  |  | Component 3 | Ex-ante
MNS | VC equipment in divisional HQ, NPCJ, MNS and Commissioners Office |  | NCB | LOT 3 |  | 50000 |  |  | Component 3 | Ex-ante
MNS | Review of curricula to include technology |  | ICB | LOT 4 |  | 180000 |  |  | Component 3 | Ex-ante
MNS | Training on use of digital registries and case management system for existing members of the Force |  | NCB | LOT 5 |  | 80000 |  |  | Component 3 | Ex-ante
MNS | Data analytics training for MNS, JCF/CIB, JCF/CSRP |  | ICB | LOT 6 |  | 500000 |  |  | Component 3 | Ex-ante
MNS | PICA training |  | ICB | LOT 7 |  | 200000 |  |  | Component 3 | Ex-ante
MNS | Provide training on use of data for evidence-based policing strategies |  | NCB | LOT 8 |  | 90000 |  |  | Component 3 | Ex-ante
MNS | Training on new protocols for domestic violence for existing members of the Force |  | ICB | LOT 9 |  | 200000 |  |  | Component 3 | Ex-ante
1535000
GRAND TOTAL | [5 empty] | 15238682
INDIVIDUAL CONSULTANTS/STAFF
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity output): | Amount in US$ : |  |  | Estimated Number of Consultants: | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments
[5 empty] | Estimated Amount, in US$: | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  |  | No Objection to TOR's | Contract Signature
Component 1.
Subcomponent 1.1. Support for the implementation of problem-oriented policing for crime prevention, including hot-spot policing
MNS | Technical Specialist Consultant - Georeferencing (24 months) |  | SL | LOT 1 |  | 120000 |  |  | Component 1 | Ex-ante
MNS | Technical Specialist Consultant - Fleet Management (28 months) |  | SL | LOT 2 |  | 170000 |  |  | Component 1 | Ex-ante
MNS | Technical Specialist Consultant - Surveillance (28 months) |  | SL | LOT 3 |  | 170000 |  |  | Component 1 | Ex-ante
Subcomponent 1.2. Equip and connect police stations, prisons, and the National Police College of Jamaica
MNS | Technical Specialist Consultant - Connectivity (36 months) |  | SL | LOT 1 |  | 190000 |  |  | Component 1 | Ex-ante
Subcomponent 1.3. Share information with the public through open data
MNS | Technical Specialist Consultant - Open Data Initiative (11 months) |  | SL | LOT 1 |  | 54318 |  |  | Component 1 | Ex-ante
Component 2.
Subcomponent 2.1. Increase the quality of casefiles
MNS | Technical Specialist Consultant - Case Management & Digital Registries (60 months) |  | ISL | LOT 1 |  | 360000 |  |  | Component 2 | Ex-ante
Subcomponent 2.3. Design and implement a data sharing exchange protocol
MNS | Technical Specialist Consultant - Data Sharing (24 months) |  | SL | LOT 1 |  | 120000 |  |  | Component 2 | Ex-ante
Component 3 - Change Management & Training (US$3,212,000 million).
Subcomponent 3.1. Change Management and Communications
MNS | Technical Specialist Consultant - Change Management & Communications (60 months) |  | ISL | LOT 1 |  | 300000 |  | 1 | Component 3 | Ex-ante
Subcomponent 3.2. Training in collaboration with the National Police College of Jamaica
MNS | Technical Specialist Consultant - Assessment Training (30 months) |  | SL | LOT 1 |  | 147000 |  |  | Component 3 | Ex-ante
MNS | Technical Specialist Consultant - NPCJ & VC Equipment (24 months) |  | SL | LOT 3 |  | 120000 |  |  | Component 3 | Ex-ante
MNS | Technical Specialist TRAINING Consultant for Sub-component 3114 and provide management over all other training components (38 months) |  | SL | LOT 5 |  | 210000 |  |  | Component 3 | Ex-ante
TOTAL | [5 empty] | 1961318
SERVICES/GOODS/INDIVIDUAL CONSULTANTS/STAFF FOR 1) MONITORING AND EVALUATION; 2)TECHNICAL ADVISORY TEAM; and 3) PROGRAM MANAGEMENT
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity output): | Amount in US$ : |  |  | Estimated Number of Consultants: | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments
[5 empty] | Estimated Amount, in US$: | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  |  | No Objection to TOR's | Contract Signature
Monitoring and Evaluation
MNS | Audits and M&E |  | ISL | LOT 1 |  | 300000 |  |  | M&E | Ex-ante
SUB-TOTAL | [5 empty] | 300000
Programme Management
MNS | Project Execution Unit |  | ISL | N/A |  | 207438 |  |  | Programme Management | Ex-ante
MNS | Project Director |  | ISL | N/A |  | 407751.938 |  |  | Programme Management | Ex-ante
MNS | Procurement Specialist - Manager |  | ISL | N/A |  | 276000 |  |  | Programme Management | Ex-ante
MNS | Financial Specialist - Manager |  | ISL | N/A |  | 314700 |  |  | Programme Management | Ex-ante
MNS | Monitoring & Evaluation Specialist |  | ISL | N/A |  | 276000 |  |  | Programme Management | Ex-ante
MNS | Administrative & Procurement Officer |  | SL | N/A |  | 170000 |  |  | Programme Management | Ex-ante
MNS | Finance & Logistics Officer |  | SL | N/A |  | 170000 |  |  | Programme Management | Ex-ante
MNS | Project Coordinator Assistant (PCA) & HR Liaison |  | SL | N/A |  | 118110.2362 |  |  | Programme Management | Ex-ante
MNS | Audit |  | SL | N/A |  | 60000 |  |  | Programme Management | Ex-ante
TOTAL | [5 empty] | 2000000.1742
| Contingency |  |  |  |  | 500000
| ICB | International competitive bidding
| NCB | National Competitive Bidding
| SL | Short list consulting services
| ISL | International Short List consulting services

## Procurement Plan - intro
SECURITY STRENGTHENING PROJECT (SSP)
JAMAICA (JA-L1074)
1. Procurement Plan Coverage
Data | From | Until
Procurement Plan Coverage: | Q1 2018 | At the end of Programme Execution 2022
2. Procurement Plan Details
Version (08-2017)
3. Amounts by Investment Category
Investment Category | Amount Financed by the Bank | Total Amount (Including counterpart)
Individual Consultants | 1961318 | 0
Consulting Firms |  | 0
Goods/Works | 15238682 | 0
Services/Goods/Individual Consultants/staff for 1)M&E; 2)Technical Advisory Team; and 3) Program Management | 2800000.1742 | 0
Total | 20000000.1742 | 0
4. Components
Project Components | Amount Financed by the Bank | Total Amount (Including counterpart)
COMPONENT 1: Violent crime prevention and management | 12176676 | 0
COMPONENT 2 - Improving investigative capabilities for violent crimes | 1811324 | 0
COMPONENT 3: Change Management & Training | 3212000
Monitoring and Evaluation | 300000 | 0
Programme Management | 2000000.1742 | 0
Contingency | 500000 | 0
Total | 20000000.1742 | 0