|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Component and sub-component** | **Risk or Opportunity** | **Mitigation Activities** | **Indicators related with the Result matrix** | **Estimated start date** | **Responsible Party** | **Related component of the mitigation activity** | **Procurement type** | **Assigned budget** |
| **Component 1. Violent crime prevention and management** | | | | | | | | |
| 1. Support the creation of location-based crime prevention strategies, including hot-spot policing. 2. Shared information with the public through open data | Based on the country's cultural nuances, low trust in Police and potential misuse of information by government officials, there may be resistance from the public to the Program | Protocols for information release including classification of all existing crime information and publication online of relevant statistics in a timely manner.  Privacy and confidentiality principles will be included to facilitate a comprehensive use and disclosure of crime-related information. | #of databases opened to public access | Year 3 | MNS | As part of the Component 1, sub-component 1.3 | TBD | US$390,000 |
| Design and implement of a communication strategy to create awareness about the changes in processes | # of change management and communication plan | Year 1 | MNS | As part of the Component 3, sub-component 3.1 | TBD | $1,160,000 |
| Support a Grievance Redress Mechanism | # of Grievances Redness Mechanisms | Year 1 | MNS | As part of the Component 3, sub-component 3.1 | TBD | US$40,000 |
| **Component 2. Improving investigative capabilities for violent crime** | | | | | | |  |  |
| 1. Increase the quality of casefiles | Opportunity to gather better information for detecting domestic violence patterns | Training activities on how to handle victims of domestic violence with a human rights approach | # of trainings on domestic violence protocol, including gender and human rights approach | Year 2 | MNS | As part of the Component 3, sub-component 3.2 | TBD[[1]](#footnote-1) | $410,000 |
| Protocol on how to handle domestic violence with a human rights approach and on how to use the technology to properly manage domestic violence records |

1. The collaboration of the Institute for Gender and Development Studies of the University of the West Indies is being evaluated to support this activity [↑](#footnote-ref-1)