## Procurement Plan
SECTION 3
PROCUREMENT PLAN
FROM ________ October 2017 to __________ December 2018
Ref. No. 1 | Reference to SEPA code | Comp. No. | Description of and Component of procurement contract | Indicative cost (USD) | Procurement Selection method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Prequalification 3 (YES/NO) | Estimated Dates |  | Actual dates |  | Status 4 (pending; in process; awarded; cancelled) | Comments
[7 empty] | IDB % | Local/Other % |  | Publication of specific procurement notice | Completion of Contract | Publication of specific procurement notice | Completion of Contract
1 |  |  | GOODS
G01/C2.00-01 |  | 02.00 | Weather Stations | 190000 | DC | ex-ante | 100 | 0 | NO | 2018-03-01 | 2018-11-01 |  |  | PENDING
stations to be purchased and installed in regions producing and reporting on climate data
G19/C2.00-02 |  | 02.00 | Redundant Storage for Regional Climate Data | 95000 | ICB | ex-ante | 100 | 0 | NO | 2018-05-01 | 2018-11-01 |  |  | PENDING | NEW ENTRY
G04/C3.00-03 |  | 03.00 | Hardware for ICZM Database | 135000 | ICB | ex-ante | 100 | 0 | NO | 2018-06-01 | 2018-12-01 |  |  | PENDING
to enhance CSGs capacity to do coastal zone climate Modelling and data Maps including GIS Mapping
G11/C6.00-04 |  | 06.00 | Office Stationery & Supplies | 5000 | PC | ex-post | 100 | 0 | NO | 2017-11-01 | 2018-12-01 |  |  | IN PROCESS
stationery and supplies needed for PMO operations
G16/C4.03-03 |  | 04.03 | Seed Bank Equipment & Standby Energy System | 47000 | PC | ex-ante | 100 | 0 | NO | 2018-03-01 | 2018-08-01 |  |  | PENDING | NEW ENTRY
G17/C4.03-04 |  | 04.03 | Seed Batch Dryers x5 | 60000 | PC | ex-ante | 100 | 0 | NO | 2018-03-01 | 2018-08-01 |  |  | PENDING | NEW ENTRY
G18/C4.03-05 |  | 04.03 | Gene Bank Equipment | 70000 | PC | ex-ante | 100 | 0 | NO | 2018-05-01 | 2018-12-01 |  |  | PENDING | NEW ENTRY
2 |  |  | WORKS
W02/C4.03-01 |  | 04.03 | Agriculture Infrastructure Upgrade: Seed Bank | 36000 | PC | ex-ante | 100 | 0 | NO | 2018-03-01 | 2019-09-01 |  |  | PENDING | "Refurbishment or construction of: (b) a gene bank in a PPCR country" removed from description and added as a new procurement entry
Refurbishment or construction of: (a) 1000 sq ft of seed bank/storage facility in PPCR countries;
W07/C4.03-06 |  | 04.03 | Agriculture Infrastructure Upgrade: Gene Bank & Weaning and Harding facilities in 4 PPCR countries | 76000 | PC | ex-ante | 100 | 0 | NO | 2018-05-01 | 2019-09-01 |  |  | PENDING | NEW ENTRY
Refurbishment or construction of: (b) a gene bank in a PPCR country
3 |  |  | Non-consulting services
NCS43/C2.00-5 |  | 02.00 | Installation of 24 Weather Stations | 24750 |  | ex post | 100 | 0 |  | 2018-08-01 | 2018-11-01 |  |  | PENDING | NEW ENTRY
|  |  | airfare | 13500 | DC | EX POST | 100 | 0 | NO | 2018-08-01 | 2018-11-01 |  |  | PENDING
|  |  | accomodation | 11250 | PC | EX POST | 100 | 0 | NO | 2018-08-01 | 2018-11-01 |  |  | PENDING
NCS44/C2.00-6 |  | 02.00 | Climate Products and Services Workshop #1 | 24000 |  | ex post | 100 | 0 |  | 2018-05-01 | 2018-05-01 |  |  | PENDING | NEW ENTRY
|  |  | airfare | 10000 | DC | EX POST | 100 | 0 | NO | 2018-05-01 | 2018-05-01 |  |  | PENDING
|  |  | accomodation | 9750 | PC | EX POST | 100 | 0 | NO | 2018-05-01 | 2018-05-01 |  |  | PENDING
|  |  | venue | 2000 | PC | EX POST | 100 | 0 | NO | 2018-05-01 | 2018-05-01 |  |  | PENDING
|  |  | catering | 2250 | PC | EX POST | 100 | 0 | NO | 2018-05-01 | 2018-05-01 |  |  | PENDING
NCS45/C2.00-7 |  | 02.00 | Climate Products and Service Workshop #2 | 24000 |  | ex post | 100 | 0 |  | 2018-06-01 | 2018-06-01 |  |  | PENDING | NEW ENTRY
|  |  | airfare | 10000 | DC | EX POST | 100 | 0 | NO | 2018-06-01 | 2018-06-01 |  |  | PENDING
|  |  | accomodation | 9750 | PC | EX POST | 100 | 0 | NO | 2018-06-01 | 2018-06-01 |  |  | PENDING
|  |  | venue | 2000 | PC | EX POST | 100 | 0 | NO | 2018-06-01 | 2018-06-01 |  |  | PENDING
|  |  | catering | 2250 | PC | EX POST | 100 | 0 | NO | 2018-06-01 | 2018-06-01 |  |  | PENDING
NCS39/C2.00-3 |  | 02.00 | Capacity Building/ Training for Meteorological Offices #3 | 4000 |  | EX POST | 100 | 0 | NO | 2018-01-01 | 2018-02-01 |  |  | IN PROCESS | NEW ENTRY No-objection granted
|  |  | airfare x4 | 4000 | DC | EX POST | 100 | 0 | NO | 2018-01-01 | 2018-01-01 |  |  | PENDING
NCS42/C2.00-4 |  | 02.00 | Capacity Building/ Training for Meteorological Offices #4 | 4000 |  | EX POST | 100 | 0 | NO | 2018-01-01 | 2018-02-01 |  |  | PENDING | NEW ENTRY
|  |  | airfare x4 | 4000 | DC | EX POST | 100 | 0 | NO | 2018-08-01 | 2018-08-01 |  |  | PENDING
NCS40/C4.05-1 |  | 04.05 | CCORAL Training Event for 25 Decision Makers in each PPCR Country | 57500 | [10 empty] | NEW ENTRY
|  |  | airfare x25 | 25000 | DC | EX POST | 100 | 0 | NO | 2018-04-01 | 2018-05-01 |  |  | PENDING
|  |  | accomodation x125 nights | 18750 | PC | EX POST | 100 | 0 | NO | 2018-04-01 | 2018-05-01 |  |  | PENDING
|  |  | venue | 5000 | PC | EX POST | 100 | 0 | NO | 2018-04-01 | 2018-05-01 |  |  | PENDING
|  |  | catering | 6250 | PC | EX POST | 100 | 0 | NO | 2018-04-01 | 2018-05-01 |  |  | PENDING
|  |  | ground transportation | 2500 | DC | EX POST | 100 | 0 | NO | 2018-04-01 | 2018-05-01 |  |  | PENDING
NCS44/C4.05-1 |  | 04.05 | Meeting on Housing of C1 Data and CCORAL Training | 4000 |  | ex post | 100 | 0 |  | 2018-02-01 | 2018-12-01 |  |  | PENDING | NEW ENTRY
|  |  | airfare | 2000 | DC | EX POST | 100 | 0 | NO | 2018-02-01 | 2018-12-01 |  |  | PENDING
|  |  | accomodation | 2000 | PC | EX POST | 100 | 0 | NO | 2018-02-01 | 2018-12-01 |  |  | PENDING
NCS45/C6.00-12 |  | 06.00 | PMU Program Inspection and Coordination Visits | 20000 |  | ex post | 100 | 0 |  | 2018-02-01 | 2018-12-01 |  |  | PENDING | NEW ENTRY
|  |  | airfare | 10000 | DC | EX POST | 100 | 0 | NO | 2018-02-01 | 2018-12-01 |  |  | PENDING
|  |  | accomodation | 10000 | PC | EX POST | 100 | 0 | NO | 2018-02-01 | 2018-12-01 |  |  | PENDING
NCS24/C5.00-02 |  | 05.00 | Regional Media Workshop | 18000 | PC | EX POST | 100 | 0 | NO | 2018-07-01 | 2018-09-01 |  |  | PENDING | review status changed to EX POST
|  |  | airfare | 9000 | DC | EX POST | 100 | 0 | NO | 2018-07-01 | 2018-09-01 |  |  | Pending
|  |  | accomodation | 4000 | PC | EX POST | 100 | 0 | NO | 2018-07-01 | 2018-09-01 |  |  | Pending
|  |  | venue | 2000 | PC | EX POST | 100 | 0 | NO | 2018-07-01 | 2018-09-01 |  |  | Pending
|  |  | catering | 2000 | PC | EX POST | 100 | 0 | NO | 2018-07-01 | 2018-09-01 |  |  | Pending
|  |  | ground transportation | 1000 | DC | EX POST | 100 | 0 | NO | 2018-07-01 | 2018-09-01 |  |  | Pending
NCS35/C4.03-5 |  | 04.03 | Agricultural Modelling Training | 27750 | [10 empty] | approved under previous caption "Knowledge Transfer of DSSAT Software"
|  |  | airfare x12 | 12000 | DC | EX POST | 100 | 0 | NO | 2018-02-01 | 2018-03-01 |  |  | Pending
|  |  | accomodation x 60 nights | 10500 | PC | EX POST | 100 | 0 | NO | 2018-02-01 | 2018-03-01 |  |  | Pending
|  |  | ground transportation | 1200 | DC | EX POST | 100 | 0 | NO | 2018-02-01 | 2018-03-01 |  |  | Pending
|  |  | catering | 3750 | PC | EX POST | 100 | 0 | NO | 2018-02-01 | 2018-03-01 |  |  | Pending
|  |  | stationery & workshop supplies | 300 | PC | EX POST | 100 | 0 | NO | 2018-02-01 | 2018-03-01 |  |  | Pending
NCS32/C5.00-09 |  | 05.00 | Graphic Designing & print of standardized communication materials | 2500 | PC | EX POST | 100 | 0 | NO | 2018-01-01 | 2018-03-01 |  |  | PENDING
professional design and printing of project brochure, five fact sheets and business cards
NCS33/C5.00-10 |  | 05.00 | Printing of Other Communications Materials | 3500 | PC | EX POST | 100 | 0 | NO | 2018-04-01 | 2018-09-01 |  |  | PENDING
for the execution of the communications strategy
NCS34/C5.00-11 |  | 05.00 | Digital Professional Camera and accessories | 1000 | PC | EX POST | 100 | 0 | NO | 2018-02-01 | 2018-04-01 |  |  | PENDING
NCS27/C5.00-5 |  | 05.00 | Launch Events | 7200 | PC | EX POST | 100 | 0 | NO | 2018-04-01 | 2018-12-01 |  |  | PENDING
|  |  | venue rental | 4000 | PC | ex post | 100 | 0 | NO | 2018-04-01 | 2018-12-01 |  |  | PENDING
|  |  | catering | 1200 | PC | ex post | 100 | 0 | NO | 2018-04-01 | 2018-12-01 |  |  | PENDING
|  |  | décor | 1000 | PC | ex post | 100 | 0 | NO | 2018-04-01 | 2018-12-01 |  |  | PENDING
|  |  | video-/photography | 1000 | PC | ex post | 100 | 0 | NO | 2018-04-01 | 2018-12-01 |  |  | PENDING
NCS28/C5.00-6 |  | 05.00 | Lessons Learnt Sessions | 9000 | PC | EX POST | 100 | 0 | NO | 2018-04-01 | 2018-12-01 |  |  | PENDING
dissemination of knowledge products across Components
NCS29/C5.00-7 |  | 05.00 | Stakeholder Engagement Workshops | 12000 | PC | EX POST | 100 | 0 | NO | 2018-02-01 | 2018-12-01 |  |  | PENDING
Engagement workshops for EWERS, ICZM, CCORAL
NCS41/C7.00-3 |  | 07.00 | Steering Committee Meeting 2018 | 26725 | [10 empty] | NEW ENTRY
|  |  | airfare x 15 | 15000 | DC | EX POST | 100 | 0 | NO | 2018-11-01 | 2018-12-01 |  |  | PENDING
|  |  | accomodation x 45 nights | 6975 | PC | EX POST | 100 | 0 | NO | 2018-11-01 | 2018-12-01 |  |  | PENDING
|  |  | venue | 1000 | PC | EX POST | 100 | 0 | NO | 2018-11-01 | 2018-12-01 |  |  | PENDING
|  |  | catering | 1500 | PC | EX POST | 100 | 0 | NO | 2018-11-01 | 2018-12-01 |  |  | PENDING
|  |  | ground transportation | 2250 | DC | EX POST | 100 | 0 | NO | 2018-11-01 | 2018-12-01 |  |  | PENDING
NCS12/C7.00-2 |  | 07.00 | Technical Advisory Meeting (face-2-face) | 10000
|  |  | airfare | 6000 | DC | EX POST | 100 | 0 | NO | 2018-12-01 | 2018-12-01 |  |  | PENDING
|  |  | accomodation | 2100 | PC | EX POST | 100 | 0 | NO | 2018-12-01 | 2018-12-01 |  |  | PENDING
|  |  | venue | 1000 | PC | EX POST | 100 | 0 | NO | 2018-12-01 | 2018-12-01 |  |  | PENDING
|  |  | catering | 300 | PC | EX POST | 100 | 0 | NO | 2018-12-01 | 2018-12-01 |  |  | PENDING
|  |  | ground transportation | 600 | DC | EX POST | 100 | 0 | NO | 2018-12-01 | 2018-12-01 |  |  | PENDING
NCS30/C3.00-7 |  | 03.00 | Climate Modellers' Workshop #2 | 30000
|  |  | airfare | 13500 | DC | EX POST | 100 | 0 | NO | 2018-07-01 | 2018-08-01 |  |  | PENDING
|  |  | accomodation | 11250 | PC | EX POST | 100 | 0 | NO | 2018-07-01 | 2018-08-01 |  |  | PENDING
|  |  | venue | 1500 | PC | EX POST | 100 | 0 | NO | 2018-07-01 | 2018-08-01 |  |  | PENDING
|  |  | catering | 2250 | PC | EX POST | 100 | 0 | NO | 2018-07-01 | 2018-08-01 |  |  | PENDING
|  |  | ground transportation | 1500 | DC | EX POST | 100 | 0 | NO | 2018-07-01 | 2018-08-01 |  |  | PENDING
NCS46/C4.04-1 |  | 04.04 | ICT EWERS Workshops x4 | 21000 | [10 empty] | NEW ENTRY
|  |  | airfare | 8000 | DC | EX POST | 100 | 0 | NO | 2018-05-01 | 2018-05-01 |  |  | PENDING
|  |  | accomodation | 12000 | PC | EX POST | 100 | 0 | NO | 2018-05-01 | 2018-05-01 |  |  | PENDING
|  |  | ground transportation | 1000 | DC | EX POST | 100 | 0 | NO | 2018-05-01 | 2018-05-01 |  |  | PENDING
NCS47/C4.04-2 |  | 04.04 | Fish Impact Assmnt & Monitoring System Workshops x2 | 31500 | [10 empty] | NEW ENTRY
|  |  | airfare x10participants x2 trips | 14000 | DC | EX POST | 100 | 0 | NO | 2018-05-01 | 2019-12-01 |  |  | PENDING
|  |  | accomodation x10 participants x11 nights | 16500 | DC | EX POST | 100 | 0 | NO | 2018-05-01 | 2019-12-01 |  |  | PENDING
|  |  | ground transportation | 1000 | DC | EX POST | 100 | 0 | NO | 2018-05-01 | 2019-12-01 |  |  | PENDING
NCS36/C3.00-8 |  | 03.00 | ICZM Workshop | 22200 | [10 empty] | NEW ENTRY
|  |  | airfare x12 | 12000 | DC | EX POST | 100 | 0 | NO | 2018-06-01 | 2018-06-01 |  |  | PENDING
|  |  | accomodation x60 nights | 9000 | PC | EX POST | 100 | 0 | NO | 2018-06-01 | 2018-06-01 |  |  | PENDING
|  |  | ground transportation x12 | 1200 | DC | EX POST | 100 | 0 | NO | 2018-06-01 | 2018-06-01 |  |  | PENDING
4 |  |  | CONSULTING SERVICES
CF30/C6.00-7 |  | 06.00 | Events Planning Coordinator | 30000 | QCII | EX ANTE | 100 | 0 | NO | 2018-02-01 | 2020-12-01 |  |  | PENDING | NEW ENTRY
IC26/C3.03-04 |  | 04.03 | Molecular Characterisation of Climate Resilient Crops | 25000 | QCII | ex-ante | 100 | 0 | NO | 2018-04-01 | 2018-12-01 |  |  | PENDING | NEW ENTRY
IC25/C8.00-1 |  | 08.00 | Mid-Term Evaluation | 30000 | QCII | ex-ante | 100 | 0 | NO | 2018-02-01 | 2018-05-01 |  |  | PENDING | NEW ENTRY
IC19/C3.00-3 |  | 03.00 | Climate Data Analyst #1 year 2 | 12000 | QCII | EX-POST | 100 | 0 | NO | 2017-12-01 | 2019-01-01 |  |  | IN PROCESS | Contract renewal
Data Analaysts to provide support to the provision of subsets of climate model data for sector related analyses
IC21/C3.00-4 |  | 03.00 | Climate Data Analyst #2 year 2 | 12000 | QCII | EX-POST | 100 | 0 | NO | 2017-12-01 | 2019-01-01 |  |  | IN PROCESS | Contract renewal
Data Analaysts to provide support to the provision of subsets of climate model data for sector related analyses
IC11/C3.00-1 |  | 03.00 | Climate Modeling Research Analysts #1 (HPCS) year 3 | 25000 | QCII | EX-POST | 100 | 0 | NO | 2018-06-01 | 2019-07-01 |  |  | PENDING | Contract renewal
Research Analysts are needed to oversee the transfer of existing data and add new modeling outputs to the HPCS and analyze four focal areas of climate
IC18/C3.00-2 |  | 03.00 | Climate Modeling Research Analysts #2 (Agriculture) year 2 | 25000 | QCII | EX-POST | 100 | 0 | NO | 2018-04-01 | 2019-05-01 |  |  | PENDING | Contract renewal
Research Analysts are needed to oversee the transfer of existing data and add new modeling outputs to the HPCS and analyze four focal areas of climate
CF02/C1.00-2 |  | 01.00 | LIDAR (Topography & Bathymetry) Data Collection and Processing | 2180000 | QCBS | ex-ante | 100 | 0 | NO | 2018-01-01 | 2019-09-01 |  |  | PENDING
this consultancy will: 1) undertake data collection, topographic and bathymetric surveys across PPCR countries and the processing of that data into specific geospatial outputs - High Resolution Maps and Digital Terrain Models and; (2) capacity building sessions for land use and coastal zone planners on the use of geospatial outputs.
IC23/C2.00-1 |  | 02.00 | Assistant Climatologist | 60000 | QCII | ex-ante | 100 | 0 | NO | 2017-10-01 | 2019-11-01 | 2017-10-01 |  | IN PROCESS | Procurement process to be restarted as top ranked consultant is not from IDB member country.
IC24/C2.00-2 |  | 02.00 | Sector Climate Products Development Specialist | 60000 | QCII | ex-ante | 100 | 0 | NO | 2018-01-01 | 2018-02-01 |  |  | IN PROCESS
CF26/C4.05-1 |  | 04.05 | CCORAL Training Consultancy | 70000 | CQS | ex-ante | 100 | 0 | NO | 2018-02-01 | 2018-05-01 |  |  | PENDING
IC13/C7.00-5 |  | 07.00 | Project Coordination CRFM | 24500 | QCII | ex-ante | 100 | 0 | NO | 2018-02-01 | 2020-12-01 |  |  | PENDING
to assist with project implementation for C4.02-CRFM
IC09/C7.00-1 |  | 07.00 | Project Coordination CARDI | 24500 | QCII | ex-ante | 100 | 0 | NO | 2018-02-01 | 2019-04-01 |  |  | PENDING
to assist with project implementation for C4.03-CARDI. Link with W02/C4.03-01
CF09/C4.01-1 |  | 04.01 | Health Audit Tool | 57300 | CQS | ex-ante | 100 | 0 | NO | 2018-02-01 | 2018-11-01 |  |  | IN PROCESS
The consultant will: (1) Conduct a regional audit of available climate and disease data for regional health institutions, such as CARPHA; (2) Prepare an audit report of climate and disease data available for regional health institutions.
CF11/C4.01-2 |  | 04.01 | Dengue/ChikV & Gender Dynamics Study | 148200 | QBS | ex-ante | 100 | 0 | NO | 2018-02-01 | 2019-03-01 |  |  | IN PROCESS
Consultancy to (1) conduct a survey of the social, epidemiological and clinical role of gender in the spread or control of dengue/Chikunguna V fever within 3 PPCR countries; (2) Prepare dengue/ChikV and gender dynamics report
CF29/C4.01-4 |  | 04.01 | Risk Assessment Study | 42000 | QBS | ex-ante | 100 | 0 | NO | 2018-02-01 | 2018-08-01 |  |  | PENDING | NEW ENTRY
to develop statistical risk assessment models for Jamaica, Saint Lucia and Haiti
CF12/C4.01-3 |  | 04.01 | Integrated Surveillance and Dengue Control System | 410500 | QCBS | ex-ante | 100 | 0 | NO | 2018-11-01 |  |  |  | PENDING
Consultancy to (1) conduct a review of the current knowledge on dengue/ChikV infectivity and surveillance and control systems and prepare dengue/ChikV infectivity, surveillance and control systems report; and (2) develop, implement and test an Integrated Surveillance and Dengue/ChikV Control System (ISDCS) in three (3) PPCR countries;
CF18/C4.04-1 |  | 04.04 | Rain Water Harvesting (RWH) Enhancement Consultancy | 100000 | QCBS | ex-ante | 100 | 0 | NO | 2018-08-01 | 2019-08-01 |  |  | PENDING
coordinate with CARPHA to recruit firm to undertake the enhancement of RWH enabling environment (policy and capacity building) and their implementation in 3 water stressed communities in the Caribbean
CF25/C4.04-2 |  | 04.04 | Rain Water Harvesting Assessment, Mapping & Manual Development and Training | 200000 | QBS | ex-ante | 100 | 0 | NO | 2017-08-01 | 2018-11-01 | 2017-08-01 |  | IN PROCESS
IC03/C6.00-1 |  | 06.00 | Program Manager 2019 | 50000 | QCII | EX POST | 100 | 0 | NO | 2018-09-01 | 2019-11-01 |  |  | PENDING
IC04/C6.00-2 |  | 06.00 | Procurement Specialist 2019 | 35000 | QCII | EX POST | 100 | 0 | NO | 2018-09-01 | 2019-11-01 |  |  | PENDING
IC06/C6.00-4 |  | 06.00 | Administrative Assistant 2019 | 25000 | QCII | EX POST | 100 | 0 | NO | 2018-09-01 | 2019-11-01 |  |  | PENDING
IC07/C6.00-5 |  | 06.00 | Communications Consultant (part-time) 2019 | 12500 | QCII | EX POST | 100 | 0 | NO | 2018-08-01 | 2019-07-01 |  |  | PENDING
IC08/C6.00-6 |  | 06.00 | Finance & Accounts Officer (part-time) 2019 | 15000 | QCII | EX POST | 100 | 0 | NO | 2018-09-01 | 2019-11-01 |  |  | PENDING
AWARDED PROCUREMENTS
CF13/C4.02-1 |  | 04.02 | Conduct of Fishery-related Ecological and Socio-economic Impact Assessments and Development of an Associated Monitoring System | 499945.24 | QCBS | ex-ante | 100 | 0 | NO | 2017-02-01 | 2019-05-01 | 2017-03-01 |  | AWARDED
coordinate with CRFM to recruit a firm to conduct ecological and socio-economic assessments of the impacts of climate change/variability on fisheries in three ecosystems (reef, pelagic and continental shelf).
CF21/C9.00-2 |  | 09.00 | Annual & Final Financial Audits | 48000 | LCS | ex-ante | 100 | 0 | NO | 2017-09-01 | 2020-12-01 | 2017-10-01 | 2020-12-01 | AWARDED | Description changed based on advice from IDB FMP to contract the audit firm for 4 years
CF01/C1.00-1 |  | 01.00 | Topographic and Bathymetric Survey Consultancy phase 1 | 84000 | CQS | ex-ante | 100 | 0 | NO | 2016-09-01 | 2017-07-01 | 2016-09-01 | 2019-04-01 | AWARDED
scoping assessment in 4 PPCR countries, development of TOR for acquisition of LIDAR services and monitoring of LIDAR Survey consultancy execution
IC17/C3.00-1 |  | 03.00 | Climate Modeling Research Analysts #1 year 2 | 25000 | QCII | ex-ante | 100 | 0 | NO | 2017-07-01 | 2018-07-01 | 2017-06-01 | 2018-07-01 | AWARDED
Research Analysts are needed to oversee the transfer of existing data and add new modeling outputs to the HPCS and analyze four focal areas of climate
CF07/C3.00-4 |  | 03.00 | ICZM Needs Analysis | 84000 | FBS | ex-ante | 100 | 0 | NO | 2017-01-01 | 2018-05-01 | 2017-02-01 | 2018-02-01 | AWARDED
Consultancy to determine the Functional Requirements & Specifications for Data, Hardware, Software, Procedures and Personnel Roles will be detailed, followed by a Sustainability and Operations Plan for the ICZM system
IC03/C6.00-1 |  | 06.00 | Program Manager 2018 | 50000 | QCII | EX POST | 100 | 0 | NO | 2017-09-01 | 2018-11-01 | 2017-10-01 | 2018-11-01 | AWARDED
IC04/C6.00-2 |  | 06.00 | Procurement Specialist 2018 | 35000 | QCII | EX POST | 100 | 0 | NO | 2017-09-01 | 2018-11-01 | 2017-10-01 | 2018-11-01 | AWARDED
IC06/C6.00-4 |  | 06.00 | Administrative Assistant 2018 | 25000 | QCII | EX POST | 100 | 0 | NO | 2017-09-01 | 2018-11-01 | 2017-10-01 | 2018-11-01 | AWARDED
IC08/C6.00-6 |  | 06.00 | Finance & Accounts Officer (part-time) 2018 | 15000 | QCII | EX POST | 100 | 0 | NO | 2017-09-01 | 2018-11-01 | 2017-10-01 | 2018-11-01 | AWARDED
IC07/C6.00-5 |  | 06.00 | Communications Consultant (part-time) 2018 | 12500 | QCII | EX POST | 100 | 0 | NO | 2017-08-01 | 2018-07-01 | 2017-08-01 | 2018-07-01 | AWARDED
NCS31/C5.00-08 |  | 05.00 | Program Website | 10000 | PC | ex ante | 100 | 0 | NO | 2017-05-01 | 2020-12-01 | 2017-04-01 |  | AWARDED
develop and host program website
G14/C4.03-02 |  | 04.03 | Data Input Computers | 5704.4 | DC | ex-ante | 100 | 0 | NO | 2017-07-01 | 2017-09-01 | 2017-07-01 | 2017-09-01 | AWARDED
to handle agriculture specific climate data input and transfer
NCS01/C6.00-2 |  | 06.00 | Office Lease | 18000 | DC | ex-ante | 100 | 0 | NO | 2016-04-01 | 2020-12-01 | 2016-04-01 | 2020-12-01 | AWARDED
NCS05/C6.00-5 |  | 06.00 | Online Meeting Space | 32 | PC | ex-ante | 100 | 0 | NO | 2016-04-01 | 2020-12-01 | 2016-04-01 | 2017-09-01 | AWARDED
NCS01/C6.00-03 |  | 06.00 | Courier Service | 2000 | DC | ex-ante | 100 | 0 | NO | n/a | 2020-12-01 | n/a | 2020-12-01 | AWARDED
IC19/C3.00-3 |  | 03.00 | Climate Data Analyst #1 | 12000 | QCII | ex-ante | 100 | 0 | NO | 2016-09-01 | 2018-01-01 | 2016-09-01 | 2018-01-01 | AWARDED
Data Analaysts to provide support to the provision of subsets of climate model data for sector related analyses
IC21/C3.00-4 |  | 03.00 | Climate Data Analyst #2 | 12000 | QCII | ex-ante | 100 | 0 | NO | 2016-09-01 | 2018-01-01 | 2016-09-01 | 2018-01-01 | AWARDED
Data Analaysts to provide support to the provision of subsets of climate model data for sector related analyses
CF14/C4.02-3 |  | 04.02 | ICT Early Warning System Consultancy (for Fishers) | 153039.47 | QBS | ex-ante | 100 | 0 | NO | 2016-05-01 | 2018-07-01 | 2016-05-01 | 2018-07-01 | AWARDED
coordinate with CRFM to recruit a firm to develop, test and install early warning and emergency response system (EWERS) for fishers to reduce vulnerability of fisheries to the impacts of climate change in PPCR countries
IC03/C6.00-1 |  | 06.00 | Program Manager 2017 | 50000 | QCII | ex-ante | 100 | 0 | NO | 2016-09-01 | 2017-11-01 | 2016-09-01 | 2017-11-01 | AWARDED
IC04/C6.00-2 |  | 06.00 | Procurement Specialist 2017 | 35000 | QCII | ex-ante | 100 | 0 | NO | 2016-09-01 | 2017-11-01 | 2016-09-01 | 2017-11-01 | AWARDED
IC06/C6.00-4 |  | 06.00 | Administrative Assistant 2017 | 25000 | QCII | ex-ante | 100 | 0 | NO | 2016-09-01 | 2017-11-01 | 2016-09-01 | 2017-11-01 | AWARDED
IC07/C6.00-5 |  | 06.00 | Communications Consultant (part-time) 2017 | 12500 | QCII | ex-ante | 100 | 0 | NO | 2016-07-01 | 2017-07-01 | 2016-07-01 | 2017-07-01 | AWARDED
IC08/C6.00-6 |  | 06.00 | Finance & Accounts Officer (part-time) 2017 | 15000 | QCII | ex-ante | 100 | 0 | NO | 2016-09-01 | 2017-11-01 | 2016-09-01 | 2017-11-01 | AWARDED
IC05/C6.00-3 |  | 06.00 | Monitoring & Evaluation Specialist (part-time) 2017 | 18750 | QCII | ex-ante | 100 | 0 | NO | 2017-01-01 | 2018-03-01 | 2017-04-01 | 2018-04-01 | AWARDED
IC11/C3.00-1 |  | 03.01 | Climate Modeling Research Analysts #1 (HPCS) | 25000 | QCII | ex-ante | 100 | 0 | NO | 2016-02-01 | 2017-04-01 | 2016-02-01 | 2017-07-01 | AWARDED
Research Analysts are needed to oversee the transfer of existing data and add new modeling outputs to the HPCS and analyze four focal areas of climate
IC18/C3.00-2 |  | 03.00 | Climate Modeling Research Analysts #2 (Agriculture) | 25000 | QCII | ex-ante | 100 | 0 | NO | 2017-03-01 | 2018-05-01 | 2017-04-01 | 2018-05-01 | AWARDED
Research Analysts are needed to oversee the transfer of existing data and add new modeling outputs to the HPCS and analyze four focal areas of climate
G16/C6.00-08 |  | 06.00 | Desk Phones | 715 | PC | ex-ante | 100 | 0 | NO | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | AWARDED
COMPLETED CONTRACTS
NCS10/C7.00-1 |  | 07.00 | Steering Committee Meeting 2017 | 26725 | [9 empty] | COMPLETED
|  |  | airfare x 15 | 15000 | DC | EX POST | 100 | 0 | NO | 2017-11-01 | 2017-12-01 | 2017-11-01 | 2017-12-01 | COMPLETED
|  |  | accomodation x 45 nights | 6975 | PC | EX POST | 100 | 0 | NO | 2017-11-01 | 2017-12-01 | 2017-11-01 | 2017-12-01 | COMPLETED
|  |  | venue | 1000 | PC | EX POST | 100 | 0 | NO | 2017-11-01 | 2017-12-01 | 2017-11-01 | 2017-12-01 | COMPLETED
|  |  | catering | 1500 | PC | EX POST | 100 | 0 | NO | 2017-11-01 | 2017-12-01 | 2017-11-01 | 2017-12-01 | COMPLETED
|  |  | ground transportation | 2250 | DC | EX POST | 100 | 0 | NO | 2017-11-01 | 2017-12-01 | 2017-11-01 | 2017-12-01 | COMPLETED
NCS37/C2.00-1 |  | 02.00 | Capacity Building/ Training for Meteorological Offices #1 | 22200 |  | EX POST | 100 | 0 | NO | 2017-11-01 | 2017-11-01 |  |  | COMPLETED | NEW ENTRY
|  |  | airfare x12 | 12000 | DC | EX POST | 100 | 0 | NO | 2017-11-01 | 2017-11-01 |  |  | COMPLETED
|  |  | accomodation x60 nights | 9000 | PC | EX POST | 100 | 0 | NO | 2017-11-01 | 2017-11-01 |  |  | COMPLETED
|  |  | ground transportation | 1200 | DC | EX POST | 100 | 0 | NO | 2017-11-01 | 2017-11-01 |  |  | COMPLETED
NCS38/C2.00-2 |  | 02.00 | Capacity Building/ Training for Meteorological Offices #2 | 3000 |  | EX POST | 100 | 0 | NO | 2018-01-01 | 2018-01-01 |  |  | COMPLETED | NEW ENTRY No-objection granted
|  |  | airfare x3 | 3000 | DC | EX POST | 100 | 0 | NO | 2018-01-01 | 2018-01-01 |  |  | COMPLETED
IC17/C3.00-1 |  | 03.00 | Climate Modeling Research Analysts #1 year 1 | 25000 | QCII | ex-ante | 100 | 0 | NO | 2016-04-01 | 2017-07-01 | 2016-04-01 | 2017-07-01 | COMPLETED
Research Analysts are needed to oversee the transfer of existing data and add new modeling outputs to the HPCS and analyze four focal areas of climate
G15/C7.00-01 |  | 07.00 | Air Conditionng Units for Conference Room | 2800 | PC | EX POST | 100 | 0 | NO | 2017-07-01 | 2017-08-01 | 2017-08-01 | 2017-09-01 | COMPLETED
to facilitate TAC, PSC and PMU team meetings
CF27/C1.00-3 |  | 01.00 | LIDAR Scoping Stakeholder Meeting- refreshments | 60 | PC | ex-post | 100 | 0 | NO | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | COMPLETED | conducted as per IDB instructions via email dated Aug 22, 2017
|  | 03.00 | Climate Modelling Workshop #1
NCS18/C3.00-1 |  |  | airfares | 7468.54 | DC | ex-ante | 100 | 0 | NO | 2016-07-01 | 2016-08-01 | 2016-07-01 | 2016-08-01 | COMPLETED
NCS19/C3.00-2 |  |  | accomodation | 5580 | PC | ex-ante | 100 | 0 | NO | 2016-07-01 | 2016-08-01 | 2016-07-01 | 2016-08-01 | COMPLETED
NCS20/C3.00-3 |  |  | ground transportation | 805 | PC | ex-ante | 100 | 0 | NO | 2016-07-01 | 2016-08-01 | 2016-07-01 | 2016-08-01 | COMPLETED
NCS21/C3.00-4 |  |  | catering | 2140 | PC | ex-ante | 100 | 0 | NO | 2016-07-01 | 2016-08-01 | 2016-07-01 | 2016-08-01 | COMPLETED
NCS21/C3.00-5 |  |  | venue | 1760 | PC | ex-ante | 100 | 0 | NO | 2016-07-01 | 2016-08-01 | 2016-07-01 | 2016-08-01 | COMPLETED
NCS22/C3.00-6 |  |  | stationery | 157 | PC | ex-ante | 100 | 0 | NO | 2016-07-01 | 2016-08-01 | 2016-07-01 | 2016-08-01 | COMPLETED
NCS23/C3.00-7 |  |  | banner | 90.3 | PC | ex-ante | 100 | 0 | NO | 2016-07-01 | 2016-08-01 | 2016-07-01 | 2016-08-01 | COMPLETED
|  | 04.03 | Agri Stakeholders Dialogue
NCS14/C4.03-1 |  |  | airfares | 14379 | DC | ex-ante | 100 | 0 | NO | 2016-09-01 | 2016-10-01 | 2016-09-01 | 2016-10-01 | COMPLETED
NCS15/C4.03-2 |  |  | accomodation | 2664 | PC | ex-ante | 100 | 0 | NO | 2016-09-01 | 2016-10-01 | 2016-09-01 | 2016-10-01 | COMPLETED
NCS16/C4.03-3 |  |  | catering | 612.48 | DC | ex-ante | 100 | 0 | NO | 2016-09-01 | 2016-10-01 | 2016-09-01 | 2016-10-01 | COMPLETED
NCS17/C4.03-4 |  |  | stationery | 140 | PC | ex-ante | 100 | 0 | NO | 2016-09-01 | 2016-10-01 | 2016-09-01 | 2016-10-01 | COMPLETED
W01/C6.00-01 |  | 06.00 | Renovation of Project Management Office | 5887.07 | PC | ex-ante | 100 | 0 | NO | 2015-09-01 | 2016-01-01 | 2015-10-01 | 2015-05-01 | COMPLETED
G07/C6.00-01 |  | 06.00 | Computers and peripherals for PMU | 8825.84 | DC | ex-ante | 100 | 0 | NO | 2015-09-01 | 2015-11-01 | 2015-09-01 | 2016-04-01 | COMPLETED
G07/C6.00-02 |  | 06.00 | Office Furniture | 7076.11 | PC | ex-ante | 100 | 0 | NO | 2015-09-01 | 2016-01-01 | 2016-01-01 | 2016-05-01 | COMPLETED
G07/C6.00-03 |  | 06.00 | Air Conditioning Units | 2851.36 | PC | ex-ante | 100 | 0 | NO | 2015-09-01 | 2016-01-01 | 2016-04-01 | 2016-05-01 | COMPLETED
NCS02/C6.00-2 |  | 06.00 | Electrical wiring for AC units | 293.7 | DC | ex-ante | 100 | 0 | NO | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | COMPLETED
NCS01/C6.00-1 |  | 06.00 | Network and electrical wiring for PMU | 900 | PC | ex-ante | 100 | 0 | NO | 2016-07-01 | 2016-09-01 | 2016-07-01 | 2016-09-01 | COMPLETED
G02/C3.00-01 |  | 03.00 | High Performance Computing System (HPCS) | 759719 | LIB | ex-ante | 100 | 0 | NO | 2016-01-01 | 2016-01-01 | 2016-02-01 | 2016-09-01 | COMPLETED
G03/C3.00-02 |  | 03.00 | Network Switches | 10306.5 | PC | ex-ante | 100 | 0 | NO | 2016-08-01 | 2016-12-01 | 2016-08-01 | 2017-01-01 | COMPLETED
to provide reliable access to the HPCS
CF20/C9.00-1 |  | 09.00 | Annual Financial Audit 2016 | 12000 | LCS | ex-ante | 100 | 0 | NO | 2016-10-01 | 2017-03-01 | 2016-10-01 | 2017-03-01 | COMPLETED
NCS31/C6.00-10 |  | 06.00 | PMU Operations- CARPHA Water Resource Mgmt Meeting
|  |  | hotel | 592.8 | DC | ex-ante | 100 | 0 | NO | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | COMPLETED
|  |  | ground transportation | 100 | DC | ex-ante | 100 | 0 | NO | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | COMPLETED
|  |  | airfare | 752.52 | PC | ex-ante | 100 | 0 | NO | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | COMPLETED
NCS33/C4.03-6 |  | 04.03 | Crop Production Models Training Workshop
|  |  | hotel | 700 | DC | ex-ante | 100 | 0 | NO | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | COMPLETED
|  |  | airfare | 860 | DC | ex-ante | 100 | 0 | NO | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | COMPLETED
|  |  | ground transportation | 280 | DC | ex-ante | 100 | 0 | NO | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | COMPLETED
G15/C6.00-07 |  | 06.00 | Water Cooler | 300 | PC | ex-ante | 100 | 0 | NO | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | COMPLETED
NCS32/C6.00-11 |  | 06.00 | PMU Operations- CIMH Outlook Forum
|  |  | airfare | 800 | DC | ex-ante | 100 | 0 | NO | 2017-05-01 | 2017-06-01 | 2017-05-01 | 2017-06-01 | COMPLETED
|  |  | hotel | 1256 | PC | ex-ante | 100 | 0 | NO | 2017-05-01 | 2017-06-01 | 2017-05-01 | 2017-06-01 | COMPLETED
|  |  | ground transportation | 260 | DC | ex-ante | 100 | 0 | NO | 2017-05-01 | 2017-06-01 | 2017-05-01 | 2017-06-01 | COMPLETED
NCS01/C6.00-01 |  | 06.00 | PPCR Project Launch Workshop
|  |  | airfare | 7114.82 | DC | ex-ante | 100 | 0 | NO | 2015-10-01 | 2015-10-01 | 2015-10-01 | 2015-11-01 | COMPLETED
|  |  | catering | 2051.27 | PC | ex-ante | 100 | 0 | NO | 2015-10-01 | 2015-10-01 | 2015-10-01 | 2015-11-01 | COMPLETED
|  |  | accomodation | 3040.2 | PC | ex-ante | 100 | 0 | NO | 2015-10-01 | 2015-10-01 | 2015-10-01 | 2015-11-01 | COMPLETED
|  |  | venue | 819.67 | PC | ex-ante | 100 | 0 | NO | 2015-10-01 | 2015-10-01 | 2015-10-01 | 2015-11-01 | COMPLETED
IC03/C6.00-1 |  | 06.00 | Program Manager 2016 | 50000 | QCII | ex-ante | 100 | 0 | NO | 2015-09-01 | 2016-11-01 | 2015-10-01 | 2016-11-01 | COMPLETED
IC04/C6.00-2 |  | 06.00 | Procurement Specialist 2016 | 35000 | QCII | ex-ante | 100 | 0 | NO | 2015-09-01 | 2016-11-01 | 2015-10-01 | 2016-11-01 | COMPLETED
IC06/C6.00-4 |  | 06.00 | Administrative Assistant 2016 | 25000 | QCII | ex-ante | 100 | 0 | NO | 2015-09-01 | 2016-11-01 | 2015-10-01 | 2016-11-01 | COMPLETED
IC08/C6.00-6 |  | 06.00 | Finance & Accounts Officer (part-time) 2017 | 15000 | QCII | ex-ante | 100 | 0 | NO | 2015-09-01 | 2016-11-01 | 2015-10-01 | 2016-11-01 | COMPLETED
NCS01/C6.00-4 |  | 06.00 | Stationery and Office Supplies | 800 | PC | ex-ante | 100 | 0 | NO | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | COMPLETED
G12/C6.00-05 |  | 06.00 | Network Printer | 850 | PC | ex-ante | 100 | 0 | NO | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | COMPLETED
NCS06/C6.00-6 |  | 06.00 | Visit to IPs re signing of Letters of Agreement
|  |  | airfare | 2268.9 | DC | ex-ante | 100 | 0 | NO | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | COMPLETED
|  |  | hotel-Barbados | 464 | DC | ex-ante | 100 | 0 | NO | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | COMPLETED
|  |  | hotel-Trinidad | 1050 | DC | ex-ante | 100 | 0 | NO | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | COMPLETED
CANCELLED PROCUREMENTS
W04/C4.03-03 |  | 04.03 | Weaning and Harding facilities in 4 PPCR countries | 61100 | PC | ex-ante | 100 | 0 | NO | 2018-02-01 | 2018-11-01 |  |  | CANCELLED | Merged with W07/C4.03-06
CF26/C4.04-03 |  | 04.04 | Rainwater Harvesting Manual Development and Training | 120000 | QBS | ex-ante | 100 | 0 | NO | 2017-08-01 | 2018-06-01 | 2017-08-01 |  | CANCELLED | Merged with CF26/C4.04-03
CF03/C2.00-1 |  | 02.00 | Strengthening of Regional Climate Monitoring Network | 90000 | CQS | ex-ante | 100 | 0 | NO | 2017-10-01 | 2018-06-01 |  |  | CANCELLED | reentered as 3 separate training sessions with reference nos. NCS37-39
Consultancy to be coordinated with CIMH with the aim of (i) improving the acquisition of weather data in PPCR countries; (ii) identifying climate products and services for development complementing ongoing initiatives under the GFCS; (iii) undertaking capacity building workshops for national meteorological offices; and (iv) increasing the capacity of back-up storage of regional climate data.
CF27/C2.00-2 |  | 02.00 | Weather Stations Needs Assessment | 30000 | CQS | ex-ante | 100 | 0 | NO | 2017-09-01 | 2018-02-01 |  |  | CANCELLED
assessment of countries to determine installation and/or upgrade. Linked to G01/C2.00-01
NCS25/C5.00-03 |  | 05.00 | Fact Sheets & Brochures | 1000 | PC | ex-ante | 100 | 0 | NO | 2017-01-01 | 2017-03-01 |  |  | CANCELLED | clarified as Graphic Designing NCS32/C5.00-09
for the execution of the communications strategy
NCS26/C5.00-04 |  | 05.00 | Informational Packages | 6000 | PC | ex-ante | 100 | 0 | NO | 2017-04-01 | 2017-09-01 |  |  | CANCELLED | Clarififed as Printing of Communication Materials NCS33/C5.00-10
production of materials to promote activities under Component 4
IC22/C3.00-5 |  | 03.00 | Climate Data Analyst #3 | 12000 | QCII | ex-ante | 100 | 0 | NO | 2016-09-01 | 2018-01-01 |  |  | CANCELLED | CSG has decided not to pursue 3rd consultant.
Data Analaysts to provide support to the provision of subsets of climate model data for sector related analyses
CF28/C4.03-3 |  | 04.03 | Agriculture Infrastructure Upgrade –Scoping and Design Consultancy | 51000 | CQS | ex-ante | 100 | 0 | NO | 2017-10-01 | 2018-05-01 |  |  | PENDING | CANCELLED and new items entered
consultancy to Formulate a transparent site selection protocol to determine the sites to be chosen for refurbishment or construction and design each facility as required.
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labeled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.
Codes from SEPA