Project: Modernization of the Barbados Statistical Service

Project number:  BA-L1009 and Loan Contract number: 2003/OC-BA

Period included in this Procurement Plan:  From:  January 2011 to Dec 2012

| Description and type of the procurement contract | Estimated Contract Cost (US$000) | Procurement method | Review (Ex-ante or Ex-post) | Source of financing and percentage |  | Prequalification (Yes/No) | Estimated Dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | IDB % | Local/other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 1. Goods º Equipment and software Hardware Software (to support strengthening component and for PCU) Office furniture for BSS Office 2. Non Consulting Services Scholarships at the Masters Level Professional Services for IT implementation. | US $1,250 US $ 610 US $ 375 US$ 800 US$ 140 | ICB ICB ICB FBS NICQ | Ex-ante Ex-ante Ex-ante Ex-ante Ex-post | 80% 80% 80% 100% 100% | 20% 20% 20% 0% 0% | No No No No No | 1Q 2012 1Q 2012 3Q 2011 N/A 3Q 2011 | 3Q 2012 3Q 2012 4Q 2011 4Q 2012 4Q 2012 | Pending Pending Pending Pending Pending | Eight (8) scholarships |

| Description and type of the procurement contract | Estimated Contract Cost (US$000) | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequalification (Yes/No) | Estimated Dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | IDB % | Local/other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 3. Consulting Services Statistics Management Consultancy In the context of strengthening activities, the agency will provide legal, sector, and institutional consulting services, as well as on-the-job technical and training program | US$2,510 | ICB/QCBS | Ex-ante | 80% | 20% | Yes | 3Q 2010 | 4Q 2012 | Awarded | Awarded to Oxford Policy Management Ltd. on 2011-01-18 |
| 4. Individual Procurement Consultant A part-time consultant to support BSS on procurement activities in line with programmed requirements (A daily rate will be applied) | N/A | NICQ | Ex-post | 100% | 0% | No | 1Q 2012 | 4Q 2012 | Pending |  |

.

| Description and type of the procurement contract | Estimated Contract Cost (US$000) | Procurement method | Review (prior or post) | Source of financing and percentage |  | Prequalification (Yes/No) | Estimated Dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | IDB % | Local/other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 5. Auditing Services Consulting Services to provide external auditing services to the BSS | US $98 | QCBS | Ex-ante | 100% | 0% | No | 1Q 2010 | 3Q 2012 | Awarded | Awarded to KPMG on 2010-10-18 |
| 6. Evaluation Mid-Term & Final Review | US$40 | NICQ | Ex-post | 100% | 0% | No | 4Q 2011 | 1Q 2012 | Pending |  |

Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through Specialized Agencies; PA: Procurement Agents; IA: Inspection Agents; PLFI: Procurement in Loans to Financial Intermediaries; BOO/BOT/BOOT: Build, Own, Operate/Build, Operate, Transfer/Build, Own, Operate, Transfer; PBP: Performance-Based Procurement; PLGB: Procurement under Loans Guaranteed by the Bank; PCP: Community participation procurement.  Consulting Firms: QCBS: Quality- and Cost-Based Selection QBS: Quality-Based Selection FBS: Selection under a Fixed Budget; LCS: Least-Cost Selection; CQS: Selection based on the Consultants’ Qualifications; SSS: Single-Source Selection.  Individual Consultants: NICQ: National Individual Consultant selection based on Qualifications; IICC: International Individual Consultant selection based on Qualifications