## SM2015 PA
Procurement Plan
Project: Mesoamerican Health 2015 - Belize Program (Second Individual Operation)
Period Comprised in this Procurement Plan: From January 2015 to January 2017
Ref. No (WBS) | Ref. No. |  | Estimated Cost in (US$ ) | Actual Cost (US$) | Actual Cost in (US$) | Procurement Method | Review (Ex ante/Ex-Post) | Source of Financing and Percentage |  | Prequalification (Yes/No) | Estimated Dates |  |  |  | Status (pending, in process awarded, cancelled) | Comments
[8 empty] | IDB | GOB |  | Publication of Specific Procurement Notice | Bids/RFP Submission Date | Contract Signing | Completion of contract
GOODS
2.1.1.5.3 | BZ/SM2/G/002 | Vehicles for Monitoring (2) | 60000 |  | 0 | NCB | Ex-ante | 100% | 0% | No | 2015-04-10 | 2015-05-10 | 2015-05-10 | 2015-07-09 | Pending
2.2.1.4 | BZ/SM2/G/003 | Basic supplies for CHWs (incentive program) | 20000 |  | 0 | PC | Ex-ante | 100% | 0% | No | 2015-09-18 | 2015-10-30 | 2015-10-30 | 2016-01-07 | Pending
3.2.1.1 | BZ/SM2/G/004 | Hardware for BHIS | 30000 |  | 0 | NCB | Ex-ante | 100% | 0% | No | 2015-04-17 | 2015-06-18 | 2015-06-18 | 2015-09-10 | Pending
3.2.1.3 | BZ/SM2/G/005 | Internet | 3600 |  | 0 | GOB's Limited Tendering Procedure | N/A | 0% | 100% | No | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | Pending
3.3.1.4 | BZ/SM2/G/006 | Cabinets and Other Office Supplies | 15000 |  | 0 | GOB's Selective Tendering Procedure | N/A | 0% | 100% | No | 2015-09-04 | 2015-10-29 | 2015-10-29 | 2015-11-26 | Pending
SUB-TOTAL - GOODS |  |  | 128600 | 0 | 0
NON-CONSULTING SERVICES
2.1.1.4.3 2.1.1.4.4 and 2.1.1.4.5 | BZ/SM2/G/001 | Quality Improvement Fund | 60000 | 0 | 0 | PC | Ex-ante | 100% | 0 | No | 2015-07-13 | 2015-07-13 | 2015-07-13 | 2016-07-24 | Pending
3.3.1.3 | BZ/SM2/NCS/001 | Printing of Monitoring Forms | 25000 |  | 0 | GOB's Selective Tendering Procedure | N/A | 0% | 100% | No | 2015-09-04 | 2015-10-15 | 2015-10-15 | 2015-11-12 | Pending
2.2.3 | BZ/SM2/CS/005 | Implementation of behavior change campaign (airing of spots) | 52500 |  | 0 | PC | Ex-ante | 38% | 62% | No | 2015-08-14 | 2015-09-01 | 2015-09-01 | 2016-12-01 | Pending
SUB-TOTAL NON-CONSULTING SERVICES |  |  | 137500 |  | 0
CONSULTING SERVICES
2.1.1.5.2 | BZ/SM2/CS/001 | Quality Improvement Officer (1) | 30600 |  | 0 | SSS | Ex-ante | 100% | 0% | No | 2015-01-16 | 2015-02-16 | 2015-02-16 | 2017-01-16 | Pending | GN-2350-9, 3.10 (a) a natural continuation of previous work.
2.1.1.5.2 | BZ/SM2/CS/002 | Drivers (2) | 28224 | 0 | 0 | SSS | Ex-ante | 48% | 52.1% | No | 2015-01-16 | 2015-02-16 | 2015-02-16 | 2017-01-16 | Pending | GN-2350-9, 3.10 (a) a natural continuation of previous work.
2.1.2.2.1 | BZ/SM2/CS/003 | Technical Assistance for training of CHWs and PHCWs on improved technical capacity | 85000 |  |  | GOB's Selective Tendering Procedure | N/A | 0% | 100% | No | 2015-03-27 | 2015-04-24 | 2015-04-24 | 2016-03-10 | Pending
2.2.2.1 | BZ/SM2/CS/004 | Technical Assistance to Develop Mass Media Behavior Change Campaign | 15000 |  | 0 | NICQ | Ex-ante | 100% | 0% | No | 2015-05-22 | 2015-06-18 | 2015-06-18 | 2015-10-08 | Pending
3.1.2 | BZ/SM2/CS/006 | Technical Assistance for Management Development Training | 39800 |  | 0 | NICQ | Ex-ante | 62.81% | 37.19% | No | 2015-05-29 | 2015-06-26 | 2015-07-09 | 2016-04-28 | Pending
4.1.3.5 | BZ/SM2/CS/007 | Technical Assistance for Capacity Development Training - PMU | 15882 |  | 0 | SSS | Ex-ante | 37% | 63% | No | 2015-01-16 | 2015-02-16 | 2015-02-16 | 2015-08-27 | Pending
5.2 | BZ/SM2/CS/008 | Financial Audit | 20000 | 0 | 0 | LCS | Ex-ante | 100% | 0% | No | 2016-03-11 | 2016-03-11 | 2016-03-11 | 2016-04-21 | Pending
SUB-TOTAL - CONSULTING SERVICES |  |  | 234506 | 0 | 0
OPERATING COST
2.1.1.5.4 | BZ/SM2/OC/001 | Maintenance Cost - Vehicles | 5400 |  | 0 | N/A | N/A | 0% | 100% | No | N/A | N/A | N/A | 2016-06-09 | Pending | Does not require hiring process because the new vehicles would be under warranty supplier / manufacturer.
2.1.1.4.1 | BZ/SM2/OC/002 | QIF Supervision Visists | 10200 |  | 0 | N/A | N/A | 0% | 100% | No | N/A | N/A | N/A | 2016-01-27 | Pending
4.1.2 | BZ/SM2/OC/003 | Operational Cost - PMU | 98500 |  | 0 | N/A | N/A | 0% | 100% | No | N/A | N/A | N/A | 2016-07-07 | Pending
SUB-TOTAL - OPERATING COST |  |  | 114100 |  | 0
GRAND TOTAL |  |  | 614706 | 0 | 0
Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
Ex ante/ex post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex post review is the standard modality. Ex ante review can be specified for critical or complex process.
Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.