Results Matrix

| Objectives | Overall: (i) Improve the effectiveness of financial institutions and markets in providing credit and other financial services to firms and households; and (ii) to reduce their vulnerability to macroeconomic shocks. Specific:(i) the enhancement of the enabling environment in which financial markets and institutions operate, both public and private; and (ii) the strengthening of Central Bank capabilities to execute its core responsibilities. |
| --- | --- |

| Impact Indicators | Baseline 2010 | Target 2014 |  | Observations/Means of Verification |
| --- | --- | --- | --- | --- |
| Effectiveness of Financial Institutions and Markets |  |  |  |  |
| Private Sector Credit to GDP | 24.1% | 26% |  | IMF Article IV Staff Reports. The forecast expected value for 2012 is 23.1% |
| Relative ranking of “Access to Finance” indicator of World Economic Forum. | 85th percentile. (109th of 130 ranked countries) | 80th percentile |  | World Economic Forum Competitiveness Indicator Annual Report.(Financial Market Development pillar) |
| Reduced Vulnerability of Financial Institutions and Markets (Baseline Date: May, 2011) (Focus on banks, given focus of reforms in first Programmatic Loan) |  |  |  |  |
| Private Sector Banks Non-performing Loans to Total Loans | 7.9% | 7.0% |  | IMF Article IV Staff Report |
| Regulatory Capital as a Percentage of Risk Weighted Assets. | 12.2% | 12.0% |  | IMF Article IV Staff Reports |
| Return on Assets of Private Banking Institutions | 2.2% | 2.0% |  | IMF Article IV Staff Reports |
| An efficient financial market that allocates the transferable savings to the most productive uses thorough the proper risk assessment. Economies require sophisticated financial markets that can make capital available for private-sector investment from such sources as loans from a sound banking sector, well-regulated securities exchanges, venture capital, and other financial products. | Because of the lack of financial data Suriname was not included in previous reports | 3.6 (observed 2011) | 3.7 (target 2014) | In order to fulfill all those functions, the banking sector needs to be trustworthy and transparent, financial markets need appropriate regulation to protect investors and other actors in the economy at large. A main indicator is the : Global Competitiveness Report, score in the eighth pillar: Financial Market Development. 8th pillar: Financial market development. Is composed by a set of indicators as follow: A. Efficiency 50% that includes: 8.01 Availability of financial services 8.02 Affordability of financial services 8.03 Financing through local equity market 8.04 Ease of access to loans 8.05 Venture capital availability and B. Trustworthiness and confidence .50% that includes: 8.06 Soundness of banks 8.07 Regulation of securities exchanges 8.08 Legal rights index* |

| Component I: Macroeconomic Framework |  |  |  |  |
| --- | --- | --- | --- | --- |
| Outcomes | Baseline 2010 | Second Programatic Loan End of 2012 | Target 2014 | Observations/Means of Verification |
| Foreign Exchange Reserves as Months of Imports | 4.4 | 5.6 | 6.0 | IMF Article IV Staff Report, Reviewed by IMF Board. October 3, 2012. |
| Consumer Price Inflation | 10.3% | 5.7% | 6.0% | IMF Article IV Staff Report, Reviewed by IMF Board. October 3, 2012 |
| Fiscal Balance as Percent of GDP. | -3.6 | 0.5 | +-1.0% | IMF Article IV Staff Report, Reviewed by IMF Board. October 3, 2012. |

| Component II: Legal and Regulatory Reform |  |  |  |  |
| --- | --- | --- | --- | --- |
| Outputs | Baseline 2010 | Second Programatic Loan End of 2012 | Target 2014 | Observations/Means of Verification |
| New Laws enacted: - Banking - Insurance - Capital Markets - Credit Bureau - Money Laundering and Terrorism financing | - - - - - | 1 1 drafted 1 drafted 1 drafted 1 | 1 1 1 1 1 | Copy of the enacted law published in the official Gazette, with an English translation of the law. |
| Regulations for the Banking law in following areas issued. Liquidity Risk Management, Operational Risk, Foreign Exchange Risk, and Interest Rate Risk. | Updated regulations 0 | 10 adopted | 10 fully implemented | Copy of approved regulations, evidence of approval by CBvS, and copies of letters announcing entry into force sent to banking institutions. |
| Regulation for the full implementation of the insurance law | 0 | 0 | 3 | Copy of approved regulations, evidence of approval by CBvS, and copies of letters announcing entry into force sent to insurance institutions. |
| Update of the regulations on Money Landry and Terrorism financing so that :Compliance with the Core Recommendations of CFTAF 2009 Mutual Evaluation | 0 | 5 | 20 | Copy of the last revised Mutual Evaluation. |
| Component II: Legal and Regulatory Reform |  |  |  |  |
| Outcomes | Baseline 2010 | Second Programatic Loan End of 2012 | Target 2014 | Observations/Means of Verification |
| Banking System solvent | 44.6 | 44.0 | 40% | Non performing loans (NPL) net of provisions as a percentage of total equity |
| Access to financing increased | Because of the lack of financial data Suriname was not included in previous reports | 2.4 | 2.5 | Global Competitiveness Report, score in the eighth pillar: Ease to access to loans (8.4) |

| Component III: Enhancement of Financial Sector Supervision |  |  |  |  |
| --- | --- | --- | --- | --- |
| Outputs | Baseline 2010 | Second Programatic Loan End of 2012 | Target 2014 | Observations/Means of Verification |
| Training program implemented | No plan | At least 70% of the Supervision Department staff received specific training for the job | At least 90% of the Supervision Department staff received specific training for the job | Copy of the semiannual informs of the Project Manager to the President of the CBvS on the implementation of the Supervision Enhancement Plan. World Economic Forum, Global competitiveness report, Financial Market Development pillar. IMF FSAP. |
| Risk based Financial Supervision in practice On-site inspection under new methodology: - Banks - Insurance companies | 0 0 | 3 0 | 9 10 | Number of on-site inspections with proper risk assessment. |
| Component III: Enhancement of Financial Sector Supervision |  |  |  |  |
| Outcomes | Baseline 2010 | Second Programatic Loan End of 2012 | Target 2014 | Observations/Means of Verification |
| - An efficient financial market that allocates the transferable savings to the most productive uses thorough the proper risk assessment. - Financial Solvency Financial Depth: - Savings as % of GDP - Loans as % of GPD | Because of the lack of financial data Suriname was not included in previous reports 41.7 23.9 | 3.6 5.6 45.0 25.0 | 3.8 5.8 55.0 30.0 | Global Competitiveness Report, score in the eighth pillar: Financial Market Development. Score in Global Competitiveness Report, score in the eighth pillar 8.06 Soundness of Banks. IMF Financial Access Survey (FAS) - Deposits in Banks as % of GDP - Loans in Banks as % of GDP |

| Component IV: Institutional Stregthening of the CBvS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Outputs | Baseline 2010 | Second Programatic Loan End of 2012 | Target 2014 | Observations/Means of Verification |
| Establishment of specialized departments for: - Procurement, - Budget and Control - Internal Audit - CBVS Training Institute. | No specialized units in these areas. | - 1 procurement manual - 1 budget manual - 1 Internal Audit manual - At least 50% of al CBvS technical staff received specialized training. | - 1 procurement manual - 1 budget manual - 1 Internal Audit manual - At least 50% of al CBvS technical staff received specialized training. | Copy of internal CBvS manual for the procedures of Budget and Control, Internal Audit, and Procurement Departments. Copy of the semiannual reports of the Project Manager on the Human Resource Policy execution and the Training Plan in execution. |
| Component IV: Institutional Stregthening of the CBvS |  |  |  |  |
| Outcomes | Baseline 2010 | Second Programatic Loan End of 2012 | Target 2014 | Observations/Means of Verification |
| Institutional capacity of the CBvS improved. Indicator: Number of specialized publications published in the CBvS web page | 0 | 0 | 5 by the end of 2014 | Institutional capacity is directly related to the capacity of the staff, and their capacity increase by the received training. This also gives the staff the capacity to produce quality documents that could by generate knowledge that could be disseminated through published. Copy of the semiannual informs of the Project Manager to the President of the CBvS. |

| Component V: Inter-Bank and Securities Market Development |  |  |  |  |
| --- | --- | --- | --- | --- |
| Outputs | Baseline 2010 | Second Programatic Loan End of 2012 | Target 2014 | Observations/Means of Verification |
| Establishment of specialized unit in CBvS to be responsible for development of money and capital markets. | No specific unit responsible for capital or money market development. | 1 new division created | 1 new division created and in operation. | Issuance of a securities market law and regulations for its enforcement. Copy of CBvS Circular announcing establishment of the Capital Market Department |
| New Capital Markets Law enacted. | No plan for development of Suriname Stock Market. | 1 new law drafted | 1 new law enacted | Copy of the enacted law published in the official Gazette, with an English translation of the law. |
| Outcomes |  |  |  |  |
| Conditions to promote the development of the capital market improved. - Financing through local equity market - Venture Capital Availability - Regulation of securities exchanges | Because of the lack of financial data Suriname was not included in previous reports | - 3.1 - 2.0 - 3.3 | - 3.2 - 2.2 - 3.5 | Scores on the Global Competitiveness Report Eighth pillar - 8.03 Size of the exchange market - 8.05 Possibilities to get capital financing - 8.07 Quality of the Exchange Regulation |

| Component VI: Complementary institutions for greater access to finance |  |  |  |  |
| --- | --- | --- | --- | --- |
| Outputs | Baseline 2010 | Second Programatic Loan End of 2012 | Target 2014 | Observations/Means of Verification |
| Creation of a Credit Bureau Agency. | Inexistence of a credit bureau. | 1 New Law to facilitated a Credit Bureau drafted | 1 New Law to facilitated a Credit Bureau enacted | Copy of the enacted law published in the official Gazette, with an English translation of the law |
| Develop a strategy to implement mobile guaranties. | Only real estate assets are acceptable as collateral guarantees |  |  | Designation by the Governor of the CBvS of a technical team to study the models of secure transactions, with technical assistance from the IDB.(Compete Caribbean) |
| Outcomes |  |  |  |  |
| Conditions for access to credit improved. - Availability of financial services - Ease to access to loans - Legal rights index | Because of the lack of financial data Suriname was not included in previous reports | - 3.7 - 2.4 - 5.0 | - 3.8 - 2.5 - 5.2 | Scores on the Global Competitiveness Report Eighth pillar. - 8.01Financial sector deepness - 8.04 Ease to access to loans - 8.08 Secured Transactions quality. |

| Component VII: Public Banks Reform |  |  |  |  |
| --- | --- | --- | --- | --- |
| Outputs | Baseline 2010 | Second Programatic Loan End of 2012 | Target 2014 | Observations/Means of Verification |
| Develop a strategy to reform of public banks such that public banks that continue to operate have: (i) have clear and specific social and economic goals; (ii) financing mechanisms that address market failure; and (iii) have a business strategy and corporate governance that ensures financial sustainability | Public Banks do not have a clear mandate, not a good solvency condition. | 1 proper valuation of these banks’ assets and liabilities contracted with an external audit. | Strategy to reform of public banks adopted. | Copy of the strategy. |

Suriname authorities have revised their National Accounts Estimates, resulting in a higher nominal GDP series. See 2012 Article IV Consultation at IMF Country Report Suriname. Also some of the figures for 2010 were updated based on the  latest figures reported by IMF and CBvS. In addition, because of the trend of some of the indicators in 2012, the targets were revised accordingly.

See the methodology note at: http://www3.weforum.org/docs/WEF_GlobalCompetitivenessReport_2012-13.pdf  page 47 and 48.