Suriname

Financial Sector Strengthening program

SU-L1034

Monitoring and Evaluation Plan

- Introduction

  - The Financial Sector Strengthening Program is a 3 phase Programmatic Loan and is supported by a complementary Technical Cooperation (SU-T1058) that provides technical assistance to the Central Bank of Suriname (CBvS) for the implementation of the Program,.  The CBvS is the executing agency of the loan, but shares supervisory responsibility with the Ministry of Finance (MoF) as it is the Borrower and signatory of the contract.

  - This  monitoring and evaluation plan proposes that the monitoring and evaluation of the operation be conducted in 4 phases;  (i) the monitoring of the indicators of the Results Matrix of the 1st programmatic loan; (ii) the monitoring of the meeting of the policy measures that are triggers for the second and third programmatic loans; (iii) If  the 2nd and 3rd loans were approved as planned by 2014, then monitoring would be done of the results matrix indicators agreed to in these subsequent loans;   (iv) the evaluation of the 1st programmatic loan.  If the 2nd and 3rd loans are approved and implemented by the planned schedule then the evaluation could be conducted jointly for all 3 of the loans or for at least the first two loans.

- Monitoring

# Indicators

  - For the second Programmatic Loan the indicators to be monitored correspond to those presented in the Results Matrix and the activities included in the Financial Institutions Supervision Enhancement Plan. The aforementioned TC will be financing substantial portions of the technical assistance required for its implementation as well as for assistance to design and implement triggers of the subsequent Loan.   The output indicators are the policy and institutional measures of the loan. As explained in the Loan Proposal, the impact indicators and the outcome indicators are the result primarily of the enactment of the Banking and Other Credit Institution Law and the implementation of the Plan.   It is only through the combination of these measures, that the CBvS will have the capabilities needed to be able to surveillance and guide the financial sector development as well to conduct financial sector supervision in a manner consistent with international standards.

- Data Collection,   Instruments, Monitoring Mechanisms and Reporting.

  - Outputs. The monitoring of the outputs of the Programmatic Loans will be completed shortly before or after the Loan Document is presented to the IDB Board for approval as part of the loan preparation process.  The CBvS has put in place a Program Manager, who is responsible for the coordination and management of the implementation of the overall Financial Sector Strengthening Program. The Program Manager is responsible for collecting this information and documentation on the part of the CBvS,   The Program Manager coordinates her activities with the Ministry of Finance, via the Joint Committee, a CBvS/Ministry of Finance jointly led group that has been established to coordinate relations with multilateral institutions. Simultaneously, the CBvS will adopt a clear financial sector data dissemination policy that will be reflected on the information periodically publish on the web page of the CBvS.

  - Outcomes and Impact Indicators.   The data on the outcome indicator target relating to the quality of bank and other credit institution development and supervision will be available in the IMF annual Article IV Staff Report  and the Global Competitiveness Annual Report of the World Bank (Financial Market Development pillar). A more detailed analysis of the condition of the financial sector will be available in the Financial Sector Assessment Report (FSAP) prepared jointly by World Bank and IMF staff.  These documents would be available publicly on the IMF website if the country authorize is publication; otherwise, the authorities will facilitate a copy of the FSAP to the IDB.

  - Financial Institutions Supervision Enhancement Plan. Data on the implementation of this plan will be provided to the Bank by the CBVS via the semi-annual progress reports of the aforementioned technical cooperation program. The Program Manager prepares these reports.    Moreover, the project team of the technical assistance program will also be in contact with the director of the CBvS Supervision department on a regular basis to discuss the implementation of this plan.

  - Triggers for 3rd Programmatic Loan. The CBvS will be responsible for providing information to the Bank on progress in the implementation of the triggers of 3rd loan via the aforementioned semi-annual progress reports.

- Monitoring, Coordination, Work Plan and Budget.

  - Monitoring and coordination activities are supported via the SU-T1058 via the payment of the fees of the Program Manager.  The monitoring and supervision activities for which the Program Manager is responsible are detailed in the Terms of Reference, but no estimation of time devoted to different activities is included.  The Work Plan is included at the end of this document.

- Evaluation

  - The ex-post evaluation of the 1st Programmatic loan will be conducted in two stages and divided between the evaluation of the meeting of outcome targets and evaluating its impact. Since one cannot be sure that the subsequent loans will be approved and implemented this plan does not envision their evaluation.  However, mention will be made to how these subsequent loans could be evaluated if implemented as planned.

  - For impact indicators, the attribution of the changes is more complicated and the evaluation will consist of two stages.  First, the technical methodology will be determined later after the completion of the 2nd Programmatic Loan.   Given that baseline data is available, the definition of the methodology can be determined at a later date without significant difficulty.

- Technical Aspects of Selected Methodology.

  - Outcome. The program has only one outcome indicator that measures the quality of supervision.  Supervision in this context means both the supervisory and regulatory actions taken by the supervisory institution, the CBvS, but also the resulting incentive structure faced by financial institutions by the enforcement of the legal and regulatory framework.  As explained in the Loan Document, the achievement of this outcome requires the combination of legal and regulatory changes (component 2 of the program) and the approval and expected implementation by the CBvS of a comprehensive Financial Institutions Supervision Enhancement Plan (component 3 of the program).  The legal and regulatory changes provide the CBvS with the authority and instruments to conduct supervision at international standards; however without sufficient technical capabilities and resources the legal and regulatory framework could not be enforced.  The FSEP is designed to fundamentally boost the capabilities and capacity of the CBvS to surveillance and guide the financial sector development as well to conduct high quality financial sector supervision in a manner consistent with international standards.

  - The attribution of the changes in the quality of supervision as a result of the policy measures (outputs) included in the program is quite direct in that the measures included in the program are comprehensive and few other factors that can affect the outcome are excluded.

  - The measurement of the outcome will be provided by the number of international supervisory standards, as defined by the Bank for International Settlement’s twenty five Basel Core Principles, which are met as reported by the Financial Sector Assessment Program (FSAPs). The Financial Institutions Supervision Enhancement Plan is scheduled to be completed by 2014, and as such the evaluation of the combine impact of the Plan and legal and regulatory changes impact will be conducted when the FSAP is completed.   The FSAP report will also provide additional qualitative information on how the CBvS is conducting its surveillance and guide to the financial sector development as well to conduct financial sector supervision in a manner consistent with international standards supervision and highlight what measures are needed to further improve the conditions of the financial sector. As an intermediate follow and evaluation it is possible to consult the IMF annual Article IV Staff Report  and the Global Competitiveness Annual Report of the World Bank, Financial Market Development pillar.

  - Impact.  Numerous rigorous cross-country studies are available that relate financial sector performance both stability and depth of provision of services with the quality of supervision and regulation. These include the study used for the estimate of the economic benefits of the program, which estimated the reduction in GDP losses obtained through enhanced supervision, via lowering the probability and the intensity of a financial crisis.  Others more directly analyze and estimate the relation between the meeting of Basel Core Principles with banking performance, both in terms of soundness and provision of finance.  Two of the most notable include: “Banking on the Principles; Compliance with Basel Core Principles and Banking Soundness” by Demirguc-Kunt, Detragiche and Tressel, IMF Working Paper, (2006), and “Bank Regulation and Supervision, What Works Best?”by Barth, Carpio and Levine, Journal of Financial Intermediation,2004. In addition, Finance for All, World Bank, 2008, by Demirguc, Beck and Honahan relates supervisory and other legal and regulatory reforms with financial access.

  - The evaluation will compare the implementation of the reforms and meeting of Basel Core Principles and their impact in Suriname with the findings of these studies and other studies.  To the degree possible, Surinamese variables will be included in their econometric estimations to compare the expected result in Suriname with the actual results, both with regard to the impact indicators already defined but other relevant dimensions as well.    As the evaluation will not be conducted until 2014 or 2015 when the data from the second FSAP is available and the Financial Institutions Supervision Enhancement Plan is completed, a literature review will be conducted to determine if other updated or even more useful studies are available.  In addition,  the evaluation in a more qualitative manner will assess how well the reforms have been implemented in particular the Financial Institutions Supervision Enhancement Plan, and whether there are still legal and regulatory shortfalls, and how these relates to both the meeting of the Core Principles and the resulting impact on banking performance and overall financial sector stability.

  - The data for the evaluation will come from: the FSAPs with regard to the meeting of Basel Core principles and existing publicly available data sources such as from the IMF and the CBvS website.  Other financial sector data that may not be publicly available will be provided by the CBvS but may need to be used in a confidential manner.

  - While this methodology does not provide for a specifically designed counterfactual, it does allow for Suriname to be compared with other countries controlling for differences in terms of income, stage of financial sector development, and institutional factors. Also, it provides for a relatively strong means to attribute impact to the program.

- Reporting Evaluation Results

  - The reporting of results will be conducted in three phases.  Based on information in the FSAPs scheduled for 2012 and 2014-15, a table will be prepared by the CBvS detailing which of the Core Principles have been met, and if not why.  A final Impact Evaluation report will be prepared and finalized in 2015.

- Evaluation Coordination, Work Plan, and Budget (Workplan Attached).

  - The CBvS will be responsible for providing the data required for the evaluation, and will contract the specialized consultant who will prepare the final methodological design and conduct the evaluation.  The terms of reference for the consultant will be prepared by the IDB Project Team.  The IDB Project Team and the CBvS Program manager will jointly supervise the consultancy and review its results.  Given that the Financial Institution Supervision Enhancement Plan agreed to with the Bank will not be completed until 2014, and the schedule for the second FSAP could fluctuate it is expected that the final evaluation will be prepared in either late 2014 or 2015.

  - Budget.  The external costs for the conduct of the evaluation will be limited to the contracting of the aforementioned consultant.  It is estimated that the cost will be US$20,000 and will be financed from SU-T1054.   Program Manager costs are covered by this technical cooperation, and the time of IDB staff will be covered from the supervisory budget for SU-T1054.

Monitoring Work Plan for Overall Program.

| Key Monitoring Activities / Products Per Activity | 2011 | 2012 | 2013 | 2014 | 2015 | Responsible Entity | Cost | Budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Monitoring of the Compliance of the Conditions of the Policy Matrix and Triggers | Policy Matrix Results Matrix Means of Verification | Progress Reports | Progress Reports Policy Matrix Results Matrix of 2nd Programmatic Loan | Progress Reports | Policy Matrix Results Matrix of 3rd Programmatic Loan | CBvS, Program Manager IDB Project Team | Depends on if 2nd and 3rd programmatic loans are prepared. If not IDB costs would be part of activities of supervision of SU-T1054, with no significant additional costs. |  |
| Monitoring of the implementation of the Financial Institutions Supervision Enhancement Plan |  | Progress Reports | Progress Reports. | Progress Reports | Progress Reports (if not completed) | CBvS IDB Project Team | 0.6 FTE | SU-T1054 Supervision |

Evaluation Work Plan

|  | 2012 | 2014-5 | Responsible | Cost | Budget |
| --- | --- | --- | --- | --- | --- |
| Evaluation of meeting outcomes, Basel Core Principles. | FSAP | FSAP | Project Team | .04 FTE | SU-T1054 supervision budget |
| Final Evaluation |  | (i) Literature Review and Final Design of Evaluation Methodology (ii) Additional Data collection (iii) Conduct of Evaluation and Preparation of Draft Report | Evaluation Consultant consultant with IDB Project team and Program Manager. Program Manager Evaluation consultant jointly supervised by IDB Project Team and Program Manager. | US$ 5,000 0.1 FTE US$ 15,000 0.2 FTE | SU-T1054 SU-T1054 Supervision budget SU-T1054 SU-T1054 supevision budget. |

the imf article iv staff reports, which are prepared on a periodic basis.  recently they have been prepared on an annual basis.