# PROJECT PROCUREMENT PLAN

General information

Country:	The Bahamas

Borrower:	Government of The Bahamas

Executing agency:	Ministry of the Environment (MTE)

Project name:	Promoting Sustainable Energy in The Bahamas

Project and loan contract numbers:	ATN/OC-11467-BH (BH-T1016)

Brief description of the project’s objectives and components:

Objectives: (i) provide technical assistance to the Borrower to achieve Energy Efficiency (EE) in public buildings, residential sector and commercial sectors, and implement demonstration projects; (ii) explore alternatives for Renewable Energy (RE) and implement pilot projects; (iii) support the Borrower with a Waste to Energy (WE) program, and; (iv) institutional strengthening and dissemination of findings.

Estimated date of project approval by the Board of Executive Directors:

Estimated date of signature of the loan contract:	Mar-2009

Estimated date of the final disbursement:	Jul-2010

- A. Introduction

Procurements for the proposed project will be carried out in accordance with the Policies for the Selection and Contracting of Consultants Financed by the Inter-American Development Bank (GN-2350-7), of January 2005, and with the provisions established in the loan contract and this procurement plan.

- B. Procurement plan

The procurement plan for Promoting Sustainable Energy in The Bahamas covering fifteen (15) months of project execution has been agreed between the Bank and MTE. The plan, which is summarized in Appendix 1, indicates the procedure to be used for the procurement of goods, the contracting of works or services, and the method of selecting consultants, for each contract or group of contracts. It also indicates cases requiring prequalification; the estimated cost of each contract or group of contracts; the requirement for prior or post review by the Bank; and estimated dates for the publication of specific procurement notices and completion of the contracts included in this project. The procurement plan will be updated annually or whenever necessary or as required by the Bank. The detailed procurement plan is available at:

The procurement plan is available on the executing agency’s website www.bahamas.gov.bs and www.best.bs . The following documents can also be found on the Bank’s website: Project Procurement Information

- C. Project procurement

The following is a general description of the procurement planned for the proposed project.

Works procurement: N/A

Goods procurement: N/A

Procurement of non-consulting services: N/A

Procurement of consulting services: Consulting services for the project include: (i) provide technical assistance to the Borrower to achieve Energy Efficiency (EE) in public buildings, residential sector and commercial sectors, and implement demonstration projects; (ii) explore alternatives for Renewable Energy (RE) and implement pilot projects; (iii) support the Borrower with a Waste to Energy (WE) program, and; (iv) institutional strengthening and dissemination of findings.

The consulting firms to be hired for the project will be selected using the standard request for proposals (RFP) issued by the Bank, or an RFP satisfactory to the Bank in cases where the standard RFP is not applicable. Individual consultants will be selected bearing in mind the provisions established in chapter V of the policy in document GN-2350-7.

Operating expenses: N/A

Others: N/A

Advance contracting and retroactive financing: N/A

- D. Bank review of procurement decisions

The following contracts will be subject to prior review by the Bank in accordance with Appendix 1 of the policies for the procurement of works and goods and the selection of consultants, respectively:

- Works contracts: N/A.

- Goods contracts: N/A.

- Contracts for Non-Consulting Services N/A.

- All direct contracting: N/A.

- Contracts for Consulting Services with firms with an estimated total cost of US$200,000 equivalent or more.

- Contracts with Individual Consultants: N/A.

- All Single-Source Selection of Consulting Firms: N/A

The remaining contracts will be subject to ex-post review by the Bank, in accordance with the aforementioned Appendix 1 of the policies.

- E. Domestic preference

Bids offering goods originating in the borrower’s country will receive a 15% price preference in contracts requiring international competitive bidding, as established in Appendix 2 of the procurement policies.

The first 18 months of project execution are counted from the date of publication of the general procurement notice, or the first specific procurement notice published following approval of the loan, whichever is earlier.